May 2002

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

Malawi

Date of submission: 23rd October, 2002 Reporting period: January-October, 2002 ( Tick only one ) : Inception report First annual progress report Financial sustainability plan attached Second annual progress report Third annual progress report Fourth annual progress report Fifth annual progress report

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds: October, 2001

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

#### 1.1.2	Statement on use of GAVI/The Vaccine Fund immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/The Vaccine Fund contribution.

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |
| --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines | UNICEF CO to provide |  |  |  |
| Injection supplies | figures | Malawi not illegible for ISS | Malawi not illegible for ISS | Malawi not illegible for ISS |
| Personnel |  |  |  |  |
| Transportation |  |  |  |  |
| Maintenance and overheads |  |  |  |  |
| Training |  |  |  |  |
| IEC / social mobilization |  |  |  |  |
| Monitoring and surveillance |  |  |  |  |
| Vehicles |  |  |  |  |
| Cold chain equipment |  |  |  |  |
| Other. (specify) |  |  |  |  |

Please indicate the date(s) of the ICC meeting(s) when the allocation of funds was discussed : ……………………….

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

## YES                              NO

Malawi has never conducted any Data Quality Audit following the approval for vaccine fund support. The country did not qualify for window 2 support (immunization strengthening support)

The plan of action has been discussed and endorsed by the ICC in the meeting of                                                  (Date).

This is not applicable to Malawi

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines 6.10.01,

#### 27.11.01,18.3.02,28.5.02,10.9.02

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/The Vaccine Fund.

- Malawi launched introduction of new vaccine (DPT-HepB+Hib) on 29th January, 2002

- Delivery of new vaccine bundled with safe injection supplies arrived in time and of required amounts.

- Almost all health workers are implementing the planned activities following successful training prior to introduction new vaccine.

- Although about 4,000 health workers were trained on new vaccine, there is still need to train the  about 4,000 more health workers in the country.

- Monitoring of the introduction of new vaccine process is done at all levels and strengths and weaknesses are being addressed accordingly.

- Vaccine wastage monitoring has been strengthened with the introduction of new vaccine

#### 1.2.2	Major activities

Please outline what major activities have been or will be undertaken to prepare for new vaccine introduction.

- Production of training guide for new vaccine

- Training of health workers on the introduction of new vaccines

- Development of posters and leaflets

- Briefing of paediatricians in central hospitals.

- Involvement of lecturers in pre-service institutions during training of health workers on new vaccine.

- Improvement of cold chain capacity in most health facilities (new refrigerators were procured through support from UNICEF and JICA)

- Construction of a national warehouse for supplies through support from UNICEF

- Regular ICC meetings where progress reports are discussed and plans for improvements endorsed.

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

The following major areas of activities have been funded (specify the amount in US$) with the GAVI/The Vaccine Fund support:

- Much of the financial support for training of health workers on new vaccine was made available by UNICEF country office. However, about US$7.500.00 was used during the launch for new vaccine.

- About US$7,000.00 has been used for compilation of the Financial Sustainability Plan (FSP) Document

- It has been planned to disburse about US$27,000.00 to district for supervisory visits by District Management Teams for monitoring the implementation of the new vaccine and routine immunization services in their respective districts. The same amount will be disbursed towards the end of 2003.

- There will be a monitoring meeting with the DHMT on experiences with the introduction of new vaccine.

## Injection safety

#### Receipt of injection safety support

- The safe injection proposal was submitted in May, 2002 and receive a conditional approval. It has been planned to re-submit a safe injection application to GAVI before the next sitting in 2003.

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

- Not Applicable as the country did not receive this support from GAVI

#### Progress of transition plan for safe injections and safe management of sharps waste.

- The EPI programme has introduced the use of AD syringes for routine and supplemental immunization activities except BCG. GAVI is supplying AD syringes for new.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

This is currently not applicable for Malawi.

# 2.  Financial sustainability

Inception Report 		:	Outline steps towards the development of a financial sustainability plan

First Annual Report 		: 	Submit completed financial sustainability plan

Subsequent Reports 	:	Summarize progress on financial sustainability

The Financial Sustainability Plan (FSP) for Malawi is currently being developed and will be submitted by 15th November, 2002

# 3.	Request for new and under-used vaccines for year :   2003

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

| Table 1 : Baseline and annual targets |
| --- |
| Number of | Baseline and targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births | 562210 | 576944 | 587903 | 599074 | 621445 | 633252 | 645284 | 657544 |
| Infants’ deaths | 58,470 | 60,002 | 61,142 | 62,304 | 64,630 | 65,858 | 67,110 | 68,385 |
| Surviving infants | 509,248 | 522,594 | 532,522 | 542,637 | 562,903 | 573,798 | 584,496 | 595601 |
| Infants vaccinated with DTP3 * | 382,587 | 469,660 |  |  |  |  |  |  |
| Infants vaccinated with DPT-HepB+Hib3 |  |  | 298,371 |  |  |  |  |  |
| Targeted infants for DPT-HepB+Hib3 vaccination |  |  | 489,919 | 510,079 | 540,387 | 562,126 | 584,496 | 595,601 |
| Wastage rate of ** ………….. ( new vaccine) | 4.1 |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in past years

** Indicate actual wastage rate obtained in past years

Please note that DPT-HepB+Hib3 doses are from March to June 2002.

If the request for supply for the coming years differs from previously approved plan:

Please indicate the reasons for those changes and, where relevant, the related modifications of targets of children to be vaccinated, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and indicate the date of the ICC meeting when the changes were endorsed. UNICEF Supply Division in Copenhagen has been notified about the revision of the target population and vaccine requirement. The last ICC was held on 22nd October 2002 and the changes were discussed and endorsed. There have been a slight increase in the new vaccine requirement, which is due to the following reasons; The target population has been raised to 5% from the previous 4% calculated in the GAVI Application Document. This is due to improvement of the infant mortality rate from 134/1000 to 104/1000 live birth. This implies that there are more children to vaccinate now. The program has exceeded the projected coverage by 10% point from the original projection of 2% each year.

3.2	Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for the year  2003

Table 2: Estimated number of doses of DPT-HepB+Hib vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2003 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 542,637 | Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilised vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 1,627,911 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.05 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 1,709,306 |  |
| G | Vaccines buffer stock | F x 0.25 | 427,327 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 400,000 |  |
| I | Total vaccine doses requested | F + G - H | 1,736,700 |  |
| J | Number of doses per vial |  | 2 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 1,655,300 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 963,870 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 29,100 |  |

The calculation for pentavalent requirement was based on first dose which  is almost 100%. Although in subsequent doses, the number of children declines, this has proved to end up with shortages of vaccines.

The projection for anticipated stock at beginning of the year was calculated basing on current stock, consumption rate and wastage rate.

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support

(If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference).

Table 4.1: Estimated supplies for safety of vaccination for the next two years with BCG

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for BCG | # | 599,074 | 621,445 |
| B | Number of doses per child |  | 1 | 1 |
| C | Number o doses | A x B | 599,074 | 621,445 |
| D | AD syringes (+10% wastage) | C x 1.11 | 664,973 | 689,804 |
| E | AD syringes buffer stock | D x 0.25 | 166,243 | 172,451 |
| F | Total AD syringes | D + E | 831,216 | 862,255 |
| G | Number of doses per vial | 20 | 20 | 20 |
| H | Vaccine wastage factor | 2 | 3.33 | 3.33 |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 110,718 | 114,853 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 10,456 | 10,846 |

Table 4.2: Estimated supplies for safety of vaccination for the next two years with Measles

|  |  | Formula | For year 2003 | For year …… |
| --- | --- | --- | --- | --- |
| A | Target of children for Measles | # | 542,637 | 562,903 |
| B | Number of doses per child | 1 | 1 | 1 |
| C | Number of doses | A x B | 542,637 | 562,903 |
| D | AD syringes (+10% wastage) | C x 1.11 | 602,327 | 624,822 |
| E | AD syringes buffer stock | D x 0.25 | 150,582 | 156,206 |
| F | Total AD syringes | D + E | 752,909 | 781,028 |
| G | Number of doses per vial | 10 | 10 | 10 |
| H | Vaccine wastage factor | 1.33 | 1.33 | 1.33 |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 80,110 | 83,102 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 9,247 | 9,592 |

Table 4.3: Estimated supplies for safety of vaccination for the next two years with TT

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for TT vaccination (for TT : target of pregnant women) | # | 599,074 | 621,445 |
| B | Number of doses per woman | 2 | 2 | 2 |
| C | Number of doses | A x B | 1,198,148 | 1,242,890 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1,329,944 | 1,379,608 |
| E | AD syringes buffer stock | D x 0.25 | 332,486 | 344,902 |
| F | Total AD syringes | D + E | 1,662,430 | 1,724,510 |
| G | Number of doses per vial | 20 | 20 | 20 |
| H | Vaccine wastage factor | 1.33 | 1.33 | 1.33 |
| I | Number of safety boxes (+10% of extra need) | ( F x 1.11 / 100 | 18,453 | 19,143 |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |
| ITEM | For the year 2003 | For the year2004 | Justification of changes from originally approved supply: |
| Total AD syringes | for BCG | 831,216 | 862,255 | Safe injection Application on conditional approval by GAVI |
|  | for other vaccines | 2,415,339 | 2,505,538 |  |
| Total of reconstitution syringes | 291449 | 197,955 |  |
| Total of safety boxes | 38,156 | 39,581 |  |

# Signatures

For the Government of  Malawi

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| MOH &P | Dr. H. Somanje |  | USAID | Mr M. Nyirongo |  |
| UNICEF | Dr J. Ortiz |  | DFID | Ms S. Mshana |  |
| WHO | Dr W. Aldis |  |  |  |  |
| JICA | Ms T. Harada |  |  |  |  |
| NORAD | Mr J. Ollson |  |  |  |  |

# Footnotes

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

# Text boxes

Partnering with The Vaccine Fund

(

(