January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Republic of Armenia

Date of submission: …01.07.05… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report √ Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The GAVI funds are on the extra- budget account of the Ministry of Health of the Republic of Armenia. The annual budget is being defined and approved during the ICC meeting. The budget approved by ICC is submitted to the Ministry of Finance of the Republic of Armenia for their verification. The annual budget includes: list of expenditures and budget allocations; timetable for expenditures. In order to receive funds for different budget allocations the request has to be submitted to State Procurement Agency (SPA). EPI Manager specifies all the technical specification to be taken into consideration by SPA. On a basis of submitted request SPA announces a tender among suppliers. The SPA also acts as decision maker on selection of supplier of requested goods or services. When decision on supplier is made EPI Manager signs a supply agreement with Supplier. Based on the terms of the Agreement, Supplier is obliged to provide the purchased goods or services within agreed deadlines (usually one month). EPI Manager is obliged to report on progress development as well as on the way of utilization of purchased goods or services on every consequent ICC meeting. One of the major problems to be addressed is necessity to pass the stage of SPA approval. The problem is that it takes around four months from the first day of submission the request to SPA until the stage of decision on supplier is made. The other question to be addressed is because the ISS Fund has been removed from International Agreement and placed as extra-budget account, during the implementation of mission activities the VAT in amount of 20% has to be paid. All the International Funds are free of VAT payments.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 ______20000USD _________

Remaining funds (carry over) from 2003 		134300 USD ________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0 |  |  |  |  |
| Injection supplies | 0 |  |  |  |  |
| Personnel | 0 | 0 | 0 | 0 | 0 |
| Transportation | 4600 | 600 | 1700 | 2300 | 0 |
| Maintenance and overheads | 0 | 0 | 0 | 0 | 0 |
| Training | 0 | 0 | 0 | 0 | 0 |
| IEC / social mobilization | 400 | 100 | 150 | 150 | 0 |
| Outreach | 0 | 0 | 0 | 0 | 0 |
| Supervision | 0 | 0 | 0 | 0 | 0 |
| Monitoring and evaluation | 0 | 0 | 0 | 0 | 0 |
| Epidemiological surveillance | 1000 | 700 | 300 | 0 | 0 |
| Vehicles | 0 | 0 | 0 | 0 | 0 |
| Cold chain equipment | 18200 | 560 | 2800 | 14840 | 0 |
| Other …………. (specify) | 0 | 0 | 0 | 0 | 0 |
| Total: | 24200 | 1960 | 4950 | 17290 | 0 |
| Remaining funds for next year: | 129800 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Note: As the funds are placed on the same account, it is impossible to separate the ex pansies

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Development of the Immunization Program as a separate field of health care (in the process); Accurate compliance to FSP requirements; Inclusion of updated Measles Elimination Program into the National Immunization Program; Maintaining 95% coverage of all vaccination on a district level throughout the country; Introduction of a new pilot system of AEFI.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

No studies/surveys were eon ducted during reporting period

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:  MONTH…January…..           YEAR…2004….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

With support of GAVI Armenia Hepatitis B vaccines were received. Vaccines were supplied in time and in requested quantities. A distribution of this vaccine is made in accordance with vaccination schedule and was delivered to Maternity Hospitals and policlinics. The major problems encountered were related to timely delivery from regional to local levels (Health centers, policlinics, ambulatories).

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Activities In order to strengthen services, new software was developed that enables monitoring of the whole program of immunization: supply of vaccines, stock of vaccines on all levels, vaccination coverage, wastage, storage, etc; Training of doctors and nurses; Monitoring of AEFI; Social mobilization; Ensuring Cold chain-refrigerators in rural ambulatories. Problems encountered. Lack of qualified staff; Not adapted system of optimisation of Health Care (rejecting the old system without proper operation of the new one); Not optimal system of budget allocation for immunization, for example: budget allocations for purchase of vaccines is made on quarterly basis during the year, meanwhile the optimal solutions would of been allocation of the entire budget at the beginning of the year.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

18 200$ were used for procurement of 65 refrigerators and distributed on district levels (especially in rural areas) 4 600$ were used for the timely transportation from airport to national level and from national level to marzes (district) level 1000$ were used for the Immunization Program monitoring and epidemiological surveillance 400 were used for the social mobilization TOTAL – 24 600 US$

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In reporting period the country is not receiving injection safety support from GAVI.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

The law of sanitary-epidemiological safety of people is being updated and comprises of the law on immunization. It will involve the injections safety, sharps waste and management. The major problem encounters is absence of efficient incinerators for used syringes and sharp waste, which will be ecologically harmless.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

After attending the training course in Moscow the working group for the FSP preparation was organized involving representatives from the Ministry of Health and Ministry of Finances. An expert from GAVI was invited to assist the working group. A questionnaire (of all immunization details) was developed and sent to all medical facilities having immunization services all over the country. The draft of FSP was developed based on the data of completed questionnaires received from all the medical institutions and information from the Ministry of Finance. After some amendments done in the draft version, the final version of FSP was prepared and approved by the Minister of Health and Minister of Finance. GAVI, WHO and UNICEF largely contributed to development of FSP.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for Hepatitis B.  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Hepatitis B (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% | 50% | 0 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 50% | 100% | 100% | 100% | 100% |
| C: Total funding for Hepatitis B (new vaccine) US$ |  | 61047 | 57827.3 | 59573 | 60426.4 | 61750 | 62702 | 63968.8 | 65568.2 | 67529.7 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Increase of the share funded by the Government to attain financial sustainability | The definite issue development in the Governmental Budget decided to submit fund for vaccines annually | The first investment (16 000$) was submitted for the OPV vaccines receipt The investment for 2005 (66000$) will submit for OPV, BCG, DTP and safety injection. | Problems in timeliness of the budget means submitting | Concordance with the FSP | Augmentation of the budget for vaccines receipt for the coming year | The changes were done according to proposals got from the GAVI secretary |
| 2. Elimination of measles | Endorsement of the Measles Elimination Plan at the Governmental level | Updating of the Measles Elimination Plan |  | Elimination of measles by 2010 | The updated Program is in the evaluation and endorsement process currently | The epidemiological situation was considered and the phases of Program implementation were revised |
| 3. Management of 100% training of doctors and nurses | Stage by stage held training courses in all the marzes | The training of nurses is completed and the training of doctors is started | Not persistent use of the got knowledge in practice; updating of the modules | Increase in skilfulness and knowledge level of the personnel | The most required marzes involvement into the training procedure | No changes |
| 4. The Immunization Program approval by the Government in general | Management of the Program development for the following approval at the Governmental level | Determination of the ideological and the juridical base for the Program |  | The Immunization Program acting independently | The required materials preparation for the Immunization Program | Having the acting Program as a base the optimisation program issues were considered |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 37811 | 38200 | 38590 | 39055 | 39640 | 40433 | 41440 | 42683 | 44200 |
| Infants’ deaths | 283 | 290 | 292 | 294 | 298 | 300 | 305 | 313 | 320 |
| Surviving infants | 37528 | 37910 | 38298 | 38761 | 39342 | 40133 | 41135 | 42370 | 43880 |
| Infants vaccinated in 2004 (JRF) 1st dose of DTP (DTP1) | 35476 | 36715 | 37150 | 37985 | 38555 | 39330 | 40312 | 41734 | 43221 |
| Infants vaccinated 2004 (JRF) 3rd dose of DTP (DTP3) | 33888 | 36015 | 36383 | 37210 | 37965 | 38525 | 39695 | 41100 | 42783 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) with 1st dose of Hepatitis B (new vaccine) | 35820 | 36900 | 37430 | 38250 | 38840 | 39625 | 40615 | 41830 | 43320 |
| Infants vaccinated 2004 (JRF) with 3rd dose of Hepatitis B ( new vaccine) | 34075 | 35300 | 36340 | 37150 | 37770 | 38930 | 39900 | 41100 | 42783 |
| Wastage rate in 2004 and plan for 2005 beyond*** of Hepatitis B ( new vaccine) | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 3 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | - | - | - | - | - | - | - | - | - |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 36223 | 37050 | 37150 | 37880 | 38450 | 39370 | 40610 | 41830 | 43760 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 31280 | 36150 | 36400 | 37210 | 38540 | 39200 | 40200 | 41400 | 43310 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Taking into consideration annual increase of population is not high changes in quantities of requested new vaccines will be not significant.

Table 4: Estimated number of doses of Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage 2. Reducing wastage | 95% 2. up to 3 % |  | In time vaccination, especially in case of new born 2. Not full understanding on storage of vaccines (cold chain) | - Improve in time vaccination; Training of medical staff; Strengthening of social mobilization Training of medical and technical staff |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | + |  |
| Reporting Period (consistent with previous calendar year) | + |  |
| Table 1 filled-in | + |  |
| DQA reported on | - |  |
| Reported on use of 100,000 US$ | + |  |
| Injection Safety Reported on | + |  |
| FSP Reported on (progress against country FSP indicators) | + |  |
| Table 2 filled-in | + |  |
| New Vaccine Request completed | + |  |
| Revised request for injection safety completed (where applicable) | + |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

7.	Signatures

For the Government of ……Republic of Armenia……………………

Signature:	……………………………………………...……………...

Minister of Health Republic of Armenia

Title:	………………………………………….………………….

Date:	20.07.2005……………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health RA | Gagik Sayadyan – Chef of Staff MOH RA |  | Ministry of Health RA | Hayk Grigoryan – Chef of the International Department |  |
| Ministry of Health RA | Vladimir Davidyants – Head Sanitary doctor of RA |  | Ministry of Finance and Economy RA | Konstantin Krityan – Chef of Heakth Department |  |
| Ministry of Health RA | Artavazd Vanyan – Chef of the Sanitary and Epidemiological Inspection MOH RA |  | Ministry of Health RA | Sirak Sukiasyan – EPI Manager |  |
| Ministry of Health RA | Vahan Poghosyan – Chef of the Health Care Department MOH RA |  | UNICEF | Liana Hovakimyan |  |
| Ministry of Health RA | Armen Karapetyan – Chef the Health Financial and Economical Department MOH RA |  | WHO | Elizabeth Danielyan |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes