January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: ALBANIA

Date of submission: May 12, 2005 Reporting period: January 1 – December 31, 2004 ( Information provided in this report MUST refer to the previous calendar year 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report X Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

On 2001 Albania received 100,000 USD only from GAVI to continue and strengthen the immunisation services for Hepatitis B vaccine (the new vaccine being introduced in 1994 in Albania’s National Calendar of mandatory immunization since 1994 through International Rotary Club financial support). On 2004 no immunization services support was provided from GAVI to Albania except Hepatitis B vaccine and the injection supplies related to Hepatitis B vaccination (according to 2001-2005 plan). On 2004 Albania has prepared the application to apply to GAVI to financially support the Haemophilus b vaccine (Hib vaccine) introduction in Albania’s National Calendar of mandatory immunization, based on the surveillance and/or cross-sectional surveys data as regards the conspicuous public health impact of Haemophilus b (invasive) infections in childhood morbidity and mortality in Albania.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _______________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Four meetings were performed during the year 2004 by the ICC, chaired by Deputy Minister of Health and secretary (the Director of Institute of Public Health), whose members are representatives from Ministry of Health, Institute of Public Health, Tirana University Hospital Centre “Mother Theresa”, UNICEF, WHO, USAID, World Bank, Albanian Red Cross, American Red Cross, Greek Embassy, Italian Cooperation Fund, and Swiss Cooperation. March 24, 2004 – 1st ICC meeting minutes: Two main topics were thoroughly discussed and the respective conclusions and recommendations were approved. 1. Presentation of Cold Chain Assessment in Expanded Programme on Immunization in Albania: A quality assessment study of Cold Chain System: 1.1. Reducing the vaccine wastage rate by proceeding a study on single doses vaccines management; 1.2. Standardization of evaluating the quality and cost-effectiveness of the top-bottom country cold chain system. 2. Presentation of Inventory of Cold Chain Equipment current State (=updated Country Cold Chain Mapping): 2.1. Redistribution of cold chain equipment (refrigerators, freezers) according to the current needs of country districts; 2.2. Action plan towards maintaining the cold chain system (from IPH or central level, to district or intermediate level, to vaccination point or bottom level); casting the respective state budget. June 17, 2004 – 2nd ICC meeting minutes: Presentation and approval of Sustainability Financial Plan (FSP) of Vaccination National Program of Albania. 1. Thoroughly discussion of each item/problem of such an important topic by all ICC members; 2. USAID kindly offering the technical assistance on the matter. September 24, 2004 – 3d ICC meeting minutes: Two important topics were thoroughly discussed: 1. Problems of hard-to-reach and/or outreach population and other problems for country remote areas. 2. On improving quarterly official reporting form of vaccination coverage for each antigen of our National EPI Calendar. November 22, 2004 – 4th ICC meeting minutes: Five main different topics were thoroughly discussed and the respective conclusions and recommendations were approved. 1. Introduction of Mumps Vaccine in National Vaccination Schedule (starting from the year 2005, mumps antigen being as the component of MMR three-vaccine). 2. Presentation of Vaccination Coverage at both National and District Level in Albania for the year 2004. 3. The Cold Chain Equipment State After its Redistribution. 4. Discussion of Sustainability Financial Plan of National Vaccination Program. 5. Application at GAVI for Haemophilus influenzae b vaccine (year 2005).

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..YEAR  2001 (by GAVI)

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

The HBV (Hepatitis B) vaccine is provided by GAVI for the Expanded Programme on Immunization since 2001. Based on our national immunization schedule HBV vaccine is implemented for all children born in Albania with three shots: immediately after birth, at 2 months of age and at 6 months of age, respectively. In order to avoid any interruption of this schedule because of any eventual cold chain failure in central level, the shipments for HBV, as for all other antigens, have been scheduled twice per year. The shipment dates and quantities were based on the documentation approved in advance. We have some concerns which are linked with the recent results of cold chain survey as follows: 1 For safety reasons, we preferred to have some reliable Freeze-Watches accompanying the HBV shipping boxes in order to improve monitoring of any harmful exposition of the vaccine towards freezing temperatures. 2 For the same safety reasons, we preferred to have HBV vaccine with VVM label attached in the vials, what will help the health staff at local level to manage the vials especially during outreach activities.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Establishing Viral Hepatitis Hospital-Based Case-Based Surveillance in Tirana and Durres Regions (accounting for around 40% of the total country population). Cross-sectional surveys for Viral Hepatitis B in pregnant women, health care workers, military recruits, and children 0-5 years of age. Establishing Hib (Heamophilus influenzae b) Hospital-Based Case-Based Surveillance (Hib paediatric severe infections such as meningitis, sepsis, severe pneumonia) in Tirana and Durres Regions. Cost effectiveness of Hib vaccine introduction. Further strengthening cold chain and injection safety. Health promotion and education on vaccine preventable diseases. Further improving monitoring of vaccination coverage. Evaluation of burden of disease for mumps. Establishing CRS (Congenital Rubella Syndrome) Hospital-Based Case-Based Surveillance in Tirana Region. Evaluation of the improved reporting form of vaccination coverage. Evaluation of central stock management and district (local) stock management.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The activities undertaken during the year 2003-2005 under GAVI/VF support are: 1 Analysis and conclusions of Lot Quality Assessment Survey on vaccination coverage in Tirana and Durres districts (carried out by the end of 2002) - 6,424USD 2. Automatic power supply for EPI national cold store (including the maintenance) inventory and maintenance of cold chain - 10,000USD 3. Establishing Congenital Rubella Syndrome (CRS) Hospital-Based Case-Based Surveillance in Tirana Region – 7,443USD 4. Establishing Viral Hepatitis Hospital-Based Case-Based Surveillance in Tirana and Durres regions - 10,755USD. 5. Carrying out cross-sectional sero-survey on Viral Hepatitis in pregnant women, health care workers, military recruits, and children aged 0-5 years – 13,000USD 6. Establishing Haemophilus influenzae b Hospital-Based Case-Based Surveillance (hospitalised infants with meningitis/severe pneumonia/sepsis) in Tirana and Durres regions – 10,562USD 7. Lab equipment (lab diagnosis component) for CRS Case-Based Surveillance, Viral Hepatitis Hospital-Based Case-Based Surveillance and Viral Hepatitis sero-survey, and Hib Hospital-Based Case-Based Surveillance – 22,100USD 8. Health promotion and education on vaccine preventable diseases including new vaccines – 11,716USD 9. Preparation of the detailed annual Financial Sustainability Plan (FSP) for the period 2004-2013 according to GAVI requirements. 10. Mopping-up/SNID activities for all National EPI antigens, namely OPV (3 doses), DTP/DT/Td (3 doses), HBV (3 doses) and MR (2 doses) in all paediatric population (subjects aged less than 15 years old) of Mirdita district and country Roma population (subjects of the same age group)- 8000USD Funds were available for program use during 2003. A delay was seen during the procurement of lab equipment but it was overcome due to the assistance of MoH. The remaining funds are 20,000USD and are going to be spent till the end of 2005.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Albanian government application for Injection Safety was approved on May 2003. The National Plan for Injection Safety (May 2003) contains the detailed plan of action, including the activities to be undertaken, the respective time frame and the expected results. No problems were encountered with the arrival, distribution or quality of AD syringe and safety boxes since the year 2003.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Proportion of health facilities provided with ADs. Proportion of health facilities provided with reconstitution disposable syringes Proportion of health facilities with one month stock of ADs Proportion of health facilities with adequate quality and sterility of injection equipment Proportion of health facilities provided with adequate quantity of safety boxes Availability of an incinerator or non incineration of safe facility Proportion of health facilities with presence of used syringes and needles in garbage, dumping area or close to the health facility Number of abscesses following injection reported Proportion of immunization injections observed with following of aseptic injection techniques (supervision reports, SIP assessment) | 100% 100% 100% 100% 100% 100% 0% 0% 95% | 100% 100% 100% 100% 100% 80% 20% 0% 96% | --- --- --- --- --- Lack of funding at central and district level Lack of incinerators or non incinerators due to lack of funding --- --- | 90% in 2005 (this updated target in 2004 was not realized due to lack of funding), 10% in 2005 |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Some of funds for introduction of new vaccines have been used for strengthening injection safety.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The FSP (Financial Sustainability Plan) for 2004-2013 period was prepared by Albanian specialists (Institute of Public Health, Ministry of Health), was analysed and discussed in ICC meeting of December 2003. The ICC meeting decided that FSP has to be reviewed by a WHO and World Bank consultant before submission to GAVI Secretariat. Following the approval of such a decision, the prepared 2004-2013 FSP was reviewed by WHO and World Bank consultants (May 2004) and submitted by June 15, 2004.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for    HBV (Hepatitis B) vaccine   (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine HBV (Hepatitis B) vaccine (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2001** | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 |
| C: Total funding for HBV (Hepatitis B) vaccine (new vaccine) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Increase Government contribution for vaccine purchase | Advocacy with Ministry of health (MoH) and Ministry of Finances (MoF) when GAVI funding ends and/or vaccine choice changes | Vaccine secured for 2006 and one antigen (mumps) added |  | 80% | 100% for all vaccines (antigens) of the National EPI Calendar (HBV vaccine being included) in 2006 onwards |  |
| 2. Increase Government contribution for program operational costs | Presentation by IPH to MoH of unfunded operational costs; advocacy with MoF (through MoH) for higher funding program |  |  |  | National expenditure on immunization program-specific operational costs as a share of GDP after adjustment for debt service |  |
| 3. Increase Government contribution for capital costs | Advocacy with MoH for funds for upgrading cold chain, vehicles, incinerators, and power supply generators |  |  |  | Program-specific capital expenditures paid for with national resources with the past fiscal year divided by total program-specific capital expenditures |  |
| 4. Introduction of Mumps antigen (MMR vaccine) in the National EPI Calendar of mandatory immunization | Starting from the year 2005 | MMR vaccine secured for 2005 |  |  |  |  |
| 5. Reduce vaccine wastage | Improve stock management in districts (local level) and health centers (basic level) |  |  |  | Trends in wastage rates by antigen |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 41,466 | 44,000 | 44,000 | 44,000 | 44,000 | 44,000 | 44,000 | 44,000 | 44,000 |
| Infants’ deaths | 620 | 600 | 580 | 560 | 535 | 510 | 490 | 465 | 440 |
| Surviving infants | 40,846 | 43,400 | 43,420 | 43,440 | 43,465 | 43,490 | 43,510 | 43,535 | 43,560 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 40,448 | 43,800 | 43,810 | 43,820 | 43,830 | 43,840 | 43,860 | 43,875 | 43,880 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 40,729 | 43,600 | 43,620 | 43,640 | 43,670 | 43,690 | 43,730 | 43,750 | 43,760 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of * HepB (HBV) [at birth].. (new vaccine) | 40,930 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of HepB (HBV) [at 6 months of age] ( new vaccine) | 41,340 | 43,600 | 43,620 | 43,640 | 43,670 | 43,690 | 43,730 | 43,750 | 43,760 |
| Wastage rate in 2004 and plan for 2005 beyond*** HepB (HBV).. ( new vaccine) | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 35,371 | 41,800 | 41,800 | 41,800 | 41,800 | 41,800 | 41,800 | 41,800 | 41,800 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 40,388 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 | 43,560 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 44,714 | 42,970 | 42,985 | 43,010 | 43,031 | 43,055 | 43,080 | 43,100 | 43,125 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

| Albania has been always trying to reach the much highest coverage rates based on an open vial policy in a country where an ongoing high internal migration has left scarce population in rural areas. At the same time the reliability of denominator figures in vaccine coverage estimates has been and continues to be a big challenge in Albania due to the ongoing very high and even unpredictable rates of population mobility (both internal migration and immigration. As a result, the UNDP annual projection (1996-2006 decade) of Albania population resulted to be not adequate. The last population census (Institute of Statistics, 2002) gave a figure of 3,067,416 population of Albania (emigrants being excluded), that is, lower compared to the 1989’s population census figure (3,187,985 people). The district local offices continue to be unable of giving the real annual estimates of the respective existing inhabitants in general and the paediatric age groups (population aged less than 15 years) in particular. The figures provided by Ministry of Health and EPI programme (Institute of Public Health) are very different compared with INSTAT ones. Very often, UNICEF and other international organisations base their calculation on MoH figures as they are more reliable and especially EPI ones due to door-to-door population monitoring. At the same time there is a high migration of fertile ages, decrease of number of births and increase use of family planning methods. This is the reason why the population numbers are changing very quickly and (as it was emphasized) in an unpredictable way. The figures provided for GAVI in 2001 were from INSTAT. As a consequence of such a matter of fact, the inconsistency of data on denominator figures (births, population according to age-structure, etc) is derived, thus explaining for instance the small differences between the expected figure of births in 2004 (GAVI Progress Report for the year 2003) and the observed one in 2004 (GAVI Progress Report for the year 2004). Meanwhile, a process of new vaccination coverage reporting form is in the process of distribution all over the country. A new policy of single and multiple vial distribution of vaccines were taken into consideration in order to improve the wastage rate: it was decided to have half of vaccines (mainly for rural areas) as single-dose vials and for urban areas as multiple-dose vials. The figures used in this report are provided by MoH/IPH and are considered as the most accurate. N.B. Numbers of infants (Table 3) vaccinated with DTP 3 and HBV3 are higher than those vaccinated with DTP1 and HBV1 simply because DTP3 and HBV3 are given in the age 6 months, thus including infants born in the preceding year 2003, whereas HBV1 is given at birth (thus not including any infants born in 2003) and DTP1 at the age 2 months (thus including much less infants born in 2003 than those receiving DTP3). |  |
| --- | --- |

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The different quantities for each Albanian National EPI antigen and injection supply equipment, based on the updated data concerning the population target and wastage rate, have been discussed within the EPI office (Institute of Public Health) and then with UNICEF Tirana Representative Office. After such a plan has been discussed within the EPI office and then with UNICEF people, there has been not any problem concerning the implementation of those quantities on the dates and quantities agreed previously with them. During the year 2004 there have been two shipments per year for each antigen and one shipment per year for injection supplies.

Table 4: Estimated number of doses of  HBV (HepB) vaccine  (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6/1: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

N.B. The wastage rate for BCG (20 doses per vial) is 3.0 based on the specificities of Albania with many remote rural areas and villages with very low births per year.

Table 6/2: Estimated supplies for safety of vaccination for the next two years with DTP

Table 6/3: Estimated supplies for safety of vaccination for the next two years with Measles (MMR)

Table 6/4: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. >95% HepB first and third dose coverage at national level in 2004 2. >90% HepB first and third dose coverage at district level in 2004 3. No stock out of vaccines at facility level in 2004 4. 100% availability of AD syringes and safety boxes in all vaccination posts of the country in 2004 5. Drop-out rate (HepB 1 – HepB 3) less than 6% in 2004 |  | 1. >95% HepB first and third dose coverage at national level in 2004 2. >90% HepB first and third dose coverage at district level in 2004 3. No stock out of vaccines at facility level in 2004 4. 100% availability of AD syringes and safety boxes in all vaccination posts of the country in 2004 5. Drop-out rate (HepB 1 – HepB 3) less than 6% in 2004 |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | YES |  |
| Reporting Period (consistent with previous calendar year) | YES |  |
| Table 1 filled-in | YES |  |
| DQA reported on | NO |  |
| Reported on use of 100,000 US$ | YES |  |
| Injection Safety Reported on | YES |  |
| FSP Reported on (progress against country FSP indicators) | YES |  |
| Table 2 filled-in | YES |  |
| New Vaccine Request completed | YES |  |
| Revised request for injection safety completed (where applicable) | YES |  |
| ICC minutes attached to the report | YES |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

Albania has been always trying to reach the much highest coverage rates based on an open vial policy in a country where an ongoing high internal migration has left scarce population in rural areas. At the same time the reliability of denominator figures in vaccine coverage estimates has been and continues to be a big challenge in Albania due to the ongoing very high and even unpredictable rates of population mobility (both internal migration and immigration. As a result, the UNDP annual projection (1996-2006 decade) of Albania population resulted to be not adequate. The last population census (Institute of Statistics, 2002) gave a figure of 3,067,416 population of Albania (emigrants being excluded), that is, lower compared to the 1989’s population census figure (3,187,985 people). The district local offices continue to be unable of giving the real annual estimates of the respective existing inhabitants in general and the paediatric age groups (population aged less than 15 years) in particular. The figures provided by Ministry of Health and EPI programme (Institute of Public Health) are very different compared with INSTAT ones. Very often, UNICEF and other international organisations base their calculation on MoH figures as they are more reliable and especially EPI ones due to door-to-door population monitoring. At the same time there is a high migration of fertile ages, decrease of number of births and increase use of family planning methods. This is the reason why the population numbers are changing very quickly and (as it was emphasized) in an unpredictable way. The figures provided for GAVI in 2001 were from INSTAT. As a consequence of such a matter of fact, the inconsistency of data on denominator figures (births, population according to age-structure, etc) is derived, thus explaining for instance the small differences between the expected figure of births in 2004 (GAVI Progress Report for the year 2003) and the observed one in 2004 (GAVI Progress Report for the year 2004). Meanwhile, a process of new vaccination coverage reporting form is in the process of distribution all over the country. A new policy of single and multiple vial distribution of vaccines were taken into consideration in order to improve the wastage rate: it was decided to have half of vaccines (mainly for rural areas) as single-dose vials and for urban areas as multiple-dose vials. The figures used in this report are provided by MoH/IPH and are considered as the most accurate. WHO EURO COMMENT 2004 PR Review – Albania This is Albania’s Fourth Annual Progress Report. It is a well-written document, containing all the information required. HepB support from GAVI is ending in 2005 and the three-year Injection Safety Support, in 2006. Nevertheless, the country has presented estimates on hepB doses needed for the year 2006 (Table 4) and Safe Injection Support for 2007. (Tables6.1-6.4) It has also updated Table 3. Remarks and recommendations: Section 1.1 Immunization Services Support is not applicable for ALB, therefore it should be left blank. Received amount of US$ 100.000 is VF financial support and should be presented in section 1.2.3 and presented there. Section 1.23 Please indicated remaining fund for 2005, if left any. Table 3: In the year 2004 column that should contain realized data, numbers of infants vaccinated with the 3rd dose of DPT and hepB are higher than those vaccinated with the first dose. HepB1 coverage rate is 98.7% and hepB3, 101.2%. Numbers of infants to get DPT3 and hepB3 are higher than numbers of surviving infants Injection Safety support Table 6.1. (BCG): wastage factor should be 2 (not 3), buffer stock of AD is not available for the years of support after the first one. Thus, F becomes 48,840, I - 4,884 and J - 596. Table 6.2. (DTP): the support is for 3 doses (not 4), buffer stock should not be included, and estimates should be based on surviving infants, not births. Correct figures are: C-130,200, D-144,522, F -144,522 and J-1,604. Table 6.3. (MMR): the support is for one dose, buffer stock should not be included, wastage factor is 1.6 and estimates should be based on surviving infants, not births. Correct figures are: C-43,400, D-48,174, I-7,708 and J-620. Section 4. Please identify indicators and targets in line with Hep B control programme. Better to choose process indicators than outcome indicators, such as; >95% Hep B first and third dose coverage at national level by 200x >90% Hep B first and third dose coverage in all districts/rayons by 200x No stock out of vaccines at facility level through out the reported year (none by 200x) Availability of AD syringes and safety boxes in all vaccination posts visited during the reported year (100% by 200x) Drop out rate (Hep B 1 – Hep B 3) less than 6% by 200x Vaccine wastage rate for ten dose vial less than x,y by 200x Vaccine wastage rate for mono dose less than x,y by 200x Choose the applicable ones or all, as you wish. And start monitoring progress and report with next year’s APR. Section 6. Please insert ICC and WHO EURO comments before submitting to GAVI/VF and do not forget to sent an electronic copy of the final version to WHO EURO as well. Second ICC Comment 4. Injection safety support Wastage rate for BCG in Albania is 3 because it has been calculated as 70% due to existing of many small remote areas with very low number of births per year ( 20 doses vial) DTP3 and HepB3 are given at 6 months of thus including infants born at preceding year. This the reason why DTP3 and HepB doses are higher than the first ones respectively at two months and birth. The support for DTP has been for four doses. The support for MMR ( AD syringes) it has been for two doses.

7.	Signatures

For the Government of  Republic of ALBANIA	Mr.  Eduard HASHORVA

Signature:	……………………………………………...……………...

Title:	Deputy Minister of Health (Ministry of Health – MoH), Head of ICC

Date:	13 May 2005

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health (MoH) Tirana, Albania | Mr. Agim SHEHI Director of PHC Directory | 12/05/2005 | UNICEF Representative Office, Tirana, Albania | Mrs. Ornela ABAZI Health Project Manager | 12/05/2005 |
| Institute of Public Health (IPH), Tirana, Albania | Mrs. Silva BINO Director | 12/05/2005 | WHO Office, MoH, Tirana, Albania | Mr. Vasil MIHO Liaison Officer | 12/05/2005 |
| Institute of Public Health (IPH), Tirana, Albania | Mr. Eduard KAKARRIQI EPI National Coordinator | 12/05/2005 | WHO Emergency Office, Tirana, Albania | Mr. Santino SEVERONI Head | 12/05/2005 |
| Ministry of Health (MoH) Tirana, Albania | Mr. Jorgo KOSTA Specialist in PHC Directory | 12/05/2005 | Albanian Red Cross, Tirana, Albania | Mr. Zamir MUÇA Secretary General | 12/05/2005 |
| Institute of Public Health (IPH), Tirana, Albania | Mrs. Ilirjana KADARE EPI Manager | 12/05/2005 | Albanian Red Cross, Tirana, Albania | Mrs. Arjana DELJANA Responsible for health projects | 12/05/2005 |
| Institute of Public Health (IPH), Tirana, Albania | Mrs. Erida NELAJ Specialist, EPI staff | 12/05/2005 | American Red Cross, Tirana, Albania | Mr. Fabian CENKO Office Coordinator | 12/05/2005 |
| Institute of Public Health (IPH), Tirana, Albania | Mrs. Nadia FRASHERI Head of National Regulator Authority | 12/05/2005 | USAID Representative Office, Tirana, Albania | Mrs. Zhaneta SHATRI Health Project Manager | 12/05/2005 |
| UNICEF Representative Office, Tirana, Albania | Mr. Vinod ALKAR Health Coordinator | 12/05/2005 | World Bank, Tirana, Albania | Mrs. Florian TOMINI | 12/05/2005 |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes