May 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: GUYANA

Date of submission: 20th May 2005…………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report √ Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

No funds received for immunization support services ( Not applicable)

#### 1.1.2	Use of Immunization Services Support (Not applicable )

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004)

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection Supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country) NOT APPLICABLE

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

NOT APPLICABLE

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Not applicable

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH…December          YEAR…2004……….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Item Amount ( US dollars) TOTAL SUM ALLOCATED FOR 2004 $124,500 EXPENDITURE IN 2004 Pentavalent vaccines- 17,000 doses ( $67,879.50 Reconstitution Syringes-18,000, 1 cc syringe, $ 3,312.00 AD syringes - 36,000 syringes ½ cc $2, 187.92 Safety boxes- 600 $1,620.00 Total in 200 4 $74,999,42 *

* Source of information,  PAHO EPI Revolving Fund, Washington

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Vaccination mop up activities were conducted during the vaccination week in the month of April 2004 in vulnerable regions. There was also a regional launch of vaccination activities with two border areas, Lethem in Region 9 and Bon Fim in Brazil. This sought to strengthen border activities in the reduction of vaccine preventable diseases across borders. Also enhanced vaccination activities were conducted in the latter part of the year in two additional hinterland Regions, 1 and 7 with low coverage. The situational analysis was completed in the hinterland regions. Common problems faced were the shortage of human resources, inadequate transportation for outreach activities and insufficient cold storage facilities. Efforts are in place through the MOH planning to procure vehicles for some of these areas and also to obtain solar refrigerators for the hinterland areas. A visit was made to the EPI programme in Suriname to look in the possibility of implementation of low cost incinerators in remote areas of Guyana.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Category in 2004 Actual Expenditure Estimated expenditure in 2003 as of the APR for December 2003 $73,918.47 Capacity building in the MOH (e. g research –situational analysis, training ) $9,243,98 Total Expenditure in 2004 $82,162,45 Balance $17,837,55 * * This money would contribute towards a portion for the procurement of a cold chamber for the national cold room at the Kingston Bond. Specifications for the cold room has been sent to PAHO/WHO , Washington who has agreed to provide the remaining funds

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Not applicable

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

. Not applicable

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Percentage of health facilities who have implemented safe disposal for syringes and needles | To have at least 70% of the health facilities implemented safe disposal of needles and syringes | About 80% of the health facilities have small burning chambers for the disposal of needles and syringes |  | To have at least 85 % o the coastland areas implemented safe disposal of needles and syringes. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Please note the following: The Ministry of Health in collaboration with USAID has started an injection safety project which will include the assessment of needs for some of the health facilities and provide resources.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Submitted first, second and third annual progress report, indicators are listed below.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 35 | 25 | 15 | 15 | 15 | 15 |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 65 | 75 | 85 | 85 | 85 | 85 |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators (same indicators chosen to be reported on in 2003 ARP report, annually)

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Increase in efficiency of resources | Indicator : The number of Regional Health Officers (RHOs) trained and actively participating in budget preparation Actions : Budget preparations done in 2004 with most of the Regional Health Officers participating at the MOH and MOF. | Participation of most of the Regional Health Officers | Nil | 3 out of 10 RHOs (2001) | 9 out of 10 RHOs (2004) | Nil |
|  | Indicator: Decrease in missed opportunities and attrition rate nationally. Actions : Visits were made to the low coverage regions and meetings organised in order to seek out defaulters | For 2004, the drop out rate was decreased although there were regional differences. | Climate and difficulties in logistics to access regions in order to provide vaccination services makes it difficult to reach some remote areas. | 15% nationally, target value 5% ( 2001) | Attrition Rate was less than zero in 2004 | Nil |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Actual | Proposed targets and estimate population |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births (live) | 16,556 | 18,346 | 18,346 | 18,346 | 18,346 | 18,346 | 18,346 | 18,346 | 18,346 |
| Infants’ deaths | 318 E | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 |
| Surviving infants | 16,238 | 17,988 | 17,988 | 17,988 | 17,988 | 17,988 | 17,988 | 17,988 | 17,988 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)*(Pentavlent Vaccine) | 14,588 | 15,100 | 15,100 | 15,100 | 15,100 | 15,100 | 15,100 | 15,100 | 15,100 |
| Infants vaccinated 2004 (JRF) /to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* Pentavlent Vaccine) | 14,844 | 16,728 | 16,728 | 16,728 | 16,728 | 16,728 | 16,728 | 16,728 | 16,728 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1) (pentavlent) …( percentage %) | 90% | 92 | 92 | 93 | 93 | 93 | 95 | 95 | 95 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of pentavalent ( Percentage) | 91% | 93 | 95 | 95 | 95 | 95 | 95 | 95 | 95 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with DT2 | 96% | 96 | 96 | 96 | 97 | 97 | 97 | 97 | 98 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 94% | 95 | 95 | 98 | 98 | 98 | 98 | 98 | 98 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 88.4% | 95 | 95 | 98 | 98 | 98 | 98 | 98 | 98 |

E –estimated deaths up to time of reporting.

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The actual target for pentavalent-1 is used for 2004; for 2005-2012, the targets are estimated using the average target for 2001-2004.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Not applicable

Table 4: Estimated number of doses of pentavalent  vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007 (not applicable)

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Not applicable

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| a) The percentage of children by the age of one year who have received one dose of BCG and three doses of OPV and pentavalent vaccines. b) Percentage of children at 12 months who are vaccinated against MMR/Yellow Fever c) Zero Prevalence of vaccine preventable | BCG- 95% OPV-90% Pentavalent -90% MMR and Yellow Fever -90% Zero cases of vaccine preventable | For 2004, 94% of children received BCG by age one and three doses of OPV, 91%, Pentavalent 91% by age of one. The targets for OPV and pentavlent were achieved. For 2004, MMR coverage was 88.4% and the YF was 89% No cases of polio, tetanus, diphtheria, measles or yellow fever. | Even though the national coverage is high, regional inequities exist , especially in the hinterland areas. This was a stock out of MMR for the last quarter in 2004, because of cold storage delay in shipment from the provider. | To have at least 95% coverage in BCG and for the rest of antigens 93%. To have at least 95% coverage in MMR and Yellow Fever. No case of vaccine preventable disease reported |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | May 2005 |  |
| Reporting Period (consistent with previous calendar year) | Jan-Dec 2004 |  |
| Table 1 filled-in | NA |  |
| DQA reported on | NA |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | NA |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | NA |  |
| Revised request for injection safety completed (where applicable) | NA |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

We the members of the ICC will strive to assist the EPI programme in Guyana by technical and financial support.

7.	Signatures

For the Government of ………Guyana………..…………………………………

Signature:	……………………………………………...……………...

Minister  of  Health

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Dr Rudolph Cummings | Chief Medical Officer, Ministry of Health |  | Mr Mohamed Hamid | National Officer, Health UNICEF |  |
| Dr Janice Woolford | Maternal and Child Health Officer, EPI Manager, MOH |  | Mr Murray Kam | CIDA |  |
| Mr Aubrey Williams | Planning Department, MOH |  | Mr Fritz Mc Lean | Rotary International |  |
| Dr Bernadette Theodore Gandi | PAHO/WHO Representative, Guyana |  |  |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

√

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes