January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Uzbekistan

Date of submission: May, 15 2005…………………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( + Fourth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. Fifth annual progress report ( *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

Since DTP 3 coverage is more than 95%, no ISS funds were allocated to Uzbekistan

## Immunization Services Support (ISS)

N\A

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

N\A

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _____N\A________

Remaining funds (carry over) from 2003 __________N\A______

Table 1: Use of funds during 2004

N\A

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH…October..           YEAR……2001….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Vaccination schedule for hepatitis B according to the National Immunization Schedule: 0-2-6 Months

Vaccines, syringes, and safety boxes were provided through GAVI according to the schedule of supply

Vaccine for Hepatitis B Vaccine Date Quantity Cost Feb 03 2004 446800 doses 120636,0 USD May 18 2004 257200 doses 72744,0 USD Aug 10 2004 257200 doses 72744,0 USD Nov 08 2004 257400 doses 69498,0 USD TOTAL 1218600 doses 335622,0 USD AD syringes Date Quantity Cost March 05, 2004 840800 44562,4 USD Sept 19, 2004 206500 14159,39 USD TOTAL 1047300 58721,79 USD Safety boxes Date Quality Cost April 10 2004 9350 7667,0 USD Sept 19 2004 2350 1186,62 USD TOTAL 11700 8853,62 USD

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

1.On the basis of order of Ministry of Finance of Uzbekistan Nr 114 dated November 21 2003 on allocation funds for special expenses item Nr 01841, from the State Republican Budget for EPI central vaccines procurement 955 000 USD were allocated. DTP, polio, measles vaccine were procured through UNICEF, BCG through “Uzbiofarm”, vaccine against mumps through”Úzmedexport”. Problem- mechanism of state vaccine procurrement not fully implemented. 2. Based on MoU with UNICEF major part of vaccines was procured through UNICEF 3. In all districts introduction of new vaccination schedule workshop and monitoring on it’s implementation was carried out (Order of MoH Nr494 dated November12 2003)(Measles 1-12 months,Measles2- 6 ears,HepB1- first 24 hours after birth, HepB2-2 months, HepB3-6 months) 4. On the basis of MoH order Nr216 dated May17 2004, monitoring on AEFI was conducted in 6 oblasts. Two day workshops were also conducted in these oblasts. Monitoring and workshop were conducted with the support of UNICEF. 5. During monitoring more than 3000 vaccination points in polyclinics, rural ambulatory points, maternity hospitals, central district hospitals and central district polyclinics were covered. 6. WHO\UNICEF mission was carried out July10-20 to assess AEFI surveillance system, a few districts were observed and final report on AEFI surveillance was presented. Experts highly appreciated AEFI surveillance activities. 7. With the support of UNICEF in 6 oblasts certification of regional, district EPI managers was carried out and more than 5000 vaccinators have been certified (MoH prikaz Nr 33 dated January,26 2004) 8. Implementation of ”VaccInfo”, computerized program for statistical analysis of immunization reports, is going on, with the support of UNICEF 9. Jointly with WHO\UNICEF a new form Nr6 on vaccination coverage has been developed and introduced. 10. National workshop on vaccination coverage , AEFI surveillance and introduction of new form Nr 6 was conducted with assistance of WHO\UNICEF (MoH prikaz Nr36, Nr 127 dated January, March 2005) 11. WHO\UNICEF Effective Vaccine Store Management assessment was carried out according to WHO’s 10 model standards. 12. Jointly with UNICEF training courses on safe practice of immunization for neonatologists, vaccinators of maternity hospitals have been conducted(366 neonatologists and vaccinators covered in total)(orderNr212 of the Ministry of Health dated March 9,2004) 13. Jointly with UNICEF training\certification courses for teachers of medical institutes, schools, colleges have been conducted. 14. Conducting training for medical facilities staff on safe immunization practice is planned to take place in 2005, however MoH encounters problem to finance this activity. 15. Jointly with WHO operational plan for measles\rubella SIA has been developed.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Allocated funds were used in 2002 year, information on it was presented in the previous reports

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

BCG syringes Date Quality Cost(USD) Jan 12, 2004 316500 22378,89 June 24, 2004 555900 35913,42 TOTAL 872400 58292,31 AD syringes Date Quantity Cost (USD) March, 03 2004 1132800 61171,20 March, 06 2004 1131600 61106,40 TOTAL 2264400 122277,6 Syringes for reconstitution of measles vaccine Date Quality Cost (USD) Jan 05 2004 22600 827,10 Apr 02, 2004 90600 3517,99 TOTAL 113200 4345,09 Safety boxes Date Quality Cost (USD) Jan 05, 2004 16525 12272,97 Apr 10, 2004 33050 27126,4 TOTAL 49575 39399,37 Syringes for reconstitution of BCG vaccine Date Quality Cost(USD) Jan 05,2004 14100 465,30 Apr 02, 2004 56600 1867,80 TOTAL 70700 2333,1 TOTAL RECEIVED 226647,47 USD Totally received support from GAVI is 226647, 47 USD for safe injection practice. (syringes, safety boxes)

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Problems: The construction of incinerators was not included into Government investment program of the MoH system, therefore this issue should be addressed for donors support Lack of funds to support SIS, donors has to be engaged to support AD syringes procurrement

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. Policy on injection safety and wastage utilization has been developed (MoH order Nr 107) and introduced in to the practice. | National policy on Immunization safety to be developed and realized in health care practice. To engage donors to support incinerators construction. | Order of MoH Nr107was issued on wastage utilization. Utilization of wastages provided through: burning in the incinerators, burning on the open air at the special places | Recourses limitation to realize order Nr 107completely in: -Construction of incinerators -Provision of AD syringes for children older than 1 year -Management of wastage utilization | To engage donor’s to support AD syringes procurement |
| To construct incinerators in the Central Rayon Hospitals | To continue construction on National budget funds: - appeal for donors’ support |  | This point was not included into investment program of construction | Negotiations with the government of France on the waste management project are going on. |
| 3. To develop methodical recommendations on safe immunization practice for vaccinators. | To provide 12000 vaccinators with methodical recommendations. | To make 12000 copies and introduce into practice(with the UNICEF support) | NO | To introduce new methodological recommendation based on WHO’s module “’Immunization in Practice”’ |
| 4. To train doctors and nurses on safe immunization practice and wastage disposal | With the support of UNICEF to conduct certification\attestation on safe immunization practice of all vaccinators, with providing certificates allowing performing their duties. To certify EPI personnel ( EPI managers and vaccinators of national, oblast and district levels) | Doctors-members of attestation committee have been certified, (Order Nr33 dated January,26 of 2004) 18 National level, 300 oblast level specialists and 5000 vaccinators have been certified as well, with the support of UNICEF. | Lack of funds to cover all oblasts of republic | To continue certification in the rest 8 oblasts of Uzbekistan with UNICEF support. |
| 5. To provide all vaccination rooms with equipment, needed for safe immunization practice. | In total 6 600 vaccination rooms are fully equipped | All vaccination rooms are equipped (100%) |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No funds recieved

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …HepB monovalent… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2001..** | 2002.. | 2003.. | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. |
| A: Proportion funded by GAVI/VF (%)*** | 50 | 100 | 100 | 100 | 100 | 50 |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  | 0 |  |  |  |  |
| C: Total funding for …………. (new vaccine) | 50 | 100 | 100 | 100 | 100 | 50 |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

Due to complete financing of EPI vaccines procurement from the State budget, some problems occur with the procurement of vaccine for Hep B. The Republic of Uzbekistan asks for your support to prolong support of Hep B vaccines supply from the second half of 2006 till 2010 under the offered scheme of co-funding.

| Proportion of vaccines supported by * | Annual proportion of vaccines |
| --- | --- |
|  | 2001..** | 2002.. | 2003.. | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. |
| A: Proportion funded by GAVI/VF (%)*** | 50 | 100 | 100 | 100 | 100 | 85 | 70 | 50 | 25 | 0 |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  | 15 | 30 | 50 | 75 | 100 |
| C: Total funding for …………. (new vaccine) | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Special budget line was given for centralized procurement of EPI vaccines. | Order of Ministry of Finance Nr 114 dated November 21, 2003 was issued on giving special budget line for centralized vaccine procurement | Ministry of Finance allocated budget for 995 000 USD | Amount allocated is not sufficient for EPI program running | 0 | 955 000 USD | To achieve complete financing of EPI program |
| 2. Conducting of regular monitoring of cold chain and providing of its uninterrupted work. | Mechanism, conducting cold chain monitoring developed | Conducting of cold chain monitoring and assessing the results based on WHO ‘s standards | Funds has not been allocated yet for financing of cold chain equipment procurement | 0 | Two assessments have been conducted: Provision of cold chain equipment of all medical facilities Effective Vaccine Management of primary Store. | 1. To assess store management system in oblast and rayon levels on the basis of EVSM assessment. 2. To purchase generator for central vaccine store. |
| 3. To strengthen knowledge and skills of EPI personnel | A number of orders have been issued to conduct trainings for doctors and vaccinators | A number of workshops and training have been conducted to certify national, oblast and district level staff | Lack of funds to cover all oblasts of republic | 35% | 48% has been covered | To conduct promotion of qualification courses for oblast EPI managers once a year at the National level. |
| 4.Improning of EPI management system | Reporting system has been improved | State form on immunization reporting developed and approved | Lack of computers on rayon (district) level | 53 % provision by computers | On oblast level computers provided by 100% with the integration of new program “VaccInfo’’ for statistical analysis | Improvement of information system |
| 5. Providing qualified and efficient immunization. | Integration of active epidemiological surveillance with timely coverage | Systematically analysis on immunization services | Problem of staff, recourses, conditions |  | Reformation of health care system is going on | Improvement of immunization practice. |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 520292 | 520292 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 | 515000 |
| Infants’ deaths | 8218 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 |
| Surviving infants | 516075 | 516075 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 | 508000 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 511430 | 511430 | 504440 | 504440 | 504440 | 504440 | 504440 | 504440 | 504440 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 510406 | 510406 | 499364 | 499364 | 499364 | 499364 | 499364 | 499364 | 499364 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 516891 | 516891 | 516891 | 516891 | 516891 | 516891 | 516891 | 516891 | 516891 |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | 512085 | 512085 | 512085 | 512085 | 512085 | 512085 | 512085 | 512085 | 512085 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 513915 | 515000 | 515000 | 507000 | 507000 | 507000 | 507000 | 507000 | 507000 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 361023 | 508334 | 508334 | 504000 | 504000 | 504000 | 504000 | 504000 | 504000 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

According to table of vaccine forecast for 2005, presented to supply division of UNICEF 1 833 178 doses of Hep B, 1. 697.900 pieces of AD syringes, 18.850 pieces of safety boxes have been ordered. Requested total amount of funds from GAVI-634.000 USD

Table 4: Estimated number of doses of Hep B…… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

|  |  |  | 2006 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of ………… (new vaccine |  | 516891 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 85% |
| C | Number of doses per child |  | 3 |
| D | Number of doses | A x B/100 x C | 1318080 |
| E | Estimated wastage factor | (см. табл. 3) | 1,18 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 1555330 |
| G | Vaccines buffer stock | F x 0.25 | 388830 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | 243 630 |
| I | Total vaccine doses requested | F + G - H | 1700530 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | ( D + G – H ) x 1,11 | 1624240 |
| L | Reconstitution syringes(+10% wastage) | I / J x 1,11 | 0 |
| M | Total safety boxes (+10% of extra need) | ( K + L) / 100 x 1,11 | 18030 |

The Republic of Uzbekistan asks for your support to prolong support of Hep B vaccines supply from the second half of 2006 till 2010 under the offered scheme of co-funding.

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. To improve the quality of Hep B vaccination management at all administrative levels | 1. Ppercentage of timely reports submission on immunization. 2. Coverage with each doses of vaccine HepB V1 HepB V2 HepB V3 | 100 % 99,0 % 99,0 % 98,9 % | Unsuccessful use of the unified software “Vaccinfo” for database collection and analysis of Immunization services in some regions | To improve software of database collection and analysis |
| 2. Quality control of provided Hep B vaccine вакцины | use of temperature monitoring cards 2. VVM | 100 % 100 % | Absence of freezing watch cards | To follow up this indicator constantly Request GAVI to support provision of freezing watch cards |
| 3. To improve waste disposal and safe immunization practices | To train doctors and nurses on safe immunization practice and wastage disposal | Doctors-members of attestation committee have been certified, (Order Nr33 dated January,26 of 2004) 18 National level(43%), 300 oblast level(43%) specialists and 5000 vaccinators(42%) have been certified as well, with the support of UNICEF | Lack of funds to cover all oblasts of republic | To continue certification in the rest 8 oblasts of Uzbekistan with UNICEF support |
| 4. To improve AEFI surveillance system. | Monitoring on AEFI surveillance Trainings on AEFI surveillance for EPI managers for all oblasts of republic | A National training on AEFI surveillance and new form Nr 6 introduction was conducted for national and regional level EPI managers and chief pediatricians. In 6 oblasts AEFI training for district level staff is going on. AEFI surveillance system has improved significantly. | Incompleteness of training in the 8 regional(oblas’s) rayons | To continue monitoring and training on AEFI |
| 5. Annual report on State financing of immunization services | Government allotment in to financing of EPI vaccines procurement | The Government has shown its commitment in self-financing of EPI vaccines procurement (100 %) A special budget line was given 0.1841 for vaccine procurement for children under 2 years | Centralization of funds assigned for vaccine procurement | To improve mechanism of vaccine procurement |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | May 6, 2005 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | ( |  |
| DQA reported on | N\A |  |
| Reported on use of 100,000 US$ | ( |  |
| Injection Safety Reported on | ( |  |
| FSP Reported on (progress against country FSP indicators) | ( |  |
| Table 2 filled-in | ( |  |
| New Vaccine Request completed | ( |  |
| Revised request for injection safety completed (where applicable) | N¦A |  |
| ICC minutes attached to the report | ( |  |
| Government signatures | ( |  |
| ICC endorsed | ( |  |

6.  	Comments

ICC/RWG comments:

# Text boxes

Partnering with The Vaccine Fund

((

Partnering with The Vaccine Fund

((