January 2005 (revised)

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Republic of Moldova

Date of submission: ……13.05.2006…………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)    NOT APPLICABLE

#### 1.1.1	Management of ISS Funds              NOT APPLICABLE

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support   NOT APPLICABLE

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 _______________

Remaining funds (carry over) from 2004 ________________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country) NOT APPLICABLE

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:            MONTH: SEPTEMBER           YEAR…2002………………..

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

FOR YEAR 2005 Date(s) of receipt of vaccines: 06 and 13.04.2005 – 131,620 doses Date(s) of receipt of syringes: 29.12.2004 – 74,400 units Date(s) of receipt of safety boxes: 29.12.2004 – 825 units Moldova's has introduced the universal immunization of newborns against Viral Hepatitis B (VHB) in 1995. Since 1998 procurement of HepB vaccines and syringes was ensured from financial funds made available by the Government of Japan/ JICA under a five year (1998-2003) Multi-bi Agreement. Rapid achievement and maintenance of high immunization coverage in the subsequent birth-cohorts resulted in a reduction of acute clinical VHB cases in children under seven years of age by more than 97% (See Appendixes 1 & 2). The hepatitis B vaccine provided by GAVI came to further support immunization against Hepatitis. During first eight months of 2002 immunization was conducted with vaccines provided previously by JICA for immunization of high risk population (health workers, contacts with acute cases, drug users etc.) and syringes procured by the Government of Moldova. Thus, GAVI support ensured avoiding any shortage of vaccine and syringes, allowing for a smooth transition to GAVI-supported vaccines. Furthermore, it allowed for re-channelling of JICA funds toward strengthening the immunization services and fortification of cold chain at all levels (procurement of 15 autonomous power generators that have been installed in the national vaccine store and at regional level vaccine storages throughout the country, 235 refrigerators and spare parts, 400 vaccine carriers and thermometers, 3000 freeze indicators, a computerized Multilog temperature monitoring system for the national vaccine, spare parts for the national vaccine store cold rooms, 2 minibuses for supervision purposes, safety boxes to enforce injection safety). During 2004 with the JICA support there was implemented an immunization campaign against hepatitis B covering health workers. It allowed immunization of more that 23,000 health workers. In 2005 with the Health Investment Fund (World Bank) and UNICEF support there was conducted an immunization campaign against Hepatitis B covering 312,860 teenagers (13-17 years of age) achieving vaccination coverage over 90% in all country districts. During 2005 no problems were encountered in reception of the GAVI provided vaccines and supplies.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

a. Undertaken activities: Since Hepatitis B vaccine has been used in Moldova since 1995, the shift to vaccine provided by GAVI did not require specific activities related to its implementation. Nevertheless, activities to reinforce the National Immunization Program and the Multi-Year Plan of Action for Immunization 2002- 2007 were rather intensive. Activities can be clustered as follows: Training on Routine Immunization Practices: (1) With the support offered by the Health Investment Fund during 2005, 275 family doctors and 639 medical assistants were trained following the training programme launched in 2004. (2) A national training seminar was conducted in February 2005 prior to the launch the Hepatitis B immunization campaign for teenagers. It involved epidemiologists and primary health care managers from all country districts. Cold Chain: (1) The cold chain inventory was carried out at primary health care facilities throughout the country and registers of selected indicators of functioning were established at district and national level. (2) In order to ensure continuous electrical power supply, 13 autonomous power electrical generators 15kW were distributed and successfully installed in regional level stores of vaccines. (6) In December 2004 the Republic of Moldova's primary, national vaccine store in Chisinau has received recognition for meeting the WHO-UNICEF global criteria for effective vaccine store management. An external evaluation team announced, after completion of the assessment (6-10 December 2004), that Chisinau primary vaccine store has scored over 80% against required indicators: pre-shipment and arrival procedures, temperature control, sufficient storage capacity, standards of buildings, equipment and transport, effective maintenance, stock management, and vaccine distribution. Monitoring and Surveillance: (1) Software for monitoring vaccination coverage before the 1st birthday and vaccine stocks was developed and installed on computers in all country districts.. Case based surveillance was established for acute Hepatitis B in children, that include laboratory investigation and notification of each case to the national level. Social mobilization: (1)A national communication campaign addressing immunization against Hepatitis B of teenagers was implemented in February/October 2005 with assistance of UNICEF and Health investment Fund (World Bank). It included production and airing of TV/radio spots, posters (4000), leaflets (350000), vaccination certificates (400,000) and a scheme of TV but also institutional mobilization activities (meetings, memoranda, briefings) radio broadcasting with national multi-sectorial professionals. Laboratory support: (1) With the support from Health Investment Fund (World Bank) the national laboratory for surveillance of viral hepatitis was equipped with a new set of ELISA laboratory equipment, refrigeration/freezing units and other consumables to strengthen laboratory based surveillance.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The financial support (US$100,000) for the introduction of the new vaccine was received on 27 June 2002 at the Treasury account of the National Center of Preventive Medicine. The use of GAVI funds started in September 2003 and included the following activities approved by the MoH and ICC: Repairs at the national vaccine storage and installation of 2 backup autonomous power generators -$17,300, Procurement of computers for the national electronic surveillance system on vaccination coverage -$28,774 Refurbishment and equipment for the national Hib and measles laboratory . - $14,165 TOTAL used in 2003 -$60,239 Finalization of the refurbishment at the national vaccine store -$ 2,966 Procurement of computers for the national electronic surveillance system on vaccination coverage -$19,385 Finalization of the refurbishment of the national Hib and measles laboratory. -$ 5,658 Printing of vaccination coverage monitoring reports. -$ 863 TOTAL used in 2004 -$28,872 installation of autonomous power generators in 11 district level vaccine stores -$ 9,727 TOTAL used in 2005 -$ 9,727 The use of the remaining balance of funds ($1,162) is scheduled for 2006.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In 2005 Republic of Moldova has received two instalments of funds from the approved GAVI support for injection safety at the Treasury account of the National Center of Preventive Medicine: 1st instalment – 06 October 2005 ($32,000) 2nd instalment - 30 December 2005 ($29,000) Due to the late arrival of funds at the time required to proceed all formal procedures to allow use of funds, in 2005 no expenditures were made using GAVI funds for injection safety activities. Injection safety equipment to conduct vaccination in 2005 was procured using Government of Moldova funds.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

In December 2004 the Moldova’s National Policy and Plan of Action for Injection Safety was approved and granted GAVI support. One hundred percent of immunizations in Moldova are conducted using AD syringes. In order to monitor the use of safety boxes at the health facility level an indicator is included in the monthly vaccination reports (no. of used safety boxes per 100 of used syringes). To compare: in 2002 the indicator value was 0.73, in 2003 it reached the value of 0.86 and in 2004 it was 0.83, and in 2005 it was 0.87, which means that almost all immunization syringes were collected properly into safety boxes. During 2005 all syringes for routine immunizations were procured with funds provided by the Government. For 2006 GAVI injection safety funds are scheduled for the procurement of Safety boxes. The Government plans to take over the procurement of Safety boxes in 2007. The MoH continued to explore possibilities of local manufacturing of safety boxes. Interested companies were identified and a cost-effectiveness assessment of local production is under way. Alternative solutions, including recycling and melting of used syringes, are also under consideration.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 6.1. SIP implementation Proportion of health facilities having MOH documents on SIP and safe disposal of used injection equipment – targets: | 100% (2005) | 100 percent of districts have received the MoH documents |  |  |
| 6.2. Adequacy of syringe and needle supplies at health facility level: Proportion of primary health facilities (PHFs) using only ADs for vaccination of children and adults Proportion of PHFs adequately supplied with reconstitution disposable syringes: Proportion of PHFs with 1-month supply of ADs and reconstitution disposable syringes for immunization Syringe wastage factor (number of used syringes per number of individuals vaccinated with injectable antigens) Proportion of HFs adequately provided with single-use disposable syringes for any injections of inpatients and outpatients (except immunization) Proportion of PHFs with adequate quality and sterility of injection equipment (integrity of package, expiry date) – targets: | 100% (achieved, to be sustained) 95%(2005), 100% (2006) 100% (2005) (1.05 (achieved, to be sustained) 50% (2005), 70% (2006), 90% (2008), 100% (2009) 100% (2005) | 100% target sustained 100% 100% 1.02 >60% 100% |  |  |
| 6.3. Adequacy of used injection equipment disposal and safety of injection providers Proportion of PHFs, giving immunization and other injections at one and the same office, provided with adequate quantity of safety boxes (one safety box in use, and at least another one on stock) Safety boxes wastage factor (number of used SBs per number of 100 used syringes) Proportion of emergency rooms, manipulation rooms and other injection providing sites with adequate quantity of safety boxes (one safety box in use, and at least another one on stock): Proportion of HFs destructing used injection equipment in accordance with the National Policy on SIP: Proportion of HFs with presence of used syringes and needles in garbage, dumping areas or close to the health facility Proportion of HCWs practicing two-hands recapping of needles (established during supervision visits/assessments) | 80% (2005), 100% (2006) ( 0.8 (2005), (1.0 (2008) 50% (2005), 75% (2006), 90% (2007), 95% (2009), 100% (2010) 70% (2005), 80% (2007), 100% (2010) 0 % by 2005 20% (2005), 10% (2006), 0% (2007) | 70% 0.87 No data No data No data No data | Collection of such data requires conducting systematic surveys. No funds were available for 2005 Collection of such data requires conducting systematic surveys. No funds were available for 2005 Collection of such data requires conducting systematic surveys. No funds were available for 2005 Collection of such data requires conducting systematic surveys. No funds were available for 2005 |  |
| 6.4. Sterility of immunization injections Proportion of first level administrative units (rayons and municipalities) having introduced active surveillance of post-injection abscesses Proportion of immunization injections observed with following of aseptic injection technique (supervision reports, SIP assessment) | 50% (2005), 75% (2006), 100% (2007) 95% by 2005 | No data No data | Passive surveillance there is established. Implementation of the active surveillance is under discussion Collection of such data requires conducting systematic surveys. No funds were available for 2005 |  |
| 6.5. Immunization injection anatomic sites Proportion of vaccination injection given in the recommended anatomic site: | 90% (2006), 99% (2008), 100% (2010) | Not applicable |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

In 2005 Republic of Moldova has received two instalments of funds from the approved GAVI support for injection safety at the Treasury account of the National Center of Preventive Medicine: 1st instalment – 06 October 2005 ($32,000) 2nd instalment - 30 December 2005 ($29,000) Due to the late arrival of funds at the time required to proceed all formal procedures to allow use of funds, in 2005 no expenditures were made using GAVI funds for injection safety activities. Injection safety equipment to conduct vaccination in 2005 was procured using Government of Moldova funds.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Reaching financial sustainability of the Moldova NIP is of high priority for both the Ministry of Health and The Moldova Government. It is worth mentioning that before 1993 the Republic of Moldova was self sufficient in terms of NIP financing. The economic crisis and the civil war in the eastern region of the country (1993-1994) compromised governmental support to the NIP during the subsequent years. During the last decade a number of international agencies, including, WHO, UNICEF, Government of Japan/JICA, USAID, CDC, SOROS Foundation, and ECHO provided their financial and technical support to Moldova NIP. In 1999 the Government of Moldova, UNICEF Programme of Cooperation and the Government of Japan have signed a Multi-bi agreement for implementation of the a five year Project (1998-2003) on Assuring Sustainability of Immunization Programme of Moldova. According to the provisions of the agreement, the Government of Japan contributed a total of $1,474,963 for vaccines, syringes and cold chain procurement; UNICEF contributed annually with $50, 000 for training, logistics and monitoring purposes; and the Government of Moldova contributed a total of $1,232,589 in salaries, maintenance costs and medical supplies. During first years of the project SOROS foundation provided support for the creation of a national electronic surveillance system. The agreement followed a “phasing-in” approach, under which the Moldova Government was planned to undertake increasing responsibilities of financing of vaccine procurements while the Government of Japan gradually phased out. In 2004 the contribution of The Government of Moldova raised up to 85% of EPI vaccines and syringes. The dynamics of Governmental financing was rather slow during the mentioned years as illustrated by the numbers below: Year Allocated US$ 1999 $54,700 2000 $87,767 2001 $78,628 2002 $182,624 2003 $226,576 2004 $369,310 (covered 85% of expenditures) 2005 $359,542 (covered 87% of expenditures) 2006 $504,000 (budgeted) Moldova Government with the Partners support has prepared its Financial Sustainability Plan for the National Immunization Programme. It is incorporated in the new 5-year National Programme for Immunization 2006-2010. An outline of main strategies, activities, indicators and targets toward financial sustainability of the National Immunization programme is provided in the Appendix 3. Strengthening of surveillance system on infectious diseases, including VPD, is an issue of continuous attention and support from WHO Euro through Mid-Term Programme of cooperation. The ICC discuses the issue of financial sustainability on regular basis at its meetings and inform partners on progress, requested assistance and its implementation The Ministry of Health and Social Protection would like to welcome the December 2005 decision of the GAVI board to provide additional 2 years of subsidized financial support to countries with monovalent HepB support ending 2005 and 2006, that will amount for 150% of Moldova’s annual vaccine needs, which is equivalent to an additional one and half years of support for monovalent HepB. Moldova asks to spread out that support for 2007 and 2008 as mentioned in the Table 2.1

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Hepatitis B monovalent (2 dose vial) (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% | 90% | 60% | 0% | 0% | 0% |
| B: Proportion funded by the Government and other sources (%) | 0% | 0% | 0% | 0% | 0% | 10% | 40% | 100% | 100% | 100% |
| C: Total funding for Hepatitis B monovalent (2 dose vial) (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Ensuring priority financing for the NIP | Developing and adopting by the Government of Moldova the National Immunization Program for the years 2006-2010; approving budget for the Program | Program and its budget developed and approved |  |  |  |  |
|  | Developing budget requirement analysis (BRA) for the NIP to include it into the MOH budget | BRA for NIP developed and approved by MoH |  |  |  |  |
|  | Reviewing the NIP implementation and financing at the MOH Board meeting | Reviewed in September 2005 |  |  |  |  |
|  | Reviewing the NIP implementation and financing at the ICC Meeting | ICC meeting minutes available |  |  |  |  |
|  | Developing and submitting proposals (requests) to potential donor agencies specifying the NIP needs, existing financing gap, requested assistance and aid-utilization plan | Under consideration |  |  |  |  |
|  | Holding a join MOH and MHI Fund working group meeting to agree on the responsibilities and mechanisms for financing procurement of vaccines and injection supplies for the NIP | Agreement reached |  |  |  |  |
| 2. Analyzing feasibility of Hib-vaccine introduction into current routine immunisation schedule | Setting up a MOH working group to analyze feasibility of Hib-vaccine introduction. Identifying criteria. Conducting analysis. | Consultation undertaken | Decision postponed pending additional epidemiological and laboratory evidence as well as observing trends of vaccine prices |  |  | With the support from WHO Euro for 2007 is scheduled an extended review of Hib burden in Moldova to assist in decision making toward Hib implementation. |
|  | Provided positive decision is taken concerning Hib-vaccine introduction, prepare application to GAVI and other potential donor agencies to get financial assistance for the vaccine introduction | Postponed | To be fulfilled after the final decision is taken |  |  |  |
| 3. Assuring staff training and improving NIP staff incentives | Provide regular (at least once in 5 years) post-graduate training courses for Family Doctors and preventive care specialists | Achieve |  |  |  |  |
|  | Developing joint proposals by the MOH and the MHI Fund on how to improve staff motivation in family medicine and preventive care and link staff payment to immunization performance and target population immunity status | Achieved |  |  |  |  |
|  | Provide short-term immunization training courses (other than in 3.b) for Family Medicine and preventive care personnel based on the WHO courses “Immunization in practice ” and “Course for mid-level managers ” | No short term trainings conducted in 2005 | Lack of funds for short term training |  |  |  |
| 4. Assuring smooth cold chain functioning at the rayon and healthcare facility level to prevent vaccine wastage due to their improper storage and transportation | Conducting regular cold chain monitoring and inventory | Conducted |  |  |  |  |
|  | Developing protocols for providing immunization with non-functioning (or missing) cold chain equipment at the healthcare facility level | Included in training guidelines |  |  |  |  |
| 5. Achieving as low as possible vaccine wastage rate through improving vaccine presentation mix | Analyzing current vaccine wastage rates and deciding on the optimal presentation mix for every vaccine shipment | Systematically conducted |  |  |  |  |
| 6. Implementing activities foreseen by the National Injection Safety Plan in immunization for 2004-2010 | Conducting regular monitoring of activities foreseen by the injection safety plan | Conducted Monthly |  |  |  |  |
| 7. Improving epidemiologic surveillance system and laboratory control over vaccine-preventable diseases | Budgeting WHO-recommended activities in epidemiologic surveillance and laboratory control of VPDs into NIP budget | Conducted Annually |  |  |  |  |
| 8. Assuring financing for: - short-term training of immunization personnel - IEC and social mobilization, - monitoring and epidemiological surveillance | Setting up a working group consisting of representatives of the MOH and donor agencies (UNICEF, WHO, EU, etc.) to agree the list of activities that may be financed through the donors’ support | All issues discussed at the ICC |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 42,383 | 43,443 | 44,529 | 45,642 | 46,326 | 47,021 | 47,727 | 48,443 | 49,169 |
| Infants’ deaths | 522 | 478 | 490 | 502 | 510 | 517 | 525 | 533 | 541 |
| Surviving infants | 41,861 | 42,965 | 44,039 | 45,140 | 45,816 | 46,504 | 47,202 | 47,910 | 48,628 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 40,850^ | 42,105 | 43,158 | 44,237 | 44,900 | 45,574 | 46,258 | 46,951 | 47,656 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 40,617^ | 41,890 | 42,938 | 44,011 | 44,671 | 45,342 | 46,022 | 46,712 | 47,413 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Hepatitis B vaccine | 42,084 | 43,008 | 44,083 | 45,185 | 45,863 | 46,551 | 47,249 | 47,958 | 48,678 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of Hepatitis B vaccine | 41,171^ | 42,535 | 43,598 | 44,688 | 45,358 | 46,039 | 46,730 | 47,431 | 48,142 |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) | 2% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 40,264 | 41,270 | 42,302 |  |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 41,266 | 43,008 | 44,083 |  |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 41,041^ | 42,105 | 43,158 |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

^    These figures represent children vaccinated by the first birthday (by 15 months of age for measles containing vaccine). They do not match the figures reported in the Joint

Reporting Form as the figures from the Joint reporting form are produced based on the birth cohort 12-23 months of age.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Denominators are changed taking into consideration the latest figures and trends of the birth rate and IMR. During 2001 and 2002 birth rates continued to decrease following the trend of the last 10 years. In 2003 there was observed a small increase (0.6%) of the birth rate comparing to the previous year. In 2004 the number of births has increased significantly (+6.3%) comparing to 2003. In 2005 the birth rate has decreased by 1.7% comparing to 2004. Denominator figures for 2006-2013 were updated in order to meet the latest demographical patterns and differ comparing to initial figures submitted in the application form and in previous annual reports. They include a projected annual increase of births by 2.5% for 2006-2009 and of 1.5% for 2010-2013. Vaccination coverage targets for 2006-2013 were updated in order to match projections of births.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of Hepatitis B vaccine, 2-dose vials… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6.1: Estimated supplies for safety of vaccination for the next two years with BCG vaccine

(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 6.2: Estimated supplies for safety of vaccination for the next two years with DTP vaccine

(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 6.3: Estimated supplies for safety of vaccination for the next two years with MMR (Measles containing vaccine)

(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 6.3: Estimated supplies for safety of vaccination for the next two years with Td* (Tetanus toxoid containing vaccine)

(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### *   According to the immunization schedule in Moldova all population receive Td  (Tetanus-Diphtheria for adults) vaccine at the age of 15, 20, 25, 30, 35, 40, 50 and 60 years. This immunization strategy allowed to eliminate neonatal tetanus many decades ago and to reduce tetanus cases amongst adults to solitaire cases over one or several years.  This is why pregnant women are not supposed to receive TT vaccine during pregnancy. The annual number of women receiving Td vaccine is estimated at 250,000. However, in order to comply to the GAVI policy the Ministry of Health of Moldova requires GAVI for the assistance based on current approved policy, using as a baseline the annual number of births and the standard 2 dose TT schedule. The balance of syringes and SB for Td vaccination that is not covered by GAVI will be ensured from the Governmental funds.

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Denominators are changed taking into consideration the latest figures and trends of the birth rate and IMR. During 2001 and 2002 birth rates continued to decrease following the trend of the last 10 years. In 2003 there was observed a small increase (0.6%) of the birth rate comparing to the previous year. In 2004 the number of births has increased significantly (+6.3%) comparing to 2003. In 2005 the birth rate has decreased by 1.7% comparing to 2004. Denominator figures for 2006-2013 were updated in order to meet the latest demographical patterns and differ comparing to initial figures submitted in the application form and in previous annual reports. They include a projected annual increase of births by 2.5% for 2006-2009 and of 1.5% for 2010-2013. Vaccination coverage targets for 2006-2013 were updated in order to match projections of births.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| HepB3 coverage | 98% | 99.0% | Not applicable | Not applicable |
| HepB drop-out <12 mo. | <5% | 2% | Not applicable | Not applicable |
| HepB wastage factor | <1.05 | 1.02 | Not applicable | Not applicable |
| Vaccine supply | No stock-outs of vaccine | There were no problems with vaccine supply in 2005 | Not applicable | Not applicable |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | YES |  |
| Reporting Period (consistent with previous calendar year) | YES |  |
| Table 1 filled-in | NO | Not applicable |
| DQA reported on | NO | Not applicable |
| Reported on use of 100,000 US$ | YES |  |
| Injection Safety Reported on | YES |  |
| FSP Reported on (progress against country FSP indicators) | YES |  |
| Table 2 filled-in | YES |  |
| New Vaccine Request completed | YES |  |
| Revised request for injection safety completed (where applicable) | YES |  |
| ICC minutes attached to the report | YES |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

No comments

7.	Signatures

For the:		Ministry of Health and Social Protection of the Republic of Moldova

Signature:   		Ion Ababii	……………………………………………...……………...

Title:		Minister of Health and Social Protection of the Republic of Moldova  ………………………………………….………………….

Date: 	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| The Ministry of Health and Social Protection | GOLOVIN Boris Deputy Minister |  | UNICEF Moldova | RAY VIRGILIO TORRES Representative |  |
| The National Centre of Preventive Medicine | BAHNAREL Ion General Director |  | WHO Liaison Office in the Republic of Moldova | URSU Pavel |  |
| The National Centre of Preventive Medicine | MELNIC Anatolie chief of the General Epidemiology department |  | National Company for health insurants | OSOIANU Iurie Deputy director |  |
| The Ministry of Financing | PEREBICOVSCHI Liuba, health sectors |  |  |  |  |

~ End ~

Appendix no.1

Appendix no. 2

Appendix no. 3 Republic of Moldova. Monitoring of vaccine coverage HepB3, DTP3, OPV3 of children under 12 month of birth, 2005

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2007: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Reported Vaccination coverage of children

(12-23 months of age)

with DTP3 and HepB3, Republic of Moldova, 1995-2004

Age specific Incidence of clinical acute Hepatitis B

among children 
Republic of Moldova, 1988-2004

Selective immunization of newborns

Age cohort has changed:

7-17 years Starting 2004

Universal immunization of newborns