May 2002

Partnering with The Vaccine Fund

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

By the Government of

Afghanistan

Date of submission: 16 October 2002 Reporting period: 2001 (previous calendar year) ( Tick only one ) : Inception report Yes  First annual progress report  Financial sustainability plan attached  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report 

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds 30 June 2002

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Considering the major political changes in Afghanistan, an ICC has been formed, which has already had its first formal meeting, strongly endorsing the GAVI support for the country.

#### 1.1.2	Statement on use of GAVI/The Vaccine Fund immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/The Vaccine Fund contribution.

Not Applicable

Please indicate the date(s) of the ICC meeting(s) when the allocation of funds was discussed :

Due to the unprecedented change in the political scenario in Afghanistan, it was considered appropriate to revisit the financial disbursement plan with the inclusion of the MoPH as a signatory.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

## YES                              NO

The plan of action has been discussed and endorsed by the ICC in the meeting of ………………………(Date).

Not Applicable

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines …………………..

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/The Vaccine Fund.

Not Applicable

#### 1.2.2	Major activities

Not Applicable

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Not Applicable

## Injection safety

#### 1.3.1	Receipt of injection safety support

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

Not Applicable

#### Progress of transition plan for safe injections and safe management of sharps waste.

Afghanistan has been using auto-destruct syringes for the past-------- years with safety disposal boxes. All the vaccinators received a refresher training in 2001, with a special emphasis on safety of injections and their safe disposal.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Not Applicable

# 2.  Financial sustainability

Inception Report:		Outline steps towards the development of a financial sustainability plan

First Annual Report: 	Submit completed financial sustainability plan

Subsequent Reports:	Summarize progress on financial sustainability

The Financial Sustainability Plan is a document that assesses the key financing challenges facing the national immunization program, and describes the government approach to mobilizing and effectively using financial resources to support medium- and long-term program objectives. The plan will be prepared by the Ministry of Public Heath & Population jointly with the Ministry of Finance, the Inter-Agency Coordinating Committee (ICC). The Financial Sustainability Plan will be including and focusing on self-sufficiency, mobilization of resources, reliabilty of resources and efficient use of resources.

# 3.	Request for new and under-used vaccines for year …………….. ( indicate forthcoming year )

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

|  |  |  |  | National Summary |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | REGION WISE IMMUNIZATION COVERAGE FOR CHILDREN UNDER ONE YEAR |  |  |  |  |  |

|  | Total | Target |  |  |  |  |  |  | Coverage January - December 2001 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REGION | Population | Population | BCG | % | OPV1 | % | OPV2 | % | OPV3 | % | DPT1 | % | DPT2 | % | DPT3 | % | Measles | % |
| Centeral | 5,570,847 | 222,834 | 120,411 | 54 | 115,442 | 52 | 118,089 | 53 | 104,406 | 47 | 117,478 | 53 | 117,515 | 53 | 99,218 | 45 | 97,679 | 44 |
| Eastern | 2,416,356 | 96,654 | 75,076 | 78 | 80,283 | 83 | 84,029 | 87 | 80,826 | 84 | 79,874 | 83 | 84,030 | 87 | 80,826 | 84 | 75,933 | 79 |
| Western | 2,607,547 | 104,302 | 68,180 | 65 | 66,237 | 64 | 57,880 | 55 | 50,750 | 49 | 66,255 | 64 | 57,906 | 56 | 50,779 | 49 | 53,931 | 52 |
| Northern | 3,332,497 | 133,300 | 68,438 | 51 | 70,391 | 53 | 71,146 | 53 | 57,142 | 43 | 57,142 | 43 | 69,381 | 52 | 56,492 | 42 | 57,070 | 43 |
| N. Eastern | 3,335,064 | 133,403 | 41,319 | 31 | 42,458 | 32 | 31,646 | 24 | 22,909 | 17 | 43,087 | 32 | 30,580 | 23 | 21,187 | 16 | 33,210 | 25 |
| Southern | 3,200,441 | 128,018 | 61,885 | 48 | 58,947 | 46 | 47,290 | 37 | 41,923 | 33 | 58,953 | 46 | 47,290 | 37 | 41,917 | 33 | 45,291 | 35 |
| S. Eastern | 2,393,688 | 94,973 | 59,319 | 62 | 66,532 | 70 | 62,158 | 65 | 52,383 | 55 | 66,293 | 70 | 62,386 | 66 | 52,574 | 55 | 54,078 | 57 |
|  | 22856440 | 913484 | 494628 | 54 | 500290 | 55 | 472238 | 52 | 410339 | 45 | 489082 | 54 | 469088 | 51 | 402993 | 44 | 417192 | 46 |

If the request for supply for the coming years differs from previously approved plan:

Please indicate the reasons for those changes and, where relevant, the related modifications of targets of children to be vaccinated, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and indicate the date of the ICC meeting when the changes were endorsed. The entire demography of Afghanistan is fast changing in the wake of the political changes initiated after 9/11 2001. An estimated 2 million Afghan refugees have returned back from Pakistan and Iran so far. Another million plus are expected to follow suit. This has changed the basic demographic data for the country.

3.2	Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for the year 2003 (indicate forthcoming year)

Table 2: Estimated number of doses of …… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  |  |  |  |  |  | Dated: 24.09.2002 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Vaccine Forecast for the Year 2003-2007 |  |  |  |  |  |  |
| Yearly Population Projections |  |  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
|  | Total Population |  | 25,000,000 | 25,600,000 | 26,214,400 | 26,843,546 | 27,487,791 | 28,147,498 |
|  | Under one (4% of pop) |  | 1,000,000 | 1,024,000 | 1,048,576 | 1,073,742 | 1,099,512 | 1,125,900 |
|  | Under 5 (22% of pop) |  | 5,500,000 | 5,632,000 | 5,767,168 | 5,905,580 | 6,047,314 | 6,192,449 |
|  | Preg. Women (5% of pop) |  | 1,250,000 | 1,280,000 | 1,310,720 | 1,342,177 | 1,374,390 | 1,407,375 |
|  | CBA Women (20% of pop.) |  | 5,000,000 | 5,120,000 | 5,242,880 | 5,368,709 | 5,497,558 | 5,629,500 |
| Total doses of vaccines required for EPI programme | BCG Doses |  | 1,500,000 | 1,536,000 | 1,572,864 | 1,610,613 | 1,649,267 | 1,688,850 |
|  | DPT Doses |  | 4,200,000 | 4,300,800 | 4,404,019 | 4,509,716 | 4,617,949 | 4,728,780 |
|  | OPV For Routine |  | 4,200,000 | 4,300,800 | 4,404,019 | 4,509,716 | 4,617,949 | 4,728,780 |
|  | OPV for NID/SNID |  | 34,375,000 | 35,200,000 | 36,044,800 |  |  |  |
|  | Measles For Routine |  | 1,500,000 | 1,536,000 | 1,572,864 | 1,610,613 | 1,649,267 | 1,688,850 |
|  | Measles For Campaign |  | 7,150,000 | 7,321,600 |  |  |  |  |
|  | TT For Routine(Preg. Only) |  | 3,500,000 | 3,584,000 | 3,670,016 | 3,758,096 | 3,848,291 | 3,940,650 |
|  | TT For SIAs (20% of CBAs) |  | 1,950,000 | 3,993,600 | 4,089,446 | 4,187,593 |  |  |
| Cost of vaccines as per 2003 price + 8% annual increase | BCG Vaccine |  |  | 98,703 | 109,566 | 120,893 | 133,591 | 147,741 |
|  | DPT Vaccine |  |  | 399,114 | 439,345 | 486,508 | 535,682 | 592,422 |
|  | OPV For Routine |  |  | 458,895 | 508,664 | 560,558 | 619,729 | 686,619 |
|  | OPV for NID/SNID |  |  | 3,333,264 | 3,683,238 | - | - | - |
|  | Measles For Routine |  |  | 217,129 | 240,271 | 266,234 | 295,186 | 327,299 |
|  | Measles For Campaign |  |  | 1,034,981 | - | - | - | - |
|  | TT For Routine(Preg. Only) |  |  | 164,434 | 182,033 | 200,382 | 219,507 | 244,320 |
|  | TT For SIAs (20% of CBAs) |  |  | 130,471 | 143,499 | 159,610 | - | - |
|  | Total Cost Of Vaccines |  |  | 5,836,992 | 5,306,615 | 1,794,184 | 1,803,694 | 1,998,400 |
| NOTES: |  |  |  |  |  |  |  |  |
| * Population projection made on the basis of 2.4% growth rate. |  |  |  |  |  |  |  |  |
| * Calculation made for 100% coverage including NID. |  |  |  |  |  |  |  |  |
| * Vaccine wastage factors:Routine EPI (BCG-50%, Measles-50%, DPT-40%, Polio-40%, TT-40%). |  |  |  |  |  |  |  |  |
| * Vaccine wastage factors: For SIAs (Poilo-25%, Measles-30% & TT-30%). |  |  |  |  |  |  |  |  |
| * TT vaccine calculation done on the basis of Pregnant women. Two doses for every preg.women. |  |  |  |  |  |  |  |  |
| In reality half of them will be eligible for one dose due to their previous TT shots. Remaining doses |  |  |  |  |  |  |  |  |
| will be utilised for non-pregnant CBAs. |  |  |  |  |  |  |  |  |
| * For TT SIAs: In 2003, 2004 & 2005 only 20% of the total CBAs are calculated as high risk population. |  |  |  |  |  |  |  |  |
| But each year different group will come under this 20% and they will be given 3 doses of TT. |  |  |  |  |  |  |  |  |

#### 3.3	Confirmed/revised request for injection safety support

(If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference).

Not Applicable

Table 4.1: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4.1 to 4.4)

# Signatures

For the Islamic Transitional Government of  Afghanistan

Signature:	……………………………………………...……………...

Title: Minister of Public Health

Date: 17 October

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/ Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| MOPH&P |  |  | WHO |  |  |
| MOPH&P |  |  | UNICEF |  |  |
| MOPH&P |  |  | JAPAN |  |  |
| MOPH&P |  |  | WORLD BANK |  |  |
| MoF |  |  |  |  |  |