Annual Progress Report 2006

Submitted by

The Government of

The People’s Republic of Bangladesh

to the

# Date of submission: 14 May 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of the People’s Republic of Bangladesh

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Secretary, MOH&FW | Title: Joint Secretary, MOF |
| Signature: | Signature: |
| Date: | Date: |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance. It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited & accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
|  | MOLGRD&C |  |  |
|  | DFID |  |  |
|  | BRAC |  |  |
|  | CIDA |  |  |
|  | Government of Japan |  |  |
|  | World Bank |  |  |
|  | Rotary International |  |  |
|  | UNICEF |  |  |
|  | USAID |  |  |
|  | WHO |  |  |

Signatures Page for HSS  (Not Applicable)

For the Government of ………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: | Title: |
| Signature: | Signature: |
| Date: | Date: |

We, the undersigned members of the National Health Sector Coordinating Committee … (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2. Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Support received from GAVI was reflected in the PIP of 2003-2006. It was shown as estimated Development Partners (DPs) support and the amount was USD 7 million. An amount of USD 1,389 million of DPs support is likely to be chanelised to the HNPSP of MOH&FW from 2005-2010 and the total amount shown from GAVI is 95.6 million USD as non-pooled support. This includes cash and in the form of kind support.

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Currently the Joint Secretary (PH & WHO) and the Program Manager, CH & LCC are the joint signatories of the account. Frequent changes of the signatories makes difficult of timely utilization of GAVI fund. The technical sub-committee prepares the annual budget and obtain approval from the ICC. To expend any approved budget including procurement and printing national EPI has to go through the existing Government procedure. This makes unnecessary delay of expenditure and even sometimes the planned activity has to be stopped. There are several approved activities which were planned in 2005 but could not be implemented due to Government lengthy system. The GAVI/VF is audited by FAFA in every financial year but there was no independent audit was carried out although it was decided in the ICC.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006:			3,182,046

Remaining funds (carry over) from 2005:	5,743,219

Balance to be carried over to 2007:		6,288,405

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 285,752 |  |  | 285,752 |  |
| Transportation | 37,663 | 831 |  | 36,832 |  |
| Maintenance and overheads | 297,475 | 20,631 |  | 276,844 |  |
| Training | 34,498 |  |  | 34,498 |  |
| IEC / social mobilization | 501,759 | 59,883 |  | 441,876 |  |
| Outreach | 143,630 |  |  | 143,630 |  |
| Supervision | 536,995 | 64,367 |  | 472,629 |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance | 12,031 |  |  | 12,031 |  |
| Vehicles | 670,407 |  |  | 670,407 |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) | 187,850 | 1,328 |  | 186,522 |  |
| Total: | 2,708,061 | 147,040 |  | 2,561,021 |  |
| Remaining funds for next year: | 6,288,405 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

- The second phase of the Measles campaign was done in February-March 2006 in rest of the country targeting around 33.5 million children aged 9 months to less than 10 years. This measles campaign is considered one of the largest campaigns in EPI ever conducted in the world. - A total of seventy30-cluster surveys were conducted in the year 2006. Out of which sixty four were conducted for District (one for each District) and six for City Corporations (one for each City Corporation). From the CES it was found that the crude coverage was 98% for BCG and DPT-1, 94% for DPT-3 and 89% for Measles. The number of fully vaccinated children was 89%. The valid coverage within one year of age for BCG was 98%, 84% for DPT-3 and 78% for Measles. The valid second dose of TT coverage was 94% among 15-49 years women. - The TT campaign was organized in the high risk areas in November 2006 targeting around 1.38 million women. A total number of 1.24 million women received any dose of TT according to their eligibility of TT five dose schedule. The campaign was organized in selected areas of 51 Districts. - Government of Bangladesh organized six rounds of national immunization day (4 rounds in 13th NID and 2 rounds in 14th NID) in 2006 as the response of importation of wild polio virus in March 2006. The plan is to organize another four rounds in 2007 (15th and 16th NID) and then 2 rounds per year till the region became polio free. - To reduce the vaccine wastage national EPI started piloting of 4 site strategy. Six Upazilas (one from each division) has been selected to pilot the strategy. In the four site strategy instead of 8 sub-blocks a ward will be divided into 4 sub-blocks. In each sub-block there will be one outreach session. Each site will operate once in a month. Therefore in each union there will be a total 12 sessions per month which was 24. - WHO in collaboration with National EPI conducted a vaccine wastage study in selected 80 Upazilas from 18 Districts. To reduce the vaccine wastage the same Upazilas were selected as sentinel site for monitoring of vaccine wastage which started from August 2006. It was planned that workshops will be organized in early 2007 to find out the factors contributing high and low vaccine wastage. The reasons for low vaccine wastage will be replicated to other intervention areas as well as in the whole country. - From the field observation it was found that occasionally cold sensitive vaccines became frozen during transportation from national to District, District to Upazila and also at the outreach site level. Based on these findings national EPI developed a guidebook to train around 700 personnel who is involved in vaccine handling. According to the new guideline chilled water packs will be used in the cold boxes for transportation of cold sensitive vaccines from national to District and District to Upazila level. For outreach sites conditioned ice pack will be used in the vaccine carrier. Out of 35 batches 28 batches already completed in 2006. - Provided additional financial support in the name of envelop budget from GAVI reward money to the field according to their micro-plan prepared based on RED strategy. Besides this fund was provided for supervision, contingency, vaccine and logistic carrying cost and reward money for best workers and supervisors. - National EPI provided support for renovation of EPI store at different level. This support was need based and GAVI reward money was used for this. - Based on the EVSM and VM recommendation a firm has been hired to implement the support to EPI program for development of logistics management system for ensuring uninterrupted supply of all logistics and ensuring effective vaccines and logistics information system. - A total number of 550 motorcycles was procured and supplied at Upazila, Municipality and City Corporation level for strengthening supervision - Training on financial management system was organized for all relevant personnel at different level for effective management of GAVI fund

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for 2008

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA?

The DQA was done in 2002 and 2003.

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

√

## If yes, please report on the degree of its implementation and attach the plan.

The plan of action was prepared based on the recommendation and shared in the previous Annual Progress Report. The issues were addressed accordingly and the DIMOs, SMOs and EPI Facilitators are regularly monitoring the implementation status of the recommendations.

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

WHO in collaboration with National EPI conducted a vaccine wastage study in 80 Upazilas. The same area has been selected for monitoring vaccine wastage as sentinel sites. The study started from August 2006 and will be continued for at least one year. The wastage is regularly monitoring by the DIMOs, SMOs and EPI Facilitators. According to national strategy in each ward there are 8 sessions per month per ward. A piloting has been started from January 2007 where 4 sessions are organizing instead of 8 sites per month to reduce the vaccine wastage. The DIMOs, SMOs and EPI Facilitators are regularly monitoring the effect of 4 sites on vaccine wastage. A coverage evaluation survey was conducted in 2006 following WHO 30-cluster sampling technique. A total number of 70 surveys were done in all sixty four Districts and six City Corporations. The unpublished data shows that the BCG coverage is 98%, DTP3 coverage is 84%, Measles coverage is 84% and the FIC by 2 year of age is 77% which is 71% by one year of age.

1.1.4. ICC meetings

How many times did the ICC meet in 2006? Four (4) Meetings. Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones?

Rotary International (National Polio Plus Committee)

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| Hepatitis-B | 10 dose | 2,512,400 | 10 April 2003 | 5 January |
| Hepatitis | 10 dose | 2,421,300 |  | 30 January |
| Hepatitis | 10 dose | 400,000 |  | 6 February |
| Hepatitis | 10 dose | 156,700 |  | 27 February |
| Hepatitis | 10 dose | 2,421,300 |  | 27 March |
| Hepatitis | 10 dose | 1,500,000 |  | 15 August |
| Hepatitis | 10 dose | 2,578,000 |  | 5 September |
| Hepatitis | 10 dose | 1,497,300 |  | 18 October |
| Hepatitis | 10 dose | 2,315,400 |  | 7 December |

Please report on any problems encountered.

There was no major problem in receiving Hepatitis-B vaccine through UNICEF supply division.

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Government of Bangladesh submitted the application for GAVI II support along with the cMYP for 2008-2010. In the application Government of Bangladesh requested for introduction of Hib (pentavalent single dose) vaccine in the routine immunization program. A countrywide training will be organized for all level of field staff if Bangladesh received the support for Hib vaccine. - The training on vaccine transportation will be completed in 2007 - Organization of quarterly multi-sectoral coordination meeting wiith participation from both Health and Family Planning Managers from District, City Corporation, NGOs and development partners - Preparation of micro-plan based on RED strategy for every Upazila, Zone, Municipality, District and City Corporation. The guideline will be reviewed and updated and will share with all concerned personnel. The yearly session plan will also be incorporated in the micro-plan. - Provision of additional financial support based on the micro-plan in the name of envelope budget. - Print and supply the wall chart for monitoring drop-out rate - Casualty assessment training for the AEFI focal persons at national level and for the AEFI investigation team at Upazila, District and City Corporation level. By using GAVI reward money national EPI is planning to organize AEFI refresher training for the field workers in the year 2007. - Training on DQA for all District Immunization Medical Officers (DIMOs) and Surveillance Medical Officers (SMOs) with assistance from WHO-Geneva and SEARO. - Organization four rounds of 15th and 16th National Immunization Day (NIDs). Vitamin-A and Anthelmintic will also be provided along with OPV. - Bangladesh is on the verge of NT elimination stage. Bangladesh is planning to conduct NT elimination validation study in second half of 2007 with the support from WHO/UNICEF HQ. - Introduction of Td vaccine and replace TT by Td

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on: November 2002

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The detailed expenditure of USD 100,000 for the introduction of the Hepatitis-B vaccine was mentioned in the previous reports.

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in 2004

Please summarize the major recommendations from the EVSM/VMA

According to the recommendation made by the EVSM assessment team the key areas to focus as first priority are as follows: - Make use of UNICEF recommended VAR for all vaccine arrivals with emphasis on all mandatory documentations. - Install continuous temperature recording system (computerised temperature monitoring and trace recorders) and acoustic alarms on all FR & CRs. - Install shelves in the new FR & CR to optimise storage space utilisation - Reorganise EPI store area. - Plan out vaccine arrivals to and dispatches from the primary store to overcome the space limitations there. - Regularly carry out physical stock verification, particularly for freeze dried vaccines /diluents and adjust stock records. - Introduce preventive maintenance procedures for building, equipment and vehicles - Replace ledger system by batch cards and computerized inventory for vaccine stock management. - Use freeze watch with every despatch of freeze sensitive vaccines. Implement recording of status of all temperature indicators during despatch and arrival of vaccines - . - The VM assessment team made the following recommendation and suggested for implementation as a priority: - Install stand by generators at district level - Install voltage regulators with every cold chain appliance - Improve stock recording system to include all vital parameters - Make use of batch cards in order to display contents of DFs & ILRs - Implement use of freeze indicators with every delivery & train the associate staff - Ensure that freeze dried vaccines are requisitioned, received, re-distributed and used with their matching diluents only - The Government should consider the possibility to apply MDVP in a pilot basis to reduce wastage - Establish a vaccine wastage monitoring system in order to reduce the currently rather high (1.5) wastage factor

Was an action plan prepared following the EVSM/VMA: Yes

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

- To address the recommendation, national EPI already increased the dry storage capacity and the expansion of cold storage capacity is under process. The extension of cold storage capacity will be completed by 2007. Use of UNICEF recommended VAR for all vaccine arrivals is established. National EPI already installed shelves in the new FR & CR to optimise storage space utilisation. MDVP introduced at fixed facility level. Established sentinel monitoring of vaccine wastage and will pilot 4 site strategy to reduce vaccine wastage. - Besides this a firm has been hired to support EPI program for development of logistics management system for ensuring uninterrupted supply of all logistics and ensuring effective vaccines and logistics information system. This includes: - Develop and install an effective Inventory Control System - Prepare an inventory of vaccines and other logistics at central, districts and upazila stores and improvement of warehousing - Set up an effective vaccine logistics management information system - Develop user friendly software for vaccines and logistics management system - Instillation an automated inventory control system - Capacity building of relevant staff-Provide training of relevant staff on use of software and automated inventory control system. Proper record keeping, reporting and data transfer. Calculation of vaccines and supplies - Prepare guideline and distribution/ transportation schedule of vaccines and logistics - Maintenance and back up support - Prepare report and submit to EPI

The next EVSM/VMA* will be conducted in: 2009

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| AD syringe 0.05 ml. (BCG) | 4,473,600 | March, June, October and December |
| AD syringe 0.5 ml. | 37,218,000 | March, June, October and December |
| Reconstitution syringe (BCG) | 4,473,600 | March, June, October and December |
| Reconstitution syringe (Measles) | 607,200 | March, June, October and December |
| Safety boxes | 474,300 | March, June, October and December |

Please report on any problems encountered.

There was no problem in receiving the injection safety support. Government of Bangladesh procured reconstitution syringe from the local syringe manufacturing companies to meet up the shortfall.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

The injection safety support from GAVI was for three years (2004-2006) which ended in 2006. With the help of WHO Government of Bangladesh explored the possibility of local production of AD syringes and a local syringe manufacturing company showed their interest. This company already started production of AD syringes and by this time national EPI procured AD syringe and safety box. This company has the capacity to supply required number of AD syringes for all routine EPI vaccines in the country.

#### Please report how sharps waste is being disposed of.

#### Currently there are two types of recommended practice for sharps waste disposal of routine EPI. The first one is incineration and the second one is open burning. The incineration is confined in the major urban areas where the incinerator is available and for most of the rural areas the choice is open burning.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

There was no major problem during the transitional period as because Government of Bangladesh completed all necessary procedures before the end of injection safety support from GAVI. A committee has been formed to finalize the national policy on sharps waste management. Before finalizing the national policy incineration and open burning is the choice for sharps waste management.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

Government of Bangladesh received the injection safety support from GAVI in the form of kind

# 2.	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines |  | 15,530,155 | 18,732,871 | 19,695,245 | 20,725,659 |
| Injection supplies |  | 2,552,287 | 3,169,842 | 3,361,284 | 3,549,003 |
| Personnel |  | 3,852,608 | 3,929,660 | 4,008,253 | 4,085,819 |
| Other operational expenditures |  | 33,056,727 | 23,661,429 | 23,250,618 | 33,458,795 |
| Cold Chain equipment |  | 362,770 | 392,918 | 426,016 | 447,317 |
| Vehicles |  | 412,115 | 291,722 | 306,308 | 316,263 |
| Other |  | 1,193,473 | 1,217,342 | 1,241,689 | 1,265,717 |
| Total Immunization Expenditures |  | 56,960,135 | 51,395,784 | 52,289,413 | 63,848,573 |
| Total Government Health Expenditures |  |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  |  |  |  |  |
| GAVI |  |  |  |  |  |
| UNICEF |  |  |  |  |  |
| WHO |  |  |  |  |  |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

It is difficult to specify the exact amount of financing source. For why the table completed in the GAVI II application is attached herewith for clarification.

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine (Hepatitis-B) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  | 50% | 60% | 70% |
| Total co-financing by country |  |  | 3,115,706 | 3,808,015 | 4,526,185 |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  | 3,115,706 | 3,808,015 | 4,526,185 |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  | 3,115,706 | 3,808,015 | 4,526,185 |

| Table 3b: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (Hib- Pentavalent one dose vial) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  | 3,116,427 | 2,539,264 | 2,586,990 |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  | 3,116,427 | 2,539,264 | 2,586,990 |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  | 3,116,427 | 2,539,264 | 2,586,990 |
| Table 3c: Country Vaccine Co-Financing in US$ |  |  |  |  |  |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  | Sources of Funds |  |
| Government Procurement- International Competitive Bidding |  |  |  |  |  |
| Government Procurement- Other |  |  |  |  |  |
| UNICEF | √ | All routine and campaign vaccines |  | IDA Pool fund, RPA and UNICEF |  |
| PAHO Revolving Fund |  |  |  |  |  |
| Donations |  |  |  |  |  |
| Other (specify) |  |  |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year |  | Delay in Co-Financing Payments |  |
|  | (month/year) | (day/month) |  | (days) |  |
| 1st Awarded Vaccine (specify) |  |  |  |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems? |  |  |  |  |  |
|  | Tick for Yes |  | List Relevant Vaccines |  |  |
| Budget line item for vaccine purchasing | Yes |  | All routine and campaign vaccines |  |  |
| National health sector plan | Yes |  | All routine and campaign vaccines |  |  |
| National health budget | Yes |  | All routine and campaign vaccines |  |  |
| Medium-term expenditure framework | Yes |  | All routine and campaign vaccines |  |  |
| SWAp | Yes |  | All routine and campaign vaccines |  |  |
| cMYP Cost & Financing Analysis | Yes |  | All routine and campaign vaccines |  |  |
| Annual immunization plan | Yes |  | All routine and campaign vaccines |  |  |
| Other |  |  |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing? |  |
| --- | --- |
| 1. | Not Applicable |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these? |  |
| 1. There will be not any challenges for co-financing |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There is no on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures from the WHO/UNICEF Joint Reporting Form

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 3,992,082 | 4,062,594 | 4,135,453 | 4,210,773 | 4,288,671 | 4,369,276 | 4,452,726 | 4,539,167 | 4,628,759 |
| Infants’ deaths | 259,485 | 264,069 | 268,804 | 273,700 | 278,764 | 284,003 | 289,427 | 295,046 | 300,869 |
| Surviving infants | 3,732,597 | 3,798,525 | 3,866,649 | 3,937,073 | 4,009,907 | 4,085,273 | 4,163,299 | 4,244,121 | 4,327,890 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 3,568,160 | 3,619,122 | 3,803,293 | 3,957,368 | 4,030,578 | 4,106,333 | 4,184,761 | 4,266,000 | 4.350,200 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 3,573,367 | 3,546,684 | 3,486,352 | 3,634,318 | 3,701,552 | 3,854,925 | 3,928,551 | 4,004,816 | 4,083,862 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of Hepatitis-B* | 2,888,735 | 3,615,165 | 3,803,293 | 3,957,368 | 4,030,578 | 4,106,333 | 4,184,761 | 4,266,000 | 4.350,200 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of Hepatitis-B | 2,319,200 | 3,566,628 | 3,486,352 | 3,634,318 | 3,701,552 | 3,854,925 | 3,928,551 | 4,004,816 | 4,083,862 |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) | 45% | 40% | 35% | 30% | 25% | 25% | 25% | 25% | 25% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 1,944,683 | 2,399,772 | 4,639,777 | 4,826,984 | 5,020,884 | 5,115,241 | 5,321,553 | 5,424,850 | 5,531,926 |
| Infants vaccinated / to be vaccinated with BCG | 3,609,535 | 3,659,951 | 4,094,098 | 4,168,665 | 4,245,784 | 4,325,583 | 4,408,199 | 4,493,775 | 4,582,471 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 3,528,007 | 3,480,917 | 3,170,652 | 3,307,141 | 3,448,520 | 3,676,746 | 3,746,969 | 3,819,709 | 3,895,101 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)  for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

There is no change for Hepatitis-B vaccine presentation.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6a.  Estimated number of doses of Hib vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 15,582,137 | 12,696,321 | 12,934,949 |
| Doses to be funded by GAVI |  |  |  |
| Doses to be funded by country |  |  |  |
| Country co-pay in US$/dose* | 0.20 | 0.20 | 0.20 |
| Total co-pay | 3,116,427 | 2,539,264 | 2,586,990 |

Table 6b.  Estimated number of doses of Hepatitis-B vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 21,783,017 | 20,193,196 | 20,572,728 |
| Doses to be funded by GAVI | 10,891,509 | 8,077,278 | 6,171,818 |
| Doses to be funded by country | 10,891,509 | 12,115,917 | 14,400,910 |
| Country co-pay in US$/dose* |  |  |  |
| Total co-pay | 3,505,505 | 3,741,119 | 4,603,642 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Government of Bangladesh awarded for injection safety support for three years which was ended in 2006. For that reason the table was not filled.

# 4.	Health Systems Strengthening (HSS)  (Not applicable)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in: _________________

Current Health Systems Support will end in: _____________

# Funds received in 2007: 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 14 May 2007 |  |
| Reporting Period (consistent with previous calendar year) | 2006 |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |
| ISS reported on |  |  |
| DQA reported on | NA |  |
| Reported on use of 100,000 US$ | NA |  |
| Injection Safety Reported on | NA |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached | Yes |  |
| Revised request for injection safety completed (where applicable) | NA |  |
| HSS reported on | NA |  |
| ICC minutes attached to the report | Yes |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report | NA |  |

6.	Comments

ICC/HSCC comments:

- The members of the ICC hope that the application for GAVI II support will be seriously considered by GAVI review committee and Government of Bangladesh will received the support for Hib vaccine in the form of single dose vial - The support for new vaccine (100,000 USD) is not sufficient enough for conducting training all over the country. Last time national EPI used the ISS money for the training of Hepatitis-B vaccine introduction. The support should not be same for every country rather this should be based on the country population and the staff strength. The ICC is requesting to review this issue. - The ICC is requesting to provide the support for injection safety equipment for Hib vaccine in the form of cash to promote the local AD syringe manufacturing company. - The ICC is requesting to get more support from the RWG in resolving some of the issues specifically the procurement.

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing