January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: BHUTAN

Date of submission: 15May 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not applicable

#### 1.1.2	Use of Immunization Services Support (No ISS fund provided ` to Bhutan)

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005

Remaining funds (carry over) from 2003

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Others …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO



## If yes, please report on the degree of its implementation.

Following the recommendation from the first training on Immunization data quality self assessment ( 18 district health supervisor officers, 2 data managers were trained), updated tally sheets and vaccine stock ledgers are being processed and will be supplied to the health centres by mid 2006.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

Injection Safety Assessment was conducted in 2005

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR:2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

DPT-Hep.B combination vaccine were received in good condition as per the dates and quantities stated below 1. DPT-Hep.B combination 5700 vials of 10 doses 2. DPT-Hep.B combination 700 vials of 10 doses

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

1.In September2005, a training workshop was conducted with support from WHO/UNICEF for the District Medical Offices on Screening and reporting of Congenital Rubella Syndrome (CRS ) a total of 19 Medical Office, 1 from Royal Institute of Health Science & 1 Medical Record Officer from JDWNRH, Thimphu have been trained. 2. Measles & Rubella campaign (MRC),guidelines for implementation of guidelines developed & advocacy & social mobilization activities were carryout 3. Joint International AFP Surveillance Review conducted from 22-31 October 2005 in 13 Districts. 4 Enchaining quality of existing supervision system and provision of regular feedback to health workers.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Reported in 2003 Progress Report

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Following injection safety were receipt in 2005 with good condition. - 5ML Syringes -4000 Nos. - AD Syringes 0.05 Ml -26,300 Nos. - AD Syringes = 0.5 Ml- 64,000 - BCG Reconstitute Syringes =26000 Nos. - Safety Box = 1250 Nos.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| A national Policy on injection safety in EPI (including) disposal of injection associated waste is prepared Introduction of AD Syringes Percentage of Health facilities with one or more incidence of syringes incidence of stock out of AD /or safety boxes in a quarter Percentage of Health facilities, disposing off injection associated waste according to given procedure (Minimum 75% in 2003 and 100% in 2004 | 2005 Dec.2003 | The injection safety policy is incorporated in the national EPI policy and is one of the core components in EPI mid level management training manual. All Mid Level manager health workers have been trained on it. AD Syringes introduced for all EPI vaccines No stock out reported All the health facilities provided with guideline on proper disposal of injection wastes. Infection Control program under Dept of Medical Services under process of developing standard guideline for the infection and waste management.. | Financial support for the refresher courses. No constraint faced while introducing the AD Syringes Monitoring visits to all the health centres to observe the safety disposal and stock is difficult due to shortage of Human resources & difficult geography Guidelines might not be followed due to non regular supervision & shortage of Human resource. |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

As per the GAVI requirement, Financial Sustainability plan was submitted in November 2004. The FSP has been approved. Strategies: 1. Mobilizing more resources through advocacy, Bhutan Health Trust Fund, strengthening partnership coordination mechanism. - Increasing efficiency of existing resources through facility based micro plan, waste reduction strategy, coverage target and forecasting, cold chain inventory and replacement plan, standard operation procedure for cold chain and vaccine management, improving monitoring and supervision. - Improving the reliability of resources.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003 | 2005 | 2006 | 2007 | 2008 | 2009 | 210 | 211 | 212 | 213 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  | 100% | 100% |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilizing more resource for BHTF | High level advocacy conducted | 18,846,978 US$ | Slow rate of mobilization of fund | 17,924,517 US$ | 18,846,978 US$ |  |
| Reduction in vaccine wastage: i) Improved stock management, ii) Introduction of a multi dose open vial policy, iii) Introduction of smaller vial sizes wherever possible | Open Vial Policy adopted in fixed clinic only i: e in basic Health Unit & hospitals only DTP-HepB combination being followed. Proposal for pentavial with 2 dose vial. | 29 hospitals & 176 BHUs practicing open vial policy. Penta vial vaccine is proposed with two dose vial. | Open vial Policy can not use beyond 28 days. High cost for smaller dose vial. Import all vaccines. | - Evidence of Vaccine Wastage rate brought down across the board to following levels by the end of 2007. BCG& Measles - 60%, T-Series Vaccines – 40% (10 dose vials) & 10% ( 2 dose vials), OPV-40% Decentralization. | - | To conduct pilot study for further utilization of open vial policy at Out reach Clinic vaccine that open during BHUs & hospital clinic. |
| Domestic resourcing for immunization services: i) Enhancing long-term RGoB commitment for EPI ii) Enhancing longer term government funding commitment to various new initiatives | Program working with Planning to create separate budget for EPI in RGoB budget from 10FYP. | Firm allocations made by BHTF for routine immunization services on a long term basis |  | Government health budget over the years increases by at least 10% in real terms per year. |  |  |
| Project grants from the existing pool of bilateral or multilateral agencies like JICA, UNICEF and explore newer donors. Additional resourcing from GAVI/ Vaccine Fund explored Development loans such as IDA credit from World Bank and ADB are explored - | Preparing for the GAVI 2nd phase support for the following components: Pentalvial dose for DTP-Hep-Hib b Measles and Rubella vaccine ISS HSS Bridge financing |  |  | Evidence of documentation from Ministry of Health (by 2006 end) made for exploring continuation of support from GAVI. |  |  |

# 3.Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |  | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 15058 | 15254 | 15452 | 15653 | 15857 | 16063 | 16272 |  | 16484 |
| Infants’ deaths | 40.1/1000 live births |  |  |  |  |  |  |  |  |
| Surviving infants | 14454 | 14642 | 14832 | 15025 | 15221 | 15419 | 15619 |  | 15823 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 14020 vaccinated | 14203 | 14387 | 14574 |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 13731 vaccinated | 13909 | 13668 | 13845 |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* Hep B | 14020 vaccinated | 14203 | 14387 | 14574 |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP-Hep B | 13731 vaccinated | 13909 | 13668 | 13845 |  |  |  |  |  |
| Wastage rate in 2005 and plan for 2005 beyond*** ………….. ( new vaccine) | 45% | 10% | 10% | 10% |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 14084 | 14261 | 14446 | 14634 |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 13435 | 13617 | 13794 | 13973 |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Despite the small size of the population, the number of facilities required to deliver services are relatively huge due to the dispersed and scanty distribution of community settlements. Immunization services are delivered through a network of 29 hospitals, 176 Basic Health Units, and 485 outreach clinics per month .Therefore, annually 5820 Outreach sessions are conducted. Given the tiny birth cohort, at any ORCs the number of new births appearing for the first contact is just around 3 or less. Further, till 2004, Bhutan was not seriously implementing the WHO multi-dose open vial policy. Consequently, vaccine wastage for all antigens has been high for Bhutan due to these unavoidable circumstances. This problem was highlighted by WHO staff visiting to assess HepB introduction progress in 2003 (Report submitted 2004 progress report). Following that, we have conducted training in vaccine management, focusing on the open vial policy and the reduction of wastage. However, even the implementation of open vial policy is unlikely to have a significant reduction on vaccine wastage as it is still difficult to implement open vial policy for outreach services; it is being implemented in fixed health facilities such as hospitals and BHUs. In order to minimise vaccine wastage, it will be most ideal if Bhutan can be supplied with 2-dose vile to be used both in outreach and in fixed clinics. The total DTP-Hep B requirement for the 2007 has been calculated using the wastage of 10 % (WR = 1.11) for 2 dose vial only. Due to high wastage pertaining to the 10 dose vial, Bhutan is requesting for 2 dose vial. Total resident population = 634982 (Source: Population and Housing census of Bhutan 2005) Population growth rate (natural increase) = 1.3 (Source: Population and Housing census of Bhutan 2005) Infant mortality rate = 40.1/1000 live birth (Source: Population and Housing census of Bhutan 2005) Wastage for 2 dose vial = 10 %

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Calculation for 2 dose vial of combined DTP-Hep B vaccine has been calculated using wastage factor of 1.11.

Copy of report sent to GAVI RWG, SEARO.

Table 4: Estimated number of doses of DTP-Hep B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fun

*Please report the same figure as in table 3.

Table 5: Wastage rates and facto

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remark

#### 3.3	Confirmed/revised request for injection safety support for the years 2007

Table 6: Estimated supplies for safety of vaccination for the next two years with DTP-Hep B vaccine (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | #### Formula | #### For 2008 | #### For 2009 |
| --- | --- | --- | --- | --- |
| #### A | #### Target if children for DTP-Hep B Vaccination | #### # | 14574 | 14841 |
| #### B | #### Number of doses per child | #### # | #### 3 | #### 3 |
| #### C | #### Number of DTP-Hep B vaccine doses | #### A x B | #### 43722 | #### 44523 |
| #### D | #### AD syringes (+10% wastage) | #### C x 1.11 | #### 48531 | #### 49420 |
| #### E | #### AD syringes buffer stock 2 | #### D x 0.25 |  |  |
| #### F | #### Total AD syringes | #### D + E | #### 48531 | #### 49420 |
| #### G | #### Number of doses per vial | #### # | #### 2 | #### 2 |
| #### H | #### Vaccine wastage factor 4 | #### Either 2 or 1.6 | #### 1.11 | #### 1.11 |
| #### I | #### Number of reconstitution syringes (+10% wastage)3 | #### Either 2 or 1.6 | #### 26935 | #### 27428 |
| #### J | #### Number of safety boxes (+10% of extra need) | #### (F + I) x1.11/100 | #### 837 | #### 853 |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Percentage of DMO & DHSOs trained on Mid Level Management Training - Percentage of Health workers trained on vaccine management | - District Medical Officers=15 - District Health Supervisory Officers= 22 - Health Assistant = 130 - Auxiliary Nurse Midwife(ANM=95 - Basic Health Workers= 171 - | - DMOs= 15 trained - DHSOs=22 trained - 19 Medical Officers trained on screnning of Congential Rubella Syndrom - HA= 198 trained - ANM=100 trained - BHW 168 trained | - All though all DMOs have been trained but few of them are on further studies. - EPI, National Services manual has to be updated for the incorporation of the revised changes and further all DMOs,& Health workers will be retrained. |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 13.5.2006 |  |
| Reporting Period (consistent with previous calendar year) | Jan.Dec.2005 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | - |  |
| Reported on use of 100,000 US$ | Filled |  |
| Injection Safety Reported on | - |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | - |  |
| ICC minutes attached to the report | - |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

Copy of the report sent to Regional Working Group, New Delh

7.	Signatures

For the Government of …………BHUTAN……..…………………………………

Signature:	……………………………………………...……………...

Title:	………Offtg. Secretary………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Secretary Chairman |  | Planning Commission Royal Government of Bhutan | Director |  |
| Ministry of Health | Director, Department of Public Health, Vice Chairman |  | Youth Guidance and Counselling Division | Program Officer |  |
| Ministry of Health | Deputy Secretary Policy & Planning Division |  | Bhutan Broad casting Service | General Manager |  |
| Ministry of Finance | Director General, Department of Debt. Aid & Management |  | World Health Organization Country Office | Representative |  |
| Bhutan Chamber of Commerce & Industry | Offtg. Secretary General |  | JICA/JOCV | Resident Representative |  |
| UNICEF, Country Office | Project Officer, Health & Nutrition. |  | District Representative | District Health Supervisory Officer |  |

~ End ~