January 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: CENTRAL AFRICAN REPUBLIC

Date of submission: 12 May 2006…………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ): Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report X Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (USD100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2007

  - Confirmed/revised request for injection safety support for the year 2007 (N/A)

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The mechanism for management of funds is documented in the GAVI guidelines concerning usage of funds ANNEX I ICC principal functions and responsibilities: (Ministerial decree no.0044 MSPP/CAB/SG/DGSPP/SPEV 7 February 2002) ANNEX II To co-ordinate the activities of the partners; To contribute to the examination and approval of routine EPI plans, National/Local Vaccination Days and integrated epidemiological monitoring of diseases; To mobilise the internal and external resources needed to implement activities; To oversee transparent and responsible management of resources while making, with the EPI team, regular audits of the use of programme resources; To encourage and sustain the exchange of information at the national operational level with the exterior; To oversee proper programme execution; To find ways and means to resolve the constraints likely to hinder the programme’s proper working. The ICC, through decree no. 113MSPP/CAB/SG/DGSPP/DMPM/SPEV 11 March 2003, set up its Technical under-committee which is a multi-sectoral and multi-disciplinary structure (ANNEX III) called the EPI Technical Support Committee (EPITSA), who’s job is to: Examine and approve the EPI operational action plans; Approve the budgets for implementation of these plans; Monitor execution of action plan activities Prepare technical dossiers for audits Produce periodic reports on the status of programme implementation; Propose to the ICC any action that might enhance programme performance Problems encountered in the use of GAVI funds in 2005 are the following: Delay in receiving ISS funds: these funds were received at end of the fourth quarter of 2005, which had a negative impact on the implementation of routine vaccination activities foreseen for the year; VAT charged at 19% on local purchases Proposed solutions: the programme recommends that the second tranche of funds for 2005 should be released immediately with the aim of implementing planned activities the Minister for Public Health and Population is negotiating with his counterpart in Finance and Budget with the aim of exempting local purchases made with GAVI funds from tax;

#### 1.1.2	Use of Immunization Services Support

In the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during year considered 111 400.00 USD

Remaining funds (carry over) from previous year 11 721.65 USD

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in USD | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation | 916.2 |  |  | 916.2 |  |
| Maintenance and overheads | 5 916.21 | 667.00 |  | 5 249.21 |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision | 808.60 |  |  | 808.60 |  |
| Monitoring and evaluation | 4 074.85 | 3 361.11 |  | 713.75 |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain paraffin |  |  |  |  |  |
| Paraffin packaging (barrels) |  |  |  |  |  |
| Total: | 11 715.87 | 4 028.11 |  | 7 687.76 |  |
| Remaining funds for next year: | 111 405.78 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Details of expenditure per level are annexed to this report

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

1. Activities already undertaken in 2005 Vaccine storage and conservation capacity at the central level were reinforced by the installation of four new cold chamber units meeting international standards: two positive units and two negative units Health district vaccination centres have been given more cold chain equipment (91 refrigerators; 148 freezers; 1750 giostyle vaccine carriers, 1000 ordinary vaccine carriers, 277 ice boxes, thermometers and refrigeration cards and 37000 litres of paraffin.) GAVI funds were used in the transport of equipment by hiring vehicle for the transport of this equipment. The country’s health district vaccination centres have had an intermittent supply of vaccines and injection safety equipment, thanks to GAVI support allowing vehicles to be serviced and fuel provided subject to fund availability; The supply of vaccines for routine vaccination, including injection equipment (auto-destruct syringes, dilution syringes and safety boxes) and other consumables; The technical capacity of 2 078 health workers and volunteers has been improved in the fields of injection safety, waste management, data collection and processing and proper handling of cases of PVARs during the two phases of the anti-measles vaccination campaign; Trained health workers were supervised during both the national anti-measles vaccination campaign and the polio SVAs. Informed families and communities participated actively in the mass anti-measles campaign and polio SVAs with a financial contribution from GAVI towards the funding of advocacy, social mobilisation and communication activities. 2. Main activities planned for 2006 GAVI funds will contribute to the implementation of the following activities planned for this year: Elaboration of district micro-plans following the “Reach Every District” approach; Regular and uninterrupted supplies to health districts of cold chain equipment, vaccines and other consumables; Improved geographical accessibility through the opening of new stationary centres and the allocation of motorcycle and bicycle vaccination units for outreach strategy implementation; Organisation of half-yearly and annual reviews of EPI activities bringing together district and regional foundation teams, and central level EPI managers; Continuing training of intermediate and district managers in the planning, management, monitoring and evaluation of EPI activities; Continuing training of vaccination agents in daily EPI management including vaccination safety Continuing dissemination of injection safety policies to all vaccination centres Development of a mechanism to ensure long-term programme funding Introduction of new vaccines to the EPI Elaboration of a communication and social mobilisation plan; Support for supplementary vaccination activities: MNT campaign and polio NIDs 3. These main activities are contained in the following documents: - Routine EPI strategic plan 2003 – 2007 (ANNEX IV) - Routine EPI action plan 2006 (ANNEX V) - Action plan to boost anti-yellow fever vaccination (ANNEX VI) - National injection safety policy (ANNEX VII) - National strategic plan for vaccination injection safety 2003-2007 (ANNEX VIII) - National strategic plan for the elimination of maternal and neonatal tetanus (MNT) in the Central African Republic (ANNEX IX) - Reduction of vaccine wastage plan CAR 2003-2007 (ANNEX X) 4. Problems encountered In summary, these are: 4.1 Programme funding The implementation of activities suffered due to the late arrival of GAVI funds for vaccination service support (end of 4th quarter 2005) The limited number of development partners to support the routine EPI The Government’s limited financial capacity after several politico-military crises does not allow for efficient EPI support despite its willingness to budget for the programme within its own spending. This limited State capacity also means insufficient funding is actually released for the EPI, even though these figure appear in its own spending. 4.2 Insufficiency of routine vaccination services rendered The quantity and quality of health workers are inadequate , which has a negative impact on the vaccination services rendered; Instability of health staff Staff are demotivated (irregular payments of salary) An obsolete vehicle fleet at all levels, resulting in multiple breakdowns and frequent repairs; Insufficient geographical coverage of vaccination units, despite the rehabilitation of vaccination centres and the replacement of obsolete cold chain equipment; The concentration of efforts on the organisation of five days of polio NIDs (vaccinating 700 000 children from 0 to 59 months per round) and two phases of a national anti-measles campaign covering 1 699 546 children aged 6 months to 14 years) did not allow the implementation of important routine vaccination activities according to the “Reach Every District” approach. 4.2 Constraints limiting better routine vaccination services Geographical inaccessibility of certain areas during the rainy season (Vakaga) Limited financial capabilities of communities to buy paraffin for cold chain operation through the medical establishment Management Committees Lack of security due to banditry in certain parts of the country, particularly in districts that account for almost half of the country’s vaccination centres.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Not Applicable (N/A)

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during the past year (for example, coverage surveys).

1. An assessment of the cold chain was made in 2005. The results of the assessment made it possible to draft a cold chain rehabilitation plan and organise a mass anti-measles campaign.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…FEBRUARY........           YEAR…1979*.......

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

In 2005, 92 700 doses of GAVI-supplied Anti-Amaril vaccine were received on 8 September 2005: lot Y5675-1, expiry date May 2007

*The year anti-yellow fever vaccination was introduced into the EPI in Central African Republic

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

| Activity type | Activities already implemented | Activities to be implemented |
| --- | --- | --- |
| Introduction of new vaccines and under-utilised vaccines | Regular and uninterrupted restocking of AAV vaccination services | Introduction of new vaccines, particularly those aiming to prevent haemophilus influenza and Hepatitis B from 2008 Continue to supply vaccination services with AAV vaccines |
| Vaccination services support | Dissemination of vaccination safety policy Cold chain assessment in the context of implementing anti-measles vaccination campaign activities; Supply of paraffin to vaccination centres; Contribution to the organisation of polio and measles SVAs 2005 | Drafting, implementation and monitoring of the execution of district micro-plans according to the “Reach Every District” approach; Improvement of geographical accessibility to EPI services through the creation of new centres and an increase in the number of outreach strategy teams; Re-training/training of intermediate and district managers in MLM; Re-training /training of vaccination workers in vaccination safety; Equipping health districts with vehicles for the supply, supervision, monitoring and assessment of activities |
| Injection safety support | Dissemination of injection safety policy; Training of 2 078 health workers during the national anti-measles campaign in injection safety; Supplying districts with injection safety equipment | Continue to disseminate injection safety policy Continue to train workers in vaccination safety Supplying districts with injection safety equipment Supervision and monitoring of activities; Negotiation with the Ministry of Finance and key EPI partners to put into place a strategy ensuring the purchase of injection safety equipment |

Problems and constraints encountered

- Insufficient integration of EPI services with the package of medical establishment activities: only 42.7% of the 786 public and private medical establishments have integrated EPI activities;

- Insufficient and obsolete transport logistics do not allow proper delivery, supervision, monitoring and even vaccination for mobile and outreach strategies in difficult-access areas;

- Concentration of efforts on the organisation of five days of polio NIDs and the first and second phases of a national anti-measles campaign) did not allow the implementation of important routine vaccination activities

- Demotivated personnel (irregular payment of salaries)

- No budget line to cover transport costs for injection safety equipment made available to the EPI Service by GAVI;

- VAT charged at 19% on local purchases is a burden on the budget allocated to the EPI service by GAVI;

- Instability of EPI trained health workers in their posts;

- Geographical inaccessibility of certain areas in the rainy season (Vakaga);

- Insecurity due to banditry in certain parts of the country;

- No activity related to new vaccines took place in 2005

- Insufficient organisation of outreach and mobile strategies at a district level;

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (USD100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 USD used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

N/A. Funds justified in the first annual progress report NB: date funds received 31 December 2003

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Quantities of injection safety equipment for 2005 awaiting delivery: BCG Auto-destruct syringes (0.05ml) = 129 000 units Other auto-destruct syringes (0.5ml) = 467 700 units BCG reconstitution syringes (2ml) = 13 000 units MEAS reconstitution syringes (5ml) = 15 000 units Safety boxes (5 litres) = 6950 units Problems encountered: Cargo Service pickup charges Proposed solutions: Despite the State’s treasury problems, the Government granted exemption from customs duties and paid cargo service pickup charges by using Public Treasury financial resources and even other financial sources, particularly medicine registration funds for which a mechanism for these funds to be used for the Extended Programme of Immunisation must be put into place.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Delay in finalising the Integrated Communication Plan; Insufficient supervision; Lack of local expertise for incinerator construction Delay in preparing media for data collection including handling of PVARs

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Increase capability at all levels of the health system for injection safety by end 2007 | % of EPI Centres with a national injection safety policy document (initial level = 0 in 2003 and 100% in 2007) | At least 80% (205 out of 308) of EPI Centres have a national injection safety policy document | Instability of health staff | Apply the national injection safety policy across the country by the end of 2007. |
|  | % of EPI Centres that have disseminated the national policy at staff level (initial level = 30% in 2003, final level =100% in 2005) | 100% of stationary centres with a national injection safety policy document have disseminated the policy to their staff in 2005 |  |  |
|  | % of EPI service agents trained in injection safety and injection waste management (initial level = 0%, final level = 100% in 2007) | 2 078 health workers were trained in vaccination safety during the anti-measles campaign |  | Strengthen injection safety capability at all levels of the health system by end 2007; 2006 objectives are as follows: Train 86 intermediate level managers (health regions) and districts in MLM ; Train 350 vaccination centre health workers in EPI management |
|  | Number of medical establishments allocated incinerators (initial level: 0, final level: at least 80% in 2007) | Activity did not take place | There is no local expertise for incinerator construction Absence of incinerators | Popularise a adapted strategy for the destruction of all vaccination centre waste |
| From now to 2007, 100% of vaccinal injections will be administered with auto-destruct syringes; | At least 75% of medical establishments using auto-destruct syringes; | At least 75% of EPI centres (231) in the 24 districts of the 7 regions regularly use this injection safety equipment; | Difficulties for the Government to ensure the availability of this equipment in a post-crisis context | By 2007, 100% of vaccinal injections will be administered with auto-destruct syringes by trained health workers NB: The Government is proposing to discuss with its development partners for bearing the cost of injection safety equipment. The Financial Sustainability Plan currently being finalised will specify the strategy in this area. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

54,000 USD for injection equipment and safety boxes in 2005

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine YELLOW FEVER……… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 75 | 50 | 25 | 25 | 25 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 25 | 50 | 75 | 75 | 75 | 100 | 100 |
| C: Total funding for yellow fever (new vaccine) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

(FSP being updated in the consolidated multi-annual plan)

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of |
| --- |
|  | 2004 | 2005 | 2006 | 2007 |
| DENOMINATORS |  |  |  |  |
| Births | 137 158 | 140 586 | 144 725 | 147 653 |
| Infants’ deaths | 17 913 | 18 557 | 19 104 | 19 490 |
| Surviving infants | 119 245 | 122 029 | 125 621 | 128 163 |
| Pregnant women | 156 752 | 160 671 | 165 400 | 168 747 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 86 531 | 77 958 | 94 216 | 115 347 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 59 307 | 55 634 | 80 398 | 96 122 |
| NEW VACCINES ** |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of AAV …......... (new vaccine) | 69 256 | 71 323 | 94 216 | 102 531 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…….… ( new vaccine) |  |  |  |  |
| Wastage rate in 2005 and plan for 2006 beyond*** AAV….. ( new vaccine) | 40% | 30% | 27% | 20% |
| INJECTION SAFETY**** |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 56 962 | 54 841 | 82 700 | 101 248 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 94 657 | 83 641 | 115 780 | 125 505 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 83 150 | 79 249 | 94 216 | 102 531 |

NB: demographic data for 2006 and 2007 take into account information from the General Population and Housing Census (GPHC) taken in 2003, the report of which was published in June 2005.

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

In 2005 the country achieved the following vaccination coverage: Antigen Vaccination coverage 2004 Vaccination coverage in 2005 BCG 69.01% 59.49% DTP3 49.73% 45.59% MEAS 69.73% 64.94% AAV 58.07% 58.45% TT2 and + for pregnant women 36.34% 34.13% Comparative analysis of vaccination coverage in 2004 and 2005 shows a general fall-off in program performance. This situation is due to the various problems and constraints outlined in the chapters on pages 11 to 14. For 2006, the Government has set the following targets for vaccination coverage in line with its second report (see sub-chapter 3.1 concerning updated targets for vaccination): BCG=80%, DTP=64%, AAV=75% and TT2+=50%. To achieve this, it is collaborating with its partners to take the necessary action to achieve the targets set for 2006. It will put particular emphasis on the application of the “Reach Every District” approach.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

N/A

Table 4: Estimated number of doses of AAV vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

N/A

#### Injection safety equipment funding after GAVI partner withdrawal.

As part of CAR/UNICEF bilateral co-operation and in line with its plan of action, UNICEF supplies vaccines and consumables to the Central African Republic The Government has included the purchase of EPI consumables including injection safety equipment in its investment budget With peace, political stability and the establishment of a democratic regime in CAR, the Government believes that several key EPI partners (notably Japan) will return for the purchase of this equipment. It also hopes that with an improvement in public finance management linked to the finalisation of its Strategic Framework for Action to Combat Poverty, the country can reach the point where it can be accepted for the HIPC initiative, the proceeds of which will serve to finance the EPI.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Targets | Indicators | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  |  | Outcomes | Effects |  |  |
| 1) To improve vaccination coverage in 2005 at the national level by at least: 75% for BCG; 50% for DTP3 and OPV3; 65% for MEAS and YF among children aged less than one year; 50% for TT2 + among pregnant women 2) To reduce drop-out rates between DTP1 and DTP3 from 46% to 30 % in 2005 | 1) % of vaccination services accessible, available and carrying out high-quality routine and supplementary activities (Initial level (IL) = to be determined and final level (FL) = at least 90%) | At least 60% of vaccination services are accessible, available and are carrying out high-quality activities | 1) Vaccination coverage: BCG 59.49% DTP3 45.49% MEAS 64.94% AAV 58.45% TT2 34.13% | • Poor integration of the EPI with the package of activities of the country’s medical establishments (only 43% of 786) • Concentration of efforts on implementation of polio and measles SVAs to the detriment of the Routine EPI • Delay in making the 1st tranche of GAVI funds available to support the vaccination service (end of 4th quarter of 2005) • Quantitative and qualitative shortcomings of vaccination service workers has had a negative impact on the vaccination services provided; • Insecurity due to the banditry in some parts of the country, particularly in the areas that account for almost half of the country’s vaccination centres; • The geographical inaccessibility of some areas during the rainy season(Vakaga) | • The targets below in the support request are maintained, viz.: Overall objective: To achieve vaccination coverage of 80% for BCG; 64 % for DTP3; 75% for AAV and 50% for TT2 + Specific objectives: To add more EPI stationary centres and put into place new outreach strategy teams; To intensify supervision of existing services at all levels; To train health workers in MLM for better programming, management, monitoring and assessment of field activities; To train vaccination centre workers in vaccination techniques, including injection safety techniques; To support the preparation, implementation and monitoring of the execution of district operational micro plans that take into account the catchment areas of the vaccination centres. |
|  | 2) % of stationary centres applying the injection safety policy (IL = at least 100% in 2005 and FL = 100%); | 100% of stationary centres are applying the injection safety policy |  |  |  |
|  | 3) % of vaccination services (central level, regions, districts and EPI centres) producing and using vaccination and surveillance data (IL= 60% in 2003 and FL=100% in 2007) | 50% of vaccination services are producing and using vaccination and surveillance data taking into account the degree of completeness of reports; | 2) Drop-out rate=29% |  |  |
|  | 4) % of vaccination services with better EPI logistics management (IL=30% in 2003 and FL=at least 80% in 2007) | 40% of vaccination services have improved logistics management; |  |  |  |
|  | 5) % of the populations informed about vaccination activities | At least 80% of the population knows about the EPI; |  |  |  |
|  | 6) % of vaccination services that are better monitored, assessed and financed at all levels (IL:TBD and FL:100% in 2007) | 30% of vaccination services are monitored, assessed and financed. |  |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | X |  |
| Table 1 filled-in | X |  |
| DQA reported on | n/a |  |
| Reported on use of 100,000 US$ | n/a |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) |  | Being updated, needs external technical support |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | n/a |  |
| ICC minutes attached to the report | n/a |  |
| Government signatures | X |  |
| ICC endorsed | X |  |

6.  	Comments

ICC/RWG comments:

The ICC: Thanks GAVI and at the same time congratulates it sincerely for its readiness to contribute to the survival and development of Central African children through its material and financial support to the Expanded Program of Immunization; Adopts and supports the Government’s request to GAVI and the Fund for support for vaccination services, new vaccines and injection safety. Notes with satisfaction that the Government of the CAR has included in its budget for the last few years a budget line for EPI expenditure that includes headings for “vaccine purchases and fuel” and welcomes the efforts made by the authorities of the country in support of child survival. Considers that despite the obvious political will of the authorities, the country is in a post-conflict situation and needs the resources required to relaunch the EPI, which is one of its priority health programs. GAVI funds therefore offer the country an OPPORTUNITY to improve vaccination coverage, implement the vaccination injection safety policy and introduce new vaccines. To that end, the immediate payment of the 2nd tranche, scheduled for September 2006, will enable the EPI of the Central-African Republic to meet its commitments in terms of results expected. Encourages the Government to meet its commitments as to implementation of the mechanisms intended to ensure the financial sustainability of the EPI. Undertakes to keep track of: - the implementation of activities in accordance with the multi-annual plan, - the management of GAVI funds and to contribute to the drafting of the management reports, and to mobilise partners and the community to improve the EPI.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date | Signature |
| --- | --- | --- | --- |
| Ministry of Public Health and the Population | Dr Bernard LALA |  |  |
| WHO | Pr. Léodégal BAZIRA Representative |  |  |
| UNICEF | Dr Joseph FOUMBI Representative |  |  |
| Ministry of Public Health and the Population | Dr Sunday NZIL’KOUE, Cabinet Director. |  |  |
| Ministry of Communication, National Reconciliation and the Culture of Peace | Mr Lucien YALIKI, mission officer, Democratic Culture |  |  |
| Ministry of the Interior responsible for Territorial Administration | Mr Bernard KPONGABA, Central Inspector of Territorial Administration |  |  |
| Ministry of the Family, Social Affairs and National Solidarity | Mr Antoine MBAGA Cabinet Director |  |  |
| Studies and Planning Office (MPHP) | Dr Philemon MBESSAN Director |  |  |
| Polio Plus /Rotary Club | Dr Prosper THIMOSSAT, Chairman |  |  |
| Central-African Red Cross | Mr Antoine MBAO BOGO, Chairman |  |  |
| UNICEF | Dr Lordfeld ACHU, EPI project administrator |  |  |
| UNICEF | Dr Eli RAMAMONJISOA, Survival Program officer |  |  |
| Ministry of Public Health and the Population | Dr David KILAYO, of Pharmacy and Medicines Director |  |  |
| UNICEF Health Program | Dr Eugène KPIZINGUI |  |  |
| WHO EPI | Dr Jean Moke KIPELA |  |  |
| WHO EPI | Dr Florentine Florentine YA’AH MBERYO |  |  |
| Office of Preventive Medicine and Action Combat Disease (MPHP) | Dr Régis MBARYDABA Director |  |  |
| Resources Office (MPHP) | Mr Faustin VOUMO Director |  |  |
| Community Health Office (MPHP) | Dr Jean Pierre BANGAMINGO |  |  |
| Expanded program of Immunization Service | Dr Régis MBARY-DABA Head of EPI Service |  |  |
| National IEC Service (MPHP) | Mr lévy ZATO |  |  |
| Financial and Costs Recovery Service | Mr YACKOTA Roger, Chief of Service |  |  |
| SOS Children’s Village | Dr Armand GADENGA, Director |  |  |
| UNICEF | Dr Emmanuel KITEZE , EPI Consultant |  |  |
| Ministry of Health | Dr. Louis NAMBOUA, General Office of Regional Services |  |  |
| Ministry of Health | Dr Patr ice FEILEMA, IMCI Coordinator |  |  |
| Ministry of Health | Mrs Jeannette MAMADOU, Administrative Assistant, GAVI Funds Manager |  |  |
| Ministry of Health | Dr B ernard BOUA, Director of Health Region N°1 |  |  |
| EPI Assessment Monitoring | Mr Antonio SATHE |  |  |
| CAR / EPI Logistics | Mr. Jerome KEIRO |  |  |
| EPI Supplies | Mr. Joseph KOSSALA |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes