January 2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: DEMOCRATIC REPUBLIC OF THE CONGO

Date of submission: ……11 May 2005……………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report x Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

In 2004 the management of ISS funds followed the main procedures set out below: Endorsement procedure The objectives, strategies, programme activities and the resources required were determined at MATADI during a workshop to prepare the Expanded Programme on Immunization (EPI) macro plan for 2004. Civil servants from the Ministry of Health and key figures from the EPI at partner level : WHO, UNICEF, USAID, ROTARY, SANRU, BASICS, CRS , participated in this workshop This macro plan was validated during the annual review of 2003 resulting inter alia in the signing of a memorandum of understanding that defines the context for collaboration between the Minister for Health and the partners. Micro plans were drawn up in all of the country’s health zones after a briefing organised by the EPI and the partners. The EPI needs were expressed for the operational level.161 of these health zones were selected for full application of the RED (Reach Every District) strategy. Payment procedure In March 2004 and June 2004 the plans for the use of GAVI funds were approved during meetings by the strategic ICC presided over by the Minister for Health. These plans were first examined within the ad hoc sub committees of the ICC technical committee. As in 2003 there was a great deal of activity in the GAVI fund bank account for centrally for the payment of planned expenses. All cheques and payment orders made to carry out the fund utilisation plan were signed by three people: for the Ministry of Health, the EPI director and the Head of the EPI Financial and Administrative Division and for the partners, the representative of the ICC partners other than the president, in this case the WHO representative. The advantage of this procedure is that it provides effective and transparent monitoring of GAVI funds by the ICC. Payments were made by bank transfer where possible. A separate account system for GAVI funds was held for the Extended Programme on Immunization using the 11 management tools provided for in the document on management mechanisms and its annexes signed in March 2003 by the Minister for Health and the partners (WHO, UNICEF, USAID and ROTARY). In total 3,082,323.04 $ were used as a GAVI fund contribution for EPI/DRC finance in 2004, distributed at three Programme execution levels as follows: operational level: 63%; intermediate level: 21% and central level: 16% as indicated in the table below. An increase in transportation logistics in terms of vehicles, motorbikes, bicycles, self-blocking syringes and other input at all levels coupled with staff motivation and, particularly, the implementation of the reach each health zone (REHZ) approach produced excellent results in 2004. Control procedure The EPI director presented at the ICC session his progress report on the activities of the Expanded Programme on Immunization for the technical section (activities carried out and results) and the financial section (amount budgeted, implemented and justified). The ICC financial sub-committee met in February 2004 to finalise the draft of the GAVI fund utilisation plan. The EPI organised missions to follow up and increase the capacity for applying financial management procedures for intermediate civil servants. In total 21 of the 36 units and 9 EPI provincial coordination systems benefited from financial supervision. It helped to increase their capacity and to improve the rate of documentary evidence for funds allocated to them. The 21 units are as follows: Bandundu, Kikwit, Inongo, Boma, Mbandaka, Gemena, Gbadolite, Lisala, Mbuji-Mayi, Mwene-Ditu, Kananga, Tshikapa, Lubumbashi, Kamina, Mbanza-Ngungu, Butembo, Bunia, Isiro, Kisangani, Goma and Bukavu. The financial management information procedure in process that covers all the aforementioned procedures will help improve the ability to trace financial flow. The above financial statement concerning the use of funds allocated to the EPI was prepared and presented in the present annual situation report to GAVI. MAIN PROBLEMS ENCOUNTERED 1. The level of dysfunction of the banking system in the country causes delays in fund transfer. 2. EPI input at a central level is transported to agencies and Health Zones (HZ) almost entirely by air (freight or charter), resulting in a high cost for distributing the input.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004      2 030 100 US $

Remaining funds (carry over) from 2003     1 129 497 US $

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | - | - | - |  |  |
| Injection supplies | - | - | - |  |  |
| Personnel | 414 866.31 | 161 803.72 | 253 062.52 |  |  |
| Transportation | 355 771.78 | - | - | 355 771.78 |  |
| Maintenance and overheads (*) | 861 396.60 | 110 997.48 | 109 862.95 | 640 536.17 |  |
| Training | 119 568.00 | 3 050.00 | 48 981.00 | 67 537.00 |  |
| IEC / social mobilization | 24 590.00 | - | 4 590.00 | 20 000.00 |  |
| Supervision | 226 365.07 | 52 108.00 | 32 200.00 | 142 057.07 |  |
| Monitoring and evaluation | 519 096.00 | 90 814.00 | 50 198.00 | 378 084.00 |  |
| Vehicles | 213 800.00 | 71 800.00 | 142 000.00 |  |  |
| Other/ advanced strategy | 339 750.00 | - | - | 339 750.00 |  |
| Bank charges | 10 820.00 | 10 820.00 | - | - |  |
| Total: | 3 086 023.76 | 501 393.20 | 640 894.54 | 1 943 736.02 |  |
| Remaining funds for next year: 73573.24 |  | 16 | 20.77 | 63 |  |

(*) institutional support

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

The implementation of the EPI macro plan in 2004 relied on the Reach Each Zone (RED) approach incorporating the 5 elements below, i.e.: Planning and management of resources involves the following, in particular: Preparing the micro plan in each health zone based on micro planning of health sites and population census; Making vaccines 100% available in all health zones by active distribution of vaccines and input; Expanding the introduction of AAV in all the health zones; Strengthening the cold chain by covering at least the requirements for the refrigerator spare parts; Re-launching the advanced immunization strategy to improve vaccinal cover and reduce drop-out rates. Providing health centres with bicycles and cash to achieve advanced immunization activities allowing access to villages situate more than 5 km from the Health Centre; Implementing appropriate strategies, according to local facts, to reach all targeted children with immunization services and other public health intervention systems (Integrated management of childhood illness (IMCI), vitamin A, inflammatory bowel disease (IBD), etc.) Increasing training supervision and staff capacity at different levels to improve support to health zones. Increasing EPI management capacity by training 6700 health agents (52 at central level, 60 at intermediate level and 6588 at operational level); Increasing training supervision from the central level to the provinces/ agencies, from the provincial level/ agency to the health zones every two months and from the health zone to the health centres every month; Increasing the links between the community and the health service to improve how the services are used; Providing the health centres and the community participation structures with educational support; Increasing civil responsibility to enhance the use of services in health zones; Implement a monitoring system to reduce drop-out rates. Monitoring of action to enhance use of data for taking adecision Organise ICC technical meetings at a provincial and district level once a month; Document the DTP and MEAS wastage rate; Apply the performance contract to health zones; Organise meetings midway between health zones at a District level; Organise validation meetings for immunization data in the health sites and central Offices of Health Zones. The following points were noted: Strong points Improving the availability of vaccines at an intermediate level (all the agencies) and Health Zones Making the data more complete Recovering the wastage by using the Community relay systems in RED health zones Producing the survey on injection safety Evaluation of the RED approach by an external team (WHO, AFRO/HQ) Government contribution to vaccine purchase for the routine EPI Improvement of the availability of oil at an operational level Weak points Slow production of reports Insufficient coordination meetings in the Province Poor intervention coordination by partners at intermediate and operational levels Insufficient finance from the Government and the Partners in the EPI routine Constraints Constant lack of safety in certain health zones Bad state of repair of the road network Absence of local providers for certain input (oil, cold chain consumables) Opportunities Presence of numerous partners in the health zones Finance for Heavily Indebted Poor County (PPTE) Lesson learned Effective application of the RED approach (with its 5 elements) enhances vaccinal coverage The availability of GAVI funds rapidly improves the availability of input and motivates staff as a result of the payment of a bonus

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

NOT APPLICABLE:

The DQA was implemented in DRC in January 2005. However, the chronogram anticipates that the plan of action to improve the reporting system based on recommendations from the DQA should be prepared in June 2005

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

NOT APPLICABLE

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Evaluation survey on injection safety in DRC Evaluation of the implementation of the ACD (RED) approach in the Democratic Republic of the Congo Quick evaluation of immunization services on the high drop-out rate

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

## NOT APPLICABLE:

AAV was introduced in 2003 into 97 Health Zones. In 2004 it was extended to the remaining Health Zones.

Start of vaccinations with the new and under-used vaccine:

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

NOT APPLICABLE

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

NOT APPLICABLE

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

NOT APPLICABLE

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

9 000 000 of the 12 000 000 syringes expected were received on 24 and 27 February 2004 and 1 March 2004 respectively PROBLEM ENCOUNTERED: Dilution syringes ran out at Management and agency level on the following dates: 17 August for 2 ml dilution syringes, 31 August for 5 ml dilution syringes and October 2004 for self-blocking syringes. However, the programme received the full quantity of syringes purchased with the GAVI fund. The problem is that the deliveries did not follow the bundling rule (SBS+dilution syringes+ boxes), adversely affecting redistribution in the country. Since delivery dates were not observed stocks ran out in certain areas.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

The first plan provided for replacement of multiple-use syringes by the SBS. During implementation, the programme distributed these self-blocking syringes to all structures at practically the same time. It should be noted that to date the boxes have hardly been used. The country does not have a national multi-sector destruction plan for biomedical waste. It is still difficult for the Programme to opt for an incinerator or other waste treatment material that could be easily disseminated and used on a grand scale. Holding a national workshop to prepare a waste destruction plan is a prerequisite.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| a) Availability indicators Number of Health Zones(HZ) with an injection safety policy document, which have ensured its dissemination at Staff level Number of Health Centres (HC) with operational incinerators built in 2004. Proportion of health agents trained in injection safety b) Use indicators Percentage of Health training schemes using the SBS for immunization No of HC using the incinerators correctly Proportion of Health Committee members active in monitoring and raising awareness of the Communities on Integrated Health (IH) Number of vaccinal post-injection abscess reported | 515 1000 50% 100% 1000 30% 0 | 437 0 30% 100% ND 25% 0 (*) | HZ not yet operational Absence of consensus on the incinerator type and make. Non-formation of the multi-sector management waste committee Information not reported in the routine information system | 515 515 (1 per HZ) 100% 515 50% 0 |

(*) Some cases of adverse post-immunization reactions were reported.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

NOT APPLICABLE

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The main strategies to improve financial sustainability in the DRC are as follows: Strategy 1: Mobilisation of adequate resources This strategy applies to the government, the committee and the partners. a) Government The following measures are envisaged by the Government to increase their level of financial participation for immunization: Increase the quota of the health sector in the State budget The EPI will make a speech at the other Programmes and Management of the Minister for health to increase its share from 1 to 5% in the budget allocated to the Ministry of Health. The Ministry of Health will make a speech in the Government and to the other institutions (National Assembly, the Senate and the Presidency of the Republic) to increase gradually the share of the health sector in the State budget from 7.5 to 15%. The Ministry of Health will organize an annual round table with the partners and the civil society to disseminate and obtain their adherence to the EPI financial sustainability plan. The Ministry for Health will monitor the government to accelerate updating and adoption of text relating to the creation of funds for promoting health (FPH). These funds will come from various environmental pollution fees, from the contribution of public and private care establishments and other bodies. The Ministry of Health will make a request to the Budget Ministry to raise the percentage of credit allocated to the health sector within the context of the Heavily Indebted Poor Country (HIPC) from 20% to 30% to grant the EPI 10% to finance basic immunization activities. The Ministry of Health will make a plea to the Government to incorporate into the programme contract and the investment code measures allowing public and private businesses to assume the health care of their staff and the surrounding populations. The EPI will make contact with the Secretary General for Health to start feasibility studies and to implement projects for health insurance and mutual insurance companies. To make a motivated request to the GAVI/IMF secretariat to spread DRC finance over 8 years. b) At partner level The resource mobilisation strategies by the partners relate to: Maintaining, indeed increasing partner support. The ICC will continue to play its resource mobilization role with the sponsors to maintain their support. The government is committed to making a speech to the partners to encourage an increase in their finance of immunization activities. Extension of the partnership Organizing round tables to identify new partners who can intervene in EPI finance Increasing co-ordination of partners intervening directly in Health Zones for the EPI through the provincial ICCs and Health Zone Management Committees (MC). While maintaining the partnership role, resource management and mobilization activities should be gradually transferred to Government programmes in the long-term. At Community level Implement mechanisms to prompt and value contributions from the population Promote mutual insurance companies and activities generating revenue (AGR). This revenue will help the population to handle payment of curative care, a percentage of which will be used to cover the preventative care costs of immunization, in particular. Management mechanisms will be implemented so that funds mobilized are really used for immunization. STRATEGY 2 : Strategy to facilitate access to finance. Develop managers’ abilities to accelerate the process for obtaining finance (mastering procedures on the public market, on expenses); Implement mechanisms for decentralising financial decisions for intermediate structures in the health sector; Develop social marketing activities for financing the health sector. STRATEGY 3 : Strategy for rational and efficient management of resources Strengthening the ICC at all levels The ICC operates at a central and Provincial level but operates differently for the intermediate level (Provinces and District). In the HZ it is represented by the Management Committee. At a provincial level this organization is currently more focused on dispersed activities such as immunization campaigns, since terms of references have not been grasped. Communication among the different levels is not always satisfactory. The following interventions were made to handle this situation: Revitalizing the operating system of different committees (technical, logistic, social, resource and financial mobilization) centrally by holding regular miscellaneous meetings of the PI; Provide supervision of the provincial ICC with precise terms of reference; Following the example of the central level, the provinces will prepare and sign a memorandum of understanding on the EPI, including performance monitoring indicators; Increase communication between the ICCs at different levels and between different commissions for regular information distribution. Particular emphasis will be placed on material and financial resource management. Consequently, ICC/MC members will participate in the planning, programming, implementation, monitoring and evaluation and control/ audit of programme activites. Taking proper care of staff: Health-care staff involved in immunization activities at all levels should receive decent and regular remuneration to ensure rational and efficient use of programme resources. In this regard, the Ministry of Health will make a plea to the Government to improve the salary of these agents. Other types of motivation such as payment of bonuses will be granted to staff based on the performance contract. This contract will be signed by field and programme staff and by the HZs and operational partners. Reducing the rate of vaccine wastage The current rate of vaccine wastage should be reduced. By way of an example, the rate of wastage for DTP-HepB-Hib should fall from 25% in 2006 to 10% in 2010. The following action will be taken to achieve this aim : regular provision of oil and spare parts for the cold chain, the use of the open vial policy, use of the vaccine vial monitor, implementation of an adequate vaccine distribution system, strengthening the cold chain in the HCs. All of this action will be supported by staff training and training supervision at all levels. Regular feedback on the rate of vaccine wastage will be given to all the structures which manage and/or handle vaccines. Promoting of efficient strategies Using the RED approach with its “advanced immunization strategy” would provide access to remote populations at an affordable cost, thereby increasing programme efficiency. By incorporating immunization activities into other primary health care interventions the EPI could benefit from the resources of other programmes. Other programmes to consider include promotion of injection safety, training, supervision and monitoring activities, immunization campaigns with vitamin A supplements and distribution of mosquito nets sprayed with insecticides. Training of staff responsible for financial management Increasing capacity is an effective method to achieve the performance expected of each actor. A training plan on financial procedures and the use of different management tools will therefore be prepared and implemented so that financial managers can manage rationally and efficiently resources mobilized. Implementation of control mechanisms The implementation of control mechanisms for the use of EPI resources followed by sanctions will improve management of said resources and thus make savings. The following actions will be taken : use of management tools, good governing, transparence and respect for management mechanisms, management training, inspection missions and audit missions.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the vaccine is not introduced throughout the country (for example, only 25% of children vaccinated by the DTP3 for the first year), the country can ask to receive the difference (in this example, 75%) at a later date. In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources.

Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| Proportion funded by GAVI/VF (%) | 100% | 80% | 80% | 70% | 60% | 50% | 30% | 20% | 10% | 0% |
| Proportion funded by the Government and other sources (%) | 0% | 20% | 20% | 30% | 40% | 50% | 70% | 80% | 90% | 100% |
| Total funding for …………. (new vaccine) *** | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine

** The first year should be the year of GAVI/VF new vaccine introduction

*** Should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

NOT APPLICABLE : the financial sustainability plan was sent to GAVI on 7 February 2005.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 2632232 | 2711199 | 2792535 | 2876311 | 2962601 | 3051479 | 3143023 | 3237314 | 3334433 |
| Infants’ deaths | 335609 | 345678 | 356048 | 366728 | 377732 | 389064 | 400736 | 412758 | 425140 |
| Surviving infants | 2296623 | 2365521 | 2436487 | 2509582 | 25848669 | 2662415 | 2742287 | 2824556 | 2909293 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated 2005 and beyond with 1st dose of DTP (DTP1)* | 1 737 875 | 1 797 796 | 2 022 284 | 2 208 432 | 2 378 079 | 2 529 294 | 2 605 173 | 2 711 574 | 27929292 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of DTP (DTP3)* | 1 462 457 | 1 655 865 | 1 876 095 | 2 057 857 | 2 248 836 | 2 449 422 | 2 522 904 | 2 626 837 | 2705642 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with AAV dose | 1 115 363 | 1 655 865 | 1 827 365 | 2007665 | 2197139 | 2396174 | 2468059 | 2570346 | 2647546 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of…….HepB… | n/a | n/a | 1250464 | 2057857 | 2248836 | 2449422 | 2522904 | 2626837 | 2705642 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | n/a | n/a | 25% | 20% | 20% | 15% | 15% | 10% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 / to be vaccinated in 2005 and beyond with TT2 | 1525764 | 1897839 | 2094401 | 2301049 | 2518210 | 2746331 | 2828721 | 2945955 | 3034334 |
| Infants vaccinated in 2004 / to be vaccinated in 2005 and beyond with BCG | 2063657 | 2168959 | 2373655 | 2588680 | 2814471 | 2959934 | 3048732 | 3172567 | 3267744 |
| Infants vaccinated in 2004 / to be vaccinated in 2005 and beyond with Measles | 1458512 | 1655865 | 1827365 | 2007665 | 2197139 | 2396174 | 2468059 | 2570346 | 2647456 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes if you wish to change vaccine presentation and/or increase the quantities.

The Yellow Fever vaccine is available in 5 dose vials. The DTP +Hep B (tetravalent) vaccine will also be available in 2006 according to the information received from UNICEF.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

1.  Yellow Fever vaccine (AAV)

|  |  | Formula | 2005 | 2006 |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with the 1st dose of AAV |  | 1655865 | 1827365 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100 | 100 |
| C | Number of doses per child |  | 1 | 1 |
| D | Number of doses | A x B/100 x C | 1655865 | 1827365 |
| E | Estimated wastage factor | (see list in table 3) | 2 | 2 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 2649384 | 2923784 |
| G | Vaccines buffer stock | F x 0.25 | 662346 | 730946 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  |  |  |
| I | Total vaccine doses requested | F + G – H | 3311730 | 3654730 |
| J | Number of doses per vial |  | 5 | 5 |
| K | Number of SB syringes ( +10% wastage) | (D + G – H) x 1.11 | 2573214 | 2839725 |
| L | Reconstitution syringes ( +10% wastage) | I/J x 1.11 | 735204 | 811350 |
| M | Total safety boxes (+10% of extra need) | (K + L) / 100 x 1.11 | 36723 | 40527 |

2.  Tetravalent DTP-Hep B vaccine

|  |  | Formula | 2005 | 2006 |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with the 1st dose of (tetravalent DTP-Hep B) |  | - | 1 347 903 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | - | 100 |
| C | Number of doses per child |  | - | 3 |
| D | Number of doses | A x B/100 x C | - | 4 043 709 |
| E | Estimated wastage factor | (see list in table 3) | - | 2 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | - | 6 469 934 |
| G | Vaccines buffer stock | F x 0.25 | - | 1 617 484 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | - |  |
| I | Total vaccine doses requested | F + G – H | - | 8 087 418 |
| J | Number of doses per vial |  | - | 10 |
| K | Number of SB syringes ( +10% wastage) | (D + G – H) x 1.11 | - | 6 283 924 |
| L | Reconstitution syringes ( +10% wastage) | I/J x 1.11 | - | 897 703 |
| M | Total safety boxes (+10% of extra need) | (K + L) / 100 x 1.11 | - | 79 716 |

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement. Anticipated vaccines in stock at start of year… ….: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes.

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 – 2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### The following tables are used to calculate the volume of equipment required for injection safety.

NOT APPLICABLE

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NOT APPLICABLE

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets for 2004 | Achievements in 2004 | Constraints | Updated targets for 2005 |
| --- | --- | --- | --- | --- |
| Infants given 3 doses of DTP | 1 457 621 | 1 462 457 |  | 1 774 323 |
| Rate of DTP wastage | 35% | 21% |  | 25% |
| Rate of MEAS wastage | 40% | 36% |  | 45% |
| Rate of AAV wastage | 30% | 32% |  | 45% |
| Drop-out rate [(DTP1 – DTP3)/ DTP1] X 100 | 10% | 16% |  | 15% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | YES |  |
| Reporting Period (consistent with previous calendar year) | YES |  |
| Table 1 filled-in | YES |  |
| DQA reported on | NO | The report will be done in 2005 since the data quality audit took place in January 2005 |
| Reported on use of 100,000 US$ | NO | This report was done in May 2004. AVV was introduced in 2003. |
| Injection Safety Reported on | YES |  |
| FSP Reported on (progress against country FSP indicators) | NO | The FSP was sent to GAVI on 7 February 2005. It was endorsed in 2005. |
| Table 2 filled-in | YES |  |
| New Vaccine Request completed | YES |  |
| Revised request for injection safety completed (where applicable) | YES |  |
| ICC minutes attached to the report | YES |  |
| Government signatures | YES |  |
| ICC endorsed | YES |  |

6.  	Comments

ICC/RWG comments:

An ICC meeting, presided over personally by his Excellency, the Minister of Health, was held on 24 March 2005 to examine the introduction hepatitis B vaccine plan and the submission form to GAVI by the DRC. At the end of this meeting the Minister of Health with all his partners retained the following points: The hepatitis B virus is a major health problem for the country. Efficient control systems should be implemented to protect the population from this plague. The endorsement of the choice made during the consensus meeting, that is, the introduction of the combined form of the vaccine against the hepatitis B virus (tetravalent) as the first choice for the first two years and the pentavalent form for the third year. The ICC wishes to extend to include other partners such as : the European Union (EU), World Bank (WB), Japanese International Cooperation Agency (JICA), Belgian Technical Cooperation (BTC), Canadian International Development Agency (CIDA) and the UK Department for International Development (DFID)…

7.	Signatures

For the Government of ……… DEMOCRATIC REPUBLIC OF THE CONGO………..…………………………………

Signature:	……Emile Bongeli Yeikelo Ya Ato [signature]………………………………………...……………...

Title:	…Minister for Health……………………………………….………………….

Date:	………………11/05/05………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| WHO | Dr Léonard Tapsoba Representative | 12/05/05 [hand-written] [signature and stamp] |
| UNICEF | Mr Anthony Blomberg Representative | 11/05/05 [hand-written] [signature] |
| ROTARY | Mr Ambroise Tshimbalanga Committee President – Polio Plus | 12/05/05 [hand-written] [signature] |
| USAID | Mr Robert Hellyer Director | 5/12/05 [hand-written] [signature and stamp] |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X