April 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: HONDURAS

Date of submission:05/10/2006……………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report P First annual progress p Second annual progress report x Third annual progress report P Fourth annual progress report P Fifth annual progress report P Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety       x

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _______________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Honduras’ injection safety proposal got approval from GAVI/VF in August 2003, for a total of US $ 452,100 for three year and initial amount of US $ 172,500 for 2004. At the time of the second annual report of progress, the three disbursements have been received; the first disbursement was assigned until September 2004, due to problems with definitions of the financial management of the funds assigned by GAVI/VF. Through consultations carried out by the Secretary of Health with PAHO /WHO, it was agreed that the PAHO/WHO Representation in Honduras would manage the funds, waving charges for this service. The first disbursement was executed from November 2004 to May 2005, and the second disbursement of US $ 138,000 began being executed from June 2005 to June 2006. Highlighting the main advances for the 2005 plan are the following: - The national plan for injection safety has been disseminated among 100% technical normative units at the Secretariat of Health and with the members of the Health Inter-agency Cooperation Committee (CCIS/PAI). At the 20 departmental regions, the national plan was discussed within work sessions with the departmental technical teams (directors, epidemiologists, EPI coordinators and education coordinators). As a result, departmental regions formulated departmental plans for injection safety. By December 30, 2005, 20 departmental plans for injection safety had been developed and are now in process of implementation nation-wide. - During 2005, the health service network of the 20 departmental regions was supplied through two semestral deliveries of AD syringes in the following manner: 228,623 syringes size 0.5cc x 27G x ½, 1,742,327 syringes size 0.5cc x 23G x 1, and 438,149 syringes size 0.5cc x 25G x 255/8, and 22,606 safety boxes; guaranteeing vaccination services that are safe for the target population and the health personnel applying the vaccines and assuring the safe elimination of related solid wastes. - Notable improvement in complying with the norm requiring no recapping of syringes used in vaccination, from 60% in 2004 to 80% in 2005, has been achieved through workshops and hands-on training sessions and through supporting educational material such as bulletins and posters, indicating the steps to assure safe vaccination without risk for the population seeking the service, for health personnel offering the service, or for the community in general. - Regarding the process of destroying the safety boxes with safe methods, the greatest advance has been the normatization by the Secretariat of Health. Through the Service Development Department, the Special Code to manage and dispose of dangerous materials generated in health establishments was formulated and is currently in the process of approva. In Articles No. 67, 69, and 71it establishes that health establishments lacking a system for the physical and chemical treatment of wastes must dispose of the dangerous materials in a security cell within the sanitary dump and that rural health services must dispose of dangerous wastes and sharp objects in a security ditch; otherwise they must dispose of said wastes in ditches within the local cemetery. While this code is in the process approval for its dissemination among service units and for coordination with local governments for the construction of the safety ditches, the safety boxes continue to be buried or burnt, or are sent to the municipal trash dump, where this service is available. - Regarding the adaptation of the vaccination environments, 49% (44) of the selected HU have a diagnosis of the environments, carried out by the Physical Resources Technological Development Unit of the Secretariat of Health, which is responsible for overseeing the adaptation and/or remodeling of vaccination environments. From these, 83% already have floor-plans and estimated costs for the execution of work. A bidding for the construction work was coordinated through PAHO. Those companies that that pre-qualified to carry out the work were selected. The goal has been re-formulated since the budget is insufficient, due to the constant increase in the prices of fuel and construction materials. - The EPI is part of the National Multi-disciplinary Commission on Solid Wastes, which developed the regulations and disseminated the ministerial agreement, which covers all aspects of safe injection and safe destruction of sharp object materials, to all the HU at the different levels of the service network. - In terms of training, safe vaccination modules for the medical personnel and professional nurses and a simplified module for the auxiliary nurses and environmental health technicians are being elaborated. 100% (20) of the departmental technical teams were trained in managing the safe vaccination auto instruction module, as well as the facilitator guide, which formulated their plan for training in safe vaccination according to levels, training 100% of the medical personnel and professional nurses of 100% (21) of the government hospitals, and 35% of medical personnel and licensed nurses of municipalities, which will carry out a multiplying effect during the first semester of 2006, at the level of local HU personnel.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- Honduras began using AD syringes (not reusable) in 1997, procuring them with national funding, through the Revolving Fund of PAHO/WHO, incorporating into the general budget of the Republic, the budget assignment to procure them. It has been eight years since the introduction of AD syringes by the EPI, which has reduced to zero the risk of re-usage of syringes in EPI vaccination actions and other health actions. Beginning in the year 2000 with the updating process of the EPI norms, the application syringe and the dilution syringe for lyophilized immunobiologicals (DPT/HB/Hib and SRP) were incorporated into the program, increasing the program operation costs. Minor problems still persist at the HUs, since the personnel, afraid of shortages, does not use two syringes for DPT/HB/Hib and SRP; the situation is being corrected by supplying with two syringes for each child to be vaccinated, based on annual programming for each HU. - The health personnel still reports lesser problems with the AD syringes, basically associated with the quality of the product and not the management or use of the syringes. - Regarding the safe elimination of sharp objects, it has been five years since the EPI began the procurement of safety boxes to eliminate the AD syringes used in vaccination, initially with the support from UNICEF and USAID; and since 2001, 100% are procured with national funds incorporating into the General Income and Outcome Budget of the Republic the assignment to procure the elimination boxes, in compliance with the vaccine legislation, assuring for each HU the supply of safety boxes for the elimination of syringes and needles used in vaccination activities. - Even when 100% of the syringes used for vaccination are eliminated in safety boxes, the safe destruction of these is still a problem, since at national level there are only two incinerators, both at hospital level. At local levels, the elimination boxes continue to be buried and/or sent to the municipal garbage dump, situation which will be corrected with the approval and dissemination of the Solid Waste Policy, which will regulate the of use, manipulation, safe elimination and final disposal of syringes and needles used for vaccination as well as for the rest of the units in the health services. The advances are slow since the construction of safety ditches requires financing, which must be negotiated and coordinated with the municipal governments. The negotiations were difficult in 2005, due to the presidential and municipal election process, therefore no out going municipal government wished to commit with financing. - Regarding the safe disposal of needles in this aspect of the program, through PLAN INTERNATIONAL and USAID, in 2001 began the supply of portable needle destroyers, basically to municipal centers. In 2004 with GAVI/ VF funds and in 2005 with national funds, the coverage was broadened to 100% of the HUs with the highest population concentrations. - The transition process to the safe injection plan has been surpassed; the plan has been incorporated as a normal activity by the health personnel.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| ### Proportion of HUs with adequate vaccination environments. | - 6% (90) of the Health Units (HU) with adequate vaccination environments and with basic equipment, (28 hospitals and 62 Odontological Health Centers). | The country has completed the selection process of 44 HU at the 20 Departmental regions, a diagnosis was made for 34US which includes the current situation and the design and budget plans for remodeling. This was carried out by the Unit for Technological Development of Physical Resources of the Secretariat of Health, which is responsible for the supervision process of the remodeling and/or adaptation of vaccination environments. The 34 HU selected correspond to seven Departmental Regions: the Metropolitan Region of MDC (Municipality of the Central District), the Metropolitan Region of San Pedro Sula ( where 25% to 30% of the HU to be remodeled are concentrated), and in the Departmental Regions of Francisco Morazán, El Paraíso, Olancho, Choluteca and Valle. Pilot models were selected to mobilize and negotiate additional funds through foreign cooperation agencies, PDOs/NGOs and Municipal Governments . | The process of departamentalization, as part of the technical administrative reorganization of the Secretariat of Health, set back the process of selection of HUs to intervene, and therefore the bidding and beginning of work. The constant increase of the price of fuel and construction materials substantially modified the initial budget cost for the remodeling and/or adaptation of the vaccination environments, reducing the initial goal of 90 HU to 44 (49%). The dispersion of the HU to be remodeled increases the remodeling cost; therefore the process will be concentrate 55% of the remodeling work in the two departmental regions with the highest population density. The goal of hospitals is reduced from 12 to 3, since those initially selected, currently only serve newborns with BCG, and the vaccination clinics are part of the CESAMOS, facilities which serve as the outpatient medical service of the hospital. | The initial goal is reduced by 51% therefore modified to: 3% (44) Health Units (HU) with adequate vaccination environments, and 3 hospitals and 41 medical-odontological health clinics (CESAMOS) with adequate basic furniture. |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Proportion of the HU using Ad syringes according to vaccine type. | - 100% of the HU supplied with AD syringes and 100% of injectable vaccines (BCG, DPT/HB/Hib, SRP, DPT, HB,) applied with Ad syringes according to vaccine type. | The 34 vaccination environments with their respective plans and budget for the work and materials requires, went through a bidding process for construction companies through PAHO. Two companies were selected for offering the best conditions regarding the project, and were contracted for 100% of the environment. Currently, 11% of the work is finished, 49% in process of being finished by the first quarter of 2006. The 40% remaining were assigned to a second company, but the company declined, therefore there will be a new bidding managed by PAHO/WHO. The health service network for the 20 departmental regions was supplied with syringes for 2005, through two deliveries per year: 228,623 0.5 CC 27gx1/2 syringes (BCG) , 1,742,327 0.5 CC 23G X 1 syringes (DPT/HB/Hib) and 438,149 0.5 CC 25G X 5/8 syringes (SRP). Gurantying the safe vaccination service, basically for the application of injectable vaccines, in the safe way, for the target population, health personnel applying the vaccines, and assuring the safe elimination. | The decline of the contract by one of the bidding companies set back 4 months the finishing of the work, which was foreseen for the fourth quarter of 2005 and the first quarter of 2006. There continue to be constant changes in technology of AD syringe models, at a lesser scale by the international providers for the rotary fund of PAHO, which have reduced the number of problems in management and use by the health personnel. | The goal of remodeling 41 HU, was increased to 44 due to the offers presented by the construction companies allowing to increase the number of HU. No goal modification. |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 3. Proportion of HU destroying needles previous to their elimination in safety boxes. | - 100% of the HU (CESAMOS) supplied with needle destroyers and destroying the needles of syringes used in vaccination previous to their elimination. | Increases in 2005 by 5% (120) the coverage of HU supplied with needle destroyers, increasing from 27% (366) in 2004 to 32% (486) in 2005. 100% of the CESAMOS destroy the needles used in vaccination actions in a safe manner. | - Limited financing from cooperation agencies for the procurement of portable needle destroyers, since besides GAVI/FV, only USAID through donations procured them. From 2005, USAID withdraws financing by donations to EPI. | The goal with the procurement of the needle destroyers with GAVI/FV funds is achieved, therefore the goal is modified to: 41% (580) of HU supplied with portable needle destroyers, to destroy needles safely. |
| 4. Proportion of the HU eliminating syringes with out recapping the needle. | - 100% of the syringes are eliminated without recapping the needle | There is an increase of 20% of the personnel carrying out the elimination of the syringe without recapping the needle used in vaccination actions, placing it directly into the safety box, increasing from 60% in 2004 to 80% in 2005, associated to the training process started in 2005 with the management of the auto instruction module on safe vaccination, directed to health personnel. | - Problems persist with health personnel not following the norm for injection safety of not recapping the needle due to a lack of an integral approach of the health services. The norms regarding the recapping with one hand are still in process of modification and updating (Administration and Management Norms for Hospital Solid Wastes 1998, ITS/VIH/SIDA 1998), which generates confusion among personnel, there being a duality regarding practice. | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 5. Proportion of HU eliminating AD syringes in safety boxes. | - 100% of HU supplied with safety boxes. | 22,606 safety boxes were distributed in 2005 in 1414 HU, which were used for the safe elimination of syringes used in vaccination actions from the sustained vaccination program and national campaigns. 100% of the HU use the safety boxes for the elimination of needles and syringes used in vaccination. | Syringes and needles used in other health actions are not eliminated in the safety boxes. Currently, only EPI eliminates the used syringes and needles in the safety boxes, which creates a shortage when the safety boxes supplied by EPI are used for the elimination of needles from other health actions. | No goal modification. |
| 6. Proportion of HU destroying safety boxes with safe methods. | - 100% of the HU destroy the safety boxes containing AD syringes and other materials used during the vaccination, following safe methods. | There is no modification in the number of HU destroying the safety boxes in safe manner (incineration or depth burial) from 35% since 2004. | The country has only two incinerators at a national level, located in hospitals. The rest of the HUs burry, burn and/or send the boxes to the municipal garbage dump. The Special Code for the management of dangerous wastes generated by the health establishments was incorporated to Articles 67, 69, and 71 indicating that the health services shall dispose of dangerous wastes and sharp objects in security ditches, or in ditches at the local cemetery. This is not being complied with due to the high cost of construction of the ditches. The Secretariat of Health has not considered the short-term incorporation of this expense into the Income and Outcome Budget of the Republic, but to negotiate for the municipal governments to incorporate into their budget the construction of the safety ditches. | No goal modification. |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 7. Supply the Municipalities with incinerators working as a collection center for the HU. | - 100% of the HU of the municipality destroy the elimination boxes in municipal incinerators. | Within the special rules for the management of dangerous wastes generated in health establishments the final disposal of such material in incinerators and safety burial is indicated. Within the 4 main cities of the country, the Secretariat of Health has concerted the construction of sanitary fillings with special cells for dangerous wastes. | High cost of incinerator technology. The construction of the safety ditches in the HUs with the highest population density of the municipality, even when it was agreed upon and negotiated with the municipal governments, did not begin in 2005 due to the electoral process , since out-going authorities did not commit with funds. This is being re-taken in 2006. | 18% (240) of the HU are consulting with the municipal governments the incorporation in development plans the construction of security burial sites. |
| 8. Proportion of the health personnel trained in safe injection and norm application | - 100% of the health personnel of the public sector trained in the components of Safe Injections. (requirement calculation, management and use of equipment for the application of immunobiological material, elimination and safe destruction). - 100% of the health personnel of the private sector trained in the components of Safe Injections. | A training plan was formulated with the auto instruction module for safe vaccination at the national and departmental level. 100% of the departmental technical teams were trained (20 epidemiologists, 12 EPI coordinators, 8 service provision coordinators, and 20 education coordinators), organizing 20 departmental facilitator teams responsible for the training process at municipal levels and at health resource formation schools. 100% (20) hospital epidemiologists were trained in the safe vaccination management module, being responsible for coordinating the training actions for the medical personnel and professional nurses at hospital level. | Work strikes continued for more than 30 days during 2005, by the health personnel demanding wage improvement. | No goal modification. . |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  |  | The departmental facilitator team trained 70% (208) of the municipal technical teams (medical personnel and professional nurses) as facilitators for the local level training. The training process continues for the medical personnel and professional nurses in the 20 departmental regions on the management and use of the programming notebook, application techniques for injectable immunobiological material and safe elimination and destruction norms.. A 40% increase in the number of community leaders in health trained in the EPI community module, component of safe injections. | 30% of the facilitator teams of some departmental regions (Colon, Islas de Bahía , El Paraíso, Yoro, Lempira and Ocotepeque) did not perform their role on the training process for the municipal facilitator teams. The budget assigned for the municipal facilitator training was insufficient according to the departmental programming, conditioned by an increase in the expenses on room and board. Lack of follow up and supervision to the norm application process at the different levels of the health service network. |  |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  | - The module for self-instruction on safe injections formulated and printed; and 100% of the health personnel and communitarian leaders trained in its management. | Formulated and validated the self instruction module at the departmental technical team and hospital epidemiologist level. 1500 module documents were printed for the auto instruction of medical personnel and professional nurses of the hospital and municipal level (annex 1). Formulated, validated and printed the Facilitator Guide (500 copies) to manage the auto instruction module for safe injection, for the facilitator teams at the departmental level (annex 2). Formulated and validated the simplified safe injection module for the local level, and final printing being negotiated (annex 3). | Slow printing process associated with administrative paper work. Slow printing shops selected for the module printing, regarding the final editing, previously revised by EPI.. | No goal modification. |
|  | - Incorporate the components of safe immunization, with an emphasis in safe injections, in the curricular plan for training schools of health human resources; and at the university level, in the formation of Physicians and Nurses. | The training plan has been agreed upon and developed with the Faculty of Medicine professor staff, for the first semester of 2006 (Medical personnel and professional nurses) in Tegucigalpa, San Pedro Sula, La Ceiba, and Choluteca . |  | Incorporate the EPI norms related with the components of safe immunization, with an emphasis in safe injections, in the curricular plan for training schools of health human resources; and at the university level, in the formation of Physicians and Nurses. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 9. Proportion of municipalities developing strategies for the promotion of safe injection. | - The strategy for safe injection formulated and implemented within the framework of the CEI/EPI plan in the 298 municipalities. | Completed only 50% of the plan for departmental safe injection, in socialization process at Municipal Government level Strategies formulated for the promotion of safe injections with in the IEC/EPI plan with the participation of the selected technical personnel from the departmental teams, and the 20 departmental education coordinators responsible for the implementation at departmental and municipal level. | The process of organization and function assigning for the departmental technical team was a limitation for the formulation and implementation process of the promotion strategy of safe vaccination. Low interest from the local governments on the implementation of the plan and strategy for the promotion of safe vaccination, due to the end of functions by January 2006 of the out-going officials and 2005 being a political year with presidential and municipal elections. | No goal modification |
|  | - Messages transmitted through the media (radio commercials and local loudspeakers) within the 298 municipalities. | - The ICC, incorporating the private enterprise (GSK) and international cooperation organizations (UNICEF, USAID ) within the design process and editing of material for the national campaign, as well as for the funding of the promotion strategy for the campaigns and the sustained program. - Formulated and edited 15 radio messages supporting the sustained program for vaccination and the safe injection plan as a pilot experience and rescue of innovations in the departmental region of Comayagua, which are being reproduced and distributed to the other 19 departmental regions negotiating free air in the local media, and establishing a loud speaker plan supporting the national campaigns | High financial cost of the media for the transmission of messages therefore re-orienting management at local level of free air in the local media (radio and cable TV). | No goal modification |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  |  | Within the IEC/EPI framework, rescue of the success experience of the departmental region of Comayagua, radio magazine on EPI, edited by community monitors for the integral care of children, reproducing 20 CDs to be distributed at national level and being broadcast in the HU supporting the sustained vaccination program., | No availability of the specialized team for the reproduction of the education material for audio and computers at EPI and departmental region level. Insufficient number of megaphones and sound equipment at national level to implement the local broadcasting plan. No documentation and systematization of the success experiences of EPI at departmental region level, difficult the broadcasting and reproduction process to other departmental regions of the country. |  |
|  | - Production and distribution of printed educational material in 100% of the HU of the service network in the country (pamphlets, posters, bulletins leaflets). | Educational material was designed and validated, and printed in the following way: 2000 posters on the steps to practice the safe elimination and destruction of syringes and needles used in the vaccination services, distributed at the national level and private sector of medicine (annex 4) . Modified poster for the community level on the vaccination schematic of EPI, distributed at the national level, 2000 copies at 100% of the HU in the country (annex 5). Formulation, design, and printing of 2000 copies of the epidemiological bulletin from EPI No. 40. |  | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  | - 100% of the municipal corporations and the Private Enterprise in the municipality incorporated within the safe injections strategy. | On the safe injection plan in Honduras, challenges, which was distributed at national level to the medical associations in the country (annex 6). Printing of 200,000 vaccination record cards to document the vaccination state of children under one year of age in 2005, distributed to 100% of the HU of the country. Promotion strategy for the safe vaccination plan formulated by a work team conformed by technical personnel from the departmental teams (epidemiologists, EPI coordinators and education coordinators), municipal level technical personnel (educators from the municipality), and local personnel (nurse auxiliaries). Only 25% of the municipalities know the promotion strategy for the vaccination plan, conditioned by the lack of interest from the municipal officials, due to the electoral process. | 2005 was the election year for president, congress, and municipal officials, which influenced in the negotiation process at local government level. | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 10. Proportion of HU carrying out surveillance of adverse events according to norms | - 100% of hospitals and HU with physician carry out surveillance of adverse severe events associated with vaccination. | Systematization of the epidemiological surveillance of adverse events in 100% of the country hospitals. Reported, investigated and classified 12 cases of hospital level adverse events, which, 100% were investigated and documented; four were classified as serious (30%) three of which were classified due to a programming error, and one associated to vaccines. Serious adverse event surveillance was systematized during the second vaccination stage in the Americas, and the third follow-up campaign against Measles, not reporting any adverse event associated during the one month long campaign. Formulated and printed a book consolidating the epidemiological surveillance of the diseases that can be prevented through vaccination, and the surveillance of adverse events at the hospital level, distributing it at the epidemiology department level of the 20 departmental regions. | Limited follow up by the departmental teams on the implementation process of the epidemiological surveillance of adverse events at the hospital and CESAMO level with highest population concentration. | 100% of hospitals will be carrying the surveillance of serious adverse events associated with vaccination, notifying, investigating and informing the community about the investigation. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  | - Training 100% of the health workers for the surveillance of adverse events and the management of the media. | 100% of the departmental technical teams and hospital epidemiologists were trained in the safe vaccination module, section III, technical and clinical aspects of the ESAVI (adverse event supposedly attributable to vaccination and immunization), section IV, ESAVI monitoring system, and section V, creation of alliances with the media. | At the hospital level there are still problems with the record of information for the epidemiological register of adverse events. The follow-up of cases has been systematized once reported and investigated. | Training of 100% of the health workers at hospital level in the surveillance of serious adverse events, management, investigation, documentation, and media management through the module of self-training on injection safety. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

The second disbursement received by EPI, was of US $ 138.000 in March 2005

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The financial sustainability of EPI is based on the political decision from the Secretariat of Health and technical decision from the EPI, to achieve 90% of the required financing for the program operation through national funds substituting gradually the activities financed with foreign funds with national funds, guarantying the sustainability of EPI. With national funds, it was possible to maintain an average of 1,8% from the total funds of the budget of the Secretariat of Health during the 1998 – 2005 period assigned to EPI, with slight variations, maintaining over 2% for the last few years. It is estimated that there will be a slight increase for the 2006 – 2010 period, conditioned by the broadening of the target population for EPI: basically in 2006, Hepatitis B for newborns and influenza for the population over 65 years of age. For the 2007 – 2009 period, with the incorporation of two new immunobiological materials (Rotavirus and Neumococus), with a unitary cost being relatively high compared to the rest of the immunobiologicals, but with an impact on the reduction of treatment costs and/or hospitalization, with also the reduction in the infant morbidity and mortality, since the diseases that these two new vaccines prevent constitute the main causes for infant mortality in our country. Working under this concept, the Enhanced Program of Immunizations of Honduras, bases its financial sustainability in the experience gained with the formulation of the five-year plans, the incorporation since 1988 into the Secretariat of Health Budget of the procurement with national funds of the vaccines to be applied to the population under five years of age and women at fertile age, according to the current vaccination schedule, as well as the syringes and safety boxes required, progressively incorporating the rest of the program components into the assigned budget of the Secretariat of Health, starting in 1998, and with the formulation and approval of the Vaccination Legislation by National Congress of the Republic, which guarantees and strengthens the financial sustainability of EPI. In 2006, the “Vaccine Legislation” will be revised by national congress to incorporate the same assignment of financial resources for the components of cold chain, the epidemiological surveillance, communication and social mobilization, safe injections, supervision, monitoring and evaluation, which are incorporated in the AOP/EPI; with the inclusion into the Vaccination Legislation it will be obligatory to comply with the program and more sustainable. Starting from this general context, EPI has defined the financial sustainability plan, considering two areas of intervention in the definition of the strategies as well as the indicators through which the plan will be monitored and evaluated, being the following: - Mobilization of additional resources from national and foreign sources. The program has gained experience in this aspect, as it annually identifies international cooperation agencies that do not already take part in the ICC and is able to obtain long term loans, formulating specific projects for the main critical EPI components, like cold chain and epidemiological surveillance. Negotiating the procurement of funds for the 2002 – 2005 period, additional funds were mobilized from the foreign cooperation to strengthen the cold chain, basically the area of solar energy refrigeration, through approval by the Government of Finland of the project proposed, which ended in 2005. With additional national funds, it was presented to the Inter-American Development Bank (IDB), project through the Management Planning and Evaluation Unit (MPEU) to strengthen the cold network regarding the construction and equipment of three departmental warehouses for biological, and the supply of cold chain equipment to four departments, which is being approved and will be in execution in 2006 – 2007. This will continue to be carried out according to the identified needs, for which no national and international cooperation funds are available. - Improve EPI efficiency, minimizing the required additional resources, through the formulation of the multi-annual plan, the annual action plan, and the operative and national funded budget plan. EPI minimizes the need for additional resources, therefore in this line of intervention, EPI has begun since the multi-annual plans of 1988 to 2005, actions oriented to improve the Program efficiency regarding: - Minimizing the additional required resources. A national monthly monitoring plan for the financial execution of the national and foreign cooperation funds has been established, which monthly indicates the percentage of the executed spending, which helps identify problems in the financial execution, minimizing the additional resources required, by indicating if there is no operative capacity for the available funds when additional resources are required basically at the departmental and municipal level. - Percentage of the vaccine waste. Since 2000 EPI normalized the percentage of loss at the national level for each of the immuno-biologicals of the current vaccination schematic; even then this is not homogenous in 100% of the departmental regions, which creates a shortage at the departmental region levels where the % of loss is higher than the national average, incrementing the costs for the procurement of more vaccines, and their distribution; therefore the planning notebook has been implemented, where the daily and monthly control of vaccines is a priority activity at the local, municipal and departmental level, activity that continues to be carried out to minimize additional costs. - Also it is important to mention that annually, through management activities that are mostly political in character, commitment is made to construct and equip new health units at the municipal level, without previously securing budget basically for equipment regarding EPI; it has therefore been established that as program policy, the program negotiates and concerts with the municipal corporation the procurement of the minimum required equipment for the vaccination service to function, regarding the cold chain. In this sense, since 2004, 100% of the health regions assume the responsibility to negotiate the incorporation within their budgets for municipal development, the procurement of the cold chain equipment to proceed to inaugurate the Health Unit, activity which will be systematized beginning in 2006 with the negotiations and agreements with the Honduran Municipality Association (AMHON) at the central, departmental and municipal level. The following is the Sustainability Plan with strategies, indicators, activities, period and responsible:

EPI FINANCIAL SUSTAINABILITY PLAN

HONDURAS 2006 AL 2010

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify)

| Proportion of vaccines supported by | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2003 | 2004 | 2005 | 2006* | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Proportion funded by GAVI/VF (%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Proportion funded by the Government and other sources (%) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| Total funding for …………. (new vaccine) + | 92 | 92 | 94 | 89.8 | 95.6 | 93.9 | 94.2 | 96.4 | 96 | 96 |

+ THERE IS A MODIFICATION OF TABLE 2.1 FROM 2006, REGARDING THE EPI MULTI-ANNUAL PLAN 2006-2010FORMULATION

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Incorporation of the EPI annual operative plan (AOP/EPI) in the General Income and Outcome Budget of the Republic assigned to the Secretariat of Health | - Concerted in June 2005 with the Management Planning and Evaluation Unit (MPEU) of the Secretariat of Health for the approval of the AOP/EPI/2006, six months before the fiscal year. - Verification of the incorporated components according to account and expenditure of the AOP/EPI in the income and outcome budget of the Secretariat of Health. - Adjusting the AOP/EPI financial plan, according to expenditures and approved amount. - Monthly monitoring of the financial execution plan of the AOP/EPI | Upon agreement with the MPEU, the 2004 AOP/EPI approved 100% of the budget according to account and expenditure as requested, with a 17% increase covering the exchange rate for the Rotatory Fund from PAHO/WHO for immunobiological material, AD syringes and safety boxes. The payment process was systematized to the rotary fund from PAHO, for pro forma vouchers, which has allowed a more efficient payment of bills. For the first time in the last 10 years, the country has ended without debts and with a positive balance with the Rotary Vaccine Fund from PAHO. | Minimized problems with the payment of bills for vaccines to rotatory fund of PAHO/WHO, conditioned by burocratic paperwork at the Secretariat of Health and Finance level, situation that has been solved with the use of the pro forma voucher procedure, normalizing the situation since April 2005. 2005 being an electoral year, there was a cut on the assigned budget according to expenditure in all government institutions and all Secretariat of Health programs respecting the assigned budget for vaccines, syringes and safety boxes assigned to EPI | 100% | 100% | The proposal for financial strategy is kept without change. |
| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
|  |  | Monitoring the financial execution by expense, monthly, achieving in December 2005, 99% of the execution of approved funds |  | 100% | 100% | The proposal for financial strategy is kept without change |
| 2. Compliance with the “Vaccine Legislation” approved in 1998, for the annual budget assignment for the procurement of vaccines, AD syringes and safe boxes, for the procurement through the PAHO rotary fund. | - Verification of the budget assignation account by expenditure 352 which corresponds to the procurement of vaccines, syringes and safety boxes, incorporated in the General Income and Outcome Budget of the Republic at the Secretariat of Health level. - Signing of the annual agreement between the Secretariat of Health and PAHO/WHO and the monthly follow-up of the payment of the agreement for vaccines and syringes between the Secretariat of Health and PAHO/WHO and the compliance of the “Vaccine Legislation”.. - Reformulation of the Vaccine Legislation for it’s approval by National Congress of the Republic, incorporating 80% of the operation costs of EPI components | A system is established to comply with the vaccine and syringe accord through the sending of pro forma vouchers through the Rotary Fund to improve monthly payment to PAHO/WHO. Computerized technical and administrative control from EPI of the vouchers to the Rotary Fund, monthly monitoring of the debt and payments executed by the Secretariat of health. |  | 100% | 100% | The proposal for financial strategy is kept without change. |

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Payments are carried out according to vaccine arrival, ending 2005 without debts with the Rotary Fund and a possitive balance The monthly monitoring and control of biologicals has been systematized for the service network through the implementation and use of the planning notebook at all levels of the service network. | Difficulty at the regional warehouse level which function as recollection centers for the departmental regions to carry out the monitoring of income and outcome of biologicals and syringes, creating shortage periods at departmental level |  |  |  |
| - National, departmental and municipal management, of the mobilization of the resources to support the EPI components, at the foreign cooperation agencies, PDOs, NGOs and Municipal Corporations. | Formulation of projects at the central level to mobilize additional resources supporting the critical EPI components, presented and following up on their execution. | Two projects have been formulated and presented supporting EPI: - Cold network and safe injections plan for departmental beneficiaries of the IDB 2005 project, which was approved for US $ 1,357,500. | There has been follow up on the project being financed by IDB, which is in process of revision and approval by the new health authorities, which has set back the execution. | 0% | 0% | The proposal for financial strategy is kept without change. |
| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
|  | At least three meetings of the CCIS/EPI carried out. 9% of the EPI operational funds being managed at the Honduran Municipality Association (AMHON), to incorporate in their annual plan actions oriented towards the cold network and safe injections. Local management to incorporate in the municipal development plans the safe injection actions with an emphasis on the construction of safety ditches for the safe destruction of the elimination safety boxes. | - Strategic plan for the introduction of the rotavirus vaccine in Honduras, for an amount of $ USA. 22,239,700 presented to RVP/PATH/USAD/PAHO. Approved by RVP-PATH, 100,000$ USA to develop the epidemiological surveillance. Proposal in process of being presented for the cold network and communication. Two meetings carried out for the CCIS/EPI, analyzing the program situation of all the components, and the monitoring of the financial support by each cooperating agency, proposing interventions to improve the identified situation. | Project in execution by the Health Surveillance Directorship, presenting problems in the documentation of suspected cases in centinel hospitals | 100% 100% | 50% 100% |  |
| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
|  |  | - Draft proposal formulated for the national guidelines for municipalities, in order for AMHON to indicate the municipal officials on the 2006 – 2010 management, incorporating in their municipal development plans the actions and budget supporting EPI. - Definition at the 20 departmental regions of the medical coordinators and nurses at the municipal level. | The process has not begun since 2005 was an electoral year, the members of the directive board of AMHON do not commit to any negotiation, which made difficult the process of coordination of and agreement on actions. | 0 | 0 |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006* | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 195,826 | 197,158 | 197,208 | 199,968 | 201,388 | 203,059 | 204,744 | 206,443 | 208,156 |
| Infants’ deaths | 6,658 | 6,703 | 6,705 | 6,799 | 6,847 | 6,904 | 6,961 | 7,019 | 7,077 |
| Surviving infants | 189,168 | 190,455 | 190,503 | 193,169 | 194,541 | 196,155 | 197,783 | 199,423 | 201,078 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 171,824 | 173,797 | 182,673 | 183,970 | 185,276 | 192,906 | 194,506 | 196,121 | 197,748 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DPT/HB/Hib (DTP3)* | 175,127 | 179,330 | 178,702 | 179,971 | 181,249 | 190,875 | 192,459 | 194,056 | 195,666 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …DPT/HB/HIB......... (new vaccine) |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of… DPT/HB/HIB ….… ( new vaccine) |  |  |  |  |  |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| WCBA (12-49 year) vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 46,037 | 33,014 | 48,882 | 50,348 | 51,858 | 53,414 | 55,017 | 56,667 | 58,367 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 181,672 | 178,776 | 182,673 | 183,970 | 185,276 | 189,908 | 190,412 | 191,991 | 193,585 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 173,254 | 173,637 | 180,932 | 182,217 | 183,510 | 186,814 | 188,364 | 189,927 | 191,503 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)  *  THE 2006 POPULATION UNDER ONE YEAR OF AGE WAS MODIFIED ACCORDING TO OFFICIAL DATA FROM THE STATISTICS DEPARTMENT/SECRETARIAT OF HEALTH, ACCORDING TO PROJECTIONS OF THE INE.

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below. The baseline in the original proposal presented to GAVI maintain the presented modifications in the progress report for 2004, making clarifications for the births in 2006 and coverage for 2005 : - Regarding the expected births, the figure was modified in 2004 -2005 according to the national population and dwelling census of Honduras carried out in 2001 by the National Statistics Institute (INE) of the Republic of Honduras. Regarding the projections for 2006- to 2012, these are preliminary and will be modified year by year according to the final population estimated by the Secretariat of Health, based on ENI projections. In the second report, 2006 is modified due to reasons before explained since these are projections and the official numbers are obtained at the end of the corresponding fiscal year. - Regarding the infant mortality rate, there were modifications starting in 2004, based on data given by the National Epidemiology and Family Health Survey (ENESF) 2001, since the data presented in the baseline of the original proposal were projected based on an ENESF carried out in 1996, starting in 2006, modifications will occur due to the VIII ENESF; the final report is not available . - The data of applied dosage to the population under one year of age, for first and third dosage of DPT, single dosage of BCG and SRP to the population between 12 and 23 months of age, has been corrected from 2004, since the data indicated corresponds to projections of 2004 and has been substituted by the correct doses applied this year and reported in the annexed form WHO/UNICEF. The doses for 2007 to 2012 are projections for the population expected to be vaccinated and will be modified year by year according to the real dosage applied . - The changes presented are kept as in the first report for the proposal initially approved by GAVI, since it considered Women in Child Bearing Age (WCBA) 12-49 years old, since the country from 1990, within the framework of the goal to eliminate neonatal tetanus, broadened the vaccination to all WCBA with a five dosage scheme, and considering that, in 2002, all cohorts of the population being eleven years old had received a minimum of three or four dosages of DPT being under five years of age, the application of a reinforcement dosage of Td to the population group entering the eleven year cohorts annually was incorporated to the national vaccination. Tthe country committed national budget funds for the procurement of syringes and elimination boxes for the estimated goal population, pending a second dosage. In the initial report formulated to GAVI for period 2003, table 6.5 was modified only considering pregnant women based on births, clarifying that the dosage to be applied in the numbering of such table do not correspond exclusively to a second dosage, but to a third, fourth and fifth dosage applied to MEF, since the country in 2004 reached accumulated coverage with the second Td dosage in MEF of 99%, 94% for the third dosage, 66% for the fourth dosage, and 54% for the fifth dosage starting in 2002 the coverage in the eleven years of age population cohorts superior to 80% ..

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No aplica

Table 4: Estimated number of doses of …BCG… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2008

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.1 BCG is modified regarding the first report due to changes in the population under one year of age according to the population projection by the Statistics Department of the Secretariat of Health, based on projections from INE.

Table 6.2. Estimated supplies for safety of vaccination with …DPT / HB / Hib

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that differenc e.

Table 6.2 DPT/HB/ is modified regarding the first report due to changes in the population under one year of age according to the population projection by the Statistics Department of the Secretariat of Health, based on projections from INE.

Table 6.3. Estimated supplies for safety of vaccination with …MMR

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.3 MMR is modified in relation to the first report due to changes in the population under 12-23 months of age, according to the population projection by the Statistics Department of the Secretariat of Health, based on projections from INE.

Table 6.4. Estimated supplies for safety of vaccination with …DPT ( 2 reinforcements: first, at 18 months of age; second, at 4-5 years of age)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 6.5. Estimated supplies for safety of vaccination with …Td).

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Item A is modified in relation to the first report due to changes in the population under one year of age according to the population projection by the Statistics Department of the Secretariat of Health, based on projections from INE.

Table 6.7. Estimated supplies for safety of vaccination with … HB (NEWBORN).

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The table for HB is modified, since starting in 2006, a dose of HB is now applied to newborns. In 2006, it will be applied starting in July, therefore the target population is of 50 % of the total expected births.

Table 6.8.Estimated supplies for safety of vaccination with … INFLUENZA (Risk prone groups).

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

ACCORDING TO THE FIRST REPORT, TABLE 6.8 IS MODIFFIED DUE TO THE FACT THAT THE COUNTRY, IN 2006, BROADENED THE POPULATION TO BE VACCINATED WITH INFLUENZA TO INCLUDE THE POPULATION OVER 65 YEARS OF AGE AND RISK GROUPS.

Table 6.9.Estimated supplies for safety of vaccination with …FA (Risk prone groups)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators |  | Targets |  | Achievements |  | Constraints |  | Updated targets |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Proportion of HUs with adequate vaccination environments. | - 6% (90) of the Health Units (HU) with adequate vaccination environments and with basic equipment, (28 hospitals and 62 Odontological Health Centers). |  | The country has completed the selection process of 44 HU at the 20 Departmental regions, a diagnosis was made for 34US which includes the current situation and the design and budget plans for remodeling. This was carried out by the Unit for Technological Development of Physical Resources of the Secretariat of Health, which is responsible for the supervision process of the remodeling and/or adaptation of vaccination environments. The 34 HU selected correspond to seven Departmental Regions: the Metropolitan Region of MDC (Municipality of the Central District), the Metropolitan Region of San Pedro Sula ( where 25% to 30% of the HU to be remodeled are concentrated), and in the Departmental Regions of Francisco Morazán, El Paraíso, Olancho, Choluteca and Valle. Pilot models were selected to mobilize and negotiate additional funds through foreign cooperation agencies, PDOs/NGOs and Municipal Governments . |  | The process of departamentalization, as part of the technical administrative reorganization of the Secretariat of Health, set back the process of selection of HUs to intervene, and therefore the bidding and beginning of work. The constant increase of the price of fuel and construction materials substantially modified the initial budget cost for the remodeling and/or adaptation of the vaccination environments, reducing the initial goal of 90 HU to 44 (49%). The dispersion of the HU to be remodeled increases the remodeling cost; therefore the process will be concentrate 55% of the remodeling work in the two departmental regions with the highest population density. The goal of hospitals is reduced from 12 to 3, since those initially selected, currently only serve newborns with BCG, and the vaccination clinics are part of the CESAMOS, facilities which serve as the outpatient medical service of the hospital. |  | The initial goal is reduced by 51% therefore modified to: 3% (44) Health Units (HU) with adequate vaccination environments, and 3 hospitals and 41 medical-odontological health clinics (CESAMOS) with adequate basic furniture. |  |  |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Proportion of the HU using Ad syringes according to vaccine type. | - 100% of the HU supplied with AD syringes and 100% of injectable vaccines (BCG, DPT/HB/Hib, SRP, DPT, HB,) applied with Ad syringes according to vaccine type. | The 34 vaccination environments with their respective plans and budget for the work and materials requires, went through a bidding process for construction companies through PAHO. Two companies were selected for offering the best conditions regarding the project, and were contracted for 100% of the environment. Currently, 11% of the work is finished, 49% in process of being finished by the first quarter of 2006. The 40% remaining were assigned to a second company, but the company declined, therefore there will be a new bidding managed by PAHO/WHO. The health service network for the 20 departmental regions was supplied with syringes for 2005, through two deliveries per year: 228,623 0.5 CC 27gx1/2 syringes (BCG) , 1,742,327 0.5 CC 23G X 1 syringes (DPT/HB/Hib) and 438,149 0.5 CC 25G X 5/8 syringes (SRP). Gurantying the safe vaccination service, basically for the application of injectable vaccines, in the safe way, for the target population, health personnel applying the vaccines, and assuring the safe elimination. | The decline of the contract by one of the bidding companies set back 4 months the finishing of the work, which was foreseen for the fourth quarter of 2005 and the first quarter of 2006. There continue to be constant changes in technology of AD syringe models, at a lesser scale by the international providers for the rotary fund of PAHO, which have reduced the number of problems in management and use by the health personnel. | The goal of remodeling 41 HU, was increased to 44 due to the offers presented by the construction companies allowing to increase the number of HU. No goal modification. |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 3. Proportion of HU destroying needles previous to their elimination in safety boxes. | - 100% of the HU (CESAMOS) supplied with needle destroyers and destroying the needles of syringes used in vaccination previous to their elimination. | Increases in 2005 by 5% (120) the coverage of HU supplied with needle destroyers, increasing from 27% (366) in 2004 to 32% (486) in 2005. 100% of the CESAMOS destroy the needles used in vaccination actions in a safe manner. | - Limited financing from cooperation agencies for the procurement of portable needle destroyers, since besides GAVI/FV, only USAID through donations procured them. From 2005, USAID withdraws financing by donations to EPI. | The goal with the procurement of the needle destroyers with GAVI/FV funds is achieved, therefore the goal is modified to: 41% (580) of HU supplied with portable needle destroyers, to destroy needles safely. |
| 4. Proportion of the HU eliminating syringes with out recapping the needle. | - 100% of the syringes are eliminated without recapping the needle | There is an increase of 20% of the personnel carrying out the elimination of the syringe without recapping the needle used in vaccination actions, placing it directly into the safety box, increasing from 60% in 2004 to 80% in 2005, associated to the training process started in 2005 with the management of the auto instruction module on safe vaccination, directed to health personnel. | - Problems persist with health personnel not following the norm for injection safety of not recapping the needle due to a lack of an integral approach of the health services. The norms regarding the recapping with one hand are still in process of modification and updating (Administration and Management Norms for Hospital Solid Wastes 1998, ITS/VIH/SIDA 1998), which generates confusion among personnel, there being a duality regarding practice. | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 5. Proportion of HU eliminating AD syringes in safety boxes. | - 100% of HU supplied with safety boxes. | 22,606 safety boxes were distributed in 2005 in 1414 HU, which were used for the safe elimination of syringes used in vaccination actions from the sustained vaccination program and national campaigns. 100% of the HU use the safety boxes for the elimination of needles and syringes used in vaccination. | Syringes and needles used in other health actions are not eliminated in the safety boxes. Currently, only EPI eliminates the used syringes and needles in the safety boxes, which creates a shortage when the safety boxes supplied by EPI are used for the elimination of needles from other health actions. | No goal modification. |
| 6. Proportion of HU destroying safety boxes with safe methods. | - 100% of the HU destroy the safety boxes containing AD syringes and other materials used during the vaccination, following safe methods. | There is no modification in the number of HU destroying the safety boxes in safe manner (incineration or depth burial) from 35% since 2004. | The country has only two incinerators at a national level, located in hospitals. The rest of the HUs burry, burn and/or send the boxes to the municipal garbage dump. The Special Code for the management of dangerous wastes generated by the health establishments was incorporated to Articles 67, 69, and 71 indicating that the health services shall dispose of dangerous wastes and sharp objects in security ditches, or in ditches at the local cemetery. This is not being complied with due to the high cost of construction of the ditches. The Secretariat of Health has not considered the short-term incorporation of this expense into the Income and Outcome Budget of the Republic, but to negotiate for the municipal governments to incorporate into their budget the construction of the safety ditches. | No goal modification. |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 7. Supply the Municipalities with incinerators working as a collection center for the HU. | - 100% of the HU of the municipality destroy the elimination boxes in municipal incinerators. | Within the special rules for the management of dangerous wastes generated in health establishments the final disposal of such material in incinerators and safety burial is indicated. Within the 4 main cities of the country, the Secretariat of Health has concerted the construction of sanitary fillings with special cells for dangerous wastes. | High cost of incinerator technology. The construction of the safety ditches in the HUs with the highest population density of the municipality, even when it was agreed upon and negotiated with the municipal governments, did not begin in 2005 due to the electoral process , since out-going authorities did not commit with funds. This is being re-taken in 2006. | 18% (240) of the HU are consulting with the municipal governments the incorporation in development plans the construction of security burial sites. |
| 8. Proportion of the health personnel trained in safe injection and norm application | - 100% of the health personnel of the public sector trained in the components of Safe Injections. (requirement calculation, management and use of equipment for the application of immunobiological material, elimination and safe destruction). - 100% of the health personnel of the private sector trained in the components of Safe Injections. | A training plan was formulated with the auto instruction module for safe vaccination at the national and departmental level. 100% of the departmental technical teams were trained (20 epidemiologists, 12 EPI coordinators, 8 service provision coordinators, and 20 education coordinators), organizing 20 departmental facilitator teams responsible for the training process at municipal levels and at health resource formation schools. 100% (20) hospital epidemiologists were trained in the safe vaccination management module, being responsible for coordinating the training actions for the medical personnel and professional nurses at hospital level. | Work strikes continued for more than 30 days during 2005, by the health personnel demanding wage improvement. | No goal modification. . |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  |  | The departmental facilitator team trained 70% (208) of the municipal technical teams (medical personnel and professional nurses) as facilitators for the local level training. The training process continues for the medical personnel and professional nurses in the 20 departmental regions on the management and use of the programming notebook, application techniques for injectable immunobiological material and safe elimination and destruction norms.. A 40% increase in the number of community leaders in health trained in the EPI community module, component of safe injections. | 30% of the facilitator teams of some departmental regions (Colon, Islas de Bahía , El Paraíso, Yoro, Lempira and Ocotepeque) did not perform their role on the training process for the municipal facilitator teams. The budget assigned for the municipal facilitator training was insufficient according to the departmental programming, conditioned by an increase in the expenses on room and board. Lack of follow up and supervision to the norm application process at the different levels of the health service network. |  |

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  | - The module for self-instruction on safe injections formulated and printed; and 100% of the health personnel and communitarian leaders trained in its management. | Formulated and validated the self instruction module at the departmental technical team and hospital epidemiologist level. 1500 module documents were printed for the auto instruction of medical personnel and professional nurses of the hospital and municipal level (annex 1). Formulated, validated and printed the Facilitator Guide (500 copies) to manage the auto instruction module for safe injection, for the facilitator teams at the departmental level (annex 2). Formulated and validated the simplified safe injection module for the local level, and final printing being negotiated (annex 3). | Slow printing process associated with administrative paper work. Slow printing shops selected for the module printing, regarding the final editing, previously revised by EPI.. | No goal modification. |
|  | - Incorporate the components of safe immunization, with an emphasis in safe injections, in the curricular plan for training schools of health human resources; and at the university level, in the formation of Physicians and Nurses. | The training plan has been agreed upon and developed with the Faculty of Medicine professor staff, for the first semester of 2006 (Medical personnel and professional nurses) in Tegucigalpa, San Pedro Sula, La Ceiba, and Choluteca . |  | Incorporate the EPI norms related with the components of safe immunization, with an emphasis in safe injections, in the curricular plan for training schools of health human resources; and at the university level, in the formation of Physicians and Nurses. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 9. Proportion of municipalities developing strategies for the promotion of safe injection. | - The strategy for safe injection formulated and implemented within the framework of the CEI/EPI plan in the 298 municipalities. | Completed only 50% of the plan for departmental safe injection, in socialization process at Municipal Government level Strategies formulated for the promotion of safe injections with in the IEC/EPI plan with the participation of the selected technical personnel from the departmental teams, and the 20 departmental education coordinators responsible for the implementation at departmental and municipal level. | The process of organization and function assigning for the departmental technical team was a limitation for the formulation and implementation process of the promotion strategy of safe vaccination. Low interest from the local governments on the implementation of the plan and strategy for the promotion of safe vaccination, due to the end of functions by January 2006 of the out-going officials and 2005 being a political year with presidential and municipal elections. | No goal modification |
|  | - Messages transmitted through the media (radio commercials and local loudspeakers) within the 298 municipalities. | - The ICC, incorporating the private enterprise (GSK) and international cooperation organizations (UNICEF, USAID ) within the design process and editing of material for the national campaign, as well as for the funding of the promotion strategy for the campaigns and the sustained program. - Formulated and edited 15 radio messages supporting the sustained program for vaccination and the safe injection plan as a pilot experience and rescue of innovations in the departmental region of Comayagua, which are being reproduced and distributed to the other 19 departmental regions negotiating free air in the local media, and establishing a loud speaker plan supporting the national campaigns | High financial cost of the media for the transmission of messages therefore re-orienting management at local level of free air in the local media (radio and cable TV). | No goal modification |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  |  | Within the IEC/EPI framework, rescue of the success experience of the departmental region of Comayagua, radio magazine on EPI, edited by community monitors for the integral care of children, reproducing 20 CDs to be distributed at national level and being broadcast in the HU supporting the sustained vaccination program., | No availability of the specialized team for the reproduction of the education material for audio and computers at EPI and departmental region level. Insufficient number of megaphones and sound equipment at national level to implement the local broadcasting plan. No documentation and systematization of the success experiences of EPI at departmental region level, difficult the broadcasting and reproduction process to other departmental regions of the country. |  |
|  | - Production and distribution of printed educational material in 100% of the HU of the service network in the country (pamphlets, posters, bulletins leaflets). | Educational material was designed and validated, and printed in the following way: 2000 posters on the steps to practice the safe elimination and destruction of syringes and needles used in the vaccination services, distributed at the national level and private sector of medicine (annex 4) . Modified poster for the community level on the vaccination schematic of EPI, distributed at the national level, 2000 copies at 100% of the HU in the country (annex 5). Formulation, design, and printing of 2000 copies of the epidemiological bulletin from EPI No. 40. |  | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  | - 100% of the municipal corporations and the Private Enterprise in the municipality incorporated within the safe injections strategy. | On the safe injection plan in Honduras, challenges, which was distributed at national level to the medical associations in the country (annex 6). Printing of 200,000 vaccination record cards to document the vaccination state of children under one year of age in 2005, distributed to 100% of the HU of the country. Promotion strategy for the safe vaccination plan formulated by a work team conformed by technical personnel from the departmental teams (epidemiologists, EPI coordinators and education coordinators), municipal level technical personnel (educators from the municipality), and local personnel (nurse auxiliaries). Only 25% of the municipalities know the promotion strategy for the vaccination plan, conditioned by the lack of interest from the municipal officials, due to the electoral process. | 2005 was the election year for president, congress, and municipal officials, which influenced in the negotiation process at local government level. | No goal modification. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
| 10. Proportion of HU carrying out surveillance of adverse events according to norms | - 100% of hospitals and HU with physician carry out surveillance of adverse severe events associated with vaccination. | Systematization of the epidemiological surveillance of adverse events in 100% of the country hospitals. Reported, investigated and classified 12 cases of hospital level adverse events, which, 100% were investigated and documented; four were classified as serious (30%) three of which were classified due to a programming error, and one associated to vaccines. Serious adverse event surveillance was systematized during the second vaccination stage in the Americas, and the third follow-up campaign against Measles, not reporting any adverse event associated during the one month long campaign. Formulated and printed a book consolidating the epidemiological surveillance of the diseases that can be prevented through vaccination, and the surveillance of adverse events at the hospital level, distributing it at the epidemiology department level of the 20 departmental regions. | Limited follow up by the departmental teams on the implementation process of the epidemiological surveillance of adverse events at the hospital and CESAMO level with highest population concentration. | 100% of hospitals will be carrying the surveillance of serious adverse events associated with vaccination, notifying, investigating and informing the community about the investigation. |
| Indicators | Targets | Achievements | Constraints | Updated targets |
|  | - Training 100% of the health workers for the surveillance of adverse events and the management of the media. | 100% of the departmental technical teams and hospital epidemiologists were trained in the safe vaccination module, section III, technical and clinical aspects of the ESAVI (adverse event supposedly attributable to vaccination and immunization), section IV, ESAVI monitoring system, and section V, creation of alliances with the media. | At the hospital level there are still problems with the record of information for the epidemiological register of adverse events. The follow-up of cases has been systematized once reported and investigated. | Training of 100% of the health workers at hospital level in the surveillance of serious adverse events, management, investigation, documentation, and media management through the module of self-training on injection safety. |

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | X |  |
| Table 1 filled-in | NA |  |
| DQA reported on | NA |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) | X |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed | NA |  |
| Revised request for injection safety completed (where applicable) | X |  |
| ICC minutes attached to the report | X |  |
| Government signatures | X |  |
| ICC endorsed | X |  |

6.  	Comments

ICC/RWG comments:

INTERAMERICAN CHILDRENS INSTITUTE : continue to give their technical support to EPI. PAHO: There must be a commitment from the country to maintain the financing within the budget for vaccines procurement; it is important that the foreign resources do not reduce the national support; PAHO support is ratified, in order to maintain the EPI achievements, which is an example for other programs within the Secretariat of Health. USAID: Congratulates the program for the achievements; even when it is a poor country, it maintains vaccination rates over 90%; recognizes the work of EPI in the safe injections component; but there must be a national policy to regulate the management of dangerous wastes for all sectors, to advocate for support from the municipal governments, within the framework for the Poverty Reduction Strategy; identify the way to maintain the cold chain, which was maintained by USAID until 2004. UNICEF: ratifies their support to EPI, for maintaining the goals and results achieved in coordination with the Cooperation Committee. Plan International: continue to give their technical and financial support to EPI and their support for the Safe Injections Plan.

RECORD ACT FOR THE HEALTH INTERAGENCY COOPERATION COMMITTEE MEETING (CCIS), No. 02, 2005

## On October 19th, 2005, at 10:35 a.m., at the National Biological Center, the CCIS meeting began with the participation of the following members and guests:

Secretariat of Health

- Dr. Merlin Fernández			Minister of Health

- Dr. Fanny Mejía				Sub Secretary of Health

- Dr. Luís Alberto Medina			General Director of Health

- Dr. José Orlando Solórzano		Director for Health Surveillance

- Dra. Ida Berenice Molina			EPI / SH Chief

- María Aparicia Palma			EPI / SH Sub Chief

- Br. I. José T. Martínez			Cold Network National Coordinator

- Claudia Siu- Meza				Professional Nurse Association

- Marcos Hernández				Foreign Cooperation Unit / SH

- Ana Barahona				Foreign Cooperation Unit / SH

- Marina Erazo					UPEG / SH

- Dr. María Isabel de Grandez			Child Care Unit

- Dr. Edith Rodríguez				Statistics Department Chief / SH

- Alonso Aguilar				Institutional Communication ship

- Dr. Gloria Pinto				Health Promotion Chief / SH

- Dr. Georgina Nassar			Food Security Program

- Dr. Dina Yaneth Castro			Virology Laboratory Chief

- Dr. Rosa María Duarte			Service Development Department

Chief / SH

- Dr. Iris Galeano				Service Control Department Chief

Committees and Associations

- Dr. Carlos Godoy Arteaga			President of CONEPO

- Dr. Renato Valenzuela			President of CCNI

- Alba Luz Vindel				Honduran Municipality Association

- María Luisa Pardo				Chief CONSUDE Program

Cooperants

- Dr. José Fiusa Lima			PAHO/Who Representative for Honduras

- Dr. Luís Amendola	Transmittable Diseases National Consultant, WHO

- Dr. Patricia Rivera	Canadian Agency for International Develpment (ACDI)

- Dr. Carlos A. Rodríguez C.		Health Advisor, Plan International

- Dr. Angel Coca 			Health Advisor, USAID

- Dr. Ramón Pereira                       	ASDI/ACCESO Project  Coordinator

- Ligia Lorena Silva			World Relief Honduras

- Geraldina Chavez			CARE Honduras

PROGRAM APPROVED

1. Meeting opening by the Secretary of State in the Office of Health, Dr. Merlin Fernandez

2. Meeting objectives by the Sub-secretariat of Health, Dr. Fanny Mejia

3. Reading of the previous meeting act by the Foreign Cooperation Unit.

4. Current EPI situation by the Chief of EPI, Dr. Ida Berenice Molina.

5. Current situation of the Surveillance of the Diseases that can be Prevented through Vaccination, by the Sub-chief of EPI, Maria Aparicia Palma.

6. Discussion, comments and agreements.

7. Closure of the meeting.

DEVELOPMENT OF THE MEETING PROGRAM:

Item 1:

The Health Minister began the meeting by welcoming all members and guests, expressing the government interest on maintaining as a priority the prevention in health, and the need to continue with the coordination of all actors of the Honduran society and cooperants who contribute to reaching the national and international goals.

Item 2:

The Foreign Cooperation Unit read the previous meeting act, which was approved without amends.

Item 3:

The Sub-secretary of Health, presented as meeting objective the current situation of the Enhanced Program of Immunizations (EPI), with an emphasis on the vaccination and surveillance components of the diseases that can be prevented through vaccination, identifying achievements, limitations, interventions and short and medium term perspectives.

As well as the expected results:

-	 Inform among the key sectors, the achievements and interventions regarding immunizations by the Secretariat of Health.

-	Sensibilize the foreign cooperation regarding the cooperation guidelines for the 2006 - 2010 quinquenium.

Item 4:

The Chief of EPI, presented the current situation of EPI regarding the vaccination coverage rates for the 2002 - 2005 period, highlighting:

- The descending tendency of the vaccination coverage rates for children under 2 years of age, beginning in 2002, sustaining a 90% at a national level, also identifying regions and municipalities at risk.

- Analysis of the identified causes, indicating that there is an analysis done by department, identifying some of the main causes as:

- Citizen insecurity which did not allow for sustained outdoor vaccination actions in the main cities during 2005.

- Monitoring and supervision at the department to the local levels, which did not allow for timely decision making, and to carry out appropriate accountability.

- Estimation of the population under one year of age in some department regions like Copan, Santa Barbara, etc.

- Information registration problems of the BCG vaccines applied in Hospitals at the department level.

- Lack of systematization of the package delivery for the basic health services in difficult access locations due to human resource, logistics and financial problems.

- Analysis of the river network state and needs.

- Facilitators, among which were highlighted the political and technical support, the vaccine supply, syringes and materials, financial support for maintaining the cold network and, special vaccination operations for municipalities in risk, highlighting the PAHO/WHO support.

- Perspectives for the 2006- 2010 period, which are part of the multi-annual plan for that period. The plan visualizes funds for the Poverty Reduction Strategy (PRS) and from the millennium account to incorporate vaccines such as Rotavirus in 2007 and Neumococus in 2009, as well as to apply the influenza vaccine.

Item 5:

The Sub-chief of EPI, presented the current situation of epidemiological surveillance for diseases that can be prevented through vaccination, highlighting:

- The tendency of the incidence and mortality due to diseases that can be prevented through vaccination is descending; this associated with vaccination coverage which is equal or over 90%, which has impacted in the reduction of infant mortality.

- Among the most significative achievements are:

- Maintaining the eradication of Polio.

- Elimination of Measles.

- Control- Elimination of neonatal tetanus

- The process of elimination of rubella an congenital rubella syndrome.

- The control of diphtheria, meningitis, TB and meningitis due to Hib.

- The support to developing the surveillance of influenza and rotavirus.

- Analysis of the identified problems and interventions carried out or in process.

- Perspectives for the 2006 – 2010 period.

Item 6:

Open discussion and comments began, among which the most important were:

- The Health Minister, Dr. Merlín Fernández, congratulated the presentations, indicating that the Secretariat is clear that the EPI achievements must be maintained, and actions to be taken to overcome weaknesses. Visualizes that one of the Secretariat's weakness is the lack of an integral planning process, which does not allow to generate the conditions of viability and feasibility to accomplish the commitments like care for the needs for cold network equipment, also not assigning the needed resources in a systematic way.

He invited the cooperants to comment regarding the support to strengthen EPI, which is a a program that does not change of national priority, and the fact that the governments are conscious that this has allowed for a systematization of achievements.

- World Relief, Ligia Silva; Congratulated the Secretariat of Health for their effort and motivated it to continue, especially by incorporating new vaccines.

- OPS/OMS, Dr. José Fiusa Lima; also congratulated the Secretariat of Health and the EPI team for the excellent work carried out, and indicated that, regarding the needs of infrastructure and cold network equipment, resources should be mobilized to consolidate what already exists and identify new cooperants.  He expressed that the PAHO budget has decreased and he commits to indicate it to the health cooperants, in order to unite the cooperation on the medium term in order to support the cold network. Also, he suggested that the Secretariat of Health clearly define the actions to receive resources from loans, since it has been clearly demonstrated that, even with limitations, it is clear that the collective effort, leadership and political commitment regarding EPI, the impact on disease elimination has been demonstrated.

Summarizing his perception, EPI has become public policy.

- USAID, Dr. Angel Coca; Congratulated EPI for sharing the current situation report and agrees with the point of view expressed by the PAHO/WHO representative; also recognizes that a component in crisis requiring support is the cold network, considering that it requires to be broadened to incorporate new vaccines and to maintain the vaccination levels, therefore he suggests a possible re-channeling of funds, and an evaluation due to the weakening of EPI in the West departments, where there is an increase in the number of municipalities in risk which have received foreign cooperation funds for health actions through the various projects.

- ACDI, Dr. Patricia Rivera; Recognizes the excellent work carried out by the Chief of EPI and her team, whose national success are internationally recognized and have raised the name of the country, and who deserves a recognition for the social response to the Vaccination Campaigns. She suggests that the EPI topic should be presented in the sector table and be incorporated in all loans from the Secretariat of Health.

- The Sub Secretary of Health, Dr. Fanny Mejía, Indicated that although she agrees with some comments, to others she does not agree, which are:

- The western departments have not received a high loan investment, since the loan from IDB has not begun.

- EPI is a transparent program with excellent management, and there has been inequity from the cooperation and the system upon assigning more budget, compared with the impact achieved; therefore the program deserves more recognition.

- The Secretary of Health, Dr. Merlín Fernández; indicated the need to deepen into the regions at risk with a coverage descending tendency; EPI reacted indicating that there is a detailed analysis by Health Region..

- The Chief of the Statistics Department, Dr. Edith Rodríguez; explained that the national issue of estimation the population under one year of age compared with the estimates from the National Statistics Institute (NSI), informing that the vaccination coverage rates are evaluated with the official population estimated by the Statistics Department. Regarding the regions with problems in estimation of the population under one year of age, will be revised.

- The General Director of Health, Dr. Luís Alberto Medina; indicated that the most serious problem is the lack of request and presenting of accounts at the departmental and municipal level, and the systematic supervision at the departmental and regional level.

- The Secretary of Health, Dr. Merlín Fernández; closed the meeting at 13:00 hours, thanking for the valuable comments and indicated a summary of the commitments and challenges for the Secretariat of Health.