January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: INDIA

Date of submission: …February,2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report   Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)       : No support received under this head

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines  :     YES

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety  :   No support received under this head

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability  Not Applicable

3.  Request for new and under-used vaccine for 2005

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2005

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)    Not Applicable

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _______________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH November     YEAR   2002   in project cities

Sept. to Dec.  YEAR   2003   in project Districts

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

The supply of first lot of Hepatitis B vaccines, for 15 project cities was received in Sept. - Oct., 2002. The supply of vaccines, the first lot for 33 districts & second lot of vaccines for 15 Project cities was received in Sept. – Oct., 2003. After that most of the times the supply of the vaccine has been received on time. No Problems were encountered in receipt of the vaccine. Four important suggestions were received as a feed back from the Nodal Officers of Project Cities regarding Vaccine Vial Monitor, AD syringes & Safety Boxes: - The needle of AD syringes in future supplies may be of gauge no. 23 or 24 & not more than half inch in length. - Current VVMs for Hepatitis-B vaccine only indicate exposure to heat. It would be more useful to have VVMs for indicating vaccine freezing, especially for Hepatitis-B vaccine as it has been observed that shake-test is not always fool-proof.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

In 15 Project Cities since Jan. 2003. Details as stated below: Details as given above at 1.2.1 - The Hepatitis B vaccination was started in Hyderabad city by Nov. 2002 & in 11 other cities by March 03. - Out of the remaining 3 cities of (Patna, Kanpur & Lucknow) the Hepatitis B vaccination started in Kanpur in Oct. 2003 & in Lucknow in Dec. 2003. The late start was due to their preoccupation in Polio eradication programme in India. - Hepatitis-B immunization could not be started in the remaining city of Patna (in the state of Bihar) due to their preoccupation with Polio eradication. However, the training of health workers and Medical Officers under the project was completed in March’2004. In 33 Project districts since Jan. 2003 are stated below. - Two Master Trainers & two Nodal Program Officers were trained from each of the 33 project districts on time (April –June 2003). - An amount of approx US $ 294963 was released by Government of India from its own budget for training in above stated 33 districts from RCH programme in June 2003 - In addition to the 32 districts already selected for Hepatitis B project, an additional district (the Union Territory of Andaman & Nicobar) was added under the project after consulting the ICC (Inter-Agency Co-ordinating Committee), due to the high prévalence rate of Hepatitis B in the islands especially the Car-Nicobar area. - Vaccine supplies for the first quarter of year 2005 have been completed for the 14 cities & 33 districts. - By December 2003, all 33-project districts had started providing Hepatitis-B vaccine as part of routine immunization. STUDIES AND ASSESSMENT - The Study on assessment of Injection Safety has been completed in the year 2003 and findings presented to GoI and ICC members in early 2004. GoI, swiftly acting on the study findings, has made a policy to use A.D. syringes for all immunization under the Universal Immunization Programme (UIP), starting 2005. An application has already been made to GAVI/VF for injection safety support in the month of September’2004 (awaiting final approval). A Rapid Assessment of Hepatitis B immunization project in the 33 districts and 14 cities has also been completed with assistance from the ICC members. A copy of the assessment report is enclosed. Problems encountered & actions taken / being taken to improve the performance: The main challenge identified during the rapid assessment is Improving Immunization Coverage and reducing Dropouts. The proposed remedial measures are summarized below. Improving Immunization Coverage and reducing Dropouts: - Improved Supervision & Monitoring: - In addition to the steps already mentioned in the MYP, some specific initiatives proposed for Hepatitis-B project cities and districts are regular field visits by the GoI nodal officer and partners. - Efforts will be made to educate District health staff on their responsibilities concerning data analysis for management decision-making and the need to provide feedback to the service delivery staff. - The recent expansion of the Hepatitis-B project to entire urban area in the 15 metropolitan cities is expected to improve the coverage in view of increased clarity and better infrastructure removing any ambiguities that may have existed earlier. - Govt. of India has now come up with a locally appropriate solution for injection waste disposal which is expected to clarify things further and improve the off take of AD syringes and vaccine by integrating them further in to the system. - States is exploring the option of involving those private practitioners who are already receiving DPT vaccines from the Government supplies, for providing Hepatitis-B vaccine as well in the project cities and districts. This initiative is expected to improve the immunization coverage. - Recently concluded National EPI review focussed on this aspect with an in-depth qualitative survey of six low performing states viz. Bihar, Jharkhand, Madhya Pradesh, Orissa, Rajasthan and Uttar Pradesh. The review, aimed at identifying state specific issues and solutions, will lay down state specific strategies. In some very low performing states which are part of Hepatitis-B project, specific strategies to address this low performance would be developed based on this assessment. - Other than the strategies proposed in the MYP for reducing dropouts and missed opportunities, some new initiatives for reducing dropouts have already been initiated in some of the Primary Health Centres and Sub-Centres where ‘defaulter’ lists were being prepared of the children who had not reported to receive the 2nd and 3rd dose of the vaccines. These lists were being used by the ANMs (Auxiliary Nurse Midwife – vaccinator) to mobilize Anganwadi workers and mothers from the nearby houses who visited the vaccination sessions to remind the parents of the defaulting children. In addition these lists were being used by the ANMs in their house visits also. - Also, the stricter implementation of Fixed Day /Fixed Site strategy for immunizations is being considered. This policy is expected to help improve the community recall and accessibility to immunization services, which, in turn will help in improving coverage/reduce dropouts. Reducing Vaccine Wastage Rates: - Open Vial Policy: Though the policy for Hepatitis-B vaccine has already been authorized and circulated by GoI for Hepatitis-B vaccine to all the project cities and districts, it has not percolated to all the project areas. With the proposed supervisory visits and follow-up from the central government, this move is expected to significantly impact the wastage rates. - Government of India is also in the process of implementing a computerized immunization monitoring system at district level. This system, when implemented, will also be able to track vaccine logistics in the Hepatitis-B project areas and provide better information in this regard. - GoI would also look to obtain the vaccine issue /usage information from a larger and more representative sample at the sub centre levels to calculate the wastage rates unlike the data presently available. It is estimated that the actual wastage rates will be much less than the earlier projected rates in some of the earlier reports. Also, India is hoping to achieve the polio eradication targets by the year 2006-07 which will help release and re-direct a lot of resources (human and financial), further strengthening routine immunization.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

This head is not applicable as the above support was provided only in the first year of the project.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Not Applicable

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Not Applicable

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

India finances over 95% of routine immunization services, including operating costs, vaccines, and other costs. This level of financing reflects the sustained commitment to immunization on part of the government. As such, supporting the cost of continuing the Hepatitis B vaccination in the existing 14 cities & 33 districts under the project could be easily absorbed under the regular Immunization Program of the country after the support from GAVI ceases at the end of five years. The immunization infrastructure is established in all states. There is also a reinforcement of Government commitment to Routine Immunization by way of establishment of National Technical Advisory Group on Immunization and preparation of a Multi Year Plan for Immunization (2004-09). This document has been validated by experts from national/international partner/donor agencies and is ready for implementation. An exhaustive exercise to cost this MYP was also undertaken and completed in late 2004 by GoI. The MYP is a part of the umbrella Reproductive and Child Health (RCH)-II program which is a sectoral approach to reproductive and child health including immunization. The Government is also working on a National Immunization Policy, first draft of which is prepared for discussions at various forums.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators   -- Not Applicable

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2005

Section 3 is related to the request for new and under used vaccines and injection safety for 2005.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 27.50 | 27.55 | 27.86 | 28.401 |  |  |  |  |  |
| Infants’ deaths | 1.81 | 1.73 | 1.48 | 1.281 |  |  |  |  |  |
| Surviving infants | 25.69 | 25.81 | 26.39 | 27.12 |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 1.27 | 2.59 2 | 2.64 | 2.69 |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 1.26 | 2.59 | 2.64 | 2.69 |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 1.49 | 2.59 2 | 2.64 | 2.69 |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | 1.28 | 2.59 | 2.64 | 2.69 |  |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 25 | 25 | 25 | 20 |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * |  |  |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

IMPORTANT EXPLANATORY NOTE FOR SUPPLIES UNDER INJECTION SAFETY- GOI has asked ONLY for Hepatitis-B vaccine supplies for year 2005 to 2007.  Syringes for all the infants in the project area , for all the antigens including Hepatitis B vaccine,  have been requested under a separate application already submitted to GAVI .

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Notes: - The Population of the country, Birth Rate & Infant Mortality Rate projected for year 2002 to 2016 by the office of Registrar General of India have been used (Reference SRS Bulletin Oct. 2002 & Projection tables) for calculating no. of births & Infant deaths stated in the above table. - In consultation with ICC the Govt. of India has planned to cover all the non slum infants of the city also from year 2005. This will help to ensure equity among all the infants & to improve the coverage of infants by expanding the provision of Hepatitis B vaccination from health care facilities in the non slum areas also. The target of 2.59 million infants in year 2005 has been reached by adding 80% coverage of non slum infants in 15 project cities that is target of 0.94 million to the existing target of 1.61 million infants in 33 districts & slum infants in 15 project cities, & applying the factor of population increase. The targets for year 2006 & 2007 have been derived by applying the factor of population increase to the no. of target infants for year 2005. However in last two years the vaccination coverage has improved & it may improve further in coming years at faster pace. Hence keeping in mind the best case scenario, if immunization coverage in all the project cities & districts reaches above 80%, additional doses of vaccine may be required. - AFTER THE PRESENT INTENSE INVESTMENT OF MANPOWER, TIME & FUNDS ON POLIO ERADICATION SUCCEEDS BY YEAR 2007 AND WE ARE ABLE TO DEVOTE MORE TIME & RESOURCES FOR OTHER IMMUNIZATION PRIORITIES, THE GOVT. OF INDIA PLANS TO CONSIDER FURTHER EXPANSION OF HEPATITIS B VACCINATION IN ADDITIONAL DISTRICTS/ STATES. WE ARE ALSO HOPEFUL TO CONSOLIDATE AND FURTHER STRENGTHEN OUR ACHIEVEMENTS IN THE PRESENT PROJECT AREAS COVERED BY HEPATITIS B VACCINATION BY THAT TIME. - The % drop out observed between 3rd & 1st dose of Hepatitis B vaccine in year 2003 is 25%. The decrease of 5% in the same has been targeted in year 2004, 10% in 2005 & 6 and 15% in year 2007 & 8. Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below In consultation with ICC the Govt. of India has planned to cover all the non slum infants of the project cities from year 2005 in addition to the slum infants already being covered. This will help to ensure equity among all the infants & to improve the coverage of infants by expanding the provision of Hepatitis B vaccination from health care facilities in the non slum areas also. The target of 2.59 million infants in year 2005 has been reached by adding 80% coverage of non slum infants in 15 project cities that is target of 0.94 million to the existing target of 1.61 million infants in 33 districts & slum infants in 15 project cities, & applying the factor of population increase. The targets for year 2006 & 2007 have been derived by applying the factor of population increase to the no. of target infants for year 2005. The situation of supply overshooting the demand will be prevented by constantly reviewing the immunization coverage each year & modifying the procurement request for next year accordingly.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2005

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The revised new quantity of supply required is yet to be communicated to UNICEF. As soon as the revised requirement stated in this progress report for Year 2005 & beyond is approved by the GAVI the same will be communicated to UNICEF.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2005 Remarks - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes. Qty in Millions |
| --- | --- | --- | --- |
| A | Infants vaccinated / to be vaccinated with 1st dose of …............... ( new vaccine) |  | 2.59 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100% |
| C | Number of doses per child |  | 3 |
| D | Number of doses | A x B/100 x C | 7.77 |
| E | Estimated wastage factor | (see list in table 3) | 25% |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 10.33 |
| G | Vaccines buffer stock | F x 0.25 | Not Applicable |
| H | Anticipated vaccines in stock at start of year …. |  | 1.92 |
| I | Total vaccine doses requested | F + G - H | 7.54 (Please See Explanatory note below) |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 8.62 |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 0.00 |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 0.00 |

*Please report the same figure as in table 3.

Explanatory Note: To avoid the over stocking of vaccine  ,in addition to using the standard calculations stated above,  the vaccine requirement has also been calculated on the basis of available data on vaccine utilization. The requirement calculated on vaccine utilization with wastage & buffer works out to be 7.54 million doses after reducing the available stock of 1.92 million doses. Hence in place of 8.41 million doses expected by using the standard calculations (10.33-1.92=8.41), the figure of 7.54 million doses has been stated.

Following is a table with actual vaccine wastage rates observed randomly from Hepatitis-B project sites during the Rapid Assessment conducted in Sept.2004.

| Vaccine Wastage under Hepatitis B vaccination Project - India |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Observations in Sample Project Areas |  |  |  |  |  |  |  |
| Sr. | Name of the Center | Project Area | Period | Vaccine | Reported | Percentage | Vaccine |
| No. |  |  |  | Doses | Vaccine doses | Vaccine | Wastage |
|  |  |  |  | Consumed | Administered | Utilization |  |
| 1 | Grace Garden Health Post (Zone II) | Chennai | July- Sept 04 | 338 | 338 | 100% | 0 |
| 2 | Sukia Street Vaccination Center Burroh-IV | Kolkatta | June-Dec 04 | 120 | 120 | 100% | 0 |
| 3 | Burroh I, 10 BT Road | Kolkatta | Oct- Dec 04 | 450 | 395 | 87.78% | 12.22 |
| 4 | Bal Mahila Chikitsa avon Prasuti Graha, Aliganj | Lucknow | Sept- Dec 04 | 590 | 590 | 100% | 0 |
| 5 | Mother & Child Welfare Centre, H-16, Kalkaji | New Delhi | May- Sept 04 | 860 | 752 | 87.44 | 12.56 |
| 6 | IPP VIII Dispensary, Defence Colony | New Delhi | June-Dec 04 | 959 | 800 | 83.42 | 16.58 |
| 7 | Post Partum Unit Kalkaji | New Delhi | May- Sept 04 | 332 | 253 | 76.2 | 23.8 |

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - DPT3 Coverage - Hepatitis B Coverage. - A D Syringe Use. - % of Health Officials & workers trained. | 19.88 Million (75.59%) A 1.65 Million B To Start in all Project Areas 2 Master Trainers & 2 Nodal Officers in each Project City & District. | 16.72 Million (63.6%) C 1.28 Million (77.85%) D Initiated in 14 Cities(out of 15) & 33 districts (out of 33 districts) Achieved in 100% in all the Project Cities & Districts. | Decrease in immunization coverage in some districts & Poor infrastructure in city slums. | 80% Coverage targeted in year 2005. |

Notes for Table 4 : A: The data are reproduced as targets set for year 2003, under point 4 , the Multi Year Immunization Plan , page 19 of the Revised Proposal submitted to GAVI for Hepatitis B Project in Nov. 2001 using Birth Cohort of 26.3 million.

B: The data are reproduced as targets set for year 2004, under Executive Summary, page 5 of the Revised Proposal submitted to GAVI for Hepatitis B Project in Nov. 2001.

C: The data are reproduced from Coverage Evaluation Survey, 2002 by UNICEF & GOI.

D: The data are based on the compilation of the Progress Reports Received by Govt. of India from states implementing the Hepatitis B Project.

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | Yes |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in |  |  |
| DQA reported on | N.A. |  |
| Reported on use of 100,000 US$ | N>A. |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) | N.A. |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | N.A. |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| DFID | Dr. Joanna Reid Senior Health Advisor |  | WHO, INDIA | Dr. Salim Habayeb, WHO Representative to India |  |
| EUROPEAN COMMISSION | Dr. Karan Singh Programme Advisor |  | WORLD BANK | Dr. G.V. Ramana Senior Public Health Specialist |  |
| Gates Children’s Vaccine Programme at PATH | Dr. Rajkumar, Project Manager |  | USAID | Dr. Marie Sinnette Director PHN |  |
| UNICEF | .Mr. Cecilo Adorna Country Representative |  |  |  |  |

~ End ~