Annual Progress Report 2006

Submitted by

The Government of

REPUBLIC OF KENYA

to the

# Date of submission: 15th MAY 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of REPUBLIC OF KENYA

Ministry of Health:

Title: …… ………………………………

Signature: ……………………………………

Date: ……………………………………

We, the undersigned members of the Child Health Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The Child Health ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr S.K. Sharif - SDDMS | Ministry of Health |  |  |
| Dr Ann. Wamae -Head-Division of Child Health | MOH |  |  |
| Dr Tatu Kamau – KEPI Manager | MOH |  |  |
| Dr Josephine Kibaru – Head Div. Reprod.Health | MOH |  |  |
| Dr David Okello – Country Representative | WHO |  |  |
| Ms. Olivia Yambi - Country Representative | UNICEF |  |  |
| Ms. A. Corea - Advisor | HSPSI (DANIDA) |  |  |
| Director of Basic Education | Ministry of Education |  |  |
| Commissioner of Social Services | Ministry of Culture & Social Services |  |  |
| Dr. Paul Kizito | NCAPD |  |  |

Signatures Page for HSS

For the Government of REPUBLIC OF KENYA

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Permanent Secretary | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Last tranche of ISS funds received on - 7th April 2004

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

This is as described in previous reports – last disbursement of ISS funds was done in January 2005 to all districts and provinces.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006  …Nil

Remaining funds (carry over) from 2006 ….US$ 222,792.00

Balance to be carried over to 2007..US$ 222,792.00

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  | No ISS funds received in 2006 from GAVI. Balances from 2005 were not disbursed to district level. |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

No ISS funds were received in 2006 hence there were no activity related to use of these funds

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for …..2009

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

Last DQA conducted 2nd-17th August 2004

What were the major recommendations of the DQA?

Priority recommendations were: - Introduction of ledgers for monitoring syringes and general supplies - Support and strengthen Health Facility staff capabilities in setting targets based on past achievements, monitoring wastage, coverage (not only for DTP and measles) through on-the –job training (OJP). The performance Monitoring Handbook (PMH) and Vaccine monitoring Handbook (VMG) are resource materials for OJT. - That systems have been developed and are functioning but with dwindling immunization coverage’s, it is important to review the strategies that could support increased immunisations.

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO                           But improvement of the reporting

√

## System is included in the cMYP 2006-2010

## If yes, please report on the degree of its implementation and attach the plan.

How recommendations have been addressed: - Ministry of Health ledgers for stock control of all non-pharmaceuticals have been in existence for very long and this is where all injection equipment is supposed to be monitored. However despite frequent support supervision this remains a very weak area from National to health facility level. - Target setting at health facility level is based on -Proportionate increase on past performance -Agreed allocation of catchment populations shared with other facilities -Wastage monitoring still remains relatively weak - Strategies to improve immunization coverage have been drawn from a new government initiative to improve performance of all government sectors through a “Result Based Management” strategy. Twice in 2006 Rapid Results Initiatives (RRIs) have been conducted in all districts specifically to raise full immunisation coverage with a fair amount of success. RRIs are intensive, focused activities to achieve a set desired goal within 100 days. Another initiative was to include measles and full immunization coverage targets in the Ministry of Health’s performance targets under the National Health Sector Strategic Plan (2005-2010), which obligates all levels of health service provision to work towards this goal. Annual operation plans drawn from this strategic plan sustain focus on the goals and especially the need to address any obstacles that may be constraining achievement of the set targets

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

## No study was conducted in 2006 but improvement of the reporting system is included in the cMYP 2006-2010

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

4 times – minutes attached Civil organisations who are members of ICC include; - (CHAK)-Christian Health Association of KENYA - (SUPKEM)- Supreme Councils for Kenyan Muslims - Kenya Catholic Secretariat Commission for health and Family Life - AMREF

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.Pentavalent vaccine was introduced in November 2000 and Yellow Fever in 2002

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| Pentavalent | 2 dose vial | 883,400 | 2002 | 17/2/2006 |
|  | 2 dose vial | 1,116,600 |  | 07/04/2006 |
|  | 2 dose vial | 766,800 |  | 12/07/2006 |
|  | 2 dose vial | 450,000 |  | 15/12/2006 |
|  | 2 dose vial | 550,000 |  | 22/12/2006 |
| Total received 2006 |  | 3,766,800 |  |  |
| Yellow fever | No vaccine received in 2006 |  |  |  |

Please report on any problems encountered.

Introduction of Pentavalent vaccine was smooth

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Rapid Result Initiative( RRI), a government initiative to improve performance in all government sectors. Inclusion of measles and full immunization targets in the National Health Sector Strategic Plan (2005-2010). All levels of health services are to work towards this goal.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on : 12th February 2002

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

These funds were received after the introduction of the vaccine and were merged with ISS funds for the next year

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in …2004

Please summarize the major recommendations from the EVSM/VMA

Was an action plan prepared following the EVSM/VMA : No – However EVSM issues are included in the cMYP 2006-2010

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

- Regular forecasting and shipment plans are conducted two months before the beginning of the calendar year. This is in collaboration with UNICEF using the UNICEF forecasting tool. - Quarterly distribution plans are made in line with shipment plans - Frequent monitoring of cold chain status.

The next EVSM/VMA* will be conducted in : 2009

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| AD syringes (GAVI) |  |  |
| Safety boxes |  |  |

Please report on any problems encountered.

No problem encountered-Safety injection practices fully operational at all EPI service delivery points

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

The Government has set aside adequate funds to cater for injection safety up to 2010 All equipments will be procured through government procedures guided by WHO

#### Please report how sharps waste is being disposed of.

- Burning and burying - Incineration

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

Inadequate training for waste handlers and incinerator operators Inadequate resources for putting up incinerators

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

There was no injection safety support received except for the Pentavalent vaccine.

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | 23,463,115 | 23,349,098 | 24,194,932 | 25,109,585 | 26,062,191 |
| Injection supplies | 1,623,932 | 1,824,134 | 2,048,575 | 2,279,060 | 2,524,346 |
| Personnel | 1,822,475 | 1,999, 453 | 2, 039, 442 | 2,080,231 | 2,121,836 |
| Other operational expenditures | 341,948 | 349,827 | 357,885 | 375,867 | 394,425 |
| Cold Chain equipment | 2,924,681 | 1,596,431 | 1,590,367 | 1,622,176 | 1,654,620 |
| Vehicles |  | 72,250 |  |  |  |
| Other | 23,448,031 | 32,520,749 | 34,801,689 | 37,139,209 | 39,578,391 |
| Total Immunization Expenditures |  |  |  |  |  |
| Total Government Health Expenditures | 19,200, 000 |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) | 7,206,200 | 5,169,044 | 5,396,926 | 5, 143,224 | 5,080,675 |
| GAVI | 19,770,887 | 19,580,265 | 20,326,143 | 21,105,923 | 21,919,757 |
| UNICEF | 248,758 | 20,644 | 21,428 | 278,207 | 23,037 |
| WHO | 1,456,079 | 1,643,485 | 1,675,573 | 2,505,823 | 1,755,950 |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify)JICA | 1,596,130 | 1,577,645 | 1,609,198 | 1,641,382 | 6,424,355 |
| Other (please specify) MERCK VACCINE INITIATIVE | 791,416 | 78,246 | 115,185 | 81,408 | 83,036 |
| Total Financing |  |  |  |  |  |

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. DTP-HepB/Hib |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country | 421,610 | 433,688 | 441,356 | 449,098 | 456,913 |
| Total co-financing by country | 1,538,876 | 1,582,962 | 1,610, 950 | 1,639,208 | 1,667,731 |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Total Co-Financing | 1,538,876 | 1,582,962 | 1,610, 950 | 1,639,208 | 1,667,731 |

| Table 3b: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Yellow Fever |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country | 13,173 | 147,25 | 16,165 | 15,790 | 18,633 |
| Total co-financing by country | 10, 538 | 11,780 | 12,932 | 13,632 | 14,906 |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Other (please specify) | 0 | 0 | 0 | 0 | 0 |
| Total Co-Financing | 10, 538 | 11,780 | 12,932 | 13,632 | 14,906 |

| Table 3c: Country Vaccine Co-Financing in US$ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF | √ | BCG,OPV,Measles,T.T, DPT-Heb/Hib | Government of Kenya GAVI (DPT-Heb/Hib) |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) | 2003 | 2007 |  |
| 2nd Awarded Vaccine (specify) | 2003 |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | √ | DTP-HepB-Hip; Yellow fever |  |
| National health sector plan |  |  |  |
| National health budget | √ | DTP-HepB-Hip; Yellow fever |  |
| Medium-term expenditure framework | √ | DTP-HepB-Hip; Yellow fever |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis |  |  |  |
| Annual immunization plan |  |  |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |
| --- | --- |
| 1.Unavailability of adequate government funds |  |
| 2.Lack of interest by the development partners |  |
| 3. |  |
| 4. |  |
| 5. |  |
| Q. 5: Do you foresee challenges with vaccine co-financing in the future? What are these ? |  |
| 1.Difficulty in scaling up the current agreed contribution of US$ 0.30 per dose of DPT-HepB-Hib & US$0.15 per dose of Yellow fever by the national government. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 1374185 | 1402126 | 1427113 | 1452346 | 1477822 | 1503537 | 1529323 | 1555421 |  |
| Infants’ deaths | 96365 | 108384 | 110315 | 112266 | 114236 | 116223 | 118217 | 120234 |  |
| Surviving infants | 1277920 | 1293742 | 1316798 | 1340080 | 1363586 | 1387314 | 1411106 | 1435187 |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 1104993 (86%) | 1158005 (90%) | 1250958 (95%) | 1273076 (95%( | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%) |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 988866 (77%) | 1036453 (80%) | 1250958 (95%) | 1273076 (95%) | 1295407 (95%) | 1317948 (95%) | 1340551 (95%) | 1363428 (95%) |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with yellow fever …......... (new vaccine) | 12600 (39%) | 15506 (47%) | 23560 (60%) | 28421 (70%) | 30257 (80%) | 38716 (90%) | 44481 (100%) |  |  |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 994253 72% | 1022779 (73%) | 1213047 85% | 1234495 85% | 1256149 85% | 1278007 85% | 1299925 85% | 1322108 85% |  |
| Infants vaccinated / to be vaccinated with BCG | 1174712 85% | 1293995 (92%) | 1398572 98% | 1423300 98% | 1448266 98% | 1473466 98% | 1498737 98% | 1524313 98% |  |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 893976 70% | 990768 (77%) | 1185118 90% | 1206072 90% | 1227228 90% | 1248582 90% | 1269996 90% | 1291668 90% |  |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No immediate intention of changing from the current DPT-HepB-Hib-two dose -presentation

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of …… vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

Table 6a (BCG)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 1,452,346 | 1,477,822 |  |
| Doses to be funded by GAVI | 0 | 0 | 0 |
| Doses to be funded by country | 1,452,346 | 1,477,822 |  |
| Country co-pay in US$/dose* | NR | NR | NR |
| Total co-pay | NR | NR | NR |

Table 6b (TT)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 7,261,730 | 7,389,110 | 7,517,685 |
| Doses to be funded by GAVI | 0 | 0 | 0 |
| Doses to be funded by country | 7,261,730 | 7,389,110 | 7,517,685 |
| Country co-pay in US$/dose* | NR | NR | NR |
| Total co-pay | NR | NR | NR |

Table 6c (DPT-HepB/Hib)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 4,020,240 | 4,090,758 | 4,161,942 |
| Doses to be funded by GAVI | 3,578,884 | 3,641,660 | 3,705,029 |
| Doses to be funded by country | 441,356 | 449,098 | 456,913 |
| Country co-pay in US$/dose* | 0.38 | 0.38 | 0.38 |
| Total co-pay | 1,610,950 | 1,639,208 | 1,667,731 |

Table 6d (Measles)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 1,340,080 | 1,363,586 | 1,387,314 |
| Doses to be funded by GAVI | 0 | 0 | 0 |
| Doses to be funded by country | 1,340,080 | 1,363,586 | 1,387,314 |
| Country co-pay in US$/dose* | NR | NR | NR |
| Total co-pay | NR | NR | NR |

Table 6e (Yellow fever)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 28,421 | 30,257 | 32,212 |
| Doses to be funded by GAVI | 12,256 | 14,467 | 13,580 |
| Doses to be funded by country | 16,165 | 15,790 | 18,633 |
| Country co-pay in US$/dose* | 0.25 | 0.25 | 0.25 |
| Total co-pay | 12,932 | 12,632 | 14,906 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same ta rgets as in Table 5)

#### Table 8a (BCG)

Table 8b (TT)

Table 8c (DPT-HepB/Hib)

#### Table 8d (Measles)

Table 8e (Yellow fever)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

N/A

# 4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 15th May 2007 |  |
| Reporting Period (consistent with previous calendar year) | Jan-Dec 2006 |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on | Yes |  |
| DQA reported on | Yes |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) | Yes |  |
| New Vaccine Request including co-financing completed and XL sheet attached | Yes |  |
| Revised request for injection safety completed (where applicable) | Not Applicable |  |
| HSS reported on | No |  |
| ICC minutes attached to the report | Yes |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report | No | Not available |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing