January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Kyrgyz Republic

Date of submission: …………………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

In 2004 GAVI financed purchase of Hepatitis B vaccines with syringes for children under 1 year old. Also GAVI supported injections safety for immunization of children under 2 years old. In 2003 100 000 $ were received to support immunization services, money left in 2003 was used in 2004.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _______________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

In 2004 we followed planned activities In summer of 2004 “Week of enrichment (with vitamins)” was conducted during that period we supplemented children (from 6 months to 5 years old) women recently confined and women who breast fed during 8 weeks after giving birth with vitamin A. In “Week of enrichment (with vitamins)” 438 677 children (from 6 months to 5 years old) were given vitamins which made 97,3%. Also 1 864 women recently confined (were in maternity hospital) and 15 271 women who breast fed during 8 weeks after giving birth. The main problem of immunization-prophylactics was not on time financing from the Government of the KR.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

In May 2004 WHO experts evaluated functioning of cold box at the level of central vaccines storage in the Kyrgyz Republic, basing on these recommendations the project of immunization of republican standards was developed.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH……May           YEAR…2001…….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

In 2004 GAVI provided 320 650 vaccines against Hepatitis B together with 333 400 syringes and 3 600 safe utilization boxes. In total it made 240 000 US $. For prophylactic vaccination for children under 2 years old we received self-blocking syringes and safe utilization boxes which made 74 000 US $. Hepatitis B vaccination (HBV) is being conducted in Kyrgyzstan since 2001 and successfully progressed in 2004. Hepatitis B vaccination was implemented in 2004 and reached 99,2% of coverage. There are no special problems in conducting immunization in the country.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Efforts of Republican Immunization Prophylactics Center and the Ministry of Health of the Kyrgyz Republic, international donors which support immunization service are intended to strengthen nowadays service, keeping high coverage with prophylactic vaccination, modernization of cold boxing, conducting seminars on safe immunization praxis. In 2004 with financial support of UNICEF we conducted teaching seminars for specialists on immunization issues and they talked about Hepatitis B. I Particular: - 9 regional seminars for FMG doctors in 9 remote areas of the country on general questions of immunization-prophylactics, there were 212 participants; - 8 oblast seminars on safe praxis of immunization and implementing of order № 430 from 07.10.04 to work of hospitals of the country, there were more than 300 participants; - 3 regional seminars for doctors – neonatologists and immunization nurses of maternity hospitals and departments on immunization of new-born children, there were 207 participants. Also in 2004 we conducted epidemiological investigation of cases when people who were already immunized got sick with Hepatitis B again in the south of the country. We gathered serum of immunized children under 5 years old and epidemiological and clinical anamnesis with purpose of more precise definition of the diagnosis and reasons of HBV. In the course of epidemiological investigation we found out that increase of Hep B was accordant to seasonal increase of Hep A, which contradicts epidemiology of HPV, which is registered evenly during a year. The diagnosis was given after finding HbsAg in blood of sick children. After repeated serological investigation of sick children (32 serums) marker of critical Hepatitis A was found.. On the basis of conducted investigation a letter was prepared on diagnosing of Hep B. We regularly covered issues of Hepatitis B in Mass Media, TV and Radio. A Guide on issues of Hepatitis B in Kyrgyzstan was prepared on the basis of review of written information, observation and epidemiological analysis and epidemiological control with purpose of increasing of level of information awareness of first level of health care and sanitary-epidemiological service.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

100 000 $ were given to the Kyrgyz republic for supporting of immunization prophylactics service in the beginning of 2003. Plan of distribution of those finance s was approved by the Ministry, spending of finances is planned to implement during several years. 58 320 US $ were left in 2004 in 2004 6 368 US $ were spent out of left money. Out of them: - 4 sets for computers were purchased for 898 $; - 3 refrigerators for remote areas of Naryn oblast were purchased for 830 $; - 995 $ were spent for organizational and overhead expenses of immunization prophylactics service; - 3411 $ were spent for informational provision of immunization prophylactics service; - 234 $ were spent for technical service of cold boxing. There were no problems in using of finance.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Since 2004 GAVI started support on injection safety. In 2004 we received self-blocking syringes and boxes of safe utilization for vaccination of children under 2 years old. The total sum was 74 000 US $. There were no special problems in receiving and distributing.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

In accordance with standards of safe praxis of immunization recommended WHO self-blocking syringes and boxes of safe utilization are used in the country since 2001. Utilization of filled with syringes boxes of safe utilization is conducted by burning them in inaccessible places: in rural area in special holes, furnaces and boiler houses; in urban area – in boiler houses, metal buckets on the place of garbage.

Support provided from GAVI on safety of vaccination will let the Kyrgyz Republic follow injections safety of WHO during several years.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - On time and enough provision of the country’s regions with self-blocking syringes. - On time and enough provision of the country’s regions with SUB. | - 100 % - 100 % | - 100 % - 100 % | 1. 2 Nowadays there are no problems, but starting from 2007 when GAVI finishes supporting of vaccines safety there will a problem with provision of syringes and SUB for vaccination of children under 2 years old. |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Kyrgyzstan didn’t receive cash finance for supporting of injections safety.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2001** | 2002.. | 2003.. | 2004.. | 2005.. | 2006. | 2007.. | 2008.. | 2009.. | 2010.. |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 100 | 100 |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  | 30/70 | 30/70 | 100 | 100 | 100 |
| C: Total funding for …………. (new vaccine) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Decrease of vaccines loss | We toughened control of vaccines storage and vaccination. | Decrease of % of vaccines loss | Many dosage packing of vaccines | DPT-20%; HBV-15%; Measles -20% | DPT-15%; HBV-10%; measles-15% |  |
| 2.Purchase of vaccines on effective prices | Kyrgyzstan purchases vaccines via UNICEF |  |  |  |  |  |

Plan on provision of sustainable financing of immunization program of the Kyrgyz Republic was developed and provided to Secretariat of GAVI in November of 2002. In purpose of Plan implementation we conducted following activities: 1. Received support from GAVI on injections safety from 2004 to 2006. 2. Toughened control on vaccines storage and vaccination to decrease loss of vaccines. 3. Didn’t change National Calendar of prophylactic vaccination. 4. Didn’t conduct campaigns of mass, not planned immunization, therefore it didn't require additional finances. 5. The Government of Japan financed 120 000 $ in terms of annual co-financing on current project of the Japanese grant for purchasing vaccines of on Vaccines Independency Initiatives. 6. The Government signed a credit agreement with Asian Development Bank on purchase of vaccines of API for 2005-2007 on project “Development of children on community base”. Financing of vaccines purchase will be implemented on share principle according to Agreement on Vaccines Independency Initiatives. According to counting from 2005 to 2007 30 % of total vaccines package for children under 8 years old will be paid from state budget, 70 % from ADB. Considering effective and long-term cooperation between Kyrgyzstan and UNICEF especially on purchase of WHO certified vaccines in September 2004 UNICEF and the Ministry of Health (The Government of the Kyrgyz Republic) memorandum was signed on mutual understanding and provision of service of vaccines for children of Kyrgyzstan during 2005-2007. 7. Introduction of HIB infections in the country and Hepatitis B vaccination delayed for indefinite time.

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 102 763 | 112000 | 116000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 |
| Infants’ deaths | 1080 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |
| Surviving infants | 101 683 | 110000 | 114000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 94 758 | 110000 | 114000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 94167 | 110000 | 114000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* ВГВ... (new vaccine) | 101683 | 112000 | 116000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of ВГВ… ( new vaccine) | 94008 | 110000 | 114000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 |
| Wastage rate in 2004 and plan for 2005 beyond*** ВГВ………….. ( new vaccine) | 10% | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 101236 | 112000 | 116000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 89676 | 110000 | 114000 | 118000 | 118000 | 118000 | 118000 | 118000 | 118000 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Since 2002 we define increase of births in accordance of sustainable provision we made prognosis of births increase until 2008 which is used by prophylactics service. Coverage with vaccination against Hepatitis B and other manageable infections in Kyrgyzstan is on level of 98-99 % because of good work of prophylactics service. Defective vaccine against Hepatitis B was not provided to our country.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

In 2005 support of GAVI with HBV to the Kyrgyz Republic ended.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with VAT, DPT, MMR, HBVVacines  (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

No difference

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Coverage of prophylactic vaccination. - Full provision of hospitals with syringes, SUB - Provision of the country with vaccines, syringes for vaccination of children under 2 years old. - Provision of the country with vaccines and syringes for vaccination of children over 2 years old and adults. | - 97 – 98 % - 100 % - 100 % - 100 % | - in 2004 coverage of TAV was 98,5 %; coverage of DPT -3 – 99,3 %; coverage of MMR vaccines – 99,3 %, HBV – 99,2 %. - Provision in 2004 with expense materials for conducting of immunization made up 100 %. - 100 % - 90 % | - No - Lack of financing from the Government of the KR (still there is a debt on VII for 2000-2002 in sum of 105 000 $) - GAVI will support vaccines safety until 2007 because of not enough financing and social and economical situation in the country, starting from 2007 Kyrgyzstan will need support on vaccines safety for children under 2 years old. - Not enough and not on-time financing from the Government of the KR. |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 30.04.05 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ | + |  |
| Injection Safety Reported on | + |  |
| FSP Reported on (progress against country FSP indicators) | + |  |
| Table 2 filled-in | + |  |
| New Vaccine Request completed | + |  |
| Revised request for injection safety completed (where applicable) | + |  |
| ICC minutes attached to the report | + |  |
| Government signatures | + |  |
| ICC endorsed | + |  |

6.  	Comments

ICC/RWG comments:

Interdepartmental Coordination Committee highly evaluates work of Republican Center of immunization prophylactics of the Ministry of Health of the KR in difficult social and economical situation in the country. The Center provides epidemiological well-being in the country, provides sustainable high coverage of prophylactics against manageable infections. Members of Interdepartmental Coordination Committee provide technical and financial assistance in conducting seminars for medical workers on immunization issues, in delivering necessary materials for immunization service.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~