Annual Progress Report 2006

Submitted by

The Government of

LESOTHO

to the

# Date of submission: _15 June 2007________

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of …LESOTHO…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

Signatures Page for HSS

For the Government of ………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Yes, it is reflected in a special vote in the MOHSW; It is jointly managed by the FHD, the EPI unit and Finance section in the PHC Department. The utilisation process is the same as per MOHSW rules and regulations.

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

- Expenditures of the funds were reported to the ICC during their meetings - Two HSAs identified as low performing areas in routine EPI did not submit their micro-plans for the utilisation of funds. - Follow up on the point #2 was done by the MOHSW and CHAL.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 __nil_____________

Remaining funds (carry over) from 2005 _Maloti 209,125______

Balance to be carried over to 2007 __XXXXXXXX_______

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0 |  |  |  |  |
| Injection supplies | 0 |  |  |  |  |
| Personnel | 0 |  |  |  |  |
| Transportation | 0 |  |  |  |  |
| Maintenance and overheads | 0 |  |  |  |  |
| Training | 0 |  |  |  |  |
| IEC / social mobilization | 0 |  |  |  |  |
| Outreach | 0 |  |  |  |  |
| Supervision | 0 |  |  |  |  |
| Monitoring and evaluation | 0 |  |  |  |  |
| Epidemiological surveillance | 0 |  |  |  |  |
| Vehicles | 0 |  |  |  |  |
| Cold chain equipment (repair) | US$ 500 (M3,500) |  |  |  |  |
| Other supportive supervisory visits (specify) | US$ 1,713 (M11,991) |  |  |  |  |
| Total: | US$ 2,213 (M 15,491) |  |  |  |  |
| Remaining funds for next year 2007: | US$ 27,662 (M 193,634) |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

Comprehensive EPI review with WHO and UNICEF… Planning for the Measles SIA is ongoing. Main problem: the high estimated population projects had diluted the EPI coverage in the last five years.

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for _November 2007______

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA ?

The last DQA 2004 recommendations were: - Improving recording practices. - Upgrading the capacity building. - Intensify supportive supervision.

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

X

## If yes, please report on the degree of its implementation and attach the plan.

The implementation of the recommendations was incorporated in the EPI national plan; however the degree of implementation is varied between the different districts. Copy of the EPI national plan is attached. Due to the problem of virus in the computers, it is not possible to copy the plan. It will follow immediately the problem is resolved.

Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.             In 2005 ICC meeting

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

Comprehensive EPI review was conducted in 2006

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

Three meetings in June August and December 2006. The same problem of virus applies here.

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| Hep-B | 10 doses | 7,200 | 2003 | 06/01/2007 |

Please report on any problems encountered.

No problems were encountered.

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Training of nurses and functionaries. - Advocacy and social mobilisation. - Revision of the child booklet to include Hep-B vaccination.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

No funds were received for this activity.

These funds were received on : ______________

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

N/A

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in _Planned to be carried out in 2008________

Please summarize the major recommendations from the EVSM/VMA

Pleases see above 1.2.4.

Was an action plan prepared following the EVSM/VMA : No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

N/A

The next EVSM/VMA* will be conducted in : __2008___________

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in kind as vaccine bundle

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| Safety boxes | 222.4 boxes of 10 each (2,224 pieces) | 06/01/2007 |
| AD syringes 0.5 ml | 1,600 boxes of 100 (160,000) | 06/01/2007 |

Please report on any problems encountered.

No problems were encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

#### The project is not ended, JICA provided injection safety supplies in 2006.

#### Please report how sharps waste is being disposed of.

All hospitals have incinerators, however sharp wastes in the health centres and the health posts are transported to the next level/ hospital for incineration.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

No problems were encountered.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

No cash received.

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | US$ 42,857 |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Other operational expenditures |  |  |  |  |  |
| Cold Chain equipment |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total Immunization Expenditures |  |  |  |  |  |
| Total Government Health Expenditures |  |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  | $25,832 | $1,150,788 | $1,420,175 | $0 |
| GAVI | US$ 50,000 | $52,258 | $1,143,074 | $856,036 | $862,000 |
| UNICEF | $ 45,074 | $200,000 | $300,000 | $300,000 | $300,000 |
| WHO |  | $42,932 | $46,357 | $0 | $74,752 |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

| Table 3a: Country Vaccine Co-Financing in US $...... Not implemented |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3b: Country Vaccine Co-Financing in US $..... Not implemented |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3c: Country Vaccine Co-Financing in US$ ….. Not implemented |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation…. Not implemented |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF |  |  |  |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? Not implemented |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) |  |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ?... Not implemented |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing |  |  |  |
| National health sector plan |  |  |  |
| National health budget |  |  |  |
| Medium-term expenditure framework |  |  |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis |  |  |  |
| Annual immunization plan |  |  |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these? |  |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

No changes; the figures are reflected in the JRF.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 59,708 | 57,327 | 58,473 | 59,642 | 60,834 | 62,050 | 63,291 | 64,556 | 65,847 |
| Infants’ deaths | 9,846 | 648 | 7614 | 7766 | 7921 | 8079 | 841 | 8405 | 8573 |
| Surviving infants | 49,862 | 50,859 | 51,859 | 51,876 | 52,913 | 53,917 | 55,050 | 56,151 | 57,274 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 46,926 | 46872 | 48809 | 48865 | 49740 | 50734 | 51748 | 52782 | 53837 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 45,667 | 46011 | 46811 | 46829 | 47765 | 48720 | 49694 | 50687 | 51700 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 46926 | 46872 | 47809 | 48865 | 49740 | 50734 | 51748 | 52782 | 53837 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of…….… ( new vaccine) | 44604 | 46011 | 46811 | 46829 | 47765 | 48720 | 49694 | 50687 | 51700 |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) | 15% | 10% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | ND | 43228 | 44200 | 45844 | 45500 | 46570 | 47953 | 48500 | 49261 |
| Infants vaccinated / to be vaccinated with BCG | 43551 | 53889 | 54966 | 56065 | 57186 | 58329 | 59495 | 60684 | 61897 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 36075 | 38896 | 39674 | 40467 | 41276 | 42101 | 42943 | 43801 | 44677 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Official MOHSW request for vaccines for 2008 will be submitted to UNICEF.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of …Pentavalent… vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 165,000 | 181,500 | 199,650 |
| Doses to be funded by GAVI | 132,000 | 108,900 | 119,790 |
| Doses to be funded by country | 33,000 (20%) | 72,600 (40%) | 79,860 (40%) |
| Country co-pay in US$/dose* | 115,500 | 254,100 | 279,510 |
| Total co-pay | 115,500 | 632,250 | 698,775 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction (est. cost of US$ 3.5/dose.

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

GAVI is providing Hep-B vaccine only.

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

LESOTHO has not submitted HSS proposal; (planned to be submitted in October 2007 for 2008 grant)

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 05/06/2007 |  |
| Reporting Period (consistent with previous calendar year) | Jan-Dec. 2006 |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |
| ISS reported on | na |  |
| DQA reported on | 2004 recommendations |  |
| Reported on use of 100,000 US$ | na |  |
| Injection Safety Reported on | na |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) | Yes |  |
| New Vaccine Request including co-financing completed and XL sheet attached | Not included |  |
| Revised request for injection safety completed (where applicable) | na |  |
| HSS reported on | na |  |
| ICC minutes attached to the report | Yes |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report | na |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing