Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: LIBERIA

Date of submission: 17 MAY 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

GAVI allocated U$ 606,188 to Liberia for use in 2003 i.e. second implementation year. Because of the postponement of the second year DQA due to security concerns, GAVI Secretariat proposed to MoH&SW that half of the allocated budget for the second year be sent during the 2003 and the other half be sent in 2004 after the DQA has been carried out. In line with this proposal the first trench of the second year GAVI funds came in May 2003 i.e. U$ 305,338. Again because of security concerns the DQA could not be carried out in 2004. However, because of programmatic understanding with the GAVI secretariat and agreed upon timetable to conduct DQA in January 2005, the second trench of the second year GAVI funds was sent in 2004 i.e. U$300,850. Once again the DQA in January 2005 could not be materialized due to reasons unknown to us from the GAVI end. We have proposed to GAVI to conduct DQA in July 2005. The EPI programme used U$11,560,50 of GAVI funds only from the balance(U$ 202,362,41 as of April 2003) and from the first trench of the second year (US 305,338), which was received in may 2003, because of the sudden closure of TRADEVCO BANK due to insecurity of the war in 2003. However, the second trench of the second year budget allocation was not affected as it was sent in 2004 and saved in ECO BANK. Of this amount, the EPI programme has used U$102, 041, 83 for programme activities in 2004. As of today U$496,139.90 is being blocked at the TRADEVCO BANK because of liquidation problem created by the Bank. The ICC through the MoH&SW has attempted to get the funds released, but to no avail. The issue is being brought to court between the Central Bank and the TRADEVCO BANK. In addition to the security concerns and delay in rehabilitation of health facilities, the problem related to the release of funds has affected smooth implementation of the EPI programme, resulting in low coverage figures in 2004. In the last quarter of 2004, reactivation of routine EPI took place after thorough review of EPI activities with and training of all county EPI supervisors. The ICC approved the payment of operational support arrears to all staff for 6 months and agreed to start payment of operational support using the GAVI funds starting from February 2005. As a result of this reactivation process and EPI field staff motivation the coverage of the antigens in the first quarter of 2005 has increases substantially. However, at the same time the remaining GAVI funds from the second trench of the second year, which was received in 2004, have been almost exhausted leaving a balance of only U$101,810,55. This means that unless GAVI support for the third year is released immediately, the reactivation process of routine EPI would have to be slowed down if not halted as there would be no or little operational funds available for the remaining quarters in 2005 for immunization service delivery to be carried out in line with the EPI POA. GAVI funds are used to support routine immunization activities that are endorsed by the ICC. Technical subcommittee of the ICC develops POA, which contains activities that will be supported by GAVI funds, and presents it for ICC approval. Based on the approved POA, quarterly implementation plans, including priority activates and costs, are prepared and presented to ICC for approval. After implementation of the quarterly plans, technical and financial reports are submitted to the ICC. Only activities approved by ICC are funded and implemented using GAVI funds. Minutes of ICC meetings are attached. Requests and reports are cross-checked by the principal signatories, i.e. the Minister of health and WHO or UNICEF representatives. GAVI funds are used: County/district level micro-planning, training, outreach EPI activities Strengthening of supportive supervision and social mobilization at national, county and district levels Operational costs at national, county and district levels (incentives, transport, office equipments and running costs) Cold chain maintenance Multi antigen campaigns

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 US 300,850 (for the second implementation year i.e. 2003)

Remaining funds (carry over) from 2003 US 496,139.90 (being blocked in TRADEVCO BANK)

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 10,085,00 | 6,760,00 | 1,125,00 | 2,200,00 | None |
| Transportation | 1,800,00 | 310,00 | 1,490,00 | None | None |
| Maintenance and overheads | 13,553,08 | None | 13,553,08 | None | None |
| Training | 13,250,00 | None | 13,250,00 | None | None |
| IEC / social mobilization | 28,575,00 | None | 28,575,00 | None | None |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other: petrol products | 34,778,75 | 8,839,50 | 25,039,25 | None | None |
| Bank service | 100,00 | 100,00 | None | None | None |
| Total: | 102,041,83 | 16,009,50 | 83,932,33 | 2,200,00 | None |
| Remaining funds for next year: | 198,808,17 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

A national cold room was installed in early 2004 Cold chain equipments have been put in place in intermediate cold stores and some priority counties in August/September 2004 Cold chain inventory was conducted at the end of 2004 All County and District EPI supervisors were provided with motor bikes for reactivation of EPI services in October 2004 All County Surveillance officers were provided with motor bikes to strengthen the reporting of EPI surveillance activities Intensive social mobilization for routine EPI was conducted during the NIDs in 2004 The Immunization in practice training manuals were adopted and simplified for use by County and District EPI supervisors in November 2004 The EPI Integrated review of 2004 EPI and surveillance activities and planning for 2005 was conducted with all county EPI supervisors and surveillance officers at national level in December 2004 Integrated training for all County EPI supervisors and County surveillance officers was conducted at national level in December 2004 Integrated training for all District EPI supervisors and District surveillance officers was conducted at regional level in December 2004 Operational support was provided to national EPI programme: including incentives to staff, fuel, vehicle maintenance and office running costs Problems: The blockage of GAVI funds in TRADEVCO BANK for routine EPI use The slow rehabilitation of health services, which delayed reactivation of routine EPI Inaccessibility of some areas in early 2004 due to insecurity Delay in resettlement of many displaced persons

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

- DQA is not conducted due to reasons given in 1.1.1. above

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

No studies conducted in 2004. Coverage survey is planned in 2005.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH - June       YEAR - 2002

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Liberia received Yellow Fever vaccine: January 18, 2000: 81,600 doses March 20, 2002: 67,700 doses December 11, 2002: 103,600 doses January 2004: 126,000 doses Problems: Insecurity in routine services delivery Recurrent outbreaks of YF and as a result use of routine YF vaccine for outbreak response immunization

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Strengthening of YF vaccine delivery in all rehabilitated health facilities Boosting infant immunity during outreach activities Improve partner collaboration and coordination Put in place early warning system for epidemics of YF in conjunction with the EPR unit at the MoH Refresher training of EPI supervisors at County and district levels Anticipated Problems: The ending of GAVI support for YF, posing serious setback in programme implementation and serious potential for YF epidemics

#### 1.2.3	Use of GAVI/the Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

No new vaccine introduced in 2004 and no fund received in 2004

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Liberia received injection equipments along with donated Yellow Fever vaccine in January 2004 Problems: No problems encountered

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

As the support of INS is ending at the end of 2005, an understanding was reached with GAVI and Liberian delegation during the January 2005 EPI Programme Managers Meeting for West African Countries in Ouagadougou that Liberia will conduct Injection safety assessment and submit proposal to GAVI in 2005. The assessment is planned for August/September 2005. Problems are anticipated if injection safety equipment would not be provided by GAVI during the 2nd Phase of GAVI

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Proportion of EPI service delivery points using AD syringes for all injectable immunization Assessment of injection safety, availability of Injection safety policy and submittal of proposal to GAVI | The use of AD syringes in all health facilities providing EPI services To develop policy by 2004 | 100% of health facilities providing EPI services have used AD syringes Not achieved | None Insecurity | Continue use of AD syringes in all health facilities providing EPI services 2nd half 2005 |

#### 1.3.3	Statement on use of GAVI/the Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Liberia has not yet received funds for injection safety from GAVI..

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Liberia planned to develop FSP in 2004. However, due to continuous insecurity and problems in bringing together health partners in development within the transitional Government, development of FSP could not be realized. FSP is not expected to be realized in Liberia in 2006 as the elections are planned in October 2005. FSP is being planned to be introduced in Liberia in 2007 and will form part of the National EPI Strategic plan of action 2006-2010, which is expected to be developed in September/October 2005.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 118,448 | 131,400 | 135,312 | 139,402 | 143,584 | 147,892 | 152,328 | 156,898 | 161,605 |
| Births | 134,143 | 160,965 | 165,794 | 170,768 | 175,891 | 181,168 | 186,603 | 182,201 | 197,976 |
| Infants’ deaths | 15,695 | 29,565 | 30,462 | 31,366 | 32,307 | 33,276 | 34,275 | 35,303 | 36,362 |
| Surviving infants | 118,448 | 131,400 | 135,312 | 139,402 | 143,584 | 147,892 | 152,328 | 156,898 | 161,605 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 57066 | 105120 | 115041 | 125462 | 127855 | 147892 | 152328 | 156898 | 161605 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 36399 | 78884 | 87972 | 97581 | 107688 | 125708 | 137095 | 141208 | 145445 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Yellow Fever.. (new vaccine) | 15378 | 78884 | 87972 | 97581 | 107688 | 125708 | 137095 | 141208 | 145445 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | NA | NA | NA | NA | NA | NA | NA | NA | NA |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | NA | NA | NA | NA | NA | NA | NA | NA | NA |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 38455 | 98550 | 109966 | 121977 | 134610 | 157135 | 171369 | 176510 | 181806 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 79942 | 128772 | 140925 | 153691 | 167096 | 181168 | 186603 | 182201 | 197976 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 49854 | 78884 | 87972 | 97581 | 107688 | 125708 | 137095 | 141208 | 145445 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There is a change in the base line and targets starting from 2005. The reason being that different organizations were using different population figures in the past. Recently the Ministry of Planning and Economic Affairs have informed the MoH&SW to use population figures as given by its Ministry for deriving surviving infants. As a result, it was agreed upon to change the target population for EPI. The target population for EPI has changed to 131,400 for the year 2005. The targets set are in line with the current EPI POA and in anticipation to the strategic EPI plan of action 2006-2010, which is expected to be developed in 2005 and in line with GAVI targets of reaching 90% coverage by 2010. As for 2004, the same target population was used and submitted to WHO and UNICEF using the Joint Reporting Form. Thus, there will be no conflict with GAVI targets. However, the increased EPI target population starting from 2005 will mean a challenge for the EPI team in the country to reach the 60% target set aside by the ICC for 2005.

3.2	Availability of revised request for new vaccine (YF vaccine) (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of YF vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Liberia has yet to submit proposal for injection safety support

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Number of children aged 0-11 months receiving: |  |  | Insecurity Delay in the rehabilitation of health facilities. Problem related to the release of funds from the Bank has affected smooth implementation of the EPI program. |  |
| 3 doses of DPT | 60% | 31% (36,399 children aged 0-11 months) |  | No updated target for 2004 but, here is an updated target for 2005 (131,400) |
| 1 dose of BCG | 80% | 60% (79,942 children aged 0-11 months) |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

The ICC is grateful for the continuous support provided by GAVI for routine immunization service delivery in Liberia. Liberia had to face several challenges in the delivery of routine immunization services in 2003 and early 2004, because of problems associated with security. This resulted in low performance of the EPI programme in 2003/2004 and postponement of the DQA several times. Taking in consideration the security situation and lack of conduct of DQA in 2003, GAVI advised the Government of Liberia to divide the Liberian allocation for 2003, which is second implementation year, into two payments in 2003 and 2004. Half of the allocation for 2003 was sent in 2003 and the other half in 2004. The allocation that was sent in 2003 was credited to the then MoH GAVI account in TRADEVCO BANK and the allocation that was sent in 2004 was sent to the MoH GAVI account in ECOBANK. Because of the security problems and subsequent liquidation of TRADEVCO BANK the allocation sent to TRADEVCO BANK and the balance, which was carried over from the first implementation year i.e. 2001/2002, could not be released from the bank. This amounts U$ 496, 139, 90. The ICC through the Minister of Health has attempted to get the money released from the Bank. It has now become a court case between the Central Bank of Liberia and TRADEVKO BANK. The ICC through the Minister will pursue the release of the funds and you will be informed on the outcome. However, the allocation that was sent and credited to the ECOBANK in 2004 was safe and used for the immunization programme. This means that Liberia did not receive GAVI allocation for immunization for the third implementation year that is 2004. In view of this, the ICC decided to use the GAVI funds, which were received in 2004 as part of the second implementation year, with other major EPI projects and emergency health partner’s contribution to augment the GAVI funds to reactivate and strengthen routine immunization service delivery as to avoid total exhaustion of the funds. As a result, GAVI funds were used during the NIDs in October and November 2004 for transportation, social mobilization and operational support as routine EPI was part of the NIDs plan, to augment EPI routine immunization training in December 2004, which was carried out with CVP and surveillance funds, cold chain training and multi antigen outreach immunization activities, which was carried out in the first half of 2005. The GAVI funds, which is remaining for routine immunization service delivery as of May 2005 is U$ 101, 810, 55. This means that the reactivation process of routine immunization service delivery as stipulated in the EPI POA will have to slow down if not halted in the second half of 2005 with anticipated negative impact on infant morbidity and mortality as the remaining fund will not cover implementation of the EPI POA in the remaining quarters of 2005 . The report supposes to reflect progress report for 2004, which is the third implementation year. However, due the reasons given above the ICC finds it extremely important to bring to your attention the necessity of : The release of 2004 GAVI allocation to Liberia in accordance with GAVI guidelines. The release of 2005 GAVI allocation to Liberia in accordance with GAVI guidelines. NB: Please note that GAVI agreed in 2004 to conduct DQA in Liberia in January 2005. However, it was not possible to conduct DQA from GAVI side in January 2005. Consequently we have proposed GAVI to conduct DQA in July 2005.

7.	Signatures

For the Government of Liberia

Signature:	……………………………………………...……………...

Title:	Minister of Health and Social Welfare

Date:             15 May 2005

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | Dr. Eugine Nyarko, WHO Country Representative |  | Rotary International | Mr. David Vinton, Head of . RI Liberia Coordinator |  |
| UNICEF | Ms. Angela Kearney, UNICEF Country Representative |  | (Safe the Children-UK) | Chair NGO (Sector Representative) |  |
| USAID | Dr. Wilbur Thomas, USAID Director |  | National Drug Service | Mr. Tom Gurley, General Manager |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes