January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Malawi

Date of submission: 21st April, 2006 Reporting period: 23rd March, 2005 to 21st April, 2006 ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report [X] Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Malawi did not qualify for the ISS funds. In the GAVI phase II Malawi will submit an application for ISS.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 ___NA____________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

NA

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

Malawi did not qualify for window II support hence no DQA

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

NA

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH January           YEAR 2002

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

A total of 1,849,000 doses of DPT-HepB+Hib were received between March 2005 and November 2005. The vaccines were received in good condition, as has been the case for the past four years. There was good communication about the arrival of vaccines. Below are details of vaccines arrivals and receipts: 23/03/05: 430,600 doses 29/03/05: 71,600 doses 10/06/05: 502,200 doses 01/10/05: 304,600 doses 24/11/05: 540,400 doses

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Supportive supervisory visits to districts - Impact assessment of the pentavalent vaccine on paediatric meningitis at the PBM sentinel surveillance site at Blantyre - District Health Management Teams (DHMTs) conducted follow up visits to health centres to monitor implementation of EPI activities including experiences with new vaccine. - Developed EPI Communication Plan - Review meeting on vaccines wastage surveillance will be conducted in third quarter of 2006. - To scale up RED implementation in the 3rd quarter - To conduct MLM trainings in the third quarter of 2006 - To construct dry store at central level - To finalize comprehensive EPI Multi-Year Plan by May, 2006

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

All the money has been used for: - Training health workers on introduction of new vaccines - Supervisory visits. - Monitoring activities .

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Shipment of some injection materials has been made and we are yet to receive the consignment

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- Malawi introduced AD syringes for all injectable vaccines in January, 2002 and BCG ADs in 2003. - Limited storage capacity for ADs syringes at some health facilities. - Proposed to construct incinerators in some health facilities - To construct dry store warehouse at central level

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Number of health facilities using AD syringes routine in routine and supplemental immunization services | 26 districts using AD syringes. | 100% of the health facilities use ADs for routine and supplemental immunization activities. GAVI has approved safe injection support for 3 years | Limited storage capacities for dry store materials. | NA |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

NA

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The FSP was approved by GAVI Independent Review Committee in January, 2005. The government contributed US$1,000,000 for procurement of DPT-Hep+Hib .

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine GAVI and Government (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2006 | 2007 | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 80 | 80 |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 20 | 20 |  |  |  |  |  |  |  |  |
| C: Total funding for DPT-HepB+Hib (new vaccine) | 100 | 100 |  |  |  |  |  |  |  |  |

GAVI support for new vaccine will end in 2006 and the percentage above reflects the contributions towards the new vaccine in 2006 as calculated in the FSP document. As outlined in previous sections, Malawi introduced the new vaccine in 2002 with 100% contribution by GAVI over a period of 5 years.

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators :  Indicators will be reported in the inception and subsequent reports

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Advocating for the maintenance of the share of funding for EPI to the Ministry of Health | Timely production of annual budget requirements for EPI to Planning department, through SWAp | Funds for new and traditional vaccines have been released | Bureaucratic delays in foreign currency transaction | 0 | One request | Nil |
| 2. Capacity building in vaccine management especially on stock levels, storage space and MDVP | Training of health workers on vaccine management | Capacity building done | It was done on job training due to limited funds | 0 | 50% | Nil |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |  | 2012 | 2013 | 2014 | 2015 | 2016 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Births | 633,252 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 |  | 797,828 | 812,987 | 828,434 | 844,174 | 860,213 | 876,557 |
| Infants’ deaths | 59,654 | 48,480 | 50,113 | 51,415 | 53,524 | 55,301 |  | 56,352 | 57,423 | 58,514 | 59,626 | 60,759 | 61,913 |
| Surviving infants | 573,598 | 637,894 | 659,382 | 676,508 | 704,267 | 727,651 |  | 741,476 | 755,564 | 769,920 | 784,548 | 799,455 | 814,644 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* DPT-HepB+Hib (new vaccine) | 616,943 | 686,374 | 695,305 | 713,365 | 742,636 | 775,122 |  | 789,850 | 804,857 | 828,434 | 844,174 | 860,213 | 876,557 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DPT-HepB+Hib ( new vaccine) | 533,707 | 605,999 | 633,006 | 649,448 | 683,139 | 713,098 |  | 726,646 | 740,453 | 762,220 | 776,703 | 791,460 | 806,498 |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) | 4 | 10 | 9 | 8 | 8 | 7 |  | 7 | 7 | 6 | 6 | 5 | 5 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 400,673 | 480,462 | 510,836 | 545,942 | 583,500 | 626,362 |  | 638,262 | 658,519 | 687,600 | 717,548 | 748,385 | 788,901 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 616,943 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 |  | 797,828 | 812,987 | 828,434 | 844,174 | 860,213 | 876,557 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 471,989 | 542,210 | 573,662 | 602,092 | 640,883 | 669,439 |  | 696,987 | 725,341 | 746,822 | 768,857 | 791,460 | 806,498 |

In the initial GAVI application,  4% was used as  <1 year old proportion. Similarly infant mortality rate reduced from 134 to 104 in 2000 (DHS 2000).  Since 2001 we have been using 5% as <1 year proportion as advised by Health Management Information Unit. This therefore meant an increase in the projected requirements. In 2005 the National Statistics Office (NSO) provided new population projections up to 2010. The figures are slightly higher than those projected by HMIS. As a programme, we are now using these official population projection made by NSO in 2005. This has resulted into the decline in the number of infants deaths in 2006 as compared to 2005. In addition, the infant mortality has dropped from 104 to 76 (DHS 2004)

There was a consensus reached to use the expected number of children to be vaccinated with DPT-HepB+Hib1 for calculation of the requirements and we have been using this formula in the past calculations. For the past two years, the coverage for DPT-HepB+Hib1 has been over 100% as reported in the JRF for 2005 and in the above table.  If we use the live births as our denominator, the coverage for 2005 was 97.42%.

Targets used for DPT-HepB+Hib1: 2007-2009: 98%;  2010-2012: 99%,  and 2013-2016: 100%

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Current new vaccine requirements have taken into account the agreed wastage rate of 10% and use of birth cohort as opposed to surviving infants.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Discussed with UNICEF country Office

Table 4: Estimated number of doses of  DPT-HepB+Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund  (GAVI 80%)

GAVI 80% contribution

*Please report the same figure as in table 3.

Government Contribution: 20%

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6.1 : Estimated supplies for safety of vaccination for the next two years with BCG

Table 6.2 : Estimated supplies for safety of vaccination for the next two years with Measles 2007-2008

Table 6.3 : Estimated supplies for safety of vaccination for the next two years with TT 2007-2008

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The current request is slightly higher than the initial approved requirement because of the use of the population projection by NSO that was provided in 2005.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Reduction of cancelled immunization clinics - DPT-HepB+Hib3 coverage increased - AFP certification status sustained | - 5% reduction by 2005 - Increase coverage to 80% - Detect 2 case per 100,000<15yrs pop | - Reduced from 7% instead of 6% - Coverage increased from 89% to 93% with 96% of the districts achieving >80% coverage - Certification status sustained - Polio-free status documentation approved by ARCC in October, 2005 | Breakdown of bicycles that are used for outreach immunization services | - Reduce by 5% in all health facilities - All district to attain >85% coverage for DPT-HepB+Hib3 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | X | 23rd March, 2005 to 21st April, 2006 |
| Table 1 filled-in | NA | Malawi did qualify for ISS |
| DQA reported on | NA |  |
| Reported on use of 100,000 US$ | X |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) | X |  |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | X |  |
| ICC minutes attached to the report | X |  |
| Government signatures | X |  |
| ICC endorsed |  | To be submitted later |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of      Malawi

Signature:	……………………………………………...……………...

Title:	Ag Director of Preventive Health Services

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Dr H.S. Somanje Director of Preventive Health Services |  |  |  |  |
| WHO | Dr Matshidiso Moeti WR |  |  |  |  |
| UNICEF | Ms Aida Girma UNICEF Rep |  |  |  |  |
| DFID | Christopher Phiri |  |  |  |  |
| USAID |  |  |  |  |  |
| JICA |  |  |  |  |  |

DOCUMENT NUMBER  4: MINUTES OF THE ICC MEETINGS

MINUTES OF THE  INTER-AGENCY COORDINATING COMMITTEE (ICC) MEETING HELD AT WHO BOARD ROOM ON 31st  MARCH, 2005

Present

Dr H. Somanje		MOH (Chairperson)

Dr C. Mwikisa		WHO Rep

Mr H. Mdebwe		UNICEF

Dr R. Banda			WHO

Mrs A.D. Katsulukuta	MOH

Mr C. Phiri			DFID

Mrs E. Mpagaja		USAID

Mr G.Z. Chirwa		MOH

Mr M.J.M. Valle		MOH

### Minute 1/03/2005		Welcome Remarks

The Chairperson welcomed all members present. He apologized for not holding the meeting on 30th March, 2005. He however hoped that members would still contribute constructively to the deliberations.  He later asked them to introduce themselves.

After going through the agenda, one additional was made: Integration of EPI into SWAp.

### Minute 2/03/2005	Measles Supplemental Immunization Activities (SIAs)

The Chairperson begun by explaining the rationale for the proposed national measles SIAs. He indicated that the mini-campaigns that were conducted last year following the measles outbreak did not have significant impact as more and more cases were being reported by districts.  He explained that ICC then agreed to have a national measles SIAs.

The total budget for the measles SIAs was US$1,680,314.00. This follows a reduction from the previous budget as requested by WHO/UNICEF. Members were informed that the UNF  has contributed US$496,000.00 towards the SIAs. It was reported that WHO/ICP had asked the government to raise its contribution to at least 10%. Members on the other hand requested  ICP to make financial contributions towards the SIAs.

It was suggested if funds for IDSR could be used for the SIAs. Members then agreed that the MOH should make a formal request to WHO for the release of US$50,000.00 for the campaign.

Members asked UNICEF and DFID to meet and discuss on release of funds for the supplies for SIAs.

It was reported that UNICEF had received US$100,000.00 for the SIAs. Members then wanted to know if this was part of the pledge made by UNF. It was agreed that UNICEF should find out from ESARO whether the funds are part of the UNF pledged funds and when would US$496,000.00 be released.

### Minute 3/03/2005	Any Other Business

3.1 Integration of EPI Into SWAp

Members sought an explanation from the Chairperson whether EPI is integrated into SWAp. The Chairperson explained that EHP, which is the basis for SWAp, includes EPI and therefore, EPI is well integrated into SWAp.

  - GAVI Documents.

The Programme Manager distributed GAVI Annual Progress Report and UNICEF/WHO Joint Report to members for their comments. She later requested members to endorse the  Safe Injection Proposal that was given to them a couple of months ago for their comments.

### Minute 4/03/2005	Closing Remarks

The Chairperson thanked all the members for their active participation. He suggested that the next meeting be conducted on Wednesday 6th March, 2005 at 3pm.

Inter-Agency Coordinating Committee Meeting Held at Ministry of Health Conference Room 12 th July, 2005

Present:

Dr H.S. Somanje				MoH

Dr Richard Banda				WHO

Mr H. Mdebwe				UNICEF

Mr C. Phiri					DFID

Mrs A. Katsulukuta				MOH

Mrs	Chipazi				USAID

Mr G.Z. Chirwa				MoH

Mr M. Valle					MoH

Minute 1/07/05	Welcome Remarks

The chairman welcomed all members present and asked  for their positive contributions in order to make the forthcoming measles campaign a success.

Minute 2/07/05	Matters Arising from Previous Minutes

Members wanted to know the position of funding from MoH, WHO and UNICEF. It was reported that UNICEF would transfer US$100,000 it got from UNF to Ministry of Health for the measles campaign.  WHO indicated that they had received an e-mail from AFRO indicating that  US$336,183 would be sent for the campaign.

Minute 3/07/05	Progress on the SIAs Preparations

The chairperson started by informing members that for the first time the Government of Malawi would contribute US$1,163,500 for procurement of vaccines, injection materials and all operational costs. He therefore informed members that there will be no shortfall for the campaign.

He then asked the partners to ensure that funds were released on time to start the preparatory activities.

The EPI Programme Manager reported that a National Task Force as `well as various Sub-Committees for the measles campaign were formed.  Similarly, all the districts  reported that they had formed committees to oversee the operation of the campaign..

A programme of events for the measles campaign was circulated and members reviewed it and made some comments which were incorporated. The Chairperson then asked the Secretariat to ensure that the National Task Force should come up with their programme in order for various sub-committees to start operating.

Minute 4/07/05	Any Other Business

The Porgarmme Manager reported that the GAVI Annual Progress Report was sent to GAVI Secretariat and it was reviewed with some clarifications which were submitted to GAVI.

Minute 5/07/05	Closing Remarks

The chairperson thanked all the members for being proactive during the deliberations and hoped that the measles campaign will again be very successful.

Finally he wished every one a safe trip back to their working stations.