12 May, 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Mongolia Date of submission: 12 May, 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _

Remaining funds (carry over) from 2003 _____

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other ( equipment for training) |  |  |  |  |  |
| Total: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

.

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

During June-August of 2004 in Dundgovi and Dornogovi aimags using random selection method, the Immunization coverage survey was conducted among 378 children under two years of age. According to this survey, the coverage of BCG vaccine was 98,5 %, Polio vaccine third dose-98.5%, DTP vaccine first dose- 98.7%, DTP vaccine third dose- 97.7 %, Measles vaccine- 92.7%, Hepatitis B vaccine first dose- 98.2%, third dose- 92.0 % respectively.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.1	   Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH       Jan       YEAR   2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

-Tritanrix HB GlaxoSmithKline Biologicals s.a. Rixensart-Belgium - 52600 doses - Hiberix SB SmithKline Beecham GlaxoSmithKline Biologicals s.a. Rixensart-Belgium-52600 doses - DTP+Hep B+ Hib vaccine (2 doses per vial) received 18.Novermber, 2004. - Status of shipping indicators: DTP+Hep B+ Hib vaccine arrived with good condition of VVM, cold chain monitoring card and 2 pcs of (COX RECORDER ) temperature recorder serial No. 866336, 8663367. - General conditions of shipment: Condition of box on arrival was good and necessary labels was attached with shipping box. - Coolant type: vaccines received with ice packs. There were not any problems during the receiving these vaccines.

#### 1.1.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

1. Release of legislations - The working group on introduction of pentavalent vaccine was established. / Health Minister’s order № 171, 2004 year/ - The National plan of introduction of pentavalent vaccine into EPI/2004-2011/ was approved / Health Minister’s order № 231, 2004 year/ - Open vial policy and rules of the cold chain monitoring was updated. / Health Minister’s order № 189, 2004 year/ - Rules of adverse events following immunization surveillance was updated. / Health Minister’s order № 242, 2004 year/ - From the Governors and Directors of Health Departments of Ulaanbaatar districts, Dornogovi and Govi-Sumber aimags have been prepared plans to introduce the pentavalent vaccine - Preparation of introduction of pentavalent vaccine 2.1 Safe injection - Procurement of safe immunization equipments - Introduction of AD syringes into whole immunization services - Developed the guidelines on safe injection technique and using of AD syringes 2.2 Procurement of pentavalent vaccine, needed for 2005 and it’s distribution to the first phase sites The instruction of pentavalent vaccine has been translated into Mongolian and distributed to all immunization units 2.3 Cold chain - The cold chain capacity has been assessed and the readiness for receiving vaccines has been provided 2.4 Report forms: - Immunization cards and coverage data reporting forms have been revised to reflect the addition of pentavalent vaccine - Other related reporting forms are revised 2.5Training and advocacy: - Conducting the National workshop on ”Introduction of pentavalent vaccine into the National EPI “ for Directors of all aimags and district Health Departments and Specialized Inspection Agency ( 60 ) - Training of trainers on introduction of pentavalent vaccine (114 health workers ) - Training of vaccinators ( 2200 people ) - Some necessary equipment for the training have been purchased - Developed, printed and distributed the guideline “Pentavalent vaccine” for medical workers ( 3000 copies) - Printed and distributed the leaflet for parents about pentavalent vaccine ( 32000 copies ) - Broadcasting of announcements by radio ( 90 times ) and TV ( 48 times ) According to the Health Minister’s order no. 213 from September 2004, The National plan of phase introduction of pentavalent vaccine was approved and starting from January 1, 2005 the pentavalent vaccine was introduced into the National EPI. By 2005 the new vaccine will be covered 6 distict of Ulaanbaatar (UB) city, Dornogovi and Govisumber, from 2006 to 2008 all the rest aimags. In 2008 the pentavalent vaccine will be introduced all over the country. In the frame of preparational work following activities have been done: - An appropriate legislations have been released, such as Health Minister’s order, UB city district and aimag‘s Health Departments Directors orders, aimags Governors orders; - The National workshop on “ Introduction of pentavalent vaccine into the National EPI” was held in November,2004 - Several training sessions have conducted for medical workers and immunization voluntary activities as well; - The sites of introduction of pentavalent vaccine were provided the training equipment and devices; - Vaccine procurement has been done on time; - Safety injection equipment has been disributed to the sites on time; - On January 3, 2005 at the Sukhbaatar District Heath Department, Ulaanbaatar City there was the openining ceremony of “ Introduction of pentavalent vaccine” held in this ceremony, there were Vice-Minister of Health, other officials from the MOH, UB city and District Governors, Representatives of WHO and UNICEF and other International Organizations have participated. This ceremony has been advertized widely through mass media at nation wide. In 2004, the immunization activities funded by the National Immunization Fund there were 247,200 doses of BCG on 54,013,200 tugrugs, 160,000 doses of polio vaccine on 51,520,000 tugrugs, 60 cold boxes on 7,200,000 tugrigs 812,346 syringes on 48,145,725 tugrugs have been purchased (27 % of all budget for EPI antigens), respectivily and around 3,339,800 tugrugs has spent for transportation of vaccines. Encountered problem: - There is no standard method for distroying used syringes and infrastructure for waste disposal item at all levels (for instance, installation of high –temperature incenerators). -Local manufacture “Monsam” is a private Mongolian-Korean joint venture in Mongolia, which is produces only disposable syringes. The local manufacture need financing support to cover technology transfers that will enable to produce AD syringes locally. Technology transfers is advantage of the sustainability to use AD syringe after GAVI.

#### 1.1.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Training – 10,226 US $ - Conducting the National workshop on ”Introduction of pentavalent vaccine into the National EPI “ for Directors of all aimags and district Health Departments and Specialized Inspection Agency ( 60 ) - Training of trainers on introduction of pentavalent vaccine (114 health workers ) - Training of vaccinators ( 2200 people ) Outputs of the training: - Adopted the knowledge about the immunization activity and particularly pentavalent vaccine among the decision makers - Upgrading the knowledge in safety injection and injection technique in accordance with introduction of pentavalent vaccine. - Improvement of the activity of health volunteers Communication advocacy and manual and guideline- 8,770 US $ - Developed, printed and distributed the guideline “Pentavalent vaccine” for medical workers ( 3000 copies) - Printed and distributed the leaflet for parents about pentavalent vaccine ( 32000 copies ) - Broadcasting of announcements by radio ( 90 times ) and TV ( 48 times ) Training equipment – 8,024 US $ - Some necessary equipment for the training have been purchased (shuch as LCD projector, photecopy machine, computer e.g) Monitoring visit- 750 US $ - 6 districts of UB city - 5 soums of Dornogovi aimag’ ( Sainshand, Khovsgol, Zuunbayan, Khatanbulag and Sulinkheer) - And 3 soums of Govi-Sumber aimag’ (Choir, Bayantal, Shivee-Ovoo soums) - 116 out of 6000 children administered DTP+Hep B+ Hib vaccine were randomly selected studied on AEFI in Ulaanbaatar, Dornogovi and Govi-Sumber. No more serious reactions and complication were registered after Pentavalent vaccine. Total- 27,770 US $, which means 27% of 100,000 US $

## Injection Safety

#### 1.2.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

1.Supplies for new and under used vaccines: - AD syringes for DTP+ Hep B +Hib 53,700 pcs and Reconstitution syringes – 29,900 pcs with 925 pcs Safety box received 30.Dec,2004 2. Supplies for injection safety -AD syringes for other vaccines- 475,900 pcs, and reconstitution syringes for measles- 9,700 pcs, - AD syringes for BCG -61,300 pcs and Reconstitution syringes for BCG – 6,300 pcs, - Safety boxes – 6,175 pcs received 16 Feb, 2005. All above supplies new and under used vaccines and Supplies for injection safety meets with our requested amount. There were no any problems

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### AD syringes are used for all immunization vaccines starting from January, 1, 2005. Now days we have distributed 226.500 pcs of AD syringes. Used AD syringes are wasted into the safety boxes and destroying open burnings. In the frame of the safe immunization project, there is project of installation of incinerators has been implementing and its installation in. The training on safe immunization technique have been conducted among 300 UB city and aimags’ medical workers. TYCO / Healthcare / monoject* KI* Auto Disable Syringe with Needle 0,.5ml 0.6.x25 mm ( 23Gx1) UK AD syringes are weak and there are same cases noticed that syringes were broken during the injection procedure. We would like to change the Autodestruct syringe, 0.5 ml into DestroJect GmbH Medical Devices , which meets requirements of WHO/UNICEF Standard E8/DS.1.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage of DTP-3 vaccine Proportion of immunization units with adequate supply of injection safety equipment Vaccine wastage rate DTP | 95% 100% 1,5 | 98,9% 100% 1,8 | National policy was unused open vial discarded after sessions. /see 15 page/ |  |

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/ The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial sustainability plan of immunization activity is not developed. We are planning to develop this plan in September 2005 with the support of WHO consultant.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| A: Proportion funded by GAVI/VF (%)*** | 25 | 50 | 75 | 100 | 100 | 100 | 50 | - | - | - |
| B: Proportion funded by the Government and other sources (%) | - | - | - | - | - | - | 50 | 100 | 100 | 100 |
| C: Total funding for DTP+HepB+ Hib (new vaccine) | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators: NA

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 44461 | 46917 | 47950 | 49005 | 50083 | 51185 | 52311 | 53462 | 54638 |
| Infants’ deaths | 1016 | 1102 | 1126 | 1151 | 1176 | 1202 | 1229 | 1256 | 1283 |
| Surviving infants | 43445 | 45815 | 46824 | 47854 | 48907 | 49983 | 51082 | 52206 | 53355 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 42691 | 32922 | 18878 | 9174 | - | - | - | - | - |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 43043 | 32182 | 18454 | 8969 | - | - | - | - | - |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* DTP+HepB+ Hib (new vaccine) | - | 11850 | 26610 | 37130 | 47152 | 48691 | 49763 | 50857 | 51976 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP+HepB+ Hib ( new vaccine) | - | 11800 | 26497 | 36971 | 46950 | 48483 | 49550 | 50640 | 51754 |
| Wastage rate in 2004 and plan for 2005 beyond*** DTP+HepB+ Hib . ( new vaccine) | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 43406 | 45040 | 46032 | 47045 | 48080 | 49649 | 50742 | 51858 | 52999 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 44064 | 43524 | 44951 | 45940 | 46950 | 47983 | 49039 | 50118 | 51220 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- Under we have been mentioned some changes into the baseline targets and wastage rates. - In 2004, The birth was less than estimated. - In 2004 the vaccine wastage factor was increased 1.8 ( this indication last year was 1.5). The reason is: National policy was unused open vial discarded after sessions. 93% were wasted according to open vial policy. In order to reduce the vaccine wastage rate, on January 1, 2005 has been approved the Health Minister’s order no. 189 according to the some changes in open vial policy, e.g. open vial liquid vaccines can be kept for subsequent sessions up to a week.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No

Table 4: Estimated number of doses of DTP+HepB+ Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

3.4 Table 6: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

3.5. Table 7: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

  - Table 8: Estimated supplies for safety of vaccination for the next two years with measles (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.6. Table 9: Estimated supplies for safety of vaccination for the next two years with  HepB -birth dose/(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.7. Table 10: Estimated supplies for safety of vaccination for the next two years with  HepB –doses 2-3(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.7. Table 11: Estimated supplies for safety of vaccination for the next two years with  DT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

If quantity of current request from the GAVI letter of approval, please present the justification for that difference.

No

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 12. May.2005 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | √ |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ | √ |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in | √ |  |
| New Vaccine Request completed | √ |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report | √ |  |
| Government signatures | √ |  |
| ICC endorsed | 12.May. 2005 |  |

6.  	Comments

ICC/RWG comments:

RWG meeting was held on 15 October, 2004 in the building of MOH. At this meeting were discussed: - The status of Hib surveillance; - The National plan of introduction of pentavalent vaccine into EPI. Following comments have been done: - Any changes of the introduction plan should be discussed by ICC - To submit progress reports to GAVI every year - To reflect the financial sustainability plan of supply of pentavalent vaccine and AD syringes after GAVI - To change the receiving of birth dose of vaccines within 24-48 hours ( according to National Schedule ) into within 24 hours During the period of preparation the Inter Agency Coordinating Committee ( ICC ) meeting were held twice. ( Minutes taken from these meetings are attached). Main topics discussed during the first meeting are: - Submission of the proposal by the MOH to GAVI - Updating the perspective financial plan of immunization program Main agenda of the second meeting is: - Report of the activities implement the plan of introduction of pentavalent vaccine and future activities. Some main comments, given by ICC members are: - Mongolia is the first country in the region, introducing pentavalent vaccine. New vaccine distribution from the center to aimags and soums is coming with the same time of winter season, so the implementing team should consider vaccine freezing during transportation and storage. - There is a need to train more medical personnels to the use of AD syringes and AEFI surveillance. - In the frame of the project “ Health Sector Development”, ADB is able to support the training of family doctors on new vaccine - ADRA International Non-government organization in the frame of it’s project, implementing in Zavkhan aimag is ready to assist in the introduction of new vaccine in Zavkhan aimag.

- Signatures

For the Government of ……….Mongolia ……..………………………………..

Signature:	……………………………………………...………………………..

Title: ………………………….Sh. Enkhbat, MD, PhD, DSc ( Med)…………….

Vice Minister of Health and Chairman of ICC

Date: ………….……………….12. May.2005…………………………………..

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/ Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Sh. Enkhbat, MD, PhD, DSc ( Med) Vice Minister of Health and Chairman of ICC | 12. May,2005 | WHO | Mr. Robert Hagan (Resident Representative ) | 12. May,2005 |
| Ministry of Health | D. Narangerel, MD, MSc, (Officer in charge of Communicable Diseases Control and National EPI Manager) | 12. May,2005 | WHO | J. Mendsaikhan MD, PhD, (EPI program In-country Advisor) | 12. May,2005 |
| National Centre for Communicable Diseases | N.Tsend, MD, PhD, (Deputy Director ) | 12. May,2005 | UNICEF | Mr. Richard Prado (Resident Representative) | 12. May,2005 |
| Public Health Institute | Mr. J. Oyunbileg, PhD, DSc ( biol) ( Deputy Director) | 12. May,2005 | JICA | Mr. Yoshio Kanzaki (Resident Representative) | 12. May,2005 |
| Ministry of Finance and Economy | Mr. J. Ochirvaani, ( Officer) | 12. May,2005 | ADB | G.Dashzeveg, MD, PhD, (Consultant, “Health Sector Development” project ) | 12. May,2005 |