January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: MOZAMBIQUE

Date of submission: 7th August 2005………………………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report 4th Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The National Health Directorate is the overall management institution for the ISS Funds within the Ministry of Health. A bank account named GAVI Fund has been opened. Once the funds are transferred by GAVI Secretariat and become available in this bank account, the information is passed on to the EPI manager, who with his team prepares and proposes the funding allocation for the different components of EPI. This proposal is then discussed with the Deputy National Director for Community Health, before its submission to the ICC for its approval. At last, the approved proposal is submitted to the National Director of Health, who authorizes its implementation. Once the implementation starts, it is the Deputy National Director for Community Health who controls the funding usage. A financial report was presented to the ICC members in the first quarter of 2004. A total of USD 95,109 was spent in 2004. The areas of expenditures are discriminated as shown bellow: Stationary, Supplies & maintenance US $ 908 Provincial/distriral and Health facility level Supervision US $ 66,590 Salaries for recruited staff + Staff Overtime payment US $ 18,440 Transport of materials to the provinces US $ 6,841 Fuel US $ 2,151 Other Expenditures US $ 179 TOTAL US $ 95,109 Distribution of Expenditure by level Level; Expenditures; (%). Central; 28,519; 30 %. Provincial + District leves*; 66,590; 70 %. Total; 95,109; 100 %. In general, no problems were encountered in the use of these funding.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 __US 329,000 received in the first quarter of 2004

Remaining funds (carry over) from 2003 –  118,751.63

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 4,744,300 | 2,054,000 (Gov) |  |  | 2,690,300 GAVI |
| Injection supplies | 861,000 | 567,000 |  |  | 294,000 GAVI |
| Personnel | 1,997,801 | 15,319.14 | 1,796,481.86 |  | OMS AFP/Disease Surveillance Focal Points officers 171,000 + 15,000 |
| Transportation | 203,775 | 2,827.3 | 158,447.7 |  | 42,500 OMS |
| Maintenance and overheads | 1,022,788 | 5,957.4 | 1,016,830.6 |  |  |
| Training | 530,004 |  | 312,703 |  | 190,000 + 27,301 (UNICEF) |
| IEC / social mobilization | 740,967 |  | 595,967 |  | 145,000 OMS community involvement |
| Outreach | 37,585 |  |  |  | 22,949 OMS Npla RED + 14,636 (UNICEF) |
| Supervision | 106,000 | 6,000 OMS |  |  | 100,000 OMS Disease Surveillance + 76,754 (GAVI) |
| Monitoring and evaluation | 51,975 |  |  |  | 51,975 |
| Epidemiological surveillance | 311,543 |  | 110,591 |  | 200,952 |
| Vehicles | 76,175.48 |  |  |  | 76,175 (OMS) |
| Cold chain equipment | 143,166 |  |  |  | 143,166 (UNICEF) |
| Other - Software | 11,670.45 |  |  |  | 11,670.45 (UNICEF) |
| Computer equipment | 5,679 |  |  |  | 5,679 (UNICEF) |
| Office furniture | 750,000 |  |  |  | 750 (UNICEF) |
| Operational Research |  |  |  |  | 7,864 (GAVI) |
| Total: | 11,588,749.93 | 2,651,103.84 | 3,991,021.16 |  | 4,938,803.93 |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

The funds allocation was not discussed in ICC meetings. The major activities conducted to strengthen immunization in 2004 were as follow: - Health worker training on EPI management during seminars - Provincial and district level Supervision and in job training - Distribution of motorcycle to increase out reach activities (through monthly health days strategy). - Injection safety survey - Conducted a study on best practices of Mobile Teams - EPI inventory (cold-chain equipment, personnel, transport, et.) - Started the pilot test of the new instruments of data collection (DQA recommendations), to be finalized in April 2005. Difficulties encountered; Activities undertaken to address these issues. Humana resources; Inadequate (shortage) staffing at central level; It has not been allocated additional staff yet. So the shortage still remains.. Weak management capacity in logistic system; There were two regional trainings in vaccine management and logistics for provincial level. The provinces in their turn, conducted trainings at district level for front line staff. There has also been supervision of staff at district level.. Overloaded staff (Usually one person is in charge of many health activities at district level); This situation is being gradually solved through specific training in different areas, such as preventive medicine (this include EPI matters), maternal and child health care, midwifery, nursing, etc. and their recruitment and allocation to provincial/district levels.. Institutional; Poor planning and weak management of mobile brigades (outreach activities); A plan of a action to conduct a survey on mobile brigades functioning was developed and implemented in early 2004, financed by Hope-USAID. Based on the results of the study, a meeting to share the best practices took place between July and September 2¦004.. Limited implementation of out reach activities (mobile brigades); We continued to allocate more motorbikes and vehicles to provinces/districts to improve access to immunization through outreach teams (implementing monthly health days). In addition funds for out reach services expenditures were also made available to districts. In 2004, we also started to implement RED approach in 5 districts of Nampula province. However, this improvement is still insufficient compared to the needs.. Cold chain; Cold chain break-down, partially due to lack of spare parts; A list of basic spare part materials necessaries to maintain functional refrigerators and freezers, and a list of appropriate dealers available in the market was sent to the provinces in order to allow them to easily budget locally and get them. We continued to train users in proper basic maintenance of the cold- chain. We also continued to repair the broken cold-chain...

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

Yes. The pilot test finished on 30th April. This pilot study last 6 months and involved six health facilities in Urban and Rural areas of Maputo City and Maputo province, some of them with mobile brigade teams (outreach services). The introduction of the new data collection tools and vaccination-recording book begins in June, and along the following months will be the scaling up over the country. By 1st January 2006 EPI at all levels will be using the new tools. The training of data managers’ focal points will be conducted in each province. These regional data managers, to be selected among the existing health staff, will be trained in November 2005, to take care of a number of districts (maximum 4). Their task would consist of supporting the districts in the process of improving the quality of data they collect, the analysis and local decision-making process (not only for EPI, but for all health data collected in the district) in the districts under their responsibility, at the same time they would help build local capacity. Due to the measles campaign, the training process at provincial level will take place in he first week of the last three months of 2005, beginning in northern region, where the campaign ends in September. In this first phase, all provincial and district EPI managers will be trained in usage of the new tools. Besides the EPI managers, the provinces and districts will be invited to indicate three and one additional people, respectively, to participate in the training. All these people, at each province, will be responsible for the scaling up of the process in the following two weeks, in their respective provinces. This will be done the same way it was in the measles campaign micro planning process. Table 1. Planned number of participants in Data Quality Management Training PROVINCE; Nr. of Provincial Participants (include EPI Managers); Nr. of District Participants (include EPI Managers); Total participants; Training period. Niassa; 4; 16 dist x 2 = 32; 36; 1st week Oct. Cabo-Delgado; 4; 17 dist x 2 = 34; 38; 1st week Oct. Nampula; 5; 21 dist x 2 = 42; 47; 1st week Oct. Zambézia; 4; 17 dist x 2 = 34; 38; 1st week Nov. Tete; 4; 13 dist x 2 = 26; 30; 1st week Nov. Manica; 4; 10 dist x 2 = 20; 24; 1st week Nov. Sofala; 4; 13 dist x 2 = 26; 30; 1st week Nov. Inhambane; 4; 14 dist x 2 = 28; 32; 1st week Dec. Gaza; 4; 12 dist x 2 = 24; 28; 1st week Dec. Maputo Prov; 4; 08 dist x 2 = 16; 20; 1st week Dec. Maputo City; 4; 03 dist x 2 = 06; 10; 1st week Dec. Total; 45; 288; 333. This activity will be covered using GAVI funds that are still available in our bank account. Given this delay in implementing the corrective measures to improve the quality of the data, we believe that the next DQA can really take place from 2007, if it is intended to measure the extent to which the improvement took place after the implementation of the plan. At central level, procedures to monitor timely reporting from provincial/district levels were set. At central level, data is now monitored by district. EPI Manual was revised and will be reproduced. Norms and procedures for data management were revised taking into account the DQA recommendations.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

The plan of action was discussed with only two members of ICC, namely WHO and UNICEF.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Injection safety Mobile brigades EPI Inventory Pilot test of the new data collection tools

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH July…………..           YEAR 2001……….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

DPT/Hepatitis B Up to date, no problems were encountered with regard to the reception of the vaccine. The vaccine has always been received in expected quantities, in good conditions and according to the delivery plan. In some cases there has been some delays, but these were previously communicated to EPI central store, and did not result in any stock outs.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

In relation to introduction of new vaccines (Pentavalent) There has been conducted a Rapid Assessment to determine the prevalence of Haemophilus Influenzae type B. The study was took place in four sites, namely Inhambane, Sofala, Nampula and Maputo province.The study found a high prevalence, but reliable data in this assessment was collected only in one surveillance site. On the other hand, the uncertainty about the cost of pentavalent in the future and the uncertainty about the future GAVI funding to the country, were the main reasons why this issue has never been discussed deeply. In relation to services strengthening Conducted MLM courses for provincial and District EPI managers in 2 northern and 3 central provinces. Trained all together 99 Health workers. Vaccine management tool – it was installed a vaccine management tool, which improved considerable the vaccine stock control at central level, and allowed a much easier follow-up of vaccine consumption at provincial level. Supervision to peripheral levels Acquisition of cars and motorbikes to strengthen services at peripheral levels. However they were sent to provinces/districts at the beginning of 2005 Allocation of additional funds to the provinces and districts for supervision and out reach activities. In relation to phasing in For 2006 DPT/Hepatitis B vaccine co-payment, please see appendix A (DPT/Hepatitis B vaccine forecast and co-payment plan) The country is going to completely take over the injection safety supplies for all injectable vaccines in the program. With regard to DPT/Hepatitis B, Mozambique intends to phase in about 15% from a baseline of $2,621,000 per year – for details, please see appendix A – (cost estimates and phasing in plan).

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

From $100,000 (2,000,000,000 MZM, 20,000 MZM/US $) available at the beginning of the year, it has been allocated to central level $7,864.38 (157,287,500.00 MZM), and $ 76,753.75 (1,535,075,000.00 MZM) totalising $ 84,618.13 (1,692,362,500.00 MZM). The amount allocated centrally, was essentially spent on seminars to discuss and implement the plan of action to improve the quality of data. At provincial/district level it was spent on supervision from provincial to district and from district to health facility level.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Syringes and safety boxes were received timely and no problems were encountered regarding their distribution and availability at the health facility level.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### Mozambique will be taking over the injection safety supplies for routine EPI completely from 2006. The money will be allocated by the Government and channeled through the Common Fund for Vaccines and Drugs. Additionally, USAID is financing through JSI a 5 years medical-injection safety intervention from 2004 -2009. By 2007 the project should have expanded gradually from pilot sites to 70 health facilities in all main cities of the country and 3 rural hospitals.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicator 1 (Adequacy of syringe and needle at the health facility level) | Verification means | Target for 2004 | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- | --- |
| Proportion of Health facilities providing EPI services supplied with AD syringes | Plan of distribution/ local feed-back Supervision Reports - feed-back on the AD syringes availability in health facilities | 100% | 100% | None | No change made |
| Adequate delivery of syringes to each facility | Supervision Reports - feed-back on the AD syringes delivery (timeliness and in adequate quantities) | 100% | 100% | None | No change made |
| Quality and sterility of syringes | Supervision Reports - feed-back on the expiry date, certified brand | 100% of syringes up-to-date with standard quality | 100% | None | No changes made |
| Indicator 2 (Disposal of used injection equipment) |  |  |  |  |  |
| Proportion of Health facilities providing EPI services supplied with AD safety boxes | Plan of distribution/ local feed-back Supervision Reports - feed-back on the AD safety boxes availability in health facilities | 100% | 100% | None | No changes made |
| Availability of an accessible incinerator | Supervision Reports - feed-back on the availability of accessible incinerators for health facilities | 6.33% (according to the injection safety survey conducted in March 2004 in a sampling of 80 health facilities | Functional Incinerators are not available in most of the health facilities. Burning and burial is the main waste destruction method in almost all health facilities with immunization activities. (*) | None | No changes made |
| Presence of used syringes and needles in garbage, dumping area or vicinity of the health facility* | Supervision Reports - feed-back on the presence of used syringes and needles in garbage, dumping area or vicinity of health facilities | 10% | See Injection Safety Survey | None | No changes made |
| Indicator 3 (a) (Number of abscesses following) injection reported (AEFI) | Provincial reports - number of reported abscesses following injection | 5% | It will be difficult to monitor adequately this indicator. | Lack of adequate monitoring system . |  |
| (*) However, a plan of building incinerators to be placed in health facilities strategically situated to serve also a number of other health facilities is in course. As for the health facilities with difficult access to the locals with an incinerator, the burning and burial method will continue to be used, until it becomes possible to build an incinerator in these places. As a first investment, almost 300 incinerators are planned to be built. However the last decision will depend on the decision to be taken by a task force, which is currently working on a national strategic plan for waste management. (a) This indicator is difficult to collect. It s collection needs a community survey but we feel that asking questions to the community on this aspect, which is not a concern may have a side effect of diverting from EPI activities. However, the EPI sector together with Health Information System Department has started to prepare the tally sheet to collecting these data at the Health Facility level. |  |  |  |  |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Mozambique receives this support in injection safety devices.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five-year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 100 | 100 |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

Taking into account the condition of a maximum of 500% GAVI/VF support, Mozambique has no other choice than taking over completely from 2006, given that the country is at its last year of GAVI support, therefore, with no chance to spread it out over years as shown in the example above. This means that if GAVI/VF withdraws completely from 2006, the MoH will have to deviate resources from other programs to fill the gap. This is not a suitable way to go, and the country believes that GAVI could find a way to continue supporting the country and allow it a much smoother transition. For a proposed phasing in by the government, please see appendix D (Cost estimates and phasing in plan).

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Advocacy to improve Government and Partners contribution to EPI program | No specific action was needed as EPI has always been a priority for the MoH | There was an increase in the budget allocated to the EPI | No problems encountered | Resource allocation to EPI in 2000 – USD 4,6 million | Resource allocation to EPI in 2004 – USD 8,7 million | The FSP was updated. However, in terms of strategy, no changes were proposed. |
| 2. Increase Program efficiency | Reduce the wastage and drop out rates; improve planning, management and better program integration at district level; improve social mobilization and community involvement, particularly in EPI outreach activities; training and supervision at all levels | Wastage was reduced to less than 15%; the dropout rate decreased to less than 18%; EPI is integrated with micronutrients supplementation (Vit A), antenatal care, growth monitoring and health education. There has been training of EPI managers at all levels, using MLM training materials. |  | Wastage rate: 25% Dropout rate: 22% No specific strategy for EPI social mobilization No funds available for specific supervision at provincial/district and health facility levels No specific booklet for EPI health education subjects | Wastage rate: 13% Dropout rate: 16% Designed a specific EPI social mobilization strategy Used ISS funds for specific supervision at provincial, district and health facility levels. Developed an EPI health education booklet, to be used as a guideline in EPI health education sessions | The strategy was essentially training of health staff and supervision at all levels; assure community involvement in the planning of outreach services |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 853,758 | 874,640 | 895,632 | 917,127 | 939,138 | 961,677 | 984,757 | 1,008,392 | 1,032,593 |
| Infants’ deaths | 94,862 | 97,182 | 99,515 | 101,903 | 104,349 | 106,853 | 109,417 | 112,044 | 114,733 |
| Surviving infants | 758,896 | 777,458 | 796,117 | 815,224 | 834,789 | 854,824 | 875,340 | 896,348 | 917,860 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | NA | NA | NA | NA | NA | NA | NA | NA | NA |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | NA | NA | NA | NA | NA | NA | NA | NA | NA |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1/Hep B)* …......... (new vaccine) | 769,411 | 682,219 | 737,403 | 763,050 | 789,902 | 816,785 | 836,387 | 856,461 | 877,016 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine - DPT/Hep B) | 666,604 | 644,318 | 698,593 | 731,256 | 765,084 | 791,781 | 810784 | 830,242 | 850,168 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 20 % | 15 % | 13 % | 11 % | 10 % | 10 % | 10 % | 10 % | 10 % |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 810,226 | 758,022 | 796,611 | 835,604 | 876,529 | 908,251 | 951,932 | 985,983 | 1,009,647 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 870,425 | 723,036 | 756,311 | 774,463 | 793,050 | 812,083 | 831,573 | 851,531 | 871,967 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 683,984 | 659,479 | 690,831 | 715,359 | 732,528 | 750,108 | 768,111 | 786,545 | 805,423 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- According to the census projections, the population of 2005 is higher than the one of the years 2006 and 2007. This is because the projection of the population of Maputo City is missing from 2006. For calculation in this report, it has been used the 2.4% of population growth (this is the estimate of the last population census in 1997) to estimate the size of the population in the following years, and this way, estimate the needs for immunization program. - In what concerns the wastage rate, the country it was supposed reach less than 15% wastage at the third year of GAVI support. Unfortunately, for reasons behind our control, we do not know yet what is our precise wastage in the country, given that only in 2004 a small number of districts started to report their wastage, despite all efforts by central level to get this information (We recall that the reporting of data by district started in 2003). However, with the implementation of the new multidose vial policy, we believe that wastage will decrease substantially.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The country did not make any request of new vaccine presentation.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets |  | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- | --- |
| Coverage Rate DPT/Hep B | 2003 | 2004 | - 1.4% | Data not reliable | No update made |
|  | 91.5% | 90.1% |  |  |  |
| Drop out Rate DPT/Hep B | 11.2% | 11% | - 0.2% | Data not reliable | No update made |
| Wastage Rate | 7.3% | 14.7% (*) | + 7.4% | Data not reliable | No update made |

(*) in 2003, the wastage rate was reported by only 7 districts out of 144. In 2004, the reporting districts increased to 79 out of 144. So, the increase of seen in the wastage rate, does not mean the worsening of the situation.

- Please note that according to the last Health Demographic Survey conducted in 2003, the DPT3 coverage was estimated at 71%, representing 11% increase compared to QUIBB Survey held in 2001 (60%). In the mean time, according to our administrative data, our progress from 2003 to 2004 was – 1.4%. It its difficult to explain this slight decrease, as there is no any clear reason. The program performed the same way it did in 2003, with no constraints. It might has to do with the fact that health workers at peripheral level, particularly where the pilot test of the new data collection tools took place, are beginning to report what they really achieve. However, we recall that our DQA conducted in 2002 fell at 55.4%, which means, according to the final report of this assessment, that our official data reporting is not reliable enough to be trusted. Another DQA assessment was expected to take place yet this year. Nevertheless, as stated earlier, the country has just finalized the pilot test of the new data collection tolls and data reporting organization. It is planned that from 1st January 2006, all EPI data will be collected using these new reporting tools and organization. Therefore, it is believed that the next DQA can effectively take place in 2007.

- The wastage rate was 14.7% for DPT/Hep B. However, only 79 districts out of 144 reported it. This represents an improvement of 72 more districts compared to 2003. Additional efforts still need to be made in order to achieve a target of 100% districts report on wastage rate.

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | √ |  |
| Reporting Period (consistent with previous calendar year) | √ |  |
| Table 1 filled-in | √ |  |
| DQA reported on | √ |  |
| Reported on use of 100,000 US$ | √ |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) | √ |  |
| Table 2 filled-in | √ |  |
| New Vaccine Request completed | √ |  |
| Revised request for injection safety completed (where applicable) | √ |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~