May 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: RWANDA

Date of submission: ……MAY 2006……………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report (X Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Updated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2007…

  - Confirmed/revised request for injection safety support for the year 2007…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

- A special GAVI account (in USD and RWF) has been opened with the National Bank of Rwanda. - Two persons designated by the Ministry of Health are authorised to sign for the withdrawal of funds. - In the health districts, funds are deposited onto accounts recognised by the Ministry of Health and withdrawals are authorised by two signatories on the basis of a district plan of activities approved by the central level. - Funds are used for activities approved by the ICC. - In the health districts there are forms for justifying use of GAVI funds. - Each health district drafts and forwards to the central level a report on the utilisation of funds received which encompasses activities implemented and contains the corresponding accounting vouchers, including the mission orders duly signed by the hierarchical superior.

Problems encountered: - Following the civil service reform and with the change in staff, some districts have not yet forwarded the accounting vouchers for funds provided in 2005.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 _____________0

Remaining funds (carry over) from 2004 __1,683,022.32

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 14700 |  |  |  |  |
| Injection supplies | 20200 |  |  |  |  |
| Personnel | 22024 | 14700 |  |  |  |
| Transportation | 72230 |  |  | 20200 |  |
| Maintenance and overheads | 65890 | 22024 |  |  |  |
| Training | 7000 |  |  | 72230 |  |
| IEC / social mobilization | 28000 | 6000 |  | 59890 |  |
| Outreach | 23450 | 1500 |  | 5500 |  |
| Supervision | 8500 |  |  | 28000 |  |
| Monitoring and evaluation |  |  |  | 23450 |  |
| Epidemiological surveillance | 500028,32 |  |  | 8500 |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment | 762.022,32 |  |  | 500028,32 |  |
| Other …………. (specify) | 921.000 |  |  |  |  |
| Total: | 14700 | 44.224 |  | 717798,32 |  |
| Remaining funds for next year: | 20200 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Preparation of plans to revitalise EPI at national and district level - Supervision of EPI activities in health districts - Organization of half-yearly EPI evaluation workshops for district medical heads and district supervisors - Capacity-building for health workers involved in EPI management, in health centres within the framework of the RED strategy - Strengthening of outreach strategy immunisation activities in health groups - Involvement of health facilitators in efforts to track down drop-outs and identify non-immunized children - National inventory of cold chain equipment - Orders placed for cold chain equipment (222 refrigerators) - Regular supply of vaccines and injection materials - Monitoring in health districts - Updating of technical EPI sheets for health centres - Preparation of message booklets for health facilitators - Strengthening of coordination and follow-up mechanisms via half-yearly self-evaluation meetings at district level Major problems encountered: - Staffing cuts following administrative reform - Limits on field visits owing to a lack of transportation means following the elimination of the State’s vehicle fleet - Energy problems (electrical energy) at the national level - Obsolete cold chain equipment on the periphery

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Problems identified with DQA in 2002 Implementation status of DQA recommendations in 2005 1. Poor reporting promptness Reporting promptness was no longer a problem in 2005 because promptness rates for the forwarding of reports topped 90%. This progress could be traced to regular phone contacts, supervisory visits and evaluation meetings 2. Dates of receipt for monthly reports are not systematically entered, making it impossible to measure promptness There is a record where the central level is supposed to enter the dates on which reports are received from the district; this is done on an irregular basis. However, these dates appear on the report forwarded by the EPI follow-up and evaluation officer At the half-yearly meetings, the districts have been asked to keep a record of when reports from health centres come in. 3. Discrepancies between data from the HIS, EPI, districts and FOSA Health Information System (HIS) and EPI staff hold monthly data harmonization meetings with a view to analysing data The data collection tool has been standardized but not yet distributed widely The data harmonization process is supervised in some districts and health centres HIS agents help to monitor and evaluate EPI at district level and in the monthly meetings between EPI staff and all central level data managers. Despite these efforts, discrepancies persist in some districts owing to staffing changes or cuts. 4. Lack of procedures for processing monthly reports A feedback bulletin on EPI activities is circulated at district level All central level data managers meet monthly to process monthly reports 5. Lack of a procedure and written, regular reports on vaccine wastage rates Written instructions concerning vaccine management have been sent to all district health officers; however, these guidelines are not followed on the periphery A section on vaccine utilization has been added to the reporting forms. 6. Absence of data displays (diagrams and tables) on vaccine coverage trends During supervisory visits and at half-yearly evaluation meetings, supervisors are reminded of the need to monitor vaccine coverage by displaying tables and graphs. Despite these guidelines, it is clear during some supervisory visits that some health groups fail to display or update these tools for monitoring immunization coverage 7. Lack of regular, written feedback to lower levels Monthly meetings are held between districts and health centres to evaluate EPI activities in health centres. Written feedback is entered in the registers after district teams pay supervisory visits to health centres 8. Failure to keep tally sheets Tally sheets suitable for use for at least three years have been bound together in the form of a register and distributed to all health centres. All of the health centres supervised in 2005 had kept these tally sheets. NB: The recommendations covered under the previous item are those for which corrective action has been taken.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

1. Nationwide inventory of cold chain equipment 2. JSI survey on injection safety in Rwanda

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…January..           YEAR…2002……….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Date Vaccine Vial Dose Batch Expiry date LTA No. 15/02/05 Tritanrix 135000 271000 0 0 082/1085084 05/10/2005 Tritanrix 100645 201290 AT15B079AA 31/07/07 082/11121143 13/09/05 Tritanrix 185900 371800 AT15B15AB 02/09/2008 082-11033256 29/11/05 Tritanrix 55000 110000 At15B187AA 31/03/08 082/11336706 15/0205 Hiberix 135500 271000 AHiIBB139AA 31/07/07 082/10850814 05/10/2005 Hiberix 135000 271000 0 0 082/1085084 13/09/05 Hiberix 17700 35400 AHiBB254CA 30/03/2008 082-11033256 6350 12700 AHIbB254DB 30/03/2008 082-11033256 4500 9000 AHIbB258DA 30/03/2008 082-11033256 2000 4000 AHIbB258CA 30/03/2008 082-11033256 35700 71400 AHIbB262AB 30/03/2008 082-11033256 62500 125000 AHIbB262AA 30/03/2008 082-11033256 29/11/05 Hiberix 47100 94200 AHiBB2777AA 04/03/2007 082/11336706 7900 15800 AHiBB293AA 04/03/2007 082/11336706 NB: No problems arose in connection with receipt.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

The new vaccines were introduced in Rwanda in January 2002, and staff members from all immunizing public and private health groups have been trained. Since then, there have not been any special problems with the introduction of the new vaccines.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

These funds were received in 2002. These funds were used to overhaul the existing cold chamber and install two new ones, including one mixed unit (+&-), and to install fire-fighting equipment during 2004.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

DATE HEADING QUANTITY RECEIVED 21/07/05 BCG syringes 200 000 09/03/05 AD syringes 756 000 21/07/05 Dilution syringes 457 000 10/03/05 Growth sheets 700 000 21/07/05 Safety boxes 12 850

#### Progress of transition plan for safe injections and safe management of sharp waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

AD syringes and safety boxes have been in use in all immunising health groups since 2001. Injection wastes are burnt outdoors at the central level. The construction of a pilot Montfort incinerator did not yield the expected results. Another attempt to build a pilot incinerator is under way. AEFI surveillance was introduced in 2005 on the periphery via training for immunizers and the preparation and distribution of AEFI notification sheets The country is prepared to start purchasing injection supplies as soon as GAVI’s ISS support is phased out

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Brochures exist and distributed. | Prepare general EPI information brochures and distribute them to the authorities | An information bulletin on EPI activities is available at the Ministry of Health Website Health districts get feedback on immunization performance | Documents were not prepared at set intervals due to staff shortages | A quarterly bulletin will be published and monthly feedback will be provided from the second half of 2006 onwards |
| Reports on quarterly awareness-building rounds in health districts exist and are available. | Strengthen information and awareness-building rounds in health districts (1x/quarter). | Rounds were conducted twice in 2005 | Lack of time and staff | At least 2 rounds will be made |
| There is a least 1 press campaign per year involving all three media | Launch awareness-building programmes in the press (TV, radio and newspapers). | Campaign not run | Priority was given to inter-personal communication through health facilitators | A press awareness-building campaign will be conducted with additional immunization activities (measles campaign) |
| A National Immunization Day is organized. The report exists and is available. | Organize a National Immunization Day (NID). | Day not organized | NIDs tied to the polio eradication initiative were discontinued in 2002. However, mass measles immunization will continue. | A nationwide measles immunization campaign is planned for 2006. |
| The State has a budget commitment goal. | Establish a budget commitment goal for the State. | The State undertakes to help purchase pentavalents (20%) |  | The State continues to pay for part of the pentavalents. |
| The EPI Financial Sustainability Plan (FSP) is incorporated into the national health plan. | Incorporate the FSP into the national health plan. | The undertaking is broadened to the purchase of vaccines and injection supplies. |  |  |
| A half-yearly information review is published and circulated. | Publish a half-yearly EPI information review for distribution to members of Government, the Ministers directly concerned, ICC members and international partners. | Published once. | It was not possible to publish documents at set intervals due to staff shortages. | A quarterly bulletin is to be published and monthly feedback will be provided starting in the second half of 2006. |
| The annual symposium report exists and is available. | Organize an annual EPI symposium. | Not applicable |  | Goal to be rejected |
| There is at least one new ICC member this year. | Try to enlarge the composition of the ICC by bringing in new members. | The ICC has been enlarged. |  | We shall broaden the composition as need be. |
| Donors are invited to attend the annual symposium (cfr list of invitations and symposium report). | Invite potential donors to the annual EPI symposium. | Not yet. | Not relevant. | Goal to be rejected |
| Funding proposals are sent out. | Submit funding proposals to GAVI. | The multi-year plan for 2006-2010 is under way. |  | The Government and GAVI are to sign a protocol of agreement to ensure that aid continues up until 2015. |
| Donors help to plan budgetary requirements, particularly at ICC quarterly meetings. | Get donors more involved in medium- and long-term planning of EPI budgetary requirements. | Most donors take part in planning. | No problems | Continue to get all partners involved in EPI budgetary planning. |
| Funding proposals cover funding periods longer than 5 years. | Try to secure funding commitments for more than 5 years. | Donors are well informed about funding problems. | Apart from GAVI, no donor has committed to funding over more than 5 years | Continue to increase donor awareness. |
| Reports are more complete and deadlines are respected: reports reach the central level at the latest by the 15th of the following month | Improve completeness and promptness for immunization reports forwarded by the districts | Instructions have been given. | Some districts continue to forward reports late following the administrative reform. | Reorganize the report forwarding system after the reform. |
| Health Information System (HIS) seminars for district health supervisors are held once a year. | Run seminars for district health supervisors to strengthen their capacity for data collection, processing and analysis. | Coordination meetings are organized on a half-yearly basis. | No problems. | Continue meetings. |
| New equipment has been purchased and is operational: ad hoc training has been provided. | Improve computer equipment for processing data at the central level. | Computer equipment is available. | No problems. | Ensure equipment maintenance. |
| Written instructions on the open via policy exist and are circulated to all districts. A component on “Follow-up of the open vial policy is incorporated into the supervisory guidelines. | Strengthen the WHO strategy with regard to the open vial policy. | Instructions exist and have been circulated. The follow-up component of this policy has already been incorporated into the supervisory manual and the EPI technical sheets | No problems. | Follow up the implementation of this policy. |
| The “Stock management verification” component is strengthened in the guidelines for supervisory missions to health districts. | Verify the implementation of the recently issued stock management guidelines | The stock management verification component has been introduced in 10 pilot districts | Lack of analysis at the central level | Introduce analysis at the central level |
| The verification component for cold chain maintenance is strengthened in supervisory visits to health districts | See to it that the cold chain technicians correctly apply the guidelines they received at the May 2002 seminar on cold chain maintenance | This component is verified as part of monitoring of integrated supervision | High turnover among trained staff | Train/retrain cold chain maintenance agents every 3 years |
| A document with proposals concerning a strategy to motivate healthcare personnel is drafted within the Ministry of Health | Make proposals concerning a strategy to motivate healthcare personnel in order to reduce turnover | The proposals have been made | Procedures are long | Continue advocacy efforts |
| The “financial information” component of periodical reviews of EPI data is strengthened | Improve financial monitoring, especially in quarterly and half-yearly reviews of data: add a financial component to the technical component | No documents | This procedure remains the responsibility of the Ministry’s Accounting Department | Recruit a managing administrator for EPI |
| There are decentralized stocks in every health district | Introduce a decentralized system for stocks of spare parts | Some parts are available in the districts | Procurement problems with spare parts | Ask our partners to set aside a large share of spare parts |
| Monthly meetings with health facilitators are held in every health group (health centres and health district hospitals) | Get health facilitators more involved | Meetings are held | No problems | Continue to hold meetings with health facilitators |
| Quarterly meetings are held in each health district, with financial support from EPI and backing from local political and administrative authorities | Increase awareness among local political and administrative authorities | Meetings are held at district level | No problems | Continue to hold meetings with local political and administrative authorities |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No GAVI funds were used to finance injection safety activities in 2005.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Not applicable for Rwanda because the plan already exists.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005** | 2006 | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 90% | 90% | NA | NA | NA | NA | NA | NA | NA | NA |
| B: Proportion funded by the Government and other sources (%) | 10% | 10% | NA | NA | NA | NA | NA | NA | NA | NA |
| C: Total funding for …………. (new vaccine) | 100% | 100% | NA | NA | NA | NA | NA | NA | NA | NA |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions TakenTowards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| Strategy 1.1 Constantly build awareness among all government bodies concerned (ministries, provincial and district authorities) of the advantages of EPI in terms of both health and economic impact | Prepare EPI general information brochures and distribute them to the authorities Step up information and awareness-building tours of health district (1 x/quarter) Launch awareness-building campaigns in the press (TV, radio and newspapers) Organise a National Immunization Day | Brochure available to local administrative authorities and health facilitators. Feedback on EPI activities provided to provincial political and administrative authorities. Supervisory tour with input from district administrative authorities Not done Not applicable | No problems Lack of transportation due to elimination of government’s vehicle fleet Priority given to interpersonal communication | Draft booklet and immunization data Two tours Not applicable | Booklet finalised Two awareness-building tours at district level Not applicable | Constantly build awareness among all government bodies concerned (ministries, provincial and district authorities) of the advantages of EPI in terms of both health and economic impact |
| Strategy 1.2: Have the ICC (Inter-agency Coordinating Committee) lobby the Government (Prime Minister, Minister of Finance and Planning, Economics, etc.) to increase the EPI budget | Set a budget commitment goal for the State Introduce the EPI FSP (Financial Sustainability Plan) into the National Health Plan Publish a half-yearly EPI information review for members of Government, ministries directly concerned, ICC members and international partners Organize an annual EPI symposium | The State pledges to pay for 10% of procurement costs for pentavalent vaccines Activity implemented Symposium not organized | No constraints Lack of time Activity to be eliminated | The Health Ministry’s budget includes a budget line for vaccine procurement | This budget line is maintained | Mobilize additional resources at the provincial level |
| Strategy 1.3: Explore other Government income sources (e.g. Poverty Reduction Strategy Paper – PRSP or Heavily Indebted Poor Countries – HIPC debt relief funds) | Include EPI in financial planning documents | EPI included in State financial planning documents (MTEF) | No constraints | Government proposes strategic health sector plan | Parliament adopts strategic plan | Strengthen the Health Ministry’s ability to negotiate effectively with the Finance Ministry to ensure that funding for health activities, including EPI, is included in Government budget planning and priorities |
| Strategy 2.1: Increase potential donors’ awareness of EPI and solicit their support | Try to enlarge ICC composition by bringing in new members Distribute EPI general information brochures to ICC members and other potential donors | ICC is enlarged Information documents (action plan, activity report) are shared with ICC | No constraints | ICC already operational All EPI-related general information documents are shared with ICC members | ICC operational with new members All EPI-related general information documents are shared with ICC members | Involve donors more in medium- and long-term planning of EPI budgetary requirements |
| Strategy 3.1: Persuade donors to make long-term financial commitments | Get donors more involved in medium- and long-term planning of EPI budgetary requirements | Traditional donors are involved in needs planning | Difficult to find donors willing to make long-term financial commitments | Sub-sectoral strategic plan under preparation | Sub-sectoral strategic plan finalized | Ensure funding availability at the operational level |
| Strategy 3.2: Improve procedures for funds transfers towards periphery to avoid funding shortages | Ensure coordination between financial officer of Ministry of Health, Ministry of Finance and Ministry of Local Administration in order to improve funds transfer procedures | Procedures exist and are applied | No constraints | Each district has a bank account | Each district has a bank account |  |
| Strategy 4.1: Improve the health information system | Improve completeness and promptness for immunization reports sent by the districts Organize capacity-building seminars for district health supervisors on data collection, processing and analysis Upgrade computers for data processing at central level | Guidelines have been transmitted to the health districts Monthly phone contacts HIS organizes quarterly coordination meetings Equipment purchased | Reform launched in late 2005 No constraints No constraints | In 2004, 99% reporting completeness rate Meetings are held regularly Computer equipment insufficient and obselete | In 2005, 100% reporting completeness Meetings are held regularly Sufficient quantity of new equipment | Strengthen communication between central level and districts Arrange for maintenance of computer equipment |
| Strategy 4.2: Reduce vaccine wastage | Strengthen WHO strategy based on open vial policy | Written instructions exist and are circulated | Poor compliance with instructions | Oral instructions provided at supervisory meetings | Written guidelines | Use supervisory visits to strengthen compliance with guidelines |
| Strategy 4.3: Generally improve allocation and utilization of human, material and financial resources | Make proposals concerning a strategy to motivate healthcare personnel in order to reduce turnover Improve financial monitoring during quarterly and half-yearly data reviews: add a financial component to the technical component | Motivation proposals are made Document not prepared | Long procedures Activity entrusted to accounting dep’t and Ministry | Bonus exists for some health sector agents Fund utilization framework already exists | Bonus exists for some health sector agents | Pay bonuses to all agents using a contractual approach |
| Strategy 4.4: Boost social mobilization with a view to raising immunization coverage rates in general and increase immunization coverage for children who can only be reached using outreach strategies in particular | Further mobilize health facilitators Increase awareness among local political and administrative leaders and other opinion leaders | Periodic awareness-building meetings are held in health centres Periodic awareness-building meetings are held at district level and in health centres | No problems | There is a Nat’l Health Facilitators Programme There is a health officer for each admin. district, sector or unit |  |  |
| Strategy 4.5: Develop an operational partnership with other ministries with regard to social mobilisation | Increase awareness among IEC Focal Points in the ministries concerned | Awareness-building not carried out | No IEC officer for EPI | Each ministry has an IEC focal point |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Updated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 8463086 | 8,674,663 | 8891530 | 9113818 | 9341663 | 9575205 | 9814585 | 10059949 | 10311448 |
| Births | 363,913 | 372,811 | 382336 | 391894 | 401692 | 411734 | 422027 | 432578 | 443392 |
| Infants’ deaths | 38,939 | 39912 | 40910 | 41933 | 42981 | 44056 | 45157 | 46286 | 47443 |
| Surviving infants | 324974 | 332899 | 341425 | 349961 | 358711 | 367678 | 376870 | 386292 | 395949 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 304472 | 331 980 | 359 396 | 360 542 | 393 658 | 403 499 | 413 586 | 423 926 | 434 524 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 290592 | 316444 | 324354 | 332463 | 340775 | 349294 | 358027 | 366977 | 376152 |
| NEW VACCINES ** | 304472 | 331980 | 359396 | 360542 | 393658 | 403499 | 413586 | 423926 | 434524 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 290592 | 316444 | 324354 | 332463 | 340775 | 349294 | 358027 | 366977 | 376152 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | 11.2% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 304472 | 331980 | 359396 | 360542 | 393658 | 403499 | 413586 | 423926 | 434524 |
| INJECTION SAFETY**** | 184089 | 184164 | 267 635 | 293 920 | 321 353 | 349 973 | 379 834 | 389320 | 399052 |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 312347 | 3543360 | 363219 | 372299 | 381607 | 391147 | 400926 | 410949 | 421222 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 272569 | 316444 | 324354 | 332463 | 340775 | 349294 | 358027 | 366977 | 376152 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 184089 | 184164 | 267 635 | 293 920 | 321 353 | 349 973 | 379 834 | 389320 | 399052 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

With regard to basic data, as we did not yet have population increase figures, we used the rate of 2.5% provided by the Planning Department of the Ministry of Health. Wastage rates may seem very high. There are two reasons for this: first, in the course of 2004, the old logistician left and a new one came in. Consequently, it was hard for the new logistician to master the district ordering system. Moreover, when we calculated wastage rates, we did not have accurate figures for remaining stocks at the district level. We therefore relied on information available on stocks at the central level.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Not applicable

Table 4: Estimated number of doses of PENTAVALENT vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006-2007

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG

Table 7: Estimated supplies for safety of vaccination for the next two years with MEAS

Table 8: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Cf previous table on progress accomplished |  |  |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | X |  |
| Table 1 filled-in | X |  |
| DQA reported on | X |  |
| Reported on use of 100,000 US$ | X |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) | X |  |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | X |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes