January 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: SAO TOME AND PRINCIPE

Date of submission: August 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report x Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3		Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The GAVI funds are used only after authorization by the ICC, whose role it is to approve the plan for use of the funds. The GAVI funds are not disbursed without the signature of the representative of WHO or UNICEF, and of a representative of the Ministry of Health. No problems have been encountered involving the use of the funds

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005:			USD 0.00

Remaining funds (carry over) from 2004:		USD 10 973.65

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization | 2014.10 |  |  | 2014.10 |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles | 2590.91 | 776.84 |  | 1814.07 |  |
| Cold chain equipment | 3683.11 | 1062.81 |  | 2620.30 |  |
| Other: Institutional strengthening of the EPI (purchase of office equipment) |  |  |  |  |  |
| Total: | 8288.12 | 1839.65 |  | 6448.47 |  |
| Remaining funds for next year: | 2685.53 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to your multi-year plan.

Social mobilization activities (dramatization, media spots, training of community health workers and traditional midwives). Strengthening of supervision. Logistical support in the area of transportation for supervisors and district immunization staff. Immunization activity evaluation meetings with responsible officials and district immunization staff.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Not applicable

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Not applicable

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH:  September           YEAR:  2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

As at 23 May 2005, we have received 3200 doses of Hepatitis B vaccine (Hepatitis B, DNA Vaccine Recombinan, 100 mcg, HB 08022, Expiry date: Sep. 2007) and 6500 doses of yellow fever vaccine (5 D X 6276, Date: June 2007). The vaccines arrived in a well-preserved state. Please note that we planned for the receipt of 20 153 doses of Hepatitis B vaccine but unfortunately received only 3200 doses, with the result that our stocks ran out in February 2006.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Advocacy and social mobilization Workshop for the evaluation and strengthening of immunization activities Production and distribution of 5000 calendars with educational messages Producation and distribution of 6300 brochures on the importance of child immunization Health education session with message on immunization in post offices and health centres, as well as through advanced teams Supervision of service provision at all levels, including the cold chain Monthly meeting with districts to evaluate activities carried out For the second half-year, the programme will organize training for service providers on cold chain management and increasing the antigen coverage Following the Hepatitis B stock outage, we intend to conduct small immunization campaigns to catch up on coverage as soon as we receive the vaccines

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The report on the proportion of the US$ used was provided in the progress report covering the period January 2003-December 2003*. There still remains a balance of US$ 83 380.32 (eighty-three thousand, three hundred and eighty dollars and thirty-two cents). * See the 2004 progress report

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

So far as the receipt of injection safety support is concerned, we received: 37 100 autodisable syringes 2300 (5ml) reconstitution syringes 600 (2ml) reconstitution syringes 525 safety boxes No problems to report.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Number of districts without stock outages of AD syringes in the last 12 months | 100% | 100% | Not applicable | 100% |
| Number of districts without stock outages of safety boxes in the last 12 months | 100% | 100% | Not applicable | 100% |
| Number of health services without stock outages during the most recent surveillance visit | 100% | 100% | Not applicable | 100% |
| Number of districts with operational incinerator | 100% | 0% | The districts do not have incinerators | 100% |
| Percentage of health stations and community stations which adequately burn and bury used injection equipment | 100% | 1000% | All health stations burn and bury their equipment using safety boxes | 100% |
| Percentage of used syringes and needles among wastes in waste deposit areas or in the vicinity of the health unit | 0% | 100% |  | 0% |
| Number of adverse post-immunization reactions reported at the national level during the year | 100% | 0% | No complaints from parents | 100% |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

We received no cash contribution by way of injection safety support.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Not applicable

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine: Hepatitis B |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2003.** | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. | 2011.. | 2012.. |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 30% | 20% | 20% | 10% | 10% | 10% |
| B: Proportion funded by the Government and other sources (%) | 0% | 0% | 0% | 0% | 70% | 80% | 80% | 90% | 90% | 90% |
| C: Total funding for Hepatitis B (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

| Table 2.1: Sources (planned) of financing of new vaccine: Yellow Fever |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2003..** | 2004.. | 2005.. | 2006.. | 20.07. | 2008.. | 2009.. | 2010.. | 2011.. | 2012. |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 30% | 20% | 20% | 10% | 10% | 10% |
| B: Proportion funded by the Government and other sources (%) | 0% | 0% | 0% | 0% | 70% | 80% | 80% | 90% | 90% | 90% |
| C: Total funding for Yellow Fever (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Not applicable

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |  |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 5236 | 5279 | 5364 | 5089 | 5097 | 5098 | 5090 | 5111 |  |
| Infants’ deaths | 232 | 223 | 215 | 225 | 237 | 252 | 267 | 282 |  |
| Surviving infants | 4823 | 5056 | 5149 | 4864 | 4860 | 4846 | 4823 | 4829 |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 5158 | 5056 | 5149 | 4987 | 4995 | 4996 | 4988 | 5009 |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 4993 | 4854 | 5046 | 4885 | 4893 | 4894 | 4886 | 4906 |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Hepatitis B (new vaccine) | 5158 | 5056 | 5149 | 4987 | 4995 | 4996 | 4988 | 5009 |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of Hepatitis B ( new vaccine) | 4928 | 4854 | 5046 | 4885 | 4893 | 4894 | 4886 | 4906 |  |
| Wastage rate in 2005 and plan for 2006 and beyond*** Hepatitis B ( new vaccine) | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Yellow Fever (new vaccine) | 3521 | 4803 | 4891 | 4834 | 4842 | 4843 | 4835 | 4855 |  |
| Wastage rate in 2005 and plan for 2006 and beyond*** Yellow Fever ( new vaccine) | 40% | 30% | 30% | 25% | 25% | 25% | 25% | 25% |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 5163 | 5689 | 5781 | 6305 | 6478 | 6649 | 6820 | 6991 |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG | 5151 | 4955 | 5097 | 5038 | 5046 | 5047 | 5039 | 5060 |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with Measles | 4557 | 4803 | 4891 | 4834 | 4842 | 4843 | 4835 | 4855 |  |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

There is no assurance from UNICEF

Table 4: Estimated number of doses of Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formule | Pour 2007 |
| --- | --- | --- | --- |
| A | Nourrissons vaccinés / à vacciner avec la 1ère dose de Hépatite B…............... (nouveau vaccin)* |  | ** 5149 |
| B | Pourcentage de vaccins demandés au Fonds mondial pour les vaccins, compte tenu du Plan de viabilité financière | % | 30 % |
| C | Nombre de doses par enfant | 3 | 3 |
| D | Nombre de doses | A x B/100 x C | 4634 |
| E | Coefficient de perte estimé | (voir liste tableau 3) | 1.25 |
| F | Nombre de doses (y compris pertes) | A x C x E x B/100 | 5793 |
| G | Stock régulateur de vaccins | F x 0,25 | 1448 |
| H | Stock anticipé de vaccins au début de l’année 2006 (y compris reste du stock régulateur) |  | 4914 |
| I | Total doses de vaccin demandées | F + G - H | 7241 |
| J | Nombre de doses par flacon |  | 10 |
| K | Nombre de seringues autobloquantes (+ 10% pertes) | ( D + G – H ) x 1,11 | 6751 |
| L | Seringues pour reconstitution (+ 10% pertes) | I / J x 1,11 | 0 |
| M | Total réceptacles de sécurité (+ 10% des besoins) | ( K + L ) / 100 x 1,11 | 75 |

*Please report the same figure as in table 3.

** Number of infants  to be vaccinated in 2007, in accordance with the latest population data available from INE

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Table 4: Estimated number of doses of  Yellow Fever vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

** Number of infants  to be vaccinated in 2007, in accordance with the latest population data available from INE

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets 2005 | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
|  |  |  |  | 2006 | 2007 |
| Total population | 146874 |  |  | * 148177 | *150.548 |
| Births | 5055 |  |  | * 5279 | *5364 |
| Infant mortality rate | 45.9 |  |  | 43.9 | 42.3 |
| Infant deaths | 232 |  |  | 223 | 215 |
| Surviving infants | 4823 |  |  | 5056 | 5149 |
| Children vaccinated with BCG | 4853 | 5151 |  | 4955 | 5097 |
| Children vaccinated with OPV3 | 4630 | 4993 |  | 4854 | 5046 |
| Children vaccinated with DTP3 | 4630 | 4993 |  | 4854 | 5046 |
| Children vaccinated with measles | 4485 | 4557 |  | 4803 | 4891 |
| Children vaccinated with monovalent Hepatitis B | 4630 | 4928 |  | 4854 | 5046 |
| Children vaccinated with yellow fever | 4485 | 3521 |  | 4803 | 4891 |
| Pregnant women vaccinated with TT | 5721 | 5163 |  | 5689 | 5781 |

** Number of infants  to be vaccinated in 2007, in accordance with the latest population data available from INE

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X |  |
| Reporting Period (consistent with previous calendar year) | 2005 |  |
| Table 1 filled-in | X |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ | X |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | X |  |
| ICC minutes attached to the report | X |  |
| Government signatures | X |  |
| ICC endorsed | X |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of   SAO TOME AND PRINCIPE

Signature:	……………………………………………...……………...

Title:	MINISTER OF HEALTH

Date:	08 AUGUST 2006

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | Grégoire BataKao, Representative |  | Embassy of Portugal | António Machado |  |
| UNICEF | Batilloi Warritay, Officer-in-charge |  | Embassy of Taiwan China | T.C. Chang |  |
| UNDP | António Viegas, Representative |  |  |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes