September 2006

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: SENEGAL

Date of submission: 04 SEPTEMBER 2006……………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharp waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2007…

  - Confirmed/revised request for injection safety support for the year   NA…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

GAVI funds are deposited onto a special account that the Ministry of Health and Prevention has opened with a local bank (Société Générale de Banques au Sénégal). Fund disbursement requires the joint signature of the Director for Medical Prevention (DMP) and the Director for the General Administration and Outfitting of the Ministry (DGAO), once expenditure has been approved by the EPI National Coordinating Committee (ICC), a body chaired by the Minister of Health and Prevention. Centralized distribution of funds is based on the track records of the districts and regions. Other factors are also taken into consideration: demographic weight, the number of health posts covered, a given district’s specific constraints, etc. Funding priority is given to outreach and mobile immunization strategies, supervisory training or other activities requiring IACC approval. Funds are transferred from the central level onto the accounts of the medical regions or districts. At the end of the defined period (3 months on average), the districts and regions funded send technical and financial reports on fund utilization to the central level.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 __397,552,150____________

Remaining funds (carry over) from 2004 _179,341,380_______________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel: immunizer per diems | 92 934.77 | 360 000 | 8 243 130 | 36 841 675 |  |
| Transportation | 38886.63 | 16 545 406 | 1 039 800 | 1 430 360 |  |
| Maintenance and overheads | 44067.68 | 21541097 |  |  |  |
| Training | 112943.86 | 12 581 940 | 10 963 110 | 31 684 500 |  |
| IEC / social mobilization | 82812.99 | 35 871 710 | 4598 345 | 25 500 |  |
| Outreach | 1972.19 | 964 401 |  |  |  |
| Supervision | 22312.65 | 2 371 120 | 6 737 320 | 1 802 450 |  |
| Monitoring and evaluation | 12009.86 | 5 872 825 |  |  |  |
| Epidemiological surveillance | 230.06 |  | 112 500 |  |  |
| Vehicles | 5963.19 | 2 916 000 |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: | 414133.88 |  |  |  |  |
| Remaining funds for next year: | 328351223 CFAF 671479.89 USD |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Throughout the year, support is granted to the districts after examination of their periodical plan of action, which includes supervisory and training immunization activities. During and in between these activities, the central level conducts supervisory visits in the districts and regions. The major difficulty is the lack of staff on all levels to implement planned activities on time and under the best possible conditions. These funds have also made it possible to train and retrain all agents when the pentavalent vaccine was introduced.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

The DQA was validated in 2003. Implementation of recommendations is continuing, with the introduction of such aids as TACOJO to improve data management, the AEFI reporting form, the development of vaccine and consumable management tools (stock registers, order/delivery forms). In addition, a new model for consolidating and analysing data at district and regional level has been developed. A training module for district and regional data managers has been worked out and will constitute the next training phase.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Two points worth mentioning are the EDSIV survey and the evaluative study of injection safety (incinerators) at district level.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…July         YEAR…2005…….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Out of the 1,312,700 doses expected, the country received 984,400 in 2005. Overall, there are no problems except with regard to the carry-over from 2005 (328,400 doses), delivered in May 2006.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Preparation and implementation of a training plan. Preparation and implementation of a communication plan. Preparation of tools for cold chain monitoring tools and aids to improve management of immunization activities and vaccines. Supervisory training to strengthen management capacity at the operational level. Overhaul of cold chain equipment in immunization units.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

This amount was used to introduce the PENTAVALENT as an aid for training and social mobilization.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

NA (GAVI injection safety support ended in 2004).

#### Progress of transition plan for safe injections and safe management of sharp waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Between 2001 and 2005, 62 De Montfort incinerators were built throughout the country to incinerate sharp waste from immunization. A 2005 study evaluating these incinerators revealed that some were no longer operational and that the majority were underused due to a lack of trained personnel. Moreover, the November 2005 WHO study on injection safety showed that none of the 80 sites visited used sterilizable injection supplies and that safety boxes were in use at 98% of the sites visited and in use in 92% of the places set aside for immunization. Between 2002 and 2005, major progress was made with regard to injection safety, with the introduction of AD syringes and disposable syringes and needles in all health groups. However, full safety boxes were found stored in some health groups, owing to the under-utilization of available incinerators.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Availability rate for AD syringes and safety boxes at district level No. of districts using incinerators for waste management | 100% 100% | 100% 60% | None Difficulties linked to incinerator use (late delivery of incinerators, ill-equipped, untrained staff) | 100% 100% |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| A: Proportion funded by GAVI/VF (%)*** | 90 | 90 | 90 | 90 | 90 | 90 | 70 | 60 | 40 | 00 |
| B: Proportion funded by the Government and other sources (%) | 10 | 10 | 10 | 10 | 10 | 10 | 30 | 40 | 60 | 100 |
| C: Total funding for …………. (new vaccine) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Updated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 384166 | 390 574 | 390 574 | 400 338 | 410 347 | 420 606 | 431 121 | 441 899 | 452 946 |
| Infants’ deaths |  |  |  |  |  |  |  |  |  |
| Surviving infants | 360732 | 366 749 | 375 917 | 385 316 | 394 949 | 404 824 | 414 945 | 425 319 | 435 952 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* DTC-HepB + Hib) | 359959 | 371045 | 380321 | 389830 | 399576 | 409565 | 419804 | 430299 | 441057 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…….… DTC-HepB + Hib) | 321541 | 351517 | 360304 | 369312 | 378545 | 388009 | 397709 | 407651 | 417843 |
| Wastage rate in 2005 and plan for 2006 beyond*** DTC-HepB + Hib) | 13% | 10% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 258616 | 312459 | 360304 | 369312 | 378545 | 388009 | 397709 | 407651 | 417843 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 351975 | 355422 | 380321 | 389830 | 399576 | 409565 | 419804 | 430299 | 441057 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 266041 | 312459 | 360304 | 369312 | 378545 | 388009 | 397709 | 407651 | 417843 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Our country proposes to use GAVI additional support for new vaccines according to the above scenario (see table 2.1), as agreed in discussions during ICC meetings. Immunization achievements and annual goals were also revised based on the results of the EDS4 survey, giving a new infant mortality rate of 60.1 per 1000 for calculating immunization coverage goals. The shares of GAVI and the State were revised further to correspondence with GAVI (see correspondence). EDS4 survey (use of the new indicator of 60.1/1000 for calculating immunization coverage goals).

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of DTP-HepB/Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| No. districts w/ penta3 cov. rates >80% No. districts w/ dropout rates < 10% Penta wastage rate | 80% 10 < 10% | 66% 43 9% | - Insufficient implementation of outreach and mobile immunization strategies - Inadequate rolling stock - Work overload due to epidemics - Insufficient human resources - IEC shortcomings | 100% 100% 5% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of …SENEGAL……………..…………………………………

Signature:	…Doctor PAPA COUMBA FAYE…………………………………………...……………...

Title:	…DIRECTOR OF MEDICAL PREVENTION……………………………………….………………….

Date:	4 SEPTEMBER 2006.………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

X

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes