Annual Progress Report 2006

Submitted by

The Government of

DEMOCRATIC SOCIALIST REPUBLIC OF SRI LANKA

to the

# Date of submission: 10 May 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of Sri Lanka

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Secretary of Health | Title: Director General, National Planning Ministry of Finance |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr HSP Kahandaliyanage Secretary of Health | MoH |  |  |
| Dr Ajith Mendis Director General of Health Services | MoH |  |  |
| Dr SM Samarage Deputy Director General (Planning) | MoH |  |  |
| Dr PG Maheepala Deputy Director General (Public Health Services) | MoH |  |  |
| Mr EA Piyadasa Chief Accountant | MoH |  |  |
| Dr . V Karunaratne Director, MCH Service | MoH |  |  |
| Dr S Amunugama Director, HE&P | MoH |  |  |
| Dr MRN Abeysinghe Chief Epidemiologist | MoH |  |  |
| Dr A. Borra WHO Representative | WHO |  |  |
| Dr Aberra Bekelle Head / ECDP | UNICEF |  |  |
| Dr Kumari Navaratne Public Health Specialist | World Bank |  |  |
| Dr Vinya Ariyaratne Executive Director | Sarvodaya |  |  |

Signatures Page for HSS

For the Government of SRI LANKA

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Secretary of Health | Title: Director General, National Planning Ministry of Finance |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee ( National Health Development Committee) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr HSP Kahandaliyanage Secretary of Health | Ministry of Health |  |  |
| Dr Ajith Mendis Director General of Health Services | Ministry of Health |  |  |
| Dr SM Samarage Deputy Director General (Planning) | Ministry of Health |  |  |
| Dr PG Maheepala Deputy Director General (Public Health Services) | Ministry of Health |  |  |
| Mr EA Piyadasa Chief Accountant | Ministry of Health |  |  |
| Dr . V Karunaratne Director, MCH Service | Ministry of Health |  |  |
| Dr S Amunugama Director, HE&P | Ministry of Health |  |  |
| Dr MRN Abeysinghe Chief Epidemiologist | Ministry of Health |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health Northen Province |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health Eastern Province |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health Southern Province |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health Uva Province |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health North – Central Province |  |  |
| Provincial Director of Health Services | Provincial Ministry of Health North-western Province |  |  |
| Dr A. Borra WHO Representative | WHO / Sri Lanka |  |  |
| Dr Aberra Bekelle Head / ECDP | UNICEF/ Sri Lanka |  |  |
| Dr Kumari Navaratne Public Health Specialist | World Bank/ Sri Lanka |  |  |
| Dr Vinya Ariyaratne Executive Director | Sarvodaya ( NGO) |  |  |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Not Necessary to fill, as advised by the GAVI Review Report July 2004

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not Necessary to fill, as advised by the GAVI Review Report July 2004

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 : Nil

Remaining funds (carry over) from 2005:  Nil

Balance to be carried over to 2007: Nil

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 629,340 |  |  |  |  |
| Injection supplies | 102,850 |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: | 732,190 |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

Comprehensive Multi Year Plan 2007-2011 Sri Lanka has developed the cMYP for five years period from 2007-2011. SEARO has provided technical support to develop cMYP. Strengthening Vaccine storage /Transport facilities (a) Central Level The new central cold room complex is ready to start functioning and this will save money by avoiding vaccine storage in private cold stores. The UNICEF has provided 1 new cold room and funded re-installation of all 03 existing cold rooms at the new cold room complex. WHO also has provided a new cold room. These new cold rooms have increased nearly two fold vaccine storage capacity at central level, which is a good preparedness in the introductions of new vaccines planned into the national EPI. Steps have been taken to strengthen the central level vaccine delivery activities. Two new vaccine transport vehicles with better delivery capacity were added to the transport fleet. These vehicles were donated by the UNICEF. Another vehicle will be purchased under the GAVI US$ 100,000 received in phase I, for which tenders are being processed. However, this has been substantially delayed due to departmental lengthy procedures, but most likely purchasing would be possible in mid 2007. (b) District Level Fifteen (15) cold rooms were installed at the Regional Medical Supply Divisions (including 8 Tsunami affected districts) to strengthen the cold store facility and ten (10) generators were provided. Further it is planned to supply another 05 cold rooms to the Regional Medical Supply divisions, where at present cold room facilities not adequate. UNICEF has expressed its willingness to fund this activity. These new cold rooms will enhance vaccine storage capacity at district level, which is also a good preparedness in the introductions of new vaccines planned into the national EPI. UNICEF has provided 5 vaccine transport vehicles to the tsunami affected Districts while another 11 are planned to be provided which will cover all Districts in Sri Lanka. ( c) Divisional Level UNICEF has provided 350 data lodgers to monitor cold chain at divisional stations and necessary training on data lodger management for the divisional staff also has been provided. The Tsunami affected health care facilities were provided with the necessary logistic facilities by the Government, local NGOO and International agencies (including WHO, UNICEF and World Bank) to ensure delivery of immunization services without any interruption. Strengthening Injection Safety Practices The Government of Sri Lanka has taken a policy decision to introduce AD syringes for all immunizations in the country. Therefore, in addition to the GAVI supply of injection safety items, the Government of Sri Lanka has procured the balance requirement of EPI injection safety items for the country. The supply of injection safety items were without any delay or interruption, even in the North and Eastern provinces affected by the conflict. Improving the quality of immunization Services The World Bank funded 5 year (2005-2009) Health Sector Development Project with US$ 1.3 million has commenced in 2005 to improve the quality of immunization services in the country. The major component of this project is to improve the infrastructure and other logistic facilities to provide the immunization services, setting model immunization and child & mother well being clinics in all 285 health divisions and the training of staff in EPI services. It is planned to conduct an Immunization Quality Assessment survey covering all health divisions in 2007. For this purpose, survey instruments were developed and training of middle level and divisional level supervisory staff was completed, except in a few districts. A national level training programme for all middle level managers on Immunization Quality Assessment was conducted in March 2006. During this training programme, cold chain management was given a priority. In addition, EPI data management software also was developed. Two regional workshops on maintenance of cold chain and enhancing AEFI surveillance were conducted and this will be continued in 2007 in other districts. UNICEF funded EPI reviews have been conducted in 22 districts jointly by the Epidemiology Unit and Family Health Bureau, MoH in 2006. EPI surveys: WHO funded 2 EPI coverage surveys were conducted in two districts. (Annex I: Reports of surveys) There are no significant problems encountered in implementing the cMYP activities.

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for _________

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA ?

Not applicable

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

X

YES                              NO

## If yes, please report on the degree of its implementation and attach the plan.

Not applicable

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

Not applicable

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

In 2006, two ICC meetings were held in February and September. Both meetings were chaired by the Additional Secretary of Health (Medical Services). High level Ministry officials including Director General of Health Services, International agencies (WHO, UNICEF, WB) and local NGOs are the members and their active participation and contribution in ICC is significant. (The minutes are attached: Annex II ) Steps have been already taken to expand and strengthen the ICC activities and the plan of action for 2007 is attached (Annex III)

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| HepB | 2 doses | 429,200 | 2003 | April 2006 Oct 2006 |
|  | 10 doses | 1,287,600 |  |  |

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Sri Lanka has submitted its application for the introduction of the new vaccine ( DTP-HepB-Hib) in January 2007 and GAVI Secretariat has informed the MoH ((Annex IV) that Independent Review Committee has given the conditional approval pending submission of additional information on the introductory plan and financial sustainability strategies. Sri Lanka has already submitted the additional information requested by the GAVI in April 2007 and is awaiting the final decision of GAVI. If GAVI approval is received, Introduction of Pentavalent (DTP-HepB-Hib) vaccine will be done from the beginning of 2008. It is important to note, that the application was submitted in January 2007 with plans to introduce new vaccine from 2007, but it is not feasible now, as the GAVI final decision is not available. Even with the GAVI approval at this point, it is impossible to get down the vaccines, as the procurement process requires a few months time period.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on: Not Applicable

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Not Applicable

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in 2005

Please summarize the major recommendations from the EVSM/VMA

Pre shipment & Arrival procedures - Standard VAR to be introduced for all vaccines. - WHO/V&B/01.05 version of the WHO Guidelines on international packaging and shipping of vaccines is to be referred. Maintaining correct storage temperatures - Weekly temperature monitoring chart as recommended in the EVSM Model Quality Plan is to be introduced. - A multi channel electronic PC based temperature monitoring system is installed for the new cold storage facility equipment. - All thermo-sensors of cold and freezer rooms should be tested for accuracy using TinyTalk devices. Building, equipment and transport - CFC units should be changed to CFC-free. Effective stock management - A computerized stock control system should be adopted. - Diluents should also be registered as a separate product either as a second line in stock registry or in a separate card. - In addition to computerized version of the stock control system, hard copies should include batch cards, inventory cards, physical inventory cards, loss reports, and requisition/issue vouchers. - All vaccines should be arranged in a way to promote EEFO principle. Reliable delivery to intermediate stores minimizing damage during distribution - Taking into consideration that the longest journey for vaccine distribution in Sri Lanka takes not more than 6 hours, it is strongly recommended that the programme stops using frozen icepacks for vaccine distribution and introduces use of cool water packs (+2oC to +8oC). Standard Operating Procedures - In order to ensure correct practices and sustain quality it is highly recommended that routine procedures be translated into SOP format. - The new version of the Immunization Manual should be in line with recent WHO recommendations on vaccine management. - Assistant storekeeper is recommended to attend GTN/VM vaccine store management training course.

Was an action plan prepared following the EVSM/VMA : Yes

Note: Sri Lanka has developed a brief activity plan, but not a comprehensive action plan. However, this activity plan is based on the recommendations of both EVSM and VMA conducted in 2005 with the support of UNICEF and WHO. (Annex V)

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

Please see Annex V, summary activity plan of EVSM

The next EVSM/VMA* will be conducted: 2007

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| 0.05ml (BCG ) AD Syringes | 416,700 | All supplies received as scheduled time, without any delay |
| 0.5ml AD Syringes | 4,129,900 |  |
| Reconstitution Syringes 2.0 ml (BCG) | 417,200 |  |
| Reconstitution Syringes 5.0 ml | 66,800 |  |
| Safety Boxes | 51,700 |  |

Please report on any problems encountered.

All injection safety items were received well on time, without any delay and in good condition. UNICEF support and coordination in this regard is appreciated.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

GAVI support for injection safety will be completely over from 2008. As requested by MoH Sri Lanka, GAVI continues to support partially in injection safety in 2007 as the final stage of Phase I of the new vaccine supply. The Government of Sri Lanka has already taken a policy decision to ensure continued supply of injection safety items through Government funds for the entire EPI programme and in 2006, the MoH has purchased the balance Injection safety items, which were not covered by GAVI support. The Government of Sri Lanka has already included a separate budget line for EPI expenses within the MoH budget from 2007 and this includes injection safety items too. Medical Supply Division (MSD) of the MoH is responsible for the procurement and distribution of injection safety items, whereas Epidemiology Unit/MoH coordinates and monitors this activity to ensure the smooth functioning of the EPI programme in the country. In 2006, MoH has procured the following quantities of injection safety items in addition to the injection safety items received from the GAVI: 0.5ml AD syringes – 8,500,000, 0.05ml AD syringes – 300,000 2 ml Reconstitution syringes – 70,000, 5ml Reconstitution syringes – 200,000 Safety boxes (5L) – 125,000 Further, if the funding application for pentavalent Hib vaccine is approved by GAVI, injection supplies will be received as part of the package from year 2008 onwards. This will reduce country’s financial burden to procure injection supplies for other EPI vaccines and JE.

#### Please report how sharps waste is being disposed of.

One of the limitations in safe injection practice is the waste disposal. Yet there is no advanced system of waste disposal following immunization. Burning of immunization waste (filled safety boxes) in open pits is the common practice. However, there is a rigorous method of monitoring this process at field level, and possibility of unsafe waste disposal is very low.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

The procurement of Injection safety items by MoH was delayed due to the lengthy tender procedures. This delay is largely due to technical evaluation of AD syringes, as MoH is much concerned on high quality products while it is in affordable cost. However, this has not affected the EPI programme, as there was no shortage of injection safety items. Availability of buffer stocks and continued GAVI injection safety supply in 2006 are the reasons for the smooth management of injection safety logistics in the country.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

Not Applicable

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | 4,561,740 | 4,670,155 | 7,106,900 | 7,163,497 | 7,234,154 |
| Injection supplies | 918,650 | 922,944 | 586,788 | 600,266 | 610,861 |
| Personnel (including shared costs) | 5,022,664 | 5,123,117 | 5,225,579 | 5,330,091 | 5,436,693 |
| Other operational expenditures | NA | 2,620,270 | 1,996,610 | 1,955,724 | 2,286,318 |
| Cold Chain equipment |  | 1,790,610 | 65,545 | 58,897 | 103,372 |
| Vehicles | NA | 25,000 | - | - | - |
| Training | 14,165 | 56,100 | 13,325 | 58,366 | 16,236 |
| Other | 667,850 | 377,145 | 255,679 | 268,751 |  |
| Campaigns | - | - | - | - | 207,469 |
| Total Immunization Expenditures |  | 9,973,369 | 15,617,242 | 15,282,373 | 15,643,016 |
| Total Government Health Expenditures | 514,709,200 | ** | ** | ** | ** |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  |  |  |  |  |
| GAVI | 732,190 | 478,800* | 5,116,411 | 3,394,022 | 2,660,881 |
| UNICEF | 287,400 | 167,000 | 100,000 | 100,000 | 100,000 |
| WHO | 27,500 | 40,000 | ** | ** | ** |
| World Bank (grant) | 654,515.5 | 543,847 | 492,458.5 | ** | ** |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

* Note: GAVI Phase I support for Hep B   ** Information not available

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine - DTP-HepB –Hib |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  | 202,409 | 249,581 | 363,423 |
| Total co-financing by country (US$) |  |  | 672,671 | 755,706 | 1.008,643 |
| Of which by |  |  |  |  |  |
| Government (US$) |  |  | 672,671 | 755,706 | 1.008,643 |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing (US$) |  |  | 5,198,849 | 3,632,058 | 3,372,749 |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other | √ | BCG, DTP, DT, TT, aTd, OPV, Measles, MR, Rubella, JE | Government of Sri Lanka |
| UNICEF |  |  |  |
| PAHO Revolving Fund |  |  |  |
| Donations | √ | Hep B | GAVI |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) | Not Applicable, as no GAVI/ NVS support for 2006 |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | √ | DTP-HepB-Hib |  |
| National health sector plan | √ | DTP-HepB-Hib, Pnemococcul |  |
| National health budget | √ | DTP-HepB-Hib |  |
| Medium-term expenditure framework |  |  |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis | √ | DTP-HepB-Hib |  |
| Annual immunization plan |  |  |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |  |
| --- | --- | --- |
| 1. No comments, as the vaccine co-financing practice in Sri Lanka has not commenced yet. |  |  |
| 2. |  |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |  |
| 1. Vaccine cost | Despite the encouraging co-financing strategy introduced by the GAVI, the actual cost of the new vaccines to be borne by the Government is increasing. Other than DTP-HepB-Hib vaccine, as to date there is no public price for other new vaccines. Therefore, sustainability of new vaccines to be introduced needs careful consideration. |  |
| 2. Regional Bulk procurement | SEARO has proposed regional bulk procurement of vaccine as a strategy to increase the bargaining power of small countries (‘Monopsony’-Few buyers) If this bulk procurement materialises, how the co-financing system will function under such a system is not clear. |  |
| 3. Procurement process | At present, except GAVI funded HepB, all other vaccines are procured by the MoH directly from the suppliers. Sri Lanka has proposed to continue with the same practice for GAVI/NVS, while GAVI can directly pay its contribution to the supplier. Regarding the transparency of this process, does GAVI has any suggestions? If GAVI disagree, what is the alternative (procure via UNICEF)? If so, any administrative charges to be paid to UNICEF? |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

1. In January 2007, Sri Lanka has submitted a NVS application to the GAVI and received conditional approval. In April 2007, Sri Lanka has submitted additional information requested by the GAVI (Independent review committee) and is awaiting GAVI decision of NVS support. It is important to note that in the January application, Sri Lanka expected to introduce the new vaccine (DTP-HepB-Hib) from 2007, but now it is unlikely that it can be done in 2007. (It takes time to procure vaccine and therefore, there is hardly any time to introduce the new vaccine in 2007) Therefore, in this APR, Sri Lanka has revised its target assuming that GAVI NVS support will be available from 2008 and therefore introduction of the new vaccine will take effect from January 2008. Because of this adjustment, the number estimated and amount of co-finance given in NVS application in January 2007 will slightly differ from the estimates and co-finance given in this APR with the XL provided with this report. 2. In the previous APR and cMYP, the survival infants were calculated based on stable IMR of 11.2/1000. However, in this APR, a slight adjustment was made, based on the assumption of that IMR which will decline gradually from 11.2/1000 in 2006 to 10.5/1000 in 2013. Therefore, the baseline target will slightly differ from the previous APR and cMYP.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 361,453 | 367,657 | 375,000 | 380,000 | 385,000 | 390,000 | 395,000 | 400,000 | 405,000 |
| Infants’ deaths ¶ | 4,410 | 3,886 | 4,162 | 4,180 | 4,196 | 4,212 | 4,226 | 4,240 | 4,252 |
| Surviving infants | 357,043 | 363,771 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 348,781 | 349,413 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 342,410 | 340,975 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of HepB (From 2008 DTP-HepB-Hib) (new vaccine) | 337,866 | 338,059 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of HepB (From 2008 DTP-HepB-Hib ( new vaccine) | 310,030 | 330,374 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| Wastage rate till 2006 and plan for 2007 beyond*** HepB (From 2008 DTP-HepB-Hib ( new vaccine) | 12% | 10% | 10% | 10% | 7.5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 331,705 | 339,759 | 375,000 | 380,000 | 385,000 | 390,000 | 395,000 | 400,000 | 405,000 |
| Infants vaccinated / to be vaccinated with BCG | 344,292 | 352,869 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 353,281 | 352,859 | 370,838 | 375,820 | 380,804 | 385,788 | 390,774 | 395,760 | 400,748 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary.

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

This is a new introduction from 2008 and there is NO significant change of the amount of the new vaccine of DTP-HepB-Hib requested in application in January 2007 as given in this report. There is no change of the presentation of the new vaccine requested in application January 2007.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of DTP-HepB-Hib vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 1,564,351 | 1,199,533 | 1,215,232 |
| Doses to be funded by GAVI | 1,361,942 | 949,951 | 851,809 |
| Doses to be funded by country | 202,409 | 249,581 | 363,423 |
| Country co-pay in US$/dose | 0.43 | 0.63 | 0.83 |
| Total co-pay (US$) | 672,671 | 755,706 | 1.008,643 |
| Country co finance as a % | 12.94% | 20.81% | 29.91% |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Note: A row is added to Table 6, to show country co finance as a percentage

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8: Estimated supplies for safety of vaccination for the next two years with DTP-HepB-Hib (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Sri Lanka expected to introduce the new vaccine (DTP-HepB-Hib) from 2007, but now it is unlikely that it can be done in 2007. Therefore, in this APR, Sri Lanka has revised its target assuming that GAVI NVS support will be available from 2008 and therefore introduction of the new vaccine will take effect from January 2008. Because of this adjustment, the estimated injection safety given in NVS application in January 2007 will slightly differ from the estimates given in this APR (Table 8).

# 4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# NOTE: Sri Lanka has submitted its HSS proposal to the GAVI in March 2007, and GAVI independent review committee decision is to resubmit in October 2007. (Annex VI)

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) | Epidemiology Unit, MoH | >98% | WHO_UNICEF_JRF_2006 | 2006 | >99% | 2008 |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | Epidemiology Unit, MoH | 100% | WHO_UNICEF_JRF_2006 |  |  |  |
| 3. Under five mortality rate (per 1000) | Family Health Bureau, MoH | 4.4 |  | 2004 | 3.5 | 2012 |
| 4. Measles Coverage | Epidemiology Unit, MoH | >98% | WHO_UNICEF_JRF_2006 | 2006 | >99% | 2008 |
| 5. Care provider: population ratio in underprivileged districts | Annual Health Bulletin 2004, MoH | *PHM 1: 8,000 *PHI 1: 40,000 |  | 2004 | *PHM 1: 3,000 *PHI 1: 15,000 | 2008 |
| 6. % of people who will have access to Primary Health Care services within a radius of 7 Km | Annual Health Bulletin 2004, MoH | <50% |  | 2004 | <10% | 2012 |

- *PHM – Public Health Midwife , PHI- Public Health Inspector

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

Not applicable, as GAVI/HSS support has not yet be started.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report |  |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

It should also be noted that this document is currently under revision and will be replaced with an updated version

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing