Updated November 2004

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: SUDAN

Date of submission: …May / 2005……………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Sudan received GAVI ISS funds up to December/2004 as follows: The first tranche of I.S.S funds (673,700 US$) received on October/2002. The second tranche of (745,581US$) received on July 2003 The first half of third tranche(584,136US$) received on May/2004 The second half of the third instalment was agreed to be received early January/2005 (not received yet) The disbursements were made through the same bank account which was agreed upon by ICC &GAVI secretariat The utilization of I.S.S funds is under the regulation of Federal Ministry of Health. The states receive monthly support based on: Revision, approval and endorsement of locality micro plans Significant performance, and efficient use of EPI supplies in regard to their different situations Feedback and monthly liquidation State contributions According to the micro plans, the states determine the number of unimmunized children expected to be reached every year in order to achieve the National coverage target of 80%. States MOH distribute the support to the districts according to the budget in their plans to conduct outreach and mobile activities, no problems were encountered during this process. Role of the I.C.C: To review & endorse the funding plan and this usually happen in the beginning of the year. To, follow-up on the implementation of endorsed plan To review the final report on performance and budget To, review & endorse the final settlement of accounts Problems encountered for use of funds: American sanctions against Sudan have delayed the transfer of the second half of the third tranche, which was supposed to be received early January/2005. This in facts has a very serious impact on the performance and implementation of RED Approach activities for the year /2005 As a result of delay in receiving the ISS funds, the districts did not receive any support since Nov/2004 in order to perform their planned outreach and mobile activities to reach children in the remote areas, thus may reflect on the achievements of 2005 target. Note: By 2004 achievements, Sudan had met the condition to receive a reward on the extra children being vaccinated, Although the covered extra children are from Northern states & the southern states under government control only. We have no objection to deduct the 12% out of the reward for the other part of the south in order to facilitate solving the problem and transfer of the money.

#### Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004:                        ___584,136  U$__________

Remaining funds (carry over) from 2003:  ___283,822  U$___________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 259,384 | 32,685 | 2,935 | 223,764 |  |
| Transportation | 387,525 | 36,207 | 8,695 | 342,623 |  |
| Maintenance and overheads | 4,040 | 4,040 | 0 | 0 |  |
| Training | 10,972 | 5,173 | 215 | 5,584 |  |
| IEC / social mobilization | 27,666 | 23,726 | 0 | 3,940 |  |
| Outreach | ** |  |  |  |  |
| Supervision | 70,871 | 10,985 | 5,337 | 54,549 |  |
| Monitoring and evaluation | 58,488 | 39,973 | 14,505 | 4010 |  |
| Epidemiological surveillance | 0 | 0 | 0 | 0 |  |
| Vehicles | 0 | 0 | 0 | 0 |  |
| Cold chain equipment | 34,150 | 15,826 | 13,216 | 5,108 |  |
| Other (stationeries) | 15,064 | 12,476 | 2,339 | 249 |  |
| Total: | 868,160 | 181,091 | 47,242 | 639,827 |  |
| Remaining funds for next year: | 0 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

** Out reach activities amount of funds are calculated under personnel and transportation funds at the district leve.l

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Major activities conducted to strengthen immunization are: Infrastructure building: - Central cold store maintenance, electronic alarm systems, monitoring for temperature and power supply were applied. - Cold chain rehabilitation and installation (63 solar rereg, 52 Frezer,11 refreg).mainly in Darfour zone and southern states. that the functionality of the cold chain in 2004 is 80% compared to 55% in 2001. - Increase accessibility through more immunization sites which increased by ( fixed sites= 72, SOS= 963, mobile = 205) than the year 2003 2- Capacity building: 2.1. Administrative Performance - Computer programs developed for different EPI sections for better communication and monitoring - 33 weekly meetings at the federal level - Data collection and data entry course for 9 participants at the Federal level 2.2. Basic data Information board - Updating and completing the basic information data for the EPI( maps, villages and health units in Sudan) - 2004 locality micro plans data entry 2.3. Training - Basic course TOT for 18 state, participants - TOT, MLM for 31 participants ( EPI officers and Zonal co-ordinators from 23 states) - Vaccine management course for 240 participants from 15 states - Cold Chain maintenance course for 10 participants in southern states - Basic course refresher training for 971 vaccinators in 7 states - 5000 copies of updated vaccinator guide/ 2004 printed 2.4. Supervision and Monitoring: - 80% Implementation of the supervision plan to the states (43 visits to 23 states), 99% of the health units supervision plan. - Analysis of the findings and feedback - Conduction of 3 National review and evaluation meetings on progress of GAVI micro plans implementation with the 23 states. 2.5. Quality of recording and reporting system: - DQA self assessment in 4 states, verification factor was 86% - Follow up on the recoding and reporting system in all states 3. Routine Immunization Activities - Sustained Outreach services & mobile activities were conducted as planned - 65 Localities achieved 80% DPT3 coverage compared to 28 localities in 2002 - Acceleration 3 rounds campaigns for routine immunization in Darfour zone (23 localities covering 86,571 children with DPT3 ) and 20 localities in Southern accessible states under government control. 4. Polio Eradication - Conduction of 2 rounds of Sub NIDs in 19 states targeting 1,669,550 children aged 1 day-5 years for polio eradication - Conduction of 2 rounds of mop-up campaigns in 3Darfur states after the importation of the first polio case targeting 1,026,051 - Conduction of 2 rounds of the 12th NIDs targeting 5,936,659 under five children, coverage was 96.1% in the first round and 99.1% for the second round - 95% of the planned AFP Surveillance active visits were conducted - Accreditation of the polio lap. (100% in quality indicators) 5. Measles Elimination - Micro planning, training and conduction of measles catch-up campaigns in 14 states vaccinating over 8,000,000 children aged 9mon. – 15 years of age, coverage was 98% 6. Others - Immunization safety focus project started in 3 states Conduction of 6 operational researches & studies on immunization (page below) Problems encountered are: 1. Insecurity 2. Population movements because of Darfour crises 3. Competing program activities ( polio & measles campaigns) 4.Lack of qualified staff at locality levels 5.Community participation and ownership

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

Planned activities to improve the documentation and reporting system are continuous since the year 2003 after the test DQA recommendations. The official DQA was implemented in Sudan on Sept-Oct./2004, final report received by mid November/2004. The result was as follows : quality of the system = 90.6% and the verification factor (VF)= 0.960 Please note that the complete plan based on the observations, findings and recommendation of the official DQA conducted Oct/2004 a plan of action for the year 2005 is under process to be endorsed by ICC and will be implemented in 2005.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

- Assessment of injection safety during measles catch up campaigns in 4 states in January/2004, the result showed: All of the vaccinators use new syringes& needles for injections The practice of recapping the used needle was observed in (5%) of the 80 health facilities in the sample Cleaning of skin before injection in most of the health centers (97%). 96% of the health facilities have safety boxes while 38% transport the safety boxes out side the health facility for disposal The mean needle skin injury were 0.6 during the campaign Study of Measles case fatality rate(CFR) in 2 states with measles outbreak, result showed: Total of 1144 cases were identified, 50% of cases were vaccinated before, 23% received treatment with vit.A, among 1144 cases investigated 10 died within 30 days of rash onset. This corresponds to a CFR of 0.9% which was higher at the rural area (1.3%) Sero-epidemiology of hepatitis B among children below 10 years of age Data and samples are collected and under processing - Coverage survey in Sennar state (high performing state after GAVI support) Results are under processing DQA self assessment in 4 states Results were satisfactory , V.F (0.86) - Study of documentation system in fixed sites in Khartoum state, (data under processing)

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH / January.           YEAR / 2005.

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

The doses of the new vaccine Hepatitis B provided by GAVI/VF received are 1,141,800 in two shipments, the last one was on October/2004 Number of AD syringes, 1,039,400 Number of safety boxes, 11,550 Problems encountered: the vaccine delivered later than the proposed dates by the EPI to receive the vaccine (maximum by 15th/June/2004) in order to be introduced into the first three states by July/2004, therefore the introduction plan was delayed till January/2005, and also because of polio epidemic in the second half of 2004

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

The main activities being implemented in the three states to introduce the new vaccine were: Refresher training courses for the vaccinator about the immunization safety policy (971 particepants). Training on the introduction of hepatitis B vaccine (T.O.T for EPI officers and training of health workers in 3 states only ) Rehabilitation of the cold chain &, installation with preventive maintenance being implemented in the targeted states Preparation of social mobilization materials and implementation of some activities Study of Sero-epidemiology of Hepatitis B among children below 10 years of age ( data and samples collected) Preparation of new immunization cards, tally sheets, reporting forms and registers (partially implemented) The vaccinator guide was updated ,reprinted and distributed including the information about the introduction of the new vaccine The problems encountered were: Delay of the arrival of the vaccine and the cash support for the introduction of the new vaccine, delayed the a phased introduction plan from it is proposed dates in 2004 to 2005

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Financial support for introduction of the new vaccine (US$100,000) has not being received up to February/2005 by the EPI This problem has delayed the complete production of the training and social mobilization materials and the printing of the updated new vaccine including cards, tally sheets and register books that needed.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Support for safety of injection was received from GAVI fund through UNICEF in form of supplies, included: BCG syringes 1,036,400 AD syringes 5,735,400 Reconstitution syringes (2.0 ml, BCG) 103,600 Reconstitution syringes (5.0 ml, Measles) 144,000 Safety boxes 77,925 No problems were encountered receiving these supplies Note: Injection safety devices received slightly vary from the approved quantities (extra safety boxes 12,189 and AD syringes 1,069,360 ) in order to accommodate export packing GAVI support for injection safety was up to the end of 2004, for 2005 the country had a balance stock of these items to cover the need for 2005 requirements partially, after the ICC meeting on May2005, UNICEF had committed to fill the gap for the year 2005. For 2006 on wards, support will be clarified after the FSP is completed and approved.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- The main problems encountered during implementation of the plan of injection safety implementation are that this policy has not implemented in all the health sector services rather than immunization services and they lack the sufficient supplies to implement the injection safety policy. - The AEFI surveillance system still not incorporated into routine EPI reporting system., although it has started during measles campaigns - Central Incinerators are not installed due to lack of special resources although this is proposed to be implemented in one state as a pilot phase.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| * Establish a national strategy according to WHO recommendations * Ensure adequate supply of AD syringes & safety boxes * Ensure proper use of safety of injection equipment * Create community awareness regarding safety of injection * Implement a system for detecting and investigating AEFI * Ensure adequate disposal of injection materials at each facility | - Revise the national strategy according to WHO recommendations - Dissemination of safety injection policy to all providers - Train EPI staff to estimate safety injection equipments required -Ensure an effective safety of injection stock management at the central level - Ensure that all partners continue providing supplies - Assess EPI staff knowledge and practice regarding safety injection - Provide systematic training on safety of injection practices - Incorporate safety injection issues in EPI training materials - Reinforce supervision at all levels - Develop a surveillance system for safety of injection - Use mass media channels to deliver messages for community - Sensitise school health program - Support local initiatives of waste disposal - Design advocating strategy targeting decision makers - Nominate an expert committee - Design a system to investigate AEFI - Training of EPI staff - Finalise the supervision check lists - Implement the system all over the country - Develop simple guidelines for appropriate waste disposal - Regular supervision to ensure proper destroy of materials - Installation of central incinerators | - Implemented - Implemented - TOT for 18 states officers - Implemented - Implemented up to 2005 - Continuous - 1039 vaccinators trained - Implemented - Continuous - Continuous - Continuous - In progress - In progress - In progress - Implemented - The system started at National level - Implemented during measles catch up campaigns in 14 states - In progress - In progress - Implemented - Continuous Not implemented | Joined with the preparation of the FSP Lack of resources | Same indicators and targets of the whole plan will be targeted for the forthcoming years |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

- No cash contribution was approved for injection safety support

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Process of FSP for Sudan has been started, development of work plan completed, some activities has been completed, others started , and some will need technical assistance. Activities being completed are as follows: 1- Core Team formation. 2- POA for the activities developed 3- Development of the methodology for data collection and tools for the costing 4- Training of the Data collectors (2) for the survey from outside EPI 5- Data collection from the selected states, localities and health units 6- Identification and collection of the relevant needed documents 7- Writing of section 1 & 2 of the FSP 8- Analysis of the data 9- Data entry for costing and projection in the FSP excel tool 10- Writing of section 3 (started) Activities to be implemented are: 1- Clarification of future commitments from partner/ stakeholders 2- Gap analysis section 4 3- Revision of FS targets, priorities, actions by ICC (meeting) 4- Revision of FSP as needed 5- Presentation of the plan to relevant ministers for approval 6- ICC meeting to sign off on FSP Remaining issues, Gap & needed Technical assistance are Financing projections and gap analysis The technical assistance is needed for: 1. To revise section 1 – 3 2. To participate in the negotiation with partners & stakeholders about their expected commitment. 3. To assist in the gap analysis. 4. To help in finalizing the FSP report. It is agreed upon that: The technical assistance mission to Sudan is planned for third week of March/2004 The submission of the complete FSP will be by June/2005

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  However, in an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for  each new vaccine.

| Table 2: Sources (planned) of financing of new vaccine ( Hepatitis B) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2005** | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| Proportion funded by GAVI/VF (%) | 58% | 86% | 90% | 92% | 95% | 95% | 95% | 95% | 95% | 0 |
| Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 48 | 100 | 100 | 100 | 100 |
| Total funding for Hepatitis B. (new vaccine) *** | 48 | 100 | 100 | 100 | 100 | 52 |  | 0 | 0 | 0 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine

** The first year should be the year of GAVI/VF new vaccine introduction

*** Should total 500% at the end of GAVI/VF support

- Note: first row indicates the targeted coverage in relation to DTP3 %(2005 is the year for implementation the first two phases of the introduction plan,  which were planned in 2004&2005 and being shifted to start both phases in 2005, first phase from Jan/2005 and the second July/ 2005.

- Second row refer to the start of the government fund supply for the new vaccine

- Third row refer to the 500% fund support by GAVI, please consider that the introduction plan started on 2005 onwards in order to calculate the 500% accordingly

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding

indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators  (Not Applicable)

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 14). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 1,213,240 | 1,302,467 | 1,334,985 | 1,368,428 | 1,402,824 | 1,438,203 | 1,474,594 | 1,512,028 | 1,550,537 |
| Infants’ deaths | 130,252 | 142,720 | 146,178 | 149,733 | 153,387 | 157,143 | 161,006 | 164,977 | 169,060 |
| Surviving infants | 1,082,988 | 1,159,747 | 1,188,807 | 1,218,695 | 1,249,438 | 1,281,060 | 1,313,588 | 1,347,051 | 1,381,477 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated 2005 and beyond with 1st dose of DTP (DTP1)* | 952,937 | 1,078,564 | 1,141,255 | 1,182,134 | 1,211,955 | 1,242,628 | 1,274,180 | 1,306,639 | 1,340,032 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of DTP (DTP3)* | 853,141 | 962,590 | 1,022,374 | 1,096,825 | 1,149,482 | 1,217,007 | 1,247,908 | 1,279,698 | 1,312,403 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 1st dose of* Hepatitis B..... ) | 0 | 511,429 | 1,092,353 | 1,120,388 | 1,161207 | 1,191,198 | 1,274,180 | 1,306,639 | 1,340,032 |
| Infants vaccinated 2004 (JRF) / to be vaccinated 2005 and beyond with 3rd dose of ( HepatitisB) | 0 | 353,829 (12 States) | 978,566 | 1,050,363 | 1,101,351 | 1,166,638 | 1,247,908 | 1,279,698 | ,312,403 |
| Wastage rate in 2004 and plan for 2005 beyond*** | 21.7% | 25% | 23% | 20% | 18% | 16% | 15% | 15% | 15% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 447,384 | 586,110 | 667,749 | 752,635 | 841,694 | 934,832 | 1,032,215 | 1,134,021 | 1,240,429 |
| Infants vaccinated / to be vaccinated with BCG | 864,386 | 976,850 | 1,067,988 | 1,163,163 | 1,262,541 | 1,323,146 | 1,400,864 | 1,436,426 | 1,473,010 |
| Infants vaccinated / to be vaccinated with Measles | 778,205 | 869,810 | 951,045 | 1,035,890 | 1,124,494 | 1,178,575 | 1,247,908 | 1,279,698 | 1,312,403 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years .                 **** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Changes of the baseline( denominators), In the years 2005 onwards is due to production of new Population Data Sheet ( in 2004) all the numbers provided are estimated and projected from the new data sheet which is provided by Central Bureau of statistics (CBS) and UNFPA , which are the official government body authorised to release such estimates for the whole country, provided that the last census in Sudan was in the year1993. For the year 2004 the old Population Data Sheet of 2003 was used Estimated target coverage for DPT and other antigens for the forthcoming years are updated after the revision of the true achievements and due to the situation of Sudan ( Darfour crises, and the south SUDAN) The new targets are updated as follows: 2004 2005 2006 2007 2008 2009 2010 2011 2012 BCG 71 75% 80% 85% 90% 92% 95% 95% 95% DPT3 79 83% 86% 90% 92% 95% 95% 95% 95% Measles 72 75% 80% 85% 90% 92% 95% 95% 95% TT 37 45% 50% 55% 60% 65% 70% 75% 80%

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

UNICEF Supply Division has assured the availability of the new quantity of supply of Hepatitis B vaccine according to the introduction plan, provided that the funds are secured by GAVI\ VF in proper time

Table 4: Estimated number of doses of Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### Note: the amounts of vaccine received late 2004, distributed to the first states in the plan since Dec/2004, the second phase 9 states will introduce the vaccine in July/2005, please consider that the introduction date is in 2005 instead of 2004 but the two first phases are in the same year.

#### 3.3	Confirmed/revised request for injection safety support for the year …… (indicate forthcoming year)

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

* Not applicable because GAVI\VF has fulfilled its commitment for the three years of support of injection safety supplies for Sudan. This has been ended by the year 2004.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - DPT3 Coverage - Localities micro-plans - Drop out rates - Wastage rate | 80% 111 Locality micro-plans - 15% - 23% | - 79% - 100% - 10% - 21.7% ( For DPT) | - Conflict situation in the West (Darfure states), increased the number of inaccessible areas & population movement out of the states | - 83% for 2005 - Updating the micr-oplans for 2005 - 10% - 20% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | May/2005 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | ( |  |
| DQA reported on | ( |  |
| Reported on use of 100,000 US$ | ( |  |
| Injection Safety Reported on | ( |  |
| FSP Reported on (progress against country FSP indicators) | ( |  |
| Table 2 filled-in | ( |  |
| New Vaccine Request completed | ( |  |
| Revised request for injection safety completed (where applicable) | NA | 3 years of support were completed by 2004 |
| ICC minutes attached to the report | ( |  |
| Government signatures | ( |  |
| ICC endorsed | ( |  |

6.  	Comments

ICC/RWG comments:

ICC Comments: The report was satisfactory to all members UNICEF enquired about the FSP and when it will be ready All the above comments were explained during the ICC meeting while presenting the 2004 GAVI progress achievements RWG Comments: Management of ISS funds 1.1.1 To highlight if the delay receiving the funds has affected the implementation plan of the planned activities. Mechanism of releasing the funds to the district levels and report if any problems encountered Report on how the reward will be distributed between north and southern part ( not under gov. control ) 1.1.2 Attach ICC minutes Indicate the places in the southern states where acceleration campaigns were conducted in the government accessible areas - Attach status of implementation of DQA recommendations - Explain how the country will take over after the end of injection supplies by GAVI Table 2: - revise the data in the table 3.2 Table 4: Since introduction of Hep B did not start in 2004, highlight that to be considered by GAVI that 2005 is the starting point and calculate the 500% support * All the above comments were considered in the report after revision

7.	Signatures

For the Government of ……SUDAN…………..…………………

Signature:	……………………………………………...…………

Title:	MINISTER OF HEALTH / FMOH.

Date:	   ……………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO |  |  | Minst. Of Finance |  |  |
| UNICEF |  |  | Minst of Interior |  |  |
| ROTARY INTERNATIONAL |  |  | Minst. Of Defence |  |  |
| IFRC |  |  | Minst of International Cooperation. |  |  |
| HAC |  |  | PHC/ FMOH |  |  |

~ End ~

# Text boxes

Partnering with The Vaccine Fund

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year… ….: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes