Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: THE SOCIALIST REPUBLIC OF VIETNAM

Date of submission: May 2006 Reporting period: 2005 (Information provided in this report MUST refer to 2005 activities) (Tick only one): Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report X  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

Nationally 1,448,721 children under 1 year old were vaccinated with 3rd dose of Hep B in 2005 (93.7% of total targeted children).

In the provinces receiving vaccine supplied by GAVI, a total of 1,205,251 of children under 1 year old (93.9% of the target population) were vaccinated with 3rd dose of Hepatitis B vaccine. Coverage with 1st dose of Hepatitis B vaccine reached 95.8%, of which 72.2% was given during the first 24 hours of life.

A total of 243,470 children (93% of the target population) received three doses of locally produced Hepatitis B vaccine. Coverage levels were: HepB1: 94.5 % and HepB2: 93.6 %.

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

None received

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 _______________

Remaining funds (carry over) from 2004 ________________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

X

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH: January           YEAR 2002

Total number of hepatitis B vaccine received for 2005

| Vaccine/Devices | Quantities in doses | Delivery date |
| --- | --- | --- |
| Hep B (1 dose/vial) | 1,352,700 | 1, 20, 22 Dec. 2004 and 26 May 2005 |
| Hep B (2 doses/vial) | 2,705,400 | 4 Jan. 2005 and 23 May 2005 |

Number of Hepatitis B vaccine doses received for 2006

| Vaccine/Devices | Quantities in doses | Delivery date |
| --- | --- | --- |
| Hep B (1 dose/vial) | 1,265,900 | ? |
| Hep B (2 doses/vial) | 1,300,000 | 21 Dec. 2005 |

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

The GAVI supplied vaccine is continued being used in 83% of the total target population, the rest use locally produced vaccine. 4,148,475 AD syringes 0.5ml and 45,000 safety boxes cost US$ 307,000 were supplied for administration of Hep B vaccine. Number of Hepatitis B vaccine doses received for 2006: 8 Q-tag 2 in 8 of 417 boxes Hep B vaccine (two doses/vial produce by LG life Sciences Ltd., Korea) with the sign ALARM (1 hour <0.5oC) when vaccine arrived in Vietnam on 21 December 2005. However, the vaccines in 8 boxes were passed shake test. All Hep B vaccine vials received with VVM attached. We are still waiting for Hep B vaccine (1 dose/vial) for 2006.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Since the year 2005, Hepatitis B vaccine for children under 1 year old nation-wide - 83 % of target population – has been using GAVI – supported vaccine. The remaining uses locally produced vaccine. Administration of Hepatitis B vaccine birth dose for children within 24 hours after birth replaced the administration of Hepatitis B vaccine birth dose within 3 days after birth in 2005. Full immunized children (FIC) under one year old has included three doses of Hep B vaccine since 2005. FIC rate for children less than one was 94.4% in 2005. 93.9 % of target children in 46 provinces using GAVI – Hepatitis B vaccine was vaccinated with HepB3; 95.8 % was vaccinated with HepB1 and 72.2 % was vaccinated with HepB1 within 24h after birth. Nationally, 93.7 % of 1,545,475 children were vaccinated with Hep B3; 95.5 % was vaccinated with HepB1 and 62.2 % was vaccinated with HepB1 within 24 hours after birth. With support from GAVI, three activities for addressing the system-wide-barriers in immunization were implemented in 2005: - Amendment of the Joint-ministry-Circular no.51 regarding EPI expenditure: Workshops on amendment of the circular were organized and the first draft of the amended circular has been done, basing on questionnaire feedback. It will soon be revised for official submission to the Ministry of Health and Ministry of Finance, expected to be completed by June 2006. - Training local health workers for ethnic minorities: The 9 month-training course for 30 village health workers of H’Mong ethnic minority people was started in August, 2005 and will be finished by June, 2006. - Communication for Private Health Sector on immunization: Has been completed: 18,000 leaflets on EPI were printed out and delivered to private health centers/ treatment services in Hanoi and Ho Chi Minh Cities.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

It was reported in the first ARP in September 2003

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Total fund for injection safety from GAVI for 2005 and 2006 were US$1,023,000 and US$1,022,000. 2006 is the last year of injection safety equipment support from GAVI for routine EPI in Vietnam. Requirement for safe injection equipment for routine EPI from 2007 will be covered by Vietnam government.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### With support from GAVI and the fund from the government all of requirement injection equipment and safety boxes for EPI is enough for EPI. With support from PATH, a demonstration of a needle remover device in Huong Khe district, Ha Tinh Province in 2005 was piloted. The results from this piloting in Huong Khe district shown that, needle remover is useful and acceptable for managing injection waste and improving injection safety at commune level in remote areas.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 100 % of Provinces with adequate access to appropriate disposal system, including exchange mechanism for new and used injection equipment where this is feasible, and local disposal in remote locations | By the end of 2004 | Some provinces and districts received industrial incinerators to destroy medical waste. Other provinces and districts that are not equipped with industrial incinerators yet, and are destroying the medical waste by building various types of local prototype incinerators | A national policy on medical waste management is not yet ratified. However, the requirement of safety boxes for EPI was coverage 100%. | By the end of 2008 (acknowledging that this target is difficult for the EPI to set) |
| 100 % of Districts with 100% AD use for all EPI vaccines and safe disposal practices | By the end of 2003 | 100% AD syringes are used in routine EPI except for syringes used for BCG. | AD syringes used for BCG is not available | 2004 (not include syringes used for BCG) |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Safe injection equipment was distributed in 2005 as follow: -BCG syringes 0,1 ml: 1,815,909 pieces -AD syringes 0,5 ml: 12,527,935 pieces -Re-constitution syringes 5ml: 472,136 pieces - Safety boxes 5 l: 163,957 pieces

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five-year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five-year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of Hepatitis B vaccine (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| A: Proportion funded by GAVI/VF (%)*** | 81 | 87 | 82 | 83 | 83 | 80 | 0 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 19 | 13 | 18 | 17 | 17 | 20 | 100 | 100 | 100 | 100 |
| C: Total funding for Hepatitis B vaccine (USD) | 1,888,873 | 2,824,637 | 2,062,189 | 2,080,507 | 2,105,473 | 2,130,739 | 2,156,307 | 2,182,183 | 2,208,369 | 2,234,870 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Enhancing Government Funding for EPI (central level) | -Featuring FSP in ICC agenda with participation of MOF and MPI. |  | -No full compliance to interim agreement of 10% annual increment of EPI budget (MOF interprets it as average increase rate, not every year.) | -No FSP at the beginning of 2003 -2003 EPI budget was 98 billion VND (6,130,000 USD). | -FSP completed and being revised. -2006 EPI budget is 117 billion VND, which is 10-% increase from 2003 level. | No change, but rather reiterate the basic agreement of 10% annual increase of EPI budget. |
| 2. Budget shifting at the national and province levels | -According to the SWB research, action plan was made and fund secured to facilitate amendment of Circular 51 stipulating remuneration for local EPI staff. It will be finalized in June 2006 |  | -Due to financial decentralization, EPI system does not have control over provincial budget allocation. |  | National health expenditure has not been officially available to date; it is not possible to indicate. |  |
| 3. Additional resource from GAVI/ Vaccine Fund | -ICC started to discuss GAVI phase II proposal. |  |  | -No existence of concrete proposal in 2003. | -Proposal development in progress. It will be submitted to GAVI in Oct. 2006 |  |
| 4. Reduce vaccine wastage | -Nationwide cold-chain training for regional, provincial and district levels in 2004 and 2005. -Cold chain inventory development in early 2005. | -Hepatitis B vaccine wastage support from GAVI was 10% (it was 12% in 2003) |  | -No district received cold-chain training in 2003. -No cold-chain inventory in 2003. | -All store keepers at district, provincial and regional received cold-chain training in 2004 and 2005. -Cold chain survey conducted and inventory being established. -A monitoring vaccine wastage network at sentinel sites will be set up in 2006. |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3: Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births |  |  |  |  |  |  |  |  |  |
| Infants’ deaths |  |  |  |  |  |  |  |  |  |
| Surviving infants | 1,523,462 | 1,545,475 | 1,567,657 | 1,594,187 | 1,616,070 |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 1,395,670 | 1,457,302 | 1,505,911 | 1,528,499 | 1,551,427 |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 1,465,548 | 1,461,520 | 1,490,224 | 1,512,578 | 1,535,266 |  |  |  |  |
| Hep B VACCINE |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Hep B (GAVI) | 1,228,128 | 1,229,155 | 1,236,886 | 1,211,581 | 0 |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of Hep B (GAVI) | 1,192,786 | 1,205,251 | 1,171,787 | 1,033,032 | 0 |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Hep B (Local) | 246,054 | 247,348 | 253,338 | 302,896 | 1,535,266 |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of Hep B (Local) | 242,294 | 243,470 | 240,005 | 258,259 | 1,454,463 |  |  |  |  |
| Wastage rate in 2005 and plan for 2005 beyond*** Hep B (GAVI) | 12 % | 10 % | 8% | 8% |  |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond***Hep B (Local) | 18% | 18 % | 18% | 18% | 15% |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 1,386,217 | 1,436,015 | 1,411,791 | 1,432,968 | 1,454,463 |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG *(96%) | 1,456,280 | 1,465,055 | 1,521,579 | 1,544,421 | 1,567,588 |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles *(96%) | 1,479,514 | 1,471,332 | 1,490,224 | 1,512,578 | 1,535,266 |  |  |  |  |

Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

2006 is the last year of injection safety equipment support from GAVI for routine EPI in Vietnam. Requirement for safe injection equipment for routine EPI from 2007 will be covered by Vietnam government. However, if support from GAVI only coverage 41% requirement of Hepatitis B vaccine in 2007 (letter dated 30 July 2004 from GAVI) it will be a problem for EPI in Vietnam in 2007. It is noted that in Table 2.1: Sources (planned) of financing of Hepatitis B vaccine “Row A should add up to the total of 500% at the end of GAVI/VF support (2007)”, at the end of 2006 support from GAVI will be added up to 416%, so the support from GAVI/VF% in 2007 should be 84%. We request GAVI continues to support for 80% of requirement for 2007. From 2008 Vietnam government will coverage 100% of Hepatitis B vaccine requirement for EPI.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request, please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of Hepatitis B vaccine in 1-dose vials (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

Table 4: Estimated number of doses of Hepatitis B  vaccine in 2-dose vials (specify for one presentation only): Please repeat this table for any other vaccine 																presentation requested from GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Shipment of Hep B vaccine 2007:

| Vaccine | Indicate delivery date | Quantity in doses |
| --- | --- | --- |
| Hep B (1 dose/vial) | November 2006 May 2007 | 700,000 631,069 |
| Hep B (2 doses/vial) | December 2006 June 2007 | 1,400,000 1,292,138 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a 10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| HepB3 coverage | 85% | 93.7% | The rate of Hep B3 in 20 out of 669 districts below 80% | 90% |
| Drop out rate HepB3 | <10% | 1.9% |  | <5% |
| Wastage rate of Hep B vaccine and other EPI vaccines. | 20% for Hep B vaccine. For OPV, DTP and measles vaccines, allowed wastage rates are 33%. | Wastage rate of GAVI’ Hep B vaccine was 10% and local vaccine was 15%. This reflects the fact that local vaccine is being used in more remote areas where wastage reduction is more difficult. Wastage rate of OPV, DPT and measles vaccines were 35%. | Wastage rates of other vaccines were 35%. Supply of local vaccines in 20-dose vials limits capacity to reduce wastage | 10% for Hep B |
| DPT3 coverage |  90% | 94.6% |  | No change |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  | May 2006 |
| Reporting Period (consistent with previous calendar year) |  | Jan to Dec 2005 |
| Table 1 filled-in |  | Yes |
| DQA reported on |  | N/A |
| Reported on use of 100,000 US$ |  | N/A |
| Injection Safety Reported on |  | Yes |
| FSP Reported on (progress against country FSP indicators) |  | Yes (2004) |
| Table 2 filled-in |  | Yes |
| New Vaccine Request completed |  | Yes |
| Revised request for injection safety completed (where applicable) |  | Yes |
| ICC minutes attached to the report |  | Yes |
| Government signatures |  | Yes |
| ICC endorsed |  | Yes |

6.  	Comments

ICC/RWG comments:

2006 is the last year Vietnam receives support from GAVI for injection safety. Vietnam has planned to replace GAVI’s support for injection safety equipment from 2007. With the support from GAVI since 2002, all of children under one were targeted for Hepatitis B vaccine. In the year 2005, nationally 93.7 % of target children were vaccinated with HepB3, 95.5 % were vaccinated with HepB1 and 62.2 % were vaccinated with HepB1 within 24 hours after birth. 2007 will be the last year GAVI support Hepatitis B vaccine for Vietnam. 80% Hepatitis B vaccine need support by GAVI for Vietnam will be good to maintain all of EPI activities in 2007. With the fund from the Vietnam Government from 2008, 100% of hepatitis B vaccine requirement will be covered by the Government of Vietnam. In GAVI Phase II, Vietnam would like to received assistance from GAVI for: 1. Immunization Systems Strengthening (ISS) funding. 2. Support for Hib vaccine introduction either as tetravalent (DPT-Hib). 3. Support for introduction of measles 2nd dose. 4. Support for health systems strengthening. The national planning cycle in Vietnam is 5 years. A comprehensive Multi-Year Plan for Immunization (cMYP) 2006 – 2010 was sent to MOH.

7.	Signatures

For the Government of Vietnam

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~