January 2005

Progress Report

Partnering with The Vaccine Fund

To the

Global Alliance for Vaccines and Immunization (GAVI)

And

The Vaccine Fund

By the Government of

COUNTRY: YEMEN Republic

Date of submission: 9 / March / 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report   Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

- MOPH issue request to M.F for the budget required initiated from EPI. - M.F issue direction to control bank to deposit the budget requested to the account of MOPH. - MOPH issue check according the budget required. - In all those procures the technical task force for I.C.C is included.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004  (283500)

Remaining funds (carry over) from 2003 (528680)

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads | 1,451 | 1,451 |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization | 54,381 | 54,381 |  |  |  |
| Outreach | 237,093 | 15000 |  | 222,093 |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation | 10,953 | 10,953 |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other (printing materials) | 46,728 | 46,728 |  |  |  |
| Total: | 350,606 | 128,513 |  | 222,093 |  |
| Remaining funds for next year: | 863,005 |  |  |  |  |

The fund remained from 2003 to 2004 was US$ 930,111 (there was a mistake in the progress report of 2003 in this regard) and an amount of US$ 283,500 was added in March 2004 , so the total of spending money and the remaining fund for 2005 is US$ 1,213,611 .

 The major amount of fund were used for conducting the 3rd round of  pulse  immunization in 159 districts ,which played  the main role of increasing the coverage.

 MOPH issue request to M.F for the budget required initiated from EPI, then the M.F issue order to central bank to deposit the budget requested to the account of MOPH. MOPH issue check according to  the planned activities which approved by ICC , then the budget transferred to the governorate bank account. There is no problem encountered in releasing fund and distributing to the governorates.

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Training for director general, P.H.C director, surveillance focal points and EPI supervisors in the 22 governorates, together with central supervisors. - Training for 22 governorates store keepers. - Training for 332 district supervisors and formulation of 189 districts plans. - Acceleration activities three rounds in 220 districts in 20 governorates. - Replacement for 200 refrigerators with new ones. - Reviving the pentavalent vaccine Dec 2004. - Some problems were remained as : delay of the government budget, which led to delay of the vaccine.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.



YES                              NO

## If yes, please report on the degree of its implementation.

- Monitoring chart for immunization coverage were distributed and utilized. - Training of the supervisors at all levels. - Instruction for the flow of information was issued and distributed. - Supply of books and forms. - Concentrating on securing safe place during the supervisory visits and trainings to keep reports. - New forms for reporting system have been developed and wastage rate has been considered. - Data back up is now promptly performed. - Stamps have been distributed to all HUs for monitoring reports. - Completeness and timelines has started to be monitored especially at central and governorates level. - Feed back was done twice to all governorates for matching and correcting the data. - Supervisory visits has been more frequent.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC. (It was attached with the report of 2003)

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

Non

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH: March           YEAR: 2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

- pentavalent vaccine was recived in Dec 2004 with good condition and stored at the central store.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Training all EPI supervisors and the vaccinators on introducing the Pentavalent. - Issuing manual for the health workers. - Social mobilisation activities intensified. - Printing of the EPI documents include (registers, cards, daily statistics, monthly reports)

#### Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

It was utilized during 2002, request for replacement was sent, but no reply. Pentavalent vaccine was introduced in March 2005 with out any support from WHO or Unicef and they have sent GAVI secretariat a letter in this regard.

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Supply of AD syringes received (1,300,400), safety boxes (143,325) were received through Unicef financed through a loan of GAVI.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- Lack of incinerators.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| AD syringes available at all vaccination sites. All health workers are aware. | 100% 80% | 100% 80% | Non Lack of supervision. | To reach 100% |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Due to availability of stock of AD syringes and safety boxes enough for more than one year , the cash contribution of GAVI hadn’t yet been used. World Bank loan will be used in the next few years to cover the cost of AD syringes and safety boxes.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

It was submitted on 10 Feb 2005.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for Pentavalent  for each new vaccine.

| Table 2.1: Sources (planned) of financing of Pentavalent:) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 90% | 80% | 70% | 60% | 50% | 40% | 30% | 20% | 10% |
| B: Proportion funded by the Government and other sources (%) | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% |
| C: Total funding for Pentavalent | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

This figure was adopted according to the agreement with government of Yemen and to adjust it to be equal to 500% needs to be deeply reviewed  with Minister of Health and Minister of Finance and then to be shared with GAVI secretariat.

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 735,058 | 764785 | 792680 | 817,729 | 845,532 | 874,280 | 904,006 | 934,742 | 966,523 |
| Infants’ deaths | 55,477 | 57359 | 59451 | 61,330 | 63,415 | 65,571 | 67,800 | 70,106 | 72,489 |
| Surviving infants | 679,408 | 707426 | 733229 | 756,400 | 782,117 | 808,709 | 836,205 | 864,636 | 894,034 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 629162 | NR | NR | NR | NR | NR | NR | NR | NR |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 532856 | NR | NR | NR | NR | NR | NR | NR | NR |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Pentavalent > |  | 672,100 | 694,951 | 718,580 | 743,011 | 768,274 | 794,395 | 821,404 | 849,332 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose Pentavalent) |  | 530,606 | 548,646 | 605,120 | 625,694 | 687,403 | 710,774 | 778,173 | 804,630 |
| Wastage rate in 2004 and plan for 2005 beyond Pentavalent. |  | 10% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 145492 | 318,363 | 365,764 | 416,020 | 469,270 | 525,661 | 585,344 | 605,245 | 625,824 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 432927 | 565,979 | 658,375 | 718,580 | 743,011 | 768,274 | 794,395 | 821,404 | 849,332 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 515400 | 636,727 | 694,951 | 741,272 | 766,475 | 792,535 | 819,481 | 847,344 | 876,153 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

 The number of infants vaccinated in 2004 is more than the children to be vaccinated in 2005 because the target for  the 3rd dose of Pentavalent vaccine  is 75% , while  we could  attain 78% for DPT3 in 2004 due to supplementary immunization activities which has been conducted thank to availability of additional resources. Although of that we will try our best to attain coverage of Pentavalent (and DPT3) more than 75%.

 This figure is a little different from the last progress report because of some correction had been made at governorate level.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There is a little difference between this report and the last progress report in the denominator. The difference is due to adjustment at the governorates level

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of Pentavalent vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Since Pentavalent was introduced in mid March thin the vaccine recived for January – March 2005 will be the balance at the beginning of 2006.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - DPT3 - Dropout rate - Wastage rate for DPT - Safety injection (availability of safety injection equipments) | 75% 10% 20% 100% | 78% 15% 19% 100% | Lack of awareness | 75% 10% 10% 100% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~