Support to strengthen the involvement of civil society organisations in vaccination and other related health services

April 2009

# Form B presented by CCSS to the secretariat of GAVI Alliance for:

# the support of GAVI Alliance for civil society organisations in ten pilot countries

Please write directly in the boxes below which can be enlarged to accommodate the text  typed on the computer

Abbreviations and acronyms

Please ensure that all abbreviations and acronyms used in the form and in the enclosures are included in the following list.

| ABUBEF | : Burundi Association for Family Well-Being |
| --- | --- |
| ASC | : Community Health Agent |
| BDS | : District Health Office |
| BPS | : Provincial Health Office |
| CCC | : Communication for Change of Conduct |
| CCIA | : Interagency Coordination Committee |
| CDS | : Health Centre |
| CED – CARITAS BURUNDI | : Centre for Cooperation and Development – CARITAS BURUNDI |
| CCSS | : Health Sector Coordination Committee |
| CEPBU | : Community of Burundi Pentecostal Churches |
| CPSD | : Partnership Framework for Health and Development |
| CRB | : Burundi Red Cross |
| CV | : Vaccination cover |
| DGSP | : General Directorate of Public Health |
| EPS | : Health education |
| GAVI | : Global Alliance for Vaccines and Immunisations |
| GTT | : Technical working group |
| IEC | : Information Education Communication |
| MEFCD | : Ministry of Economics, Finance and Development Cooperation |
| MSP | : Ministry of Public Health |
| OMD | : Millennium Development Objectives |
| ONG | : Non-Government Organisation |
| OSC | : Civil Society Organisation |
| PCIME | : Integrated Management of Child Illnesses |
| PEV | : Extended Vaccination Programme |
| PNSR | : National Programme for Reproductive Health |
| PPAC | : Complete long-term plan |
| RSS | : Strengthening of the Health System |
| VAT | : Anti-tetanus vaccine |

NB: the Ministry of Public Health and the Fight against Aids has been renamed; it is now known as the Ministry of Public Health

Summary (one page)

Please provide a summary of the application for support. This should contain useful information on all technical working groups created to support the process, examine the files etc.

For the purpose of explaining this proposal for submission to GAVI Alliance concerning support for an OSC, a multi-sector technical working group was appointed by the Minister of Public Health. In addition to the managers of the MSP, it includes representatives of certain OSC working in the health sector, managers from the Ministry of Economics, Finance and Development Cooperation, managers of the Vice Ministry in charge of planning, a consultant responsible for the health sector in the second Vice Presidency of the Republic as well as the focal points of the international partner organisations.

The technical working group (GTT) is chaired by the General Director of Public Health and its duties are as follows:

- To broadly communicate the opportunities and the eligibility criteria of the OSC to make a submission proposal for financing to GAVI and to carry out selection

- To explain to the chosen OSC the instructions for filling out the proposal submission forms, to accompany their preparation of form C and to ensure the adaptation of their proposals to the PPAC and to the proposal for GAVI support for strengthening of the health system (RSS),

- To complete form B and submit the proposal to the CCIA for approval and sending of the submission.

This request is aimed at helping maintain and improve vaccination cover via the promotion of health, social mobilisation and strengthening the capicities of the community health agents and of the providers.

This project will be implemented by the following OSC:

- CED – CARITAS BURUNDI via its network of health structures including 63 CDS spread over the entire country, 6 hospitals, 2 maternity units and 7 prevention centres

- CEPBU with 29 CDS located in 10 health provinces and one hospital

- CRB via its network of volunteers in the 4 provinces with low vaccination coverage

- ABUBEF in its 7 fixed centres and two mobile clinics.

The project will last one year (2010) and has a budget of 461,520 USD.

Section 1: Application development process (one-two pages)

The aim of this section is to present the application development process concerning support from GAVI Alliance to the OSC. Begin with a description of the Health Sector Coordinating Committee (HSCC) or its equivalent, stating:

- the name of the HSCC (or its equivalent)

- the date on which the HSCC took up its duties

- the frequency of meetings

- the overall role and function of the HSCC

- the names of all OSC represented on the HSCC

The Health Sector Coordination Committee (CCSS) is known as Partnership Framework for Health and Development (CPSD). Chaired by the Ministry of Public Health with the representative of the partners from the health sector as its Vice Chairman (DFID representative in Burundi) and the General Directorate of Public Health and OMS as secretariat. The CPSD is made up of managers from different key ministries, international organisations a well as from local and international NGO involved in the health sector.

The CPSD officially took up its duties in March 2007 and meets on the last Friday in the month. Larger quarterly meetings are also organised.

The principal objective of the CPSD is to support the MSP in a concerted manner in the planning, implermentation, follow-up and evaluation of the national policies and strategies for sustainable health development.

The principal functions include:

- Developing/adpting a common vision for the development of the health sector and on necessary reforms in the sector

- Helping the government to analyse the situation in the health sector, proposing appropriate strategies to accelerate health development, achievement of the OMD and reductrion in poverty

- Argumentation at the highest level to enable the main health problems to be treated in an adequate manner in macroeconomic and sectorial politics by giving special importance to the efficient use of the sector’s resources

- Reflecting on possible modalities for effective inclusion of the health measures in Burundi within the framework of peace consolidation

- Supporting the installation of socio-health databases based on an appropriate group of indicators accepted by all parties concerned, and constituting the reference framework for monitoring and evaluating progress

- Creating operational technical groups if needed, in order to study specific subjects more intensively

- Ensuring an exchange of information so as to guarantee excellent communication between the various partners.

The CPSD is made up of the following local and international OSC: ABS, ABUBEF, CED CARITAS Burundi, CEPBU, CORDAID, BURUNDI RED CROSS, ECHO/CE, FHI-BURUNDI, GTZ, HEALTHNET/TPO, OAG, PATHFINDER INTERNATIONAL, PSI BURUNDI, RPB+, SWAA -BURUNDI.

Then describe the process followed by your country in preparation of the application, in particular information on the technical working group (if any such group has been created/used) and also covering the following points:

- Who coordinated and supervised preparation of the application for support?

- Who managed the drafting of the overall application? Was any technical assistance provided?

- Describe the process of presentation of the applications for support by the individual OSC.

- What mechanism was used for selecting the OSC with regard to possible support?

An inclusive process comprising representatives of the government and of the OSC working in vaccination and in the health system was followed for preparation of this submission. A technical working group has been appointed by the Ministry of Public Health. It is made up of representatives from various sectors. In addition to the MSP managers, it comprises representatives of the OSC selected (CEPBU, ABUBEF, CRB and CED CARITAS) and not selected (ABS and RENACODE) working in the health sector, managers from the Ministry of Economics, Finance and Development Cooperation, managers of the Deputy Minister in charge of planning, a consultant in the health sector for the second Vice Presidency of the Republic as well as focal points of international partner organisations.

The GTT manages the drafting of the overall application with no external technical assistance.

After discussion meetings between the GTT and the representatives of all the OSC responding, the latter compiled their respective proposals and defended them during a working meeting of the GTT organised for analysis and enrichment.

As regards the selection of the OSC, the GTT based its work on the directives of GAVI Alliance for support of OSC activities in the field of vaccination, in infant health care and in strengthening of the health system. These OSC must satisfy the following criteria:

- be competent and work in the sector concerned

- have been officially registered for at least three years

- practice transparent and democratic decision-making procedures

- keep satisfactory financial records (auditing of annual accounts)

- respect an OSC code of conduct accepted internationally.

Please describe the precise roles and responsibilities of the key partners involved in this process using the table below:

## Roles and responsibilities of the key partners (HSCC/GTT members and others)

| Title/position | Organisation | HSCC/GTT member? | Roles in the preparation of the application for support of GAVI Alliance to the OSC? |
| --- | --- | --- | --- |
| Vice President | DFID | CPSD | Validation |
| Secretariat | OMS | CPSD/GTT | Drafting/validation |
| Member | UNICEF | CPSD | Drafting/validation |
| Member | UNFPA | CPSD | Validation |
| Member | CTB | CPSD | Validation |
| Member | CED CARITAS BURUNDI | CPSD/GTT | Drafting/validation |
| Member | CORDAID | CPSD | Validation |
| Member | ECHO/CE | CPSD | Validation |
| Member | USAID/BURUNDI | CPSD | Validation |
| Member | RPB+ | CPSD | Validation |
| Member | ABS | CPSD/GTT | Drafting/validation |
| Member | JICA | CPSD | Drafting/validation |
| Member | BM | CPSD | Validation |
| Member | SWISS TROPICAL INSTITUTE | CPSD | Validation |
| Member | ONUSIDA | CPSD | Validation |
| Member | SWAA-BURUNDI | CPSD | Validation |
| Member | PSI BURUNDI | CPSD | Validation |
| Member | HEALTHNET/TPO | CPSD | Validation |
| Member | CRB | CPSD/GTT | Drafting/validation |
| Member | ABUBEF | CPSD/GTT | Drafting/validation |
| Member | CEPBU | CPSD/GTT | Validation |
| Member | FRENCH COOPERATION | CPSD | Validation |

Finally, if the HSCC (or the GTT) wishes to make any comment or recommendation concerning the application for support to the secretariat of GAVI Alliance and to the Independent Review Committee, it can do so below.

Comment of the GTT:

- The OSC have a large network of health structures and ASC spread over the entire country. They play an important role in the development of the health sector in general and in the field of vaccination in particular. They are in permanent and direct contact with the community. We strongly recommend favourable analysis of their proposals by the IRC.

- Given the magnitude, the composition of the CPSD and the time constraints for submission of the project, the CPSD will not be able to validate this document in the time available. It will be validated by the CCIA. Furthermore, most members of the CCIA are also members of the CPSD.

Section 2: Overview of the support of GAVI Alliance to the OSC (one – two pages)

The aim of this section is to describe the current and envisaged role of the OSC in the provision or strengthening of the health services, in particular vaccination, child health care and strengthening the health system.

The introduction of care structures in Burundi began with the Christian missions (CED CARITAS BURUNDI and CEPBU). Their number, quality and capacity increased over time. These structures represent approximately 25% of all health structures in the country. The CRB has been working in the health sector since 1963 and is represented in all communes of the country by approximately 50, 000 volunteers. For its part, ABUBEF was created in 1992. It plays a pioneering role in family planning and reproduction health and is represented in 6 provinces.

Their role is essentially the provision of vaccination services, infant health and strengthening the health system. CED CARITAS BURUNDI has a network of 78 care structures spread over the entire country including 6 hospitals, 63 CDS, 7 prevention centres, 2 maternity units. The CEPBU has 29 CDS and one district hospital. The structures of the two confessional organisations provide the same services as the public structures and are oriented towards government policy in health matters.

The CRB has a vast network of 50,000 volunteers and is represented in all communes of the country. It is involved above all in training the population, social mobilisation and creating awareness of mothers and child minders in terms of use of the vaccination and child health services.

ABUBEF is involved in maternity and infant health services; it has 6 fixed centres and one mobile clinic which vaccinate. It is also active in social mobilisation and education of mothers and child minders. (See maps in appendix 1).

In this submission, the role of these OSC is to assist the government vaccination and child health programme and to contact children where government structures are not accessible. They also play the role of mobilising the population in terms of use of the vaccination and other related health services. They likewise carry out lobbying of decision-makers and sponsors.

The overall objective of this proposal is to contribute to maintaining and increasing vaccination cover via promotion of health, social mobilisation and strengthening of the capacities of the community health agents and of the providers.

The specific objectives are:

By the end of 2010

- Achieving a level of vaccination coverage amongst children aged 0 to 11 months of 76.93 to 86.90 % for pentavalent 3 in the respective  areas of attraction of the OSC structures

- Achieving a level of vaccination cover of 69.8 to 80.5  % amongst women for VAT

- Achieving a level of vaccination cover of 1.63 to 16.66  % amongst women of child-bearing age for VAT

The OSC selected as potential recipients of support from GAVI Alliance are  ABUBEF, CED - CARITAS BURUNDI, CEPBU and CRB.

Start by explaining the current role of the OSC in the provision or strengthening of vaccination or child health services and in the health system. Then indicate the overall objectives of this application for support of GAVI Alliance to the OSC. Make sure that you choose SMART objectives (specific, measurable, acceptable, realistic and determined within the time available)

Then draw up a list of the OSC chosen as potential recipients of the support of GAVI Alliance to the OSC. In the table below, summarise the principal activities to be undertaken by each OSC during the support of GAVI Alliance and the results expected for each year.

## Principal activities and results for each OSC during the period of support by GAVI

| Name of OSC | Specific objectives | Principal activities | Expected results end 2010 |
| --- | --- | --- | --- |
| CRB | -increasing the level of community mobilisation in 4 provinces from 3% to 50%, i.e. from 12,412 to 228,033 of women of child-bearing age, in terms of vaccination of women (VAT) and children (BCG, VPO, PENTAVALENT and VAR) | Training 320 volunteers in community mobilisation and awareness in terms of vaccination of children and women of child-bearing age, and providing them with the corresponding working tools . | 320 volunteers/community health agents trained and provided with working tools |
|  |  | Organising the sessions to create awareness for vaccination amongst 228,033 women of child-bearing age. | 228,033 or 50 % of women of child-bearing age in the target provinces are aware of vaccination of women (VAT) and children (BCG, VPO, PENTAVALENT and VAR) |
|  | -reducing the number of children lost from sight in the 4 provinces from 10.26 to 4%, i.e. from 8,660 to 4,442 children. | Identification and referencing of 4,442 children lost from sight | 4,442 children lost from sight or 51.29% have been found again |
| CED CARITAS BURUNDI | Improving the quality of infant health care in 78 CDS spread over all provinces by strengthening the capacity of 156 providers in terms of the PCIME clinical approach, i.e. 46.27% and 156 ASC concerning the community PCIME, i.e. 20%. | Training/further training of the providers in interpersonal communication techniques | 156 providers trained/further trained in interpersonal communication techniques |
|  |  | Training of community health agents in communication techniques (CCC) and in the importance of vaccination for children aged 0 to 11 months and for women of child-bearing age. | 156 community health agents trained in communication techniques and in the importance of vaccination |
|  |  | Creating awareness amongst community leaders (religious, local government and school) for vaccination of children aged 0 to 11 months, women of child-bearing age and pregnant women. | 160 of the very highest community leaders have been trained. |
|  | Raising vaccination levels amongst children aged 0 to 11 months from -65.4 to 80%; for all vaccines in the FOSA of CARITAS | Vaccination of children aged 0 to 11 months with all antigens (BCG, VAR, Pentavalent3, VAP) i.e. 45,080 children with a coverage of 80%. | 45,080 children aged 0 to 11 months will be vaccinated. |
|  | Raising vaccination levels amongst pregnant women from 86.9 to 90 %, and amongst women of child-bearing age from 3.40 to 10% in the FOSA of CARITAS. | Vaccinating 30,463 women of child-bearing age with a coverage of 10 % and 61,784 pregnant women with a vaccination coverage of 90% of VAT. | - 30,463 women of child-bearing age will be vaccinated. - 61,784 pregnant women will be vaccinated. |
|  |  | Organising the EPS sessions on routine vaccination of children aged 0 to 11 months and on VAT for women of child-bearing age and girls at school. | 1 EPS session organised per week. |
| CEPBU | Improving the quality of infant health care in 29 health structures spread over 10 provinces by strengthening the capacity of 93 providers in terms of the PCIME clinical approach, i.e. 96% and 150 ASC concerning communication on changing habits in terms of vaccination and community PCIME i.e. 30%. | Training 93 providers of care (4 doctors and 89 nurses) in clinical PCIME | 93 providers of care or 96% will be trained in clinical PCIME |
|  |  | Training community leaders (religious, government, school and ASC) concerning communication on changing habits in terms of vaccination and community PCIME. | 150 community leaders will be trained concerning communication on changing habits in terms of vaccination and community PCIME. |
|  | Raising vaccination levels in 10 provinces amongst children aged 0 to 11 months from 84.4 to 90%; for all vaccines in the FOSA of CEPBU | Vaccination of 8,920 children aged 0 to 11 months with the antigens targeted by PEV BCG, VAP, Pentavalent and VAR). | 8,920 children aged 0 to 11 months or 90% will be fully vaccinated. |
|  | Raising vaccination levels amongst protected pregnant women (VAT 2 to 5 + fully vaccinated) from 61.0 to 80 %, and amongst women of child-bearing age from 1.3 to 20% in the FOSA of CEPBU. | Vaccinating 9,660 pregnant women and 10,716 women of child-bearing age with the antigen VAT. | 9,660 pregnant women or 80%, and 10,716 women of child-bearing age, i.e. 20%, will be fully vaccinated |
| ABUBEF | Increasing vaccination cover for PENTAVALENT 3 in 6 provinces from 80.7% to 90.7% of children aged 0 to 11 months in the catchment area of the ABUBEF centres and mobile clinics | - Training/further training of 40 providers in routine and mass vaccination - Vaccinating 12,374 children aged 0 - 11 months. | 12,374 children aged 0 to 11 months will be vaccinated. |
|  | Increasing vaccination cover for VAT in the 6 provinces from 61.5% to 71.5% of all pregnant women, and vaccination cover for VAT amongst woman of child-bearing age from 0.2% to 20% in the catchment area of the ABUBEF service centres. | - Training 80 ASC in the importance of vaccination and PEV innovations. - Vaccinating 10,778 pregnant women and 13,378 women of child-bearing age. | 10,778 pregnant women protected against VAT 13,378 women of child-bearing age will be vaccinated against VAT |

Finally, indicate how you intend to implement the programme from a technical and financial point of view, when the GAVI resources will end (if applicable) and stating the source and level of potential financing.

Following completion of the project, the OSC providers of FOSA will have been trained in vaccination techniques, in the PCIME approach and in CCC techniques, and will continue the awareness, social mobilisation and vaccination activities in order to ensure perpetuation of the project oprations using the knowledge acquired. In addition, argumentation work with respect to our traditional and new partners will continue in order to close any gaps. The involvement of the community leaders and the volunbtary work will also constitute the other method of perpetuating these activities. Furthermore, the moptivation of the health personnel and of the ASC based on performance is a government strategy which is currently being extended to all structures within the country and represents another possible source of finance.

Section 3: Programme implementation plan (one - two pages)

Please prepare and present an overall programme implementation plan for the entire duration of the support to the OSC, based on the individual programme implementation plans received in the requests from the OSC. You must determine the most appropriate framework for your plan and ensure that it includes the following information:

- Introduction: justification and recapitulation of the expected results, objectives and reference points

- Specific activities for implementation of the project and implementation schedule

- Organisation and management of the project

- Overall strategy for achieving the results

- How the project will support the PPAC and/or a proposal for support of GAVI for RSS

- How the project will be coordinated with other activities and the role of the key players

Since 2002, progressive improvement of the vaccination cover has been observed for all antigens. Nevertheless, disparities remain between the health districts which are essentially due to the insufficient numbers of providers and the low community involvement. In line with the aim of maintaining the good results and increasing vaccination cover in the health districts that are lagging behind, the OSC undertake to support the MSP in order to achieve the objectives of the PPAC by:

- Vaccination cover equivalent to 90% for the pentavalent on the level of health training of the beneficiary OSC of this project for children aged 0 to 11 months

- VAT cover equivalent to 60% for all pregnant women

- Vaccination cover equivalent to 17% for all women of child-bearing age between now and the end of 2010.

The OSC also undertake to strengthen the capacities as well as the mechanisms for information and awareness creation in the community as a whole, with community leaders (religious, government, school) and of the ASC, in particular concerning CCC for vaccination and child health.

The implementation of the project will make it possible to vaccinate 66,374 children aged between 0 and 11 months, 82,222 pregnant women and 54,557 women of child-bearing age and the entire population of the regions covered by the project.

In 2008 :

- 55,204 children aged 0 – 11 received pentavalent 3 ;

- 76,328 pregnant women and 11,301 women of child-bearing age were vaccinated.

To achieve the results stated above, implementation of this project will be based on three strategic axes: intensification of vaccination and child health activities, CCC and improving working conditions. In addition, new activities will be initiated, namely: creation of awareness amongst community leaders (for CED CARITAS and CEPBU), identification and referencing of those lost from sight (for the CRB), just to mention these.

In difficult access zones, the various OSC will adopt advanced strategies. Mobile strategies for administering VAT to girls of child-bearing age will be organised in secondary schools.  Trained community leaders and the media will support the mobilisation of the various target groups for vaccination.

The legal representative of each OSC retained is the legal guarantor and backs up all project activities. The health coordinator is the person responsible for execution and daily monitoring of the project. Under the responsibility of the project coordinator, supervisors from the central level will ensure quarterly training supervision within all the FOSA. On an intermediary level, health coordinators will be entrusted with monitoring activities in collaboration with the BDS, the BPS and their respective national levels. On the level of the peripheral and community structures, those responsible are entrusted with implementation of the project.

As far as project management is concerned, it will follow the procedures in place within the OSC. The funds will be deposited in a GAVI-RSS account, then transferred on a half-yearly basis to the respective accounts of the OSC. Upon presentation of a plan of action approved by a follow-up committee for follow-up of GAVI Alliance support to the OSC, the first instalment will be paid. As regards the 2nd and final instalment, payment will be conditional on presentation and approval of the financial report.

The OSC will strengthen their support for the MSPLS in achievement of the objectives of the PPAC and RSS  via vaccination and child health activities as well as strengthening of the health system. They will also add new impetus to the CCC and social mobilisation in all provinces. Furthermore, the project will strengthen coordination and follow-up – evaluation in the implementation of these activities.

As regards implementation, planning and follow-up of the activities are ensured quarterly by the internal coordination of each OSC and a follow-up report will be produced. In addition, half-yearly coordination meetings are organised by each OSC.

On the intermediary level, quarterly meetings will be organised by the BPS and BDS with the various OSC.

At national level, half-yearly coordination meetings will be organised by the CCIA to coordinate all work as well as use of the funds within the framework of the project.

The technical services of MSPLS, such as the PEV, the PNSR, RSS – GAVI, PCIME, …. , will provide the OSC with the necessary IEC and didactic tools.

Section 4: Follow-up and evaluation (one page)

The aim of this section is to present the indicators that will be used to monitor results during the course of the GAVI Alliance support of the OSC. The indicators included here must be based on the indicators provided in the requests of the OSC, which must reflect the indicators used in the PPAC and/or the proposal for support of GAVI for RSS. Please include the relevant information in the table below.

## Indicators to be used for monitoring results

| Indicator | Reference estimation | Source of facts (if applicable) | Date of reference estimation | Objective | Intermediate objective | Date for objective |
| --- | --- | --- | --- | --- | --- | --- |
| % of volunteers/community health agents trained and provided with working tools | 29% | CRB Annual Report 2008 | 2008 | 71% |  | Beginning of April |
| % of women of child-bearing age made aware of female vaccination (VAT) and child vaccination (BCG,VPO,PENTAVALENT and VAR) in the target provinces | 3% | CRB Annual Report 2008 | 2008 | 100% | 30% (End of June) | Beginning of April |
| % of children lost from sight have been found again | 260 | CRB Annual Report 2008 | 2008 | 100% | 30% (End of June) | End of project |
| % supervision | 2 | CRB annual situation report | 2008 |  | 30 % supervision |  |
| % supervision | 0 |  |  |  | -100% (supervision every 3 months by CDS) - 100% (2) coordination/planning meetings per annum - 100% (one evaluation at the end of the project). |  |
| % of providers trained/further trained in clinical PCIME | 0 |  | 2008 | 46,27% 1st half-year | 1st half-year 2010 | 46.27% End of project |
| % of ASC, religious, local government and school leaders made aware of community PCIME | 0 |  | 2008 | 20% 1st half-year | 1st half-year 2010 | 20% End of project |
| % of community leaders (religious, local government and school) will be made aware or 160 out of 390 leaders | 0 |  | 2008 | 40 % 1st half-year | 1st quarter 2010 | 100% End of project |
| % of children aged 0 to 11 months vaccinated with all antigens | 65,4% | Annual Report of CED CARITAS | 2008 | 40% 1st half-year | End of project | 80% End of project |
| % of women of child-bearing age and % of pregnant women vaccinated | 3,4% 86 ,9% | Annual Report of CED CARITAS Annual Report of CED CARITAS | 2008 2008 | 5% 1st half-year 45 % 1st half-year | End of project End of project | 10% End of project 90% End of project |
| % of CDS organising an EPS session once per week on vaccination | 80% | Annual Report of CED CARITAS | 2008 | 45 % 1st half-year | End of project | 100% End of project |
| % of CDS and hospitals supervised quarterly | 50% | Annual Report of CED CARITAS | 2008 | 50 % 1st half-year | End of project | 100% End of project |
| % of providers trained in clinical PCIME | 3 | Annual Report of PCIME | 2008 | 96% End of project | 96% 1st half-year | April 2010 |
| % of community leaders (religious, government, school and ASC) trained concerning communication on changing habits in terms of vaccination and community PCIME. | ND |  | 2008 | 150 community leaders (religious, government, school and ASC | 150 community leaders (religious, government, school and ASC) | April 2010 |
| % of children aged 0 to 11 months will be vaccinated with the antigens targeted by PEV BCG, VAP, Pentavalent). | 8.367 children aged 0 - 11 months have been vaccinated | Annual Report of PEV | 2008 | 90% End of project | 40% 1st half-year | End of project |
| % of pregnant women % of women of child-bearing age will be vaccinated against VAT | 7.367 pregnant women vaccinated 707 women of child-bearing age have been vaccinated | Annual Report of PEV Annual Report of PEV | 2008 2008 | 80% End of project 20% End of project | 4% 1st half-year 5 % 1st half-year | End of project End of project |
| % of CDS and hospitals supervised quarterly | 50% | CEPBU annual situation report | 2008 | 100% End of project | 50 % 1st half-year | End of project |
| % of clinic providers trained/further trained | 11% | ABUBEF Annual Report | 2008 | 89% |  | March 2010 |
| % of ASC identified trained | 50% | ABUBEF Annual Report | 2008 | 50% |  | March 2010 |
| % of children aged 0 to 11 months will have received DTC 3 | 80,7% | ABUBEF Annual Report | 2008 | 90,7% | 40% (end of June) | End of project |
| % of pregnant women will have received VAT 2 and % of women of child-bearing age will have received VAT 2 | 61,5% 0,2% | ABUBEF Annual Report ABUBEF Annual Report | 2008 2008 | 71,5% 20% | 30% (end of June) | End of project End of project |
| % of ASC supervised monthly | 0% | ABUBEF Annual Report | 20O8 | 100% | 50% (end of June) | End of project |
| % of ABUBEF centres supervised quarterly | 80% | ABUBEF Annual Report | 2008 | 100% | 50% (end of June) | End of project |
| Number of evaluation meetings held | 0 | Evaluation report on project activities | 2008 | 1 |  | End of project |

1 If the reference facts are not available, please indicate if collection of reference facts is envisaged and by what date.

NB : with certain indicators, exact specification of the denominator is difficult.

Finally, provide detailed information on the mechanisms to be used in monitoring these indicators, including the role of the recipients in monitoring the progress of activities if applicable.

Those responsible for the structures of the OSC will produce monthly reports for the BDS/BPS and the health coordinators of the respective OSC. For their part, the health coordinators will organise coordination and follow-up meetings with those responsible for their structures. The legal representatives of the OSC will forward quarterly activity reports to the Director General of Public Health. A follow-up committee, made up of members of the OSC and the MSP, will organise evaluation meetings and on-site visits to monitor the progress of activities.

Section 5 : Implementation arrangements (one - two pages)

In this section, you should describe the methods for managing the support of GAVI Alliance to the OSC. The following information should be provided:

- Name of the organisation responsible for management of the programme implementation

- Name of the organisation responsible for coordination, follow-up and quality control

- Role of the HSCC (or its equivalent) in implementation

- Mechanism for coordinating the support of GAVI Alliance to the OSC

Under the supervision of the DGSP, management of the project implementation will be carried out by the management unit of the RSS – GAVI.

Coordination, follow-up and quality control will be carried out by the follow-up committee chaired by the Director General of Public Health and made up of:

- The representatives of the OSC

- The representatives of the partners

- The representative of the second Vice President

- The representative of the MEFCD,

- The MSP managers responsible for general health inspection, vaccination, child health and the RSS.

The follow-up committee will receive half-yearly reports from the OSC on activities and the use of the support funds for analysis and validation with a view to enabling payment of the 2nd instalment and/or closure of the project.

Then use the table below to describe the precise roles and responsibilities of the key implementation partners.

## Roles and responsibilities of the key partners (HSCC/GTT members and others)

| Title/position | Organisation | HSCC/GTT member? | Roles in the implementation of the application for support of GAVI Alliance to the OSC |
| --- | --- | --- | --- |
| Vice President | DFID | CPSD | Guarantor |
| Secretariat | OMS | CPSD/GTT | Follow-up/guarantor |
| Member | UNICEF | CPSD | Follow-up/guarantor |
| Member | UNFPA | CPSD | Guarantor |
| Member | CED CARITAS BURUNDI | CPSD/GTT | Execution/follow-up |
| Member | ABS | CPSD/GTT | Follow-up |
| Member | CRB | CPSD/GTT | Execution/follow-up |
| Member | ABUBEF | CPSD/GTT | Execution/follow-up |
| Member | CEPBU | CPSD/GTT | Execution/follow-up |

Also describe the financial management arrangements for the support of GAVI Alliance to the OSC.

- Mechanism for channelling the funds provided to the OSC by GAVI Alliance in the country

- Mechanism (and responsibility) for budget use and approval

- Expected duration of the budget approval and transfer process

- Mechanism for disbursement of funds provided by GAVI Alliance to the OSC

- Auditing procedures (and details of auditors, if known)

- Justification of management fees (if applicable)

Finally, please describe the arrangements for reporting on the progress in implementing and using the funds provided by GAVI Alliance to the OSC, including the body responsible for preparing the annual situation reports.

- The GAVI Alliance funds for supporting the OSC will be transferred to the GAVI – RSS account in the country at the Banque de la République du Burundi. They will then be transferred on  a half-yearly basis to the accounts of the respective OSC upon presentation of a plan of action for the first instalment. Payment of the 2nd instalment will depend on reception and approval of a financial report by the follow-up committee.

- Use of the budget must be in strict adherence to the plan of action of each OSC. The legal representative of each OSC is responsible for efficient use of the GAVI Alliance support. Approval of the use of the funds by the OSC will be by the follow-up committee.

- The application for funds by an OSC will be examined and settled within a maximum period of two weeks.

- Following approval of the application for transfer of funds to the OSC by the Ministry of Public Health, the Director of Public Accounts at the Ministry of Finance and the coordinator of the RSS-GAVI management unit will sign the order for payment of the funds jointly. The Director General of Resources at the MSP will be the co-signatory as deputy for the RSS-GAVI coordinator.

- The internal audit will be carried out by the internal services of the OSC. As regards the external audit, each OSC will hire a specialist company.

- The members of the follow-up committee will be paid a fee for meetings and on-site visits.

The legal representatives of the OSC will send annual technical and financial reports to the Director General of Public Health. The follow-up committee will analyse these and submit them to the CPSD for validation.

Together with the OSC concerned by the project, the RSS-GAVI management unit will prepare the annual situation report, which will be forwarded to the follow-up committee following analysis.

Section 6: Costs and financing of the support of GAVI Alliance to the OSC (one page)

The aim of this section is to confirm the total amount of GAVI Alliance funds available for the OSC, and to calculate the annual costs of all activities proposed. You are advised to ensure that the costs do not exceed the total funds available.

The amount of GAVI Alliance funds available for the OSC is shown in table 2 of chapter 4 of the GAVI Alliance Guidelines on Support to the OSC. Please indicate this total at the beginning of this section.

Then, please prepare a budget based on the costs of all activities (of the OSC) for the period of the GAVI Alliance support. Add or delete lines in the table below to arrive at the exact number of activities for each OSC. Ensure that the total costs of managing the support (from the perspective of the HSCC or GGT as well as the OSC) are included together with the costs of audit.

The total amount allocated to the Burundi OSC  by GAVI Alliance is USD 461,520.

Please convert all costs in the OSC applications into $US (at the current exchange rate).

## Implementation costs for support of GAVI Alliance to the OSC

| Support of activities (for each OSC) | Annual costs in $US (‘000) |  |  | TOTAL COSTS |
| --- | --- | --- | --- | --- |
|  | 2008 | 2009 | 2010 |  |
| ABUBEF |  |  |  | 65 747 |
| - Training of 80 ASC in community mobilisation and awareness |  |  | 5 417 | 5 417 |
| - Training of 40 providers in vaccination and CCC techniques |  |  | 3 866 | 3 866 |
| - Vaccination of children aged 0 – 11 months, of pregnant women and of women of child-bearing age. |  |  | 40 425 | 40 425 |
| - Coordination, follow-up, evaluation and supervision of the activities of the providers and of the ASC. |  |  | 16 039 | 16 039 |
| CRB |  |  |  | 71 138 |
| - Training of 320 volunteers in community mobilisation and awareness |  |  | 12 942 | 12 942 |
| 2. Identification and referencing of: - Children not contacted and those lost from sight - Women of child-bearing age - pregnant women |  |  | 10 252 | 10 252 |
| 3. Creating awareness amongst mothers and child minders in terms of vaccination. |  |  | 37 910 | 37 910 |
| - Coordination, follow-up and evaluation of the project |  |  | 10 034 | 10 034 |
| CEPBU |  |  |  | 111 349 |
| - Training/further training of the providers in vaccination and CCC techniques |  |  | 21 073 | 21 073 |
| - Training of religious, government, school and ASC leaders in CCC techniques for vaccination and child health |  |  | 16 441 | 16 441 |
| - Daily vaccination of children aged 0 – 11 months, of pregnant women and of women of child-bearing age. |  |  | 55 243 | 55 243 |
| - Coordination and follow-up - evaluation |  |  | 18 592 | 18 592 |
| CED CARITAS BURUNDI |  |  |  | 150 730 |
| - Training/further training of the providers and of ASC in vaccination, PCIME, interpersonal communication techniques and CCC |  |  | 34 671 | 34 671 |
| - Creating awareness amongst religious, local government and school leaders for vaccination of children aged 0 to 11 months and for VAT of women of child-bearing age and of pregnant women. |  |  | 19 680 | 19 680 |
| - Vaccination of children aged 0 – 11 months, of pregnant women and of women of child-bearing age. |  |  | 45 347 | 45 347 |
| - Organising EPS sessions on routine vaccination of children aged 0 to 11 months, and on VAT for women of child-bearing age and girls at school. |  |  | 18 006 | 18 006 |
| - Coordination, supervision and follow-up - evaluation |  |  | 33 026 | 33 026 |
| Management costs (of all OSC) |  |  | 27 447 | 27 447 |
| Management costs (of HSCC/GTT) |  |  | 23 143 | 23 143 |
| Costs of financial audits (of all OSC) |  |  | 11 966 | 11 966 |
| TOTAL COSTS |  |  | 461 520 | 461 520 |

NB. The unit costs of the various activities are shown in the appendices

Section 7 : Approval of the application for support

Representatives of the Health Sector Coordination Committee (HSCC), or its equivalent, must approve the application and the Chairman of the HSCC must sign the application on their behalf All members of the HSCC (or its equivalent) must sign the minutes of the meeting at which the application for GAVI Alliance support to the OSC has been approved. The  minutes must be enclosed with the application for support.

The signature of the members of the HSCC shall apply as approval of the information and projects presented in this application, and as support for the implementation of these projects. Signature does not imply any financial or legal involvement by the partner institution or by the individual.

The Partner Dialogue Framework for Health and Development  (CPSD) representing the members of the government and partners, undertakes to provide its support to the civil society organisations in this application for implementation of the strategy. The CPSD also certifies that the OSC are organisations of good faith with the management expertise and capacity to enable them to perform the work described well.

The CPSD/CCIA requires that the GAVI Alliance funding partners provide financial assistance to support OSC that can contribute to the implementation of the GAVI RSS proposal and/or the PPAC as outlined in this application.

- Chairman of the CPSD: name, position, organisation, date, signature

| Name and first name | Position | Organisation | Date | Signature |
| --- | --- | --- | --- | --- |
| Dr GIKORO Emmanuel | Minister | Ministry of Public Health | 29/04/09 |  |

The members of the Health Sector Coordination Committee (or its equivalent) have approved this application at a meeting held on 10/09//08; the signed minutes are enclosed.”

This section must also include the name and contact details of the person to be contacted by the secretariat of GAVI Alliance for any information required. Please provide the following information:

- Contact person: Name, function, organisation, telephone no., fax no., address, e-mail.

| Name and first name | Position | Organisation | Address |
| --- | --- | --- | --- |
| Dr BIRINTANYA Norbert | Director General of Public Health | Ministry of Public Health | Tél : +257 22 22 51 67 Fax : +257 22 24 25 42 P.O Box : 1820 Bujumbura E- Mail : birintanya@yahoo.fr |

APPENDIX Documents submitted in support of the application for support for OSC by GAVI

Please enclose the following documents (if possible in electronic corm) with this application. Please number all documents submitted with the application for support and list them in the table below.

| Document (with equivalent customary name in the respective country) | Available (yes/no) | Duration | Enclosure no. |
| --- | --- | --- | --- |
| Last annual report and audit report of the OSC | OK |  |  |
| Registration document | OK |  |  |
| Status of OSC | OK |  |  |
| Strategic plan (if available) | OK |  |  |
| Reports on similar projects recently completed (if applicable) | OK |  |  |
| Reports on all external evaluations of the OSC (if applicable) | OK |  |  |
| Bank form | OK |  |  |

# CLARIFICATIONS SENT AFTER THE REVIEW to the GAVI Secretariat:

| Soutien des activités (pour chaque OSC) | Coût par an en $US (,000) |  |  | COÛTS TOTAUX |
| --- | --- | --- | --- | --- |
|  | 2008 | 2009 | 2010 |  |
| ABUBEF |  |  |  | 65 747 |
| - Formation de 80 ASC sur la mobilisation et sensibilisation communautaire |  |  | 5 417 | 5 417 |
| - Formation de 40 prestataires sur la vaccination et les techniques de CCC |  |  | 3 866 | 3 866 |
| - Vaccination des enfants de 0 – 11 mois, des femmes enceintes, et des femmes en âge de procréer. |  |  | 40 425 | 40 425 |
| - Coordination, suivi évaluation et supervision des activités des prestataires et des ASC. |  |  | 16 039 | 16 039 |
| CRB |  |  |  | 71 138 |
| - Formation de 320 volontaires sur la mobilisation et la sensibilisation communautaire |  |  | 12 942 | 12 942 |
| 2. Identification et référence de : - Enfants non atteints et les perdus de vue ; - femmes en âge de procréer ; - femmes enceintes. |  |  | 10 252 | 10 252 |
| 3. Sensibilisation des mères et des gardiens d’enfants à la vaccination. |  |  | 37 910 | 37 910 |
| - Coordination, suivi et évaluation du projet |  |  | 10 034 | 10 034 |
| CEPBU |  |  |  | 111 349 |
| - Formation/recyclage des prestataires sur la vaccination et les techniques de CCC |  |  | 21 073 | 21 073 |
| - Formation des responsables religieux, administratifs, scolaires et ASC sur les techniques de CCC en faveur vaccination et de la santé infantile. |  |  | 16 441 | 16 441 |
| - Vaccination journalière des enfants de 0 à 11 mois, des femmes enceintes et des femmes en âge de procréer. |  |  | 55 243 | 55 243 |
| - Coordination et Suivi - évaluation |  |  | 18 592 | 18 592 |
| CED CARITAS BURUNDI |  |  |  | 150 730 |
| - Formation/recyclage des prestataires et les ASC sur la vaccination, PCIME, les techniques de communication interpersonnelle et la CCC. |  |  | 34 671 | 34 671 |
| - Sensibilisation des leaders religieux, l’administration locale et scolaires sur la vaccination des enfants de 0 à 11mois et la VAT des femmes en âge de procréer et des femmes enceintes |  |  | 19 680 | 19 680 |
| - Vaccination des enfants de 0 à 11 mois, des femmes en âge de procréer et des femmes enceintes |  |  | 45 347 | 45 347 |
| - Organisation des séances d’EPS sur vaccination de routine des enfants de 0 à 11mois et la VAT des femmes en âge de procréer et des filles dans les écoles |  |  | 18 006 | 18 006 |
| - Coordination, supervision et suivi - évaluation |  |  | 33 026 | 33 026 |
| Frais de gestion (de toutes les OSC) |  |  | 27 447 | 27 447 |
| Frais de gestion (du CCSS/GTT) |  |  | 23 143 | 23 143 |
| 1. Coordination |  |  | 1 000 | 1 000 |
| 2. Suivi évaluation |  |  | 15 000 | 15 000 |
| 3. Fonctionnement |  |  | 7 143 | 7 143 |
| Coûts des audits financiers (de toutes les OSC) |  |  | 11 966 | 11 966 |
| COÛTS TOTAUX |  |  | 461 520 | 461 520 |