## Annual Disbursement Figures
Lead Implementers | Budget for Year 1 | Budget for Year 2 | Budget for Year 3 | Total
UNDP | 5.6656 | 18.5474 | 15.7855 | 39.9985
UNICEF | 13.9764 | 13.6305 | 12.3937 | 40.0006
WHO | 7.6445 | 8.9161 | 10.4387 | 26.9993
Total | 27.2865 | 41.094 | 38.6179 | 106.9984

## Consolidated Budget
NAME OF PARTNERS : WHO, UNICEF, UNDP
Project Title: GAVI HSS
Duration: 2013-2015
Year 1
|  |  | Funds In US $ Millions |  |  |  | FUNDS ( In US $ Millions)
Activity | Description | Agency | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | YR 1 | YR 2 | YR 3 | Total
Objective 1 | Strengthen vaccine logistics and cold chain management in poor performing states through public-private partnerships and through improved human resources capacity, institutional strengthening and supporting supervision
1.1 | Implement Public-Private Partnership Models of Vaccine Logistics and Cold Chain Management | UNDP | 0 | 0.062963 | 0.15378 | 0.38781 | 0.60456 | 4.6496 | 4.9452 | 10.1993
1.2 | Improve Human Resources to improve cold chain performance | UNICEF | 0.072222 | 0.072222 | 0.072222 | 0.3114 | 0.52806 | 1.6292 | 0.40788 | 2.5652
1.3 | Supportive Supervision to ensure quality implementation | UNICEF | 0.14133 | 0.14133 | 0.21675 | 0.29217 | 0.79158 | 1.2799 | 1.5477 | 3.6193
1.4 | Implement EVM improvement plans | UNICEF | 0 | 0 | 0.18359 | 0.25857 | 0.44217 | 1.2728 | 1.8171 | 3.532
1.5 | Institutional Capacity building to strengthen the cold chain system | UNICEF | 0 | 0 | 0.2 | 3.0059 | 3.2059 | 0.23889 | 0.24444 | 3.6893
| Sub- Total |  | 0.21356 | 0.27652 | 0.82634 | 4.2559 | 5.5723 | 9.0704 | 8.9623 | 23.605
Objective 2 | Design and implement an eVIN that will enable real time information on cold chain temperatures and vaccine stocks and flows
2.1 | Scale up a system for SMS-enabled real time MIS for cold chain and VLM | UNDP | 0.11852 | 0.19583 | 0.42593 | 0.10509 | 0.84537 | 5.0614 | 2.8322 | 8.739
2.2 | Human Resource and capacity buidling for vaccine intelligence | UNDP | 0.0018519 | 0.05588 | 0.90278 | 0.20237 | 1.1629 | 3.6085 | 3.7211 | 8.4925
| Sub- Total |  | 0.12037 | 0.25171 | 1.3287 | 0.30746 | 2.0082 | 8.6699 | 6.5534 | 17.2315
Objective 3 | Increase demand for RI through a national BCC strategy
3.1 | Implement Multi pronged national BCC strategy development and operational plans | UNICEF | 0 | 0 | 0.31081 | 0.38852 | 0.69933 | 0.45741 | 0.67963 | 1.8364
3.2 | Enhance Infrastructure and HR Capacity to develop and implement BCC strategies | UNICEF | 0.69444 | 0.72754 | 0.9462 | 0.89444 | 3.2626 | 3.5713 | 3.5172 | 10.3512
3.3 | Develop and Broadcast immunisation messages through mass media | UNICEF | 0 | 0.58767 | 0.68476 | 0.67656 | 1.949 | 1.9027 | 1.763 | 5.6147
3.4 | Promote advocacy with media for creating an enabling environment for increasing demand for RI services | UNICEF | 0 | 0.307 | 0.35772 | 0.48222 | 1.1469 | 1.1825 | 0.16137 | 2.4908
3.5 | Monitoring and Evaluation | UNDP | 0.0022222 | 0.0022222 | 0.0040741 | 0.12444 | 0.13296 | 0.13852 | 0.13481 | 0.4063
| Sub- Total |  | 0.69667 | 1.6244 | 2.3036 | 2.5662 | 7.1909 | 7.2524 | 6.256 | 20.6993
Objective 4 | Strengthen the evidence base for improved policy-making (at all levels) on programmatic areas like procurement and vaccine delivery and on sequencing and adoption of new antigens
4.1 | Build the capacity of existing institutions at the national, state, district, and block levels in generating and interpreting evidence through measles and other VPD surveillance for improved policy-making | WHO | 0.26876 | 0.19394 | 0.22084 | 0.15876 | 0.84229 | 0.87352 | 0.96727 | 2.6831
4.2 | Expand Model based strategy development approaches to support policy decisions in seven additional states | UNDP | 0.0037037 | 0.64815 | 0.089037 | 0.089037 | 0.82993 | 0.35615 | 0.35615 | 1.5422
4.3 | Support Eveidence generation to assess the case of new antigens based on system readiness, avertable burden, programme costs and cost effectiveness | UNDP | 0 | 0.051111 | 0.73278 | 0.074259 | 0.85815 | 2.0809 | 1.4377 | 4.3767
| Sub- Total |  | 0.27246 | 0.8932 | 1.0427 | 0.32205 | 2.5304 | 3.3106 | 2.7611 | 8.602
Objective 5 | Leverage the success of the National Polio Surveillance Project to strengthen RI service delivery in 8 priority states
5 | Human resources at national and state level (both technical and support staff) | WHO | 0.65315 | 0.65315 | 0.65315 | 0.65315 | 2.6126 | 3.4723 | 4.4777 | 10.5626
5.2 | Intensified RI Monitoring | WHO | 0.46402 | 0.46402 | 0.46402 | 0.46402 | 1.8561 | 2.0417 | 2.2459 | 6.1436
5.3 | AFP surveillance, UIP reviews, Evaluations | WHO | 0 | 0 | 0.024889 | 0 | 0.024889 | 0.027378 | 0.027606 | 0.079873
5.4 | SDA Facility management and organization | WHO | 0.10694 | 0.10694 | 0.10694 | 0.10694 | 0.42775 | 0.44914 | 0.47159 | 1.3485
5.5 | Build capacity of frontline workers at state and district levels in high priority states | WHO | 0 | 0.44038 | 0 | 0.44038 | 0.88076 | 0.96883 | 1.0657 | 2.9153
| Sub- Total |  | 1.2241 | 1.6645 | 1.249 | 1.6645 | 5.8021 | 6.9593 | 8.2885 | 21.0499
Programme Management
| National M&E plan | UNDP/WHO/UNICEF | 0.375 | 0.375 | 0.375 | 0.375 | 1.5 | 1.5 | 1.5 | 4.5
| Secretarial Support to the Ministry | UNDP | 0.0275 | 0.0275 | 0.0275 | 0.0275 | 0.10899 | 0.11352 | 0.1231 | 0.34561
| Technical Assistance (UNDP @ 5 %) |  | 0.063035 | 0.063035 | 0.063035 | 0.063035 | 0.25214 | 0.82543 | 0.70251 | 1.7801
| Technical Assistance (Health specialists in 9 States and Delhi) @5% of total cost |  | 0.1512 | 0.1512 | 0.1512 | 0.1512 | 0.6048 | 0.66528 | 0.73181 | 2.0019
| Grant Management Services (UNDP @ 7% ) | UNDP | 0.092662 | 0.092662 | 0.092662 | 0.092662 | 0.37065 | 1.2134 | 1.0327 | 2.6167
| Recovery Cost (UNICEF @ 7%) | UNICEF | 0 | 0 | 0 | 0 | 0.84592 | 0.93051 | 1.0236 | 2.8
| Programme Support Cost (WHO @ 7%) | WHO | 0.12503 | 0.12503 | 0.12503 | 0.12503 | 0.50011 | 0.5833 | 0.6829 | 1.7663
| Sub- Total |  | 0.83442 | 0.83442 | 0.83442 | 0.83442 | 4.1826 | 5.8314 | 5.7966 | 15.8106
| Grand Total |  | 3.3616 | 5.5448 | 7.5847 | 9.9505 | 27.2865 | 41.094 | 38.6179 | 106.9984

## UNDP
NAME OF PARTNER: UNDP
Project Title: GAVI HSS
Duration: 2013-2015
Year 1
|  | Funds In US $ Millions |  |  |  | FUNDS ( In US $ Millions)
Activity | Description | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | YR 1 | YR 2 | YR 3 | Total
1.1 | Implement Public-Private Partnership Models of Vaccine Logistics and Cold Chain Management
| Design a business model in detail with exact roles and responsibilities defined for outsourced agency and government officials | 0 | 0.059259 | 0.11852 | 0.11852 | 0.2963 | 0 | 0 | 0.2963
| Pilot the model in 10 low performing districts | 0 | 0.0037037 | 0.035259 | 0.26652 | 0.30548 | 4.5718 | 4.8081 | 9.6854
| Establish benchmarks for vaccine inventory management | 0 | 0 | 0 | 0.0027778 | 0.0027778 | 0.077778 | 0.13704 | 0.21759
| Sub Total | 0 | 0.062963 | 0.15378 | 0.38781 | 0.60456 | 4.6496 | 4.9452 | 10.1993
2.1 | Scale up a system for SMS-enabled real time MIS for cold chain and VLM
| Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh | 0.025926 | 0.038426 | 0.18519 | 0.077315 | 0.32685 | 1.8188 | 1.2731 | 3.4188
| Develop & install monitoring systems at all levels (UP & Bihar) to monitor real time vaccine stock situations, status of equipment and other transactions | 0.092593 | 0.15741 | 0.24074 | 0.027778 | 0.51852 | 3.2426 | 1.5591 | 5.3202
| Sub Total | 0.11852 | 0.19583 | 0.42593 | 0.10509 | 0.84537 | 5.0614 | 2.8322 | 8.739
2.2 | Human Resource and capacity buidling for vaccine intelligence
| Development and piloting of training modules and curriculum | 0.0018519 | 0.05588 | 0.69444 | 0 | 0.75218 | 0 | 0 | 0.75218
| Capacity buidling workshops and inititatives | 0 | 0 | 0.20833 | 0.20237 | 0.4107 | 3.6085 | 3.7211 | 7.7403
| Sub Total | 0.0018519 | 0.05588 | 0.90278 | 0.20237 | 1.1629 | 3.6085 | 3.7211 | 8.4925
3.5 | Monitoring and Evaluation
| Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions | 0 | 0 | 0.0018519 | 0.11111 | 0.11296 | 0.11852 | 0.11481 | 0.3463
| Analysis of media reporting at the end of 2013, 2014, and 2015. | 0.0022222 | 0.0022222 | 0.0022222 | 0.013333 | 0.02 | 0.02 | 0.02 | 0.06
| Sub Total | 0.0022222 | 0.0022222 | 0.0040741 | 0.12444 | 0.13296 | 0.13852 | 0.13481 | 0.4063
4.2 | Expand Model based strategy development approaches to support policy decisions in seven additional states
| Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain | 0.0037037 | 0.64815 | 0 | 0 | 0.65185 | 0 | 0 | 0.65185
| Scale up use of the model based strategy development approaches such as HERMES in seven focus states | 0 | 0 | 0.089037 | 0.089037 | 0.17807 | 0.35615 | 0.35615 | 0.89037
| Sub Total | 0.0037037 | 0.64815 | 0.089037 | 0.089037 | 0.82993 | 0.35615 | 0.35615 | 1.5422
4.3 | Support Eveidence generation to assess the case of new antigens based on system readiness, avertable burden, programme costs and cost effectiveness
| Setup a research network | 0 | 0.051111 | 0.082778 | 0.051111 | 0.185 | 0.11333 | 0.11822 | 0.41656
| Support research studies on vaccines | 0 | 0 | 0.65 | 0.023148 | 0.67315 | 1.9676 | 1.3194 | 3.9602
| Sub Total | 0 | 0.051111 | 0.73278 | 0.074259 | 0.85815 | 2.0809 | 1.4377 | 4.3767
| Programme Activities |  |  |  |  | 12.59 | 12.15 | 10.6 | 35.34
| National M&E plan | 0.125 | 0.125 | 0.125 | 0.125 | 0.5 | 0.5 | 0.5 | 1.5
| Secretarial Support to the Ministry | 0.0275 | 0.0275 | 0.0275 | 0.0275 | 0.10899 | 0.11352 | 0.1231 | 0.34561
| Sub Total | 0.1525 | 0.1525 | 0.1525 | 0.1525 | 0.60899 | 0.61352 | 0.6231 | 1.8456
| Total Programmable amount |  |  |  |  | 5.0428 | 16.5086 | 14.0503 | 35.6017
| Technical Assistance (UNDP @ 5%) includes costs of 4 specialists for programme and operations assurance at Delhi and 1 each in the 8 project states |  |  |  |  | 0.25214 | 0.82543 | 0.70251 | 1.7801
| Sub Total |  |  |  |  | 5.295 | 17.334 | 14.7528 | 37.3818
| GMS (@7% of total cost) |  |  |  |  | 0.37065 | 1.2134 | 1.0327 | 2.6167
| Grand Total |  |  |  |  | 5.6656 | 18.5474 | 15.7855 | 39.9985

## 1.1
1.1 | Implement Public-Private Partnership Models of Vaccine Logistics and Cold Chain Management | Year 1 | Year 2 | Year 3 | Total
1.1.1 | Design a business model in detail with exact roles and responsibilities defined for outsourced agency and government officials | 296296.2963 | 0 | 0 | 296296.2963
1.1.2 | Pilot and evaluate the model in 10 low performing districts | 305481.4815 | 4571814.8148 | 4808148.1481 | 9685444.4444
1.1.3 | Establish benchmarks for vaccine inventory management | 2777.7778 | 77777.7778 | 137037.037 | 217592.5926
| Sub Total | 604555.5556 | 4649592.5926 | 4945185.1852 | 10199333.3333
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand
1.1.1 | Design a business model in detail with exact roles and responsibilities defined for outsourced agency and government officials
1 | Idenfication of the 10 districts | [6 empty] | X
2 | Development of the TOR | [6 empty] | X |  |  |  | 1
3 | Identification of Implementing agency | [7 empty] | 2 | 4 | 4 | 10 | [10 empty] | 10
4 | Preparatory Assessments | [7 empty] | 2 | 4 | 4 | 10 | [10 empty] | 10
5 | Development of operational plans | [7 empty] | 2 | 4 | 4 | 10 | [10 empty] | 10
1.1.2 | Pilot and evaluate the model in 10 low performing districts
1 | Initiation of Activities at the state level | [7 empty] | 2 |  | 2 | 4 | 6 |  |  |  | 10 | [5 empty] | 10
2 | Initiation of the activitiees at the district level | [7 empty] | 2 |  | 2 | 4 | 6 |  |  |  | 10 | [5 empty] | 10
3 | Setting up coordination centre at the district level | [8 empty] | 2 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10
4 | Identification of Public and/or Private stakeholders | [8 empty] | 2 | 2 | 4 | 4 | 2 |  |  | 10 |  |  |  |  | 0 | 10
5 | Contractual and administrative agreements | [9 empty] | 2 | 2 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
6 | District level coordination | [9 empty] | 2 | 2 | 4 | 10 |  |  | 8 |  |  |  |  | 0 | 10
7 | Monitoring of activities | [8 empty] | 2 | 2 | 4 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10
8 | Quarterly monitoring and progress meetings | [8 empty] | 2 | 2 | 4 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
9 | Documentation of activities | [9 empty] | 4 | 4 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10
10 | Evaluation and assessments | [10 empty] | 0 |  | 2 | 4 | 4 | 10 |  | 5 | 5 |  | 10 | 10
1.1.3 | Establish benchmarks for vaccine inventory management
1 | Developing at expert group to develop the benchmarks | [9 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 (4) | 1
2 | Travel and Data collection | [11 empty] | 1 |  |  | 1 |  | 1
3 | Data Analysis | [16 empty] | 1
4 | Development of vaccine inventory management | [16 empty] | 1
5 | Piloting the vaccine management Inventory | [17 empty] | 1 |  |  | 10
6 | Finalisation of vaccine inventory management | [17 empty] | 1 |  |  | 1
7 | Printing | [18 empty] | 1 |  | 1
8 | Dissemination | [18 empty] | 1 |  | 1
Design a business model in detail with exact roles and responsibilities defined for outsourced agency and government officials | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
1.1.1 | Developmentment of Public-Private models involving private sectors based on best practices
1 | Idenfication of the 10 districts | 0 | 0 | 0 | 100% | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
2 | Development of the TOR | 0 | 0 | 0 | 100% | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
3 | Identification of Implementing agency | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  | 3703.7037 | 7407.4074 | 7407.4074 | 18518.5185 |  |  |  |  | 0 |  |  |  |  | 0 | 18518.5185
4 | Preparatory Assessments | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  | 18518.5185 | 37037.037 | 37037.037 | 92592.5926 |  |  |  |  | 0 |  |  |  |  | 0 | 92592.5926
5 | Development of operational Plans | 1000000 | 1 | 1 | 100% | 1000000 | 18518.5185 |  | 37037.037 | 74074.0741 | 74074.0741 | 185185.1852 |  |  |  |  | 0 |  |  |  |  | 0 | 185185.1852
| Subtotal | [5 empty] | 29629.6296 |  | 59259.2593 | 118518.5185 | 118518.5185 | 296296.2963 |  |  |  |  | 0 |  |  |  |  | 0 | 296296.2963
Pilot and evaluate the model in 10 low performing districts | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
1.1.2 | Pilot and evaluate the model in 10 low performing districts
1 | Initiation of Activities at the state level | 50000 | 1 | 1 | 100% | 50000 | 925.9259 |  | 1851.8519 |  | 1851.8519 | 3703.7037 | 5555.5556 |  |  |  | 5555.5556 |  |  |  |  | 0 | 9259.2593
2 | Initiation of the activitiees at the district level | 50000 | 1 | 1 | 100% | 50000 | 925.9259 |  | 1851.8519 |  | 1851.8519 | 3703.7037 | 5555.5556 |  |  |  | 5555.5556 |  |  |  |  | 0 | 9259.2593
3 | Setting up coordination centre at the district level | 1740000 | 1 | 1 | 25% | 435000 | 8055.5556 |  |  | 16111.1111 | 32222.2222 | 48333.3333 | 80555.5556 | 80555.5556 | 80555.5556 | 80555.5556 | 322222.2222 | 80555.5556 | 80555.5556 | 80555.5556 | 80555.5556 | 322222.2222 | 692777.7778
4 | Identification of Public and/or Private stakeholders | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  | 18518.5185 | 18518.5185 | 37037.037 | 37037.037 | 18518.5185 |  |  | 55555.5556 |  |  |  |  | 0 | 92592.5926
5 | Contractual and administrative agreements | 1873000 | 1 | 12 | 25% | 5619000 | 104055.5556 |  |  |  | 208111.1111 | 208111.1111 | 832444.4444 | 1040555.5556 | 1040555.5556 | 1040555.5556 | 3954111.1111 | 1040555.5556 | 1040555.5556 | 1040555.5556 | 1040555.5556 | 4162222.2222 | 8324444.4444
6 | District Level Coordination | 0 | 0 | 0 | 100% | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
7 | Monitoring of activities | 5000 | 1 | 12 | 25% | 15000 | 277.7778 |  |  | 555.5556 | 555.5556 | 1111.1111 | 2222.2222 | 2777.7778 | 2777.7778 | 2777.7778 | 10555.5556 | 2777.7778 | 2777.7778 | 2777.7778 | 2777.7778 | 11111.1111 | 22777.7778
8 | Quarterly monitoring and progress meetings | 2000 | 1 | 4 | 25% | 2000 | 37.037 |  |  | 74.0741 | 74.0741 | 148.1481 | 296.2963 | 370.3704 | 370.3704 | 370.3704 | 1407.4074 | 370.3704 | 370.3704 | 370.3704 | 370.3704 | 1481.4815 | 3037.037
9 | Documentation of activities | 15000 | 1 | 12 | 25% | 45000 | 833.3333 |  |  |  | 3333.3333 | 3333.3333 | 6666.6667 | 8333.3333 | 8333.3333 | 8333.3333 | 31666.6667 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 33333.3333 | 68333.3333
10 | Evaluation and assessments | 1000000 | 1 | 1 | 100% | 1000000 | 18518.5185 |  | 0 |  |  |  |  | 37037.037 | 74074.0741 | 74074.0741 | 185185.1852 |  | 92592.5926 | 92592.5926 | 92592.5926 | 277777.7778 | 462962.963
| Subtotal |  |  |  |  | 7716000 | 142888.8889 | 0 | 3703.7037 | 35259.2593 | 266518.5185 | 305481.4815 | 970333.3333 | 1188148.1481 | 1206666.6667 | 1206666.6667 | 4571814.8148 | 1132592.5926 | 1225185.1852 | 1225185.1852 | 1225185.1852 | 4808148.1481 | 9685444.4444
Establish benchmarks for vaccine inventory management | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
1.1.3 | Establish benchmarks for vaccine inventory management | [10 empty] | 0
1 | Developing at expert group to develop the benchmarks | 600000 | 1 | 1 | 25% | 150000 | 2777.7778 |  |  |  | 2777.7778 | 2777.7778 | 2777.7778 | 2777.7778 | 2777.7778 |  | 8333.3333 | 2777.7778 |  |  |  | 2777.7778 | 13888.8889
2 | Travel and Data collection | 5000000 | 1 | 1 | 25% | 1250000 | 23148.1481 |  |  |  |  | 0 | 23148.1481 |  | 23148.1481 | 23148.1481 | 69444.4444 | 23148.1481 |  |  |  | 23148.1481 | 92592.5926
3 | Data Analysis | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 9259.2593 |  |  |  | 9259.2593 | 9259.2593
4 | Development of vaccine inventory management | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0
5 | Piloting the vaccine management Inventory | 1000000 | 1 | 4 | 100% | 4000000 | 74074.0741 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74074.0741 |  | 0 | 74074.0741 | 74074.0741
6 | Finalisation of vaccine inventory management | 0 | 0 | 0 | 100% | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
7 | Printing | 1000000 | 1 | 1 | 100% | 1000000 | 18518.5185 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18518.5185 |  | 18518.5185 | 18518.5185
8 | Dissemination | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9259.2593 |  | 9259.2593 | 9259.2593
| Subtotal |  |  |  |  | 7900000 | 146296.2963 | 0 | 0 | 0 | 2777.7778 | 2777.7778 | 25925.9259 | 2777.7778 | 25925.9259 | 23148.1481 | 77777.7778 | 35185.1852 | 74074.0741 | 27777.7778 | 0 | 137037.037 | 217592.5926
| Head | [6 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
Grand Totals
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
1.1.1 | Developmentment of Public-Private models involving private sectors based on best practices | [6 empty] | 0 | 59259.2593 | 118518.5185 | 118518.5185 | 296296.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296296.2963
1.1.2 | Pilot and evaluate the model in 10 low performing districts | [6 empty] | 0 | 3703.7037 | 35259.2593 | 266518.5185 | 305481.4815 | 970333.3333 | 1188148.1481 | 1206666.6667 | 1206666.6667 | 4571814.8148 | 1132592.5926 | 1225185.1852 | 1225185.1852 | 1225185.1852 | 4808148.1481 | 9685444.4444
1.1.3 | Establish benchmarks for vaccine inventory management | [6 empty] | 0 | 0 | 0 | 2777.7778 | 2777.7778 | 25925.9259 | 2777.7778 | 25925.9259 | 23148.1481 | 77777.7778 | 35185.1852 | 74074.0741 | 27777.7778 | 0 | 137037.037 | 217592.5926
| Grand Totals | [6 empty] | 0 | 62962.963 | 153777.7778 | 387814.8148 | 604555.5556 | 996259.2593 | 1190925.9259 | 1232592.5926 | 1229814.8148 | 4649592.5926 | 1167777.7778 | 1299259.2593 | 1252962.963 | 1225185.1852 | 4945185.1852 | 10199333.3333
Budget Assumptions
|  | Unit Cost | Unit | Frequency | Percentage | Total INR | Total USD
Setting up coordination centre at the district level
| Human Resources | 50000 | 2 | 12 | 1 | 1200000 | 22222.2222
| Rent and Maintainance | 25000 | 1 | 12 | 1 | 300000 | 5555.5556
| Travel and Monitoring | 10000 | 2 | 12 | 1 | 240000 | 4444.4444
| Total |  |  |  |  | 1740000 | 32222.2222
|  | Unit Cost | Unit | Frequency | Percentage | Total INR | Total USD
Establish benchmarks for vaccine inventory management
| Human Resources | 50000 | 10 | 1 | 1 | 500000 | 9259.2593
| Meetings and workshops | 100000 | 1 | 1 | 1 | 100000 | 1851.8519
| Travel and Monitoring | 500000 | 1 | 10 | 1 | 5000000 | 92592.5926
| Total |  |  |  |  | 5600000 | 103703.7037

## 2.1
2.1 | Scale up a system for SMS enabled real time MIS for cold chain and VLM
2.1.1 | Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh | 326851.8519 | 1818814.8148 | 1273148.1481 | 3418814.8148
2.1.2 & 2.1.3 | Pilot and scale up monitoring systems at all levels (UP & Bihar) to monitor real-time vaccine stock situations, status of equipment and other transactions | 518518.5185 | 3242592.5926 | 1559074.0741 | 5320185.1852
| Sub Total | 845370.3704 | 5061407.4074 | 2832222.2222 | 8739000
Work Plan
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand
2.1.1 | Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh
1 | Idenfication of the district and cold chain points | [6 empty] | 1
2 | Development of the TOR | [6 empty] | 1
3 | Identification of Implementing agency | [6 empty] | 1
4 | Preparatory Assessments | [6 empty] | 2
5 | Development of operational Plans | [6 empty] | 2
6 | Device Cost | [7 empty] | 250 | 500 | 250 | 1000 | 1500 | 1500 | 2000 | 2000 | 7000 | [5 empty] | 7000
7 | Installation cost | [7 empty] | 250 | 500 | 250 | 1000 | 1500 | 1500 | 2000 | 2000 | 7000 | [5 empty] | 7000
8 | Running cost (includes website cost, SMS usage cost, etc.) | [7 empty] | 250 | 750 | 1000 | 1000 | 2500 | 4000 | 6000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
9 | Annual Maintainace Cost | [7 empty] | 250 | 500 | 250 | 1000 | 1500 | 1750 | 2500 | 2250 | 8000 | 2500 | 4000 | 6000 | 8000 | 8000 | 8000
10 | Monitoring & Feedback | [7 empty] | 250 | 750 | 1000 | 1000 | 2500 | 4000 | 6000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
11 | Research & Development | [8 empty] | 1 |  | 4 |  |  | 1 |  |  |  |  | 1 |  |  | 5
12 | Evaluation & Assessment | [8 empty] | 50 |  | 109 | 100 |  | 100 |  |  | 200 |  | 200 |  |  | 159
2.1.2 & 2.1.3 | Pilot and scale up monitoring systems at all levels (UP & Bihar) to monitor real-time vaccine stock situations, status of equipment and other transactions
1 | Developing the framework for monitoring systems | [6 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 (4)
2 | Alligning the system with ongoing monitoring tools | [7 empty] | 1 |  |  |  | 1 |  |  | 1
3 | Development of the real time website | [7 empty] | 1
4 | Installing the device and codiing | [7 empty] | 250 | 500 | 250 | 1000 | 1500 | 1500 | 2000 | 2000 | 7000
5 | Piloting the website at select districts | [8 empty] | 20 |  | 20
6 | Up scale real time website to all districts | [11 empty] | 40 |  | 75 | 110 | 110 |  | 1 |  |  | 110 | 110
7 | Maintainace and Technical Assistance | [11 empty] | 60 | 60 | 110 | 110 | 110 | 109 | 109 | 109 | 109 | 110 | 110
8 | Development of Operational Manual | [11 empty] | 1 |  | 1 |  |  |  |  | 1
9 | Printing and Dissemination | [18 empty] | 1
2.1.1 | Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3
| Activities | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand
2.1.1 | Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh
1 | Idenfication of the district and cold chain points | 0 | 0 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
2 | Development of the TOR | 0 | 0 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
3 | Identification of Implementing agency | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 | 3703.7037 |  |  |  | 3703.7037 |  |  |  |  | 0 |  |  |  |  | 0 | 3703.7037
4 | Preparatory Assessments | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 | 18518.5185 |  |  |  | 18518.5185 |  |  |  |  | 0 |  |  |  |  | 0 | 18518.5185
5 | Development of operational Plans | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 | 3703.7037 |  |  |  | 3703.7037 |  |  |  |  | 0 |  |  |  |  | 0 | 3703.7037
6 | Device Cost | 4500 | 1 | 1 | 100% | 4500 | 83.3333 |  | 20833.3333 | 41666.6667 | 20833.3333 | 83333.3333 | 125000 | 125000 | 166666.6667 | 166666.6667 | 583333.3333 |  |  |  |  | 0 | 666666.6667
7 | Installation cost | 1400 | 1 | 1 | 100% | 1400 | 25.9259 | 0 | 6481.4815 | 12962.963 | 25925.9259 | 45370.3704 | 38888.8889 | 38888.8889 | 51851.8519 | 51851.8519 | 181481.4815 |  |  |  |  | 0 | 226851.8519
8 | Running cost (includes website cost, SMS usage cost, etc.) | 1000 | 1 | 1 | 100% | 1000 | 18.5185 | 0 | 4629.6296 | 13888.8889 | 4629.6296 | 23148.1481 | 46296.2963 | 4000 | 111111.1111 | 148148.1481 | 309555.5556 | 148148.1481 | 148148.1481 | 148148.1481 | 148148.1481 | 592592.5926 | 925296.2963
9 | Annual Maintainace Cost | 700 | 1 | 1 | 100% | 700 | 12.963 | 0 | 3240.7407 | 9722.2222 | 12962.963 | 25925.9259 | 19444.4444 | 22685.1852 | 32407.4074 | 29166.6667 | 103703.7037 | 32407.4074 | 51851.8519 | 77777.7778 | 103703.7037 | 265740.7407 | 395370.3704
10 | Monitoring & Feedback | 700 | 1 | 1 | 100% | 700 | 12.963 | 0 | 3240.7407 | 9722.2222 | 12962.963 | 25925.9259 | 32407.4074 | 51851.8519 | 77777.7778 | 103703.7037 | 265740.7407 | 103703.7037 | 103703.7037 | 103703.7037 | 103703.7037 | 414814.8148 | 706481.4815
11 | Research & Development | 250000 | 1 | 1 | 100% | 250000 | 4629.6296 |  |  | 4629.6296 |  | 4629.6296 |  |  | 4629.6296 |  | 4629.6296 |  |  | 4629.6296 |  |  | 9259.2593
12 | Evaluation & Assessment | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  |  | 92592.5926 |  | 92592.5926 | 185185.1852 |  | 185185.1852 |  | 370370.3704 | 14814814.8148 |  | 14814814.8148 |  |  | 462962.963
| Subtotal | [6 empty] | 25925.9259 | 38425.9259 | 185185.1852 | 77314.8148 | 326851.8519 | 447222.2222 | 242425.9259 | 629629.6296 | 499537.037 | 1818814.8148 | 15099074.0741 | 303703.7037 | 15149074.0741 | 355555.5556 | 1273148.1481 | 3418814.8148
2.1.2 & 2.1.3 | Pilot and scale up monitoring systems at all levels (UP & Bihar) to monitor real-time vaccine stock situations, status of equipment and other transactions
|  | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD
2.1.2 & 2.1.3 | Pilot and scale up monitoring systems at all levels (UP & Bihar) to monitor real-time vaccine stock situations, status of equipment and other transactions
1 | Developing the framework for monitoring systems | 5000000 | 1 | 1 | 100% | 5000000 | 92592.5926 | 92592.5926 |  |  |  | 92592.5926 |  |  |  |  | 0 |  |  |  |  | 0 | 92592.5926
2 | Alligning the system with ongoing monitoring tools | 5000000 | 1 | 1 | 100% | 5000000 | 92592.5926 |  | 92592.5926 |  |  | 92592.5926 |  |  |  |  | 0 |  |  |  |  | 0 | 92592.5926
3 | Development of the real time website | 2000000 | 1 | 1 | 100% | 2000000 | 37037.037 |  | 37037.037 |  |  | 37037.037 |  |  |  |  | 0 |  |  |  |  | 0 | 37037.037
4 | Installing the device and coding | 6000 | 1 | 1 | 100% | 6000 | 111.1111 |  | 27777.7778 | 55555.5556 | 27777.7778 | 111111.1111 | 166666.6667 | 166666.6667 | 222222.2222 | 222222.2222 | 777777.7778 | [5 empty] | 888888.8889
5 | Piloting the website at select districts | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  | 185185.1852 |  | 185185.1852 |  |  |  |  | 0 |  |  |  |  | 0 | 185185.1852
6 | Up scale real time website to all districts | 300000 | 1 | 1 | 100% | 300000 | 5555.5556 |  |  |  | 0 | 0 | 222222.2222 | 0 | 416666.6667 | 611111.1111 | 1250000 | [5 empty] | 1250000
7 | Maintainace and Technical Assistance | 190000 | 1 | 1 | 100% | 190000 | 3518.5185 |  |  |  | 0 | 0 | 211111.1111 | 211111.1111 | 387037.037 | 387037.037 | 1196296.2963 | 383518.5185 | 383518.5185 | 383518.5185 | 383518.5185 | 1534074.0741 | 2730370.3704
8 | Development of Operational Manual | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  |  |  | 0 | 9259.2593 |  | 9259.2593 |  | 18518.5185 |  |  | 9259.2593 |  | 9259.2593 | 27777.7778
9 | Printing and Dissemination | 850000 | 1 | 1 | 100% | 850000 | 15740.7407 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 15740.7407 |  | 15740.7407 | 15740.7407
| Subtotal | [6 empty] | 92592.5926 | 157407.4074 | 240740.7407 | 27777.7778 | 518518.5185 | 609259.2593 | 377777.7778 | 1035185.1852 | 1220370.3704 | 3242592.5926 | 383518.5185 | 383518.5185 | 408518.5185 | 383518.5185 | 1559074.0741 | 5320185.1852
Grand Totals
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
2.1.1 | Scale up SMS logger to all cold chain points in Bihar and Uttar Pradesh | [6 empty] | 25925.9259 | 38425.9259 | 185185.1852 | 77314.8148 | 326851.8519 | 447222.2222 | 242425.9259 | 629629.6296 | 499537.037 | 1818814.8148 | 15099074.0741 | 303703.7037 | 15149074.0741 | 355555.5556 | 1273148.1481 | 3418814.8148
2.1.2 | Pilot and scale up monitoring systems at all levels (UP & Bihar) to monitor real-time vaccine stock situations, status of equipment and other transactions | [6 empty] | 92592.5926 | 157407.4074 | 240740.7407 | 27777.7778 | 518518.5185 | 609259.2593 | 377777.7778 | 1035185.1852 | 1220370.3704 | 3242592.5926 | 383518.5185 | 383518.5185 | 408518.5185 | 383518.5185 | 1559074.0741 | 5320185.1852
| Grand Totals | [6 empty] | 118518.5185 | 195833.3333 | 425925.9259 | 105092.5926 | 845370.3704 | 1056481.4815 | 620203.7037 | 1664814.8148 | 1719907.4074 | 5061407.4074 | 15482592.5926 | 687222.2222 | 15557592.5926 | 739074.0741 | 2832222.2222 | 8739000

## 2.2
| 2.2 | Human Resource and capacity buidling for vaccine Intelligence | Year 1 | Year 2 | Year 3 | Total
| 2.2.1 | Development and Piloting of training modules and Curriculum | 752175.9259 | 0 | 0 | 752175.9259
| 2.2.2 | Capacity Buidling workshops and inititatives | 410703.7037 | 3608458.3333 | 3721134.2593 | 7740296.2963
|  | Sub Total | 1162879.6296 | 3608458.3333 | 3721134.2593 | 8492472.2222 | [11 empty] | 1260
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
| 2.2.1 | Development and Piloting of training modules and Curriculum
|  | Development of the TOR | [7 empty] | 1 |  |  |  | 1 | [10 empty] | 1
|  | Indentification of consultant (s) | [7 empty] | 1 |  |  |  | 1 | [10 empty] | 1
|  | Development of training Module | [8 empty] | 1 |  |  | 1 | [10 empty] | 1
|  | Piloting the trainining modules | [8 empty] | 40 |  |  | 40 | [10 empty] | 40
|  | Finalisation of training module | [9 empty] | 36 |  | 36 | [10 empty] | 36
|  | Printing of the training modules | [9 empty] | 1 |  | 1 | [10 empty] | 1
| 2.2.2 | Capacity Buidling workshops and inititatives
|  | National Level Consultation | [9 empty] | 40 |  | 1 |  |  | 40 |  |  |  |  | 40
|  | National Level Training of Trainers | [9 empty] | 36 |  | 1
|  | State level training of Trainers | [10 empty] | 160 | 4 | 160 | 160 |  |  | 8
|  | District Level Trainings | [10 empty] | 0 | 1 | 2413 | 2411 | 635 | 635 | 6094 | 1765 | 2065 |  |  | 3830 | 9924
|  | Evaluation and assessments | [12 empty] | 4 |  | 4 |  | 8 | 4 |  |  |  | 4
|  | Refresher Trainings | [17 empty] | 1200 | 1900 |  |  | 3100 | 3100
Budget
| Development and Piloting of training modules and Curriculum | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
|  | Activities | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
| 2.2.1 | Development and Piloting of training modules and Curriculum | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
|  | Development of the TOR | 0 | 0 | 0 | 100% | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
|  | Indentification of consultant (s) | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  | 1851.8519 |  |  |  | 1851.8519 |  |  |  |  | 0 |  |  |  |  | 0 | 1851.8519
|  | Development of training Module | 1000000 | 1 | 1 | 100% | 1000000 | 18518.5185 |  |  | 18518.5185 |  |  | 18518.5185 |  |  |  |  | 0 |  |  |  |  | 0 | 18518.5185
|  | Piloting the trainining modules | 50437.5 | 1 | 1 | 100% | 50437.5 | 934.0278 |  |  | 37361.1111 |  |  | 37361.1111 |  |  |  |  | 0 |  |  |  |  | 0 | 37361.1111
|  | Finalisation of training module | 1000000 | 1 | 1 | 100% | 1000000 | 18518.5185 |  |  |  | 666666.6667 |  | 666666.6667 |  |  |  |  | 0 |  |  |  |  | 0 | 666666.6667
|  | Printing of the training modules | 1500000 | 1 | 1 | 100% | 1500000 | 27777.7778 |  |  |  | 27777.7778 |  | 27777.7778 |  |  |  |  | 0 |  |  |  |  | 0 | 27777.7778
|  | Subtotal | [7 empty] | 1851.8519 | 55879.6296 | 694444.4444 | 0 | 752175.9259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752175.9259
| Capacity Buidling workshops and inititatives | [12 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| 2.2.2 | Capacity Buidling workshops and inititatives | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
|  | National Level Consultation | 50437.5 | 2 | 1 | 100% | 100875 | 1868.0556 |  |  |  | 74722.2222 |  | 74722.2222 |  |  | 74722.2222 |  | 74722.2222 |  |  | 74722.2222 |  | 74722.2222 | 224166.6667
|  | National Level Training of Trainers | 40083.3333 | 5 | 1 | 100% | 200416.6667 | 3711.4198 |  |  |  | 133611.1111 |  | 133611.1111 |  |  |  |  | 0 |  |  |  |  | 0 | 133611.1111
|  | State level training of Trainers | 22766.6667 | 3 | 1 | 100% | 68300 | 1264.8148 |  |  |  |  | 202370.3704 | 202370.3704 | 202370.3704 | 83333.3333 |  |  | 285703.7037 |  |  |  |  | 0 | 488074.0741
|  | District Level Trainings | 14062.5 | 2 | 1 | 100% | 28125 | 520.8333 |  |  |  |  | 0 | 0 | 1256770.8333 | 1255729.1667 | 330729.1667 | 330729.1667 | 3173958.3333 | 919270.8333 | 1075520.8333 |  |  | 1994791.6667 | 5168750
|  | Evaluation and assessments | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 | [5 empty] | 0 | 37037.037 |  | 37037.037 |  | 74074.0741 | 37037.037 |  |  |  | 37037.037 | 111111.1111
|  | Refresher Trainings | 14062.5 | 2 | 1 | 100% | 28125 | 520.8333 | [5 empty] | 0 |  |  |  |  | 0 | 625000 | 989583.3333 | 0 | 0 | 1614583.3333 | 1614583.3333
|  | Subtotal | [7 empty] | 0 | 0 | 208333.3333 | 202370.3704 | 410703.7037 | 1496178.2407 | 1339062.5 | 442488.4259 | 330729.1667 | 3608458.3333 | 1581307.8704 | 2065104.1667 | 74722.2222 | 0 | 3721134.2593 | 7740296.2963
Grand Totals
[10 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 2.2.1 | Development and Piloting of training modules and Curriculum | [7 empty] | 1851.8519 | 55879.6296 | 694444.4444 | 0 | 752175.9259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752175.9259
| 2.2.2 | Capacity Buidling workshops and inititatives | [7 empty] | 0 | 0 | 208333.3333 | 202370.3704 | 410703.7037 | 1496178.2407 | 1339062.5 | 442488.4259 | 330729.1667 | 3608458.3333 | 1581307.8704 | 2065104.1667 | 74722.2222 | 0 | 3721134.2593 | 7740296.2963
|  | Grand Totals | [7 empty] | 1851.8519 | 55879.6296 | 902777.7778 | 202370.3704 | 1162879.6296 | 1496178.2407 | 1339062.5 | 442488.4259 | 330729.1667 | 3608458.3333 | 1581307.8704 | 2065104.1667 | 74722.2222 | 0 | 3721134.2593 | 8492472.2222
Budget Assumptions
National Level Consultation or workshop
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
International Participation
1 | International Experts or Participants
| a |  | Technical Expert | 5 | 50000 | 4 | 100% | 1000000 | 18518.5185
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 5 | 100000 | 1 | 100% | 500000 | 9259.2593
|  | Local Travel |  | 5 | 2500 | 4 | 100% | 50000 | 925.9259
|  | Lodging+DSA |  | 5 | 10000 | 4 | 100% | 200000 | 3703.7037
|  |  | Sub Total |  |  |  |  | 1750000 | 32407.4074
National Participants
| a | Venue and Hall |  | 40 | 2000 | 2 | 100% | 160000 | 2962.963
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 2 | 25000 | 1 | 100% | 50000 | 925.9259
| g | Reporting and printing | Documentation | 2 | 25000 | 2 | 100% | 100000 | 1851.8519
| h | Miscellaneous |  | 40 | 500 | 2 | 100% | 40000 | 740.7407
|  |  | Sub Total |  |  |  |  | 2285000 | 42314.8148
Unit Cost
|  |  | Grand Total |  |  |  |  | 4035000 | 74722.2222 | 50437.5
National Level training of Trainers workshops
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
International Participation
1 | Experts or Master Trainers
| a |  | Technical Expert | 4 | 50000 | 10 | 100% | 2000000 | 37037.037
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 4 | 25000 | 1 | 100% | 100000 | 1851.8519
|  | Local Travel |  | 4 | 2500 | 10 | 100% | 100000 | 1851.8519
|  | Lodging+DSA |  | 4 | 10000 | 10 | 100% | 400000 | 7407.4074
|  |  | Sub Total |  |  |  |  | 2600000 | 48148.1481
National Participants
| a | Venue and Hall |  | 36 | 2000 | 5 | 100% | 360000 | 6666.6667
| b | Travel | Assuming all require | 36 | 20000 | 1 | 100% | 720000 | 13333.3333
| c | Lodging | Assuming all require | 36 | 10000 | 3 | 100% | 1080000 | 20000
| d | Local Travel and DSA | all 40 | 36 | 2500 | 6 | 100% | 540000 | 10000
| e | Facilitation |  | 5 | 45000 | 5 | 100% | 1125000 | 20833.3333
| f | Sound and Recording |  | 5 | 25000 | 5 | 100% | 625000 | 11574.0741
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 2 | 100% | 40000 | 740.7407
|  |  | Sub Total |  |  |  |  | 4615000 | 85462.963
[10 empty] | Unit Cost | USD Unit Cost
|  |  | Grand Total |  |  |  |  | 7215000 | 133611.1111 | 200416.6667 | 40083.3333
State Level training of Trainers workshops
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 30000 | 5 | 100% | 300000 | 5555.5556
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 25000 | 1 | 100% | 50000 | 925.9259
|  | Local Travel |  | 2 | 2500 | 5 | 100% | 25000 | 462.963
|  | Lodging+DSA |  | 2 | 10000 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 475000 | 8796.2963
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 40 | 5000 | 1 | 100% | 200000 | 3703.7037
| c | Lodging | Assuming all require | 40 | 10000 | 3 | 100% | 1200000 | 22222.2222
| d | Local Travel and DSA | Assuming all require | 40 | 3500 | 3 | 100% | 420000 | 7777.7778
| e | Facilitation | 1 facilitators | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 2 | 100% | 32000 | 592.5926
|  |  | Sub Total |  |  |  |  | 2257000 | 41796.2963
[10 empty] | Unit Cost | USD Unit Cost
|  |  | Grand Total |  |  |  |  | 2732000 | 50592.5926 | 68300 | 22766.6667
District Level Trainings
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
| b | Travel (Related Expenses)
|  | Travel |  | 2 | 10000 | 1 | 100% | 20000 | 370.3704
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 6500 | 4 | 100% | 52000 | 962.963
|  |  | Sub Total |  |  |  |  | 172000 | 3185.1852
National Participants
| a | Venue and Hall |  | 40 | 500 | 2 | 100% | 40000 | 740.7407
| b | Travel | Assuming all require | 40 | 2000 | 1 | 100% | 80000 | 1481.4815
| c | Lodging | Assuming all require | 40 | 4000 | 3 | 100% | 480000 | 8888.8889
| d | Local Travel and DSA | all 40 | 40 | 2425 | 3 | 100% | 291000 | 5388.8889
| e | Facilitation |  | 0 | 45000 | 0 | 100% | 0 | 0
| f | Sound and Recording | 2 days | 1 | 10000 | 2 | 100% | 20000 | 370.3704
| g | Reporting and printing | Documentation | 1 | 5000 | 2 | 100% | 10000 | 185.1852
| h | Miscellaneous |  | 40 | 400 | 2 | 100% | 32000 | 592.5926
|  |  | Sub Total |  |  |  |  | 953000 | 17648.1481
[10 empty] | Unit Cost | USD Unit Cost
|  |  | Grand Total |  |  |  |  | 1125000 | 20833.3333 | 28125 | 14062.5

## 3.5
3.5 | Monitoring and Evaluation | Year 1 | Year 2 | Year 3 | Total
3.5.1 | Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions | 112962.963 | 118518.5185 | 114814.8148 | 346296.2963
3.5.2 | Analyse media reporting at the end of 2014, 2015 & 2016 | 20000 | 20000 | 20000 | 60000
| Sub Total | 132962.963 | 138518.5185 | 134814.8148 | 406296.2963
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [6 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
3.5.1 | Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions
1 | Development of the TOR | [6 empty] | 1 |  |  |  | 1 | [10 empty] | 1
2 | Indentification of consultant (s) | [8 empty] | 1 |  | 1 | [10 empty] | 1
3 | Data Collection and assessment | [9 empty] | 12 | 12 |  |  | 12 |  |  |  |  | 12 |  |  | 12
4 | Dissemination | [11 empty] | 1 |  |  | 1 |  |  |  |  | 1 |  | 0
3.5.2 | Analyse media reporting at the end of 2014, 2015 & 2016
1 | Complition of Media Reports | [6 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 |  | 1
2 | Annual Analysis and Report | [9 empty] | 1 | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1
3 | Printing of Report | [9 empty] | 1 | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1
4 | Dissemination | [9 empty] | 1 | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 0
Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand
3.5.1 | Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions | [10 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
1 | Development of the TOR | 0 | 0 | 0 | 100% | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
2 | Indentification of consultant (s) | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  |  | 1851.8519 |  | 1851.8519 |  |  |  |  | 0 |  |  |  |  | 0 | 1851.8519
3 | Data Collection and assessment | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  |  | 111111.1111 | 111111.1111 |  |  | 111111.1111 |  | 111111.1111 |  |  | 111111.1111 |  | 111111.1111 | 333333.3333
4 | Dissemination | 200000 | 1 | 1 | 100% | 200000 | 3703.7037 |  |  |  |  | 0 | 3703.7037 |  |  | 3703.7037 | 7407.4074 |  |  |  | 3703.7037 | 3703.7037 | 11111.1111
| Subtotal | [6 empty] | 0 | 0 | 1851.8519 | 111111.1111 | 112962.963 | 3703.7037 | 0 | 111111.1111 | 3703.7037 | 118518.5185 | 0 | 0 | 111111.1111 | 3703.7037 | 114814.8148 | 346296.2963
Analyse media reporting at the end of 2014, 2015 & 2016 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
3.5.2 | Analyse media reporting at the end of 2014, 2015 & 2016 |  |  |  |  | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
1 | Complition of Media Reports | 10000 | 1 | 1 | 100% | 10000 | 185.1852 | 2222.2222 | 2222.2222 | 2222.2222 | 2222.2222 | 8888.8889 | 2222.2222 | 2222.2222 | 2222.2222 | 2222.2222 | 8888.8889 | 2222.2222 | 2222.2222 | 2222.2222 | 2222.2222 | 8888.8889 | 26666.6667
2 | Annual Analysis and Report | 200000 | 1 | 1 | 100% | 200000 | 3703.7037 |  |  |  | 3703.7037 | 3703.7037 |  |  |  | 3703.7037 | 3703.7037 |  |  |  | 3703.7037 | 3703.7037 | 11111.1111
3 | Printing of Report | 300000 | 1 | 1 | 100% | 300000 | 5555.5556 |  |  |  | 5555.5556 | 5555.5556 |  |  |  | 5555.5556 | 5555.5556 |  |  |  | 5555.5556 | 5555.5556 | 16666.6667
4 | Dissemination | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  |  |  | 1851.8519 | 1851.8519 |  |  |  | 1851.8519 | 1851.8519 |  |  |  | 1851.8519 | 1851.8519 | 5555.5556
| Subtotal | [6 empty] | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 60000
Grand Totals
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
3.5.1 | Periodically conduct qualitative and quantitative assessment on ongoing IEC/BCC interventions | [6 empty] | 0 | 0 | 1851.8519 | 111111.1111 | 112962.963 | 3703.7037 | 0 | 111111.1111 | 3703.7037 | 118518.5185 | 0 | 0 | 111111.1111 | 3703.7037 | 114814.8148 | 346296.2963
3.5.2 | Analyse media reporting at the end of 2014, 2015 & 2016 | [6 empty] | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 2222.2222 | 2222.2222 | 2222.2222 | 13333.3333 | 20000 | 60000
| Grand Totals | [6 empty] | 2222.2222 | 2222.2222 | 4074.0741 | 124444.4444 | 132962.963 | 5925.9259 | 2222.2222 | 113333.3333 | 17037.037 | 138518.5185 | 2222.2222 | 2222.2222 | 113333.3333 | 17037.037 | 134814.8148 | 406296.2963

## 4.2
4.2 | Expand Model based strategy development approaches to support policy decisions in seven additional states | Year 1 | Year 2 | Year 3 | Total
4.2.1 | Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain | 651851.8519 | 0 | 0 | 651851.8519
4.2.2 | Scale up use of the model based strategy development approaches such as HERMES in seven focus states | 178073.6296 | 356147.2593 | 356147.2593 | 890368.1481
| Sub Total | 829925.4815 | 356147.2593 | 356147.2593 | 1542220
Work Plan
[9 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
4.2.1 | Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain
1 | Development of the TOR | [7 empty] | 1 | [14 empty] | 1
2 | Identification of the Agency | [7 empty] | 1 | [14 empty] | 1
3 | Development of stimulation model | [8 empty] | 1 | [13 empty] | 1
4.2.2 | Scale up use of the model based strategy development approaches such as HERMES in seven focus states
1 | Consultant Cost | [9 empty] | X | X |  | X | X | X | X |  | X | X | X | X
2 | Travel | [9 empty] | X | X |  | X | X | X | X |  | X | X | X | X
3 | Supplies | [9 empty] | X | X |  | X | X | X | X |  | X | X | X | X
4 | Field Offices | [9 empty] | X | X |  | X | X | X | X |  | X | X | X | X
Budget
Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
4.2.1 | Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
1 | Development of the TOR | 0 | 0 | 0 | 100% | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
2 | Identification of the Agency | 200000 | 1 | 1 | 100% | 200000 | 3703.7037 |  | 3703.7037 |  |  |  | 3703.7037 |  |  |  |  | 0 |  |  |  |  | 0 | 3703.7037
3 | Development of stimulation model | 35000000 | 1 | 1 | 100% | 35000000 | 648148.1481 |  |  | 648148.1481 |  |  | 648148.1481 |  |  |  |  | 0 |  |  |  |  | 0 | 648148.1481
| Subtotal | [7 empty] | 3703.7037 | 648148.1481 | 0 | 0 | 651851.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651851.8519
Scale up use of the model based strategy development approaches such as HERMES in seven focus states
4.2.2 | Scale up use of the model based strategy development approaches such as HERMES in seven focus states |  |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
1 | Consultant Cost | 13580000 | 1 | 1 | 100% | 13580000 | 251481.4815 |  |  |  | 25148.1481 | 25148.1481 | 50296.2963 | 25148.1481 | 25148.1481 | 25148.1481 | 25148.1481 | 100592.5926 | 25148.1481 | 25148.1481 | 25148.1481 | 25148.1481 | 100592.5926 | 251481.4815
2 | Travel | 19708500 | 1 | 1 | 100% | 19708500 | 364972.2222 |  |  |  | 36497.2222 | 36497.2222 | 72994.4444 | 36497.2222 | 36497.2222 | 36497.2222 | 36497.2222 | 145988.8889 | 36497.2222 | 36497.2222 | 36497.2222 | 36497.2222 | 145988.8889 | 364972.2222
3 | Supplies | 13741380 | 1 | 1 | 100% | 13741380 | 254470 |  |  |  | 25447 | 25447 | 50894 | 25447 | 25447 | 25447 | 25447 | 101788 | 25447 | 25447 | 25447 | 25447 | 101788 | 254470
4 | Field Offices | 1050000 | 1 | 1 | 100% | 1050000 | 19444.4444 |  |  |  | 1944.4444 | 1944.4444 | 3888.8889 | 1944.4444 | 1944.4444 | 1944.4444 | 1944.4444 | 7777.7778 | 1944.4444 | 1944.4444 | 1944.4444 | 1944.4444 | 7777.7778 | 19444.4444
| Subtotal | [7 empty] | 0 | 0 | 89036.8148 | 89036.8148 | 178073.6296 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 890368.1481
Grand Totals
[9 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
[9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
4.2.1 | Development and Designing HERMES or similar dyanamic computer simulation model for vaccine supply chain | [7 empty] | 3703.7037 | 648148.1481 | 0 | 0 | 651851.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651851.8519
4.2.2 | Scale up use of the model based strategy development approaches such as HERMES in seven focus states | [7 empty] | 0 | 0 | 89036.8148 | 89036.8148 | 178073.6296 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 890368.1481
| Grand Totals | [7 empty] | 3703.7037 | 648148.1481 | 89036.8148 | 89036.8148 | 829925.4815 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 89036.8148 | 89036.8148 | 89036.8148 | 89036.8148 | 356147.2593 | 1542220
Budget Assumptions
| Development Cost | 35000000
Operational Cost
| Consultant costs | 13580000
| Travel (Internal/Domestic) | 19708500
| Supplies | 13741380
| Running Cost of field offices | 1050000
| Total | 48079880
| Item heads | UP | BH | JH | MP | RJ | CG | GJ | Total
| Districts | 72 | 38 | 24 | 50 | 33 | 27 | 26 | 270
| CC points | 1112 | 588 | 224 | 1068 | 2010 | 529 | 1829 | 7360
| Study districts (1/3rd districts) | 24 | 13 | 8 | 17 | 11 | 9 | 9 | 91
| Study CC points (1/3rd districts) | 375 | 200 | 75 | 360 | 680 | 180 | 620 | 2490
| Number of teams | 12 | 7 | 4 | 9 | 10 | 5 | 9 | 56
| Days needed | 2 mons | 2 Mon | 1.5 mon | 2 mon | 3 Mon | 2 Mon | 3 Mon | 3 mon
| Cost of travel | 618750 | 330000 | 123750 | 594000 | 1122000 | 297000 | 1023000 | 4108500
| Contingency (food & stationary) | 360000 | 210000 | 120000 | 270000 | 300000 | 150000 | 270000 | 1680000
| Stay | 1440000 | 780000 | 300000 | 1485000 | 4575000 | 750000 | 4590000 | 13920000
| Supplies | 3664368 | 1933972 | 1221456 | 2544700 | 1679502 | 1374138 | 1323244 | 13741380
| Honorarium for study teams | 2760000 | 1610000 | 920000 | 2070000 | 2300000 | 1150000 | 2070000 | 12880000
| State coordinator honorarium | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 700000
| Field office expenses | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 1050000
48079880

## 4.3
| 4.3 | Support Evidence generation to assess the case of new antigens based on system readiness, avertable burden, programme costs, and cost effectiveness | Year 1 | Year 2 | Year 3 | Total
| 4.3.1 | Setup a research network | 185000 | 113333.3333 | 118222.2222 | 416555.5556
| 4.3.2 | Support research studes on vaccines | 673148.1481 | 1967592.5926 | 1319444.4444 | 3960185.1852
|  | Sub Total | 858148.1481 | 2080925.9259 | 1437666.6667 | 4376740.7407
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
|  | Activities | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
| 4.3.1 | Setup a research network
| 1 | Development of the TOR | [7 empty] | X
| 2 | Indentification of network participants | [7 empty] | X
| 3 | Biannual Meeting | [9 empty] | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
| 4 | Web Platform | [8 empty] | X | X | X |  | X | X | X | X |  | X | X | X | X
| 4.3.2 | Support research studes on vaccines
| 1 | Development of TOR | [7 empty] | X
| 2 | Identification of the Agency (S)
| 3 | Data Collection and Analysis | [9 empty] | 1 |  |  | 1 | 1 | 1 |  |  | 1 |  | 1
| 4 | Printing | [10 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1
| 5 | Dissemination | [10 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1
Budget
| Setup a research network | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
|  | Activities | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
| 4.3.1 | Setup a research network |  |  |  | 100% | 0 | 0
| 1 | Development of the TOR | 0 | 0 | 0 | 100% | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 2 | Indentification of network participants | 0 | 0 | 0 | 100% | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
| 3 | Biannual Meeting | 1710000 | 1 | 1 | 100% | 1710000 | 31666.6667 |  |  |  | 31666.6667 |  | 31666.6667 | 31666.6667 |  | 31666.6667 |  | 63333.3333 | 31666.6667 |  | 31666.6667 |  | 63333.3333 | 158333.3333
| 4 | Web Platform | 8424000 | 1 | 1 | 100% | 8424000 | 156000 |  |  | 51111.1111 | 51111.1111 | 51111.1111 | 153333.3333 | 12500 | 12500 | 12500 | 12500 | 50000 | 13722.2222 | 13722.2222 | 13722.2222 | 13722.2222 | 54888.8889 | 258222.2222
|  | Subtotal | [7 empty] | 0 | 51111.1111 | 82777.7778 | 51111.1111 | 185000 | 44166.6667 | 12500 | 44166.6667 | 12500 | 113333.3333 | 45388.8889 | 13722.2222 | 45388.8889 | 13722.2222 | 118222.2222 | 416555.5556
| Support research studes on vaccines | [12 empty] | 0 |  |  |  |  | 0
| 4.3.2 | Support research studes on vaccines |  |  |  |  | 0 | 0
| 1 | Development of TOR | 0 | 0 | 0 | 100% | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 0
| 2 | Identification of the Agency (S) | 100000 | 1 | 1 | 100% | 100000 | 1851.8519 |  |  |  | 1851.8519 |  | 1851.8519 |  |  |  |  | 0 |  |  |  |  | 0 | 1851.8519
| 3 | Data Collection and Analysis | 35000000 | 1 | 1 | 100% | 35000000 | 648148.1481 |  |  |  | 648148.1481 |  | 648148.1481 | 648148.1481 | 648148.1481 | 648148.1481 |  | 1944444.4444 | 648148.1481 |  | 648148.1481 |  | 1296296.2963 | 3888888.8889
| 4 | Printing | 750000 | 1 | 1 | 100% | 750000 | 13888.8889 |  |  |  |  | 13888.8889 | 13888.8889 |  |  |  | 13888.8889 | 13888.8889 |  |  |  | 13888.8889 | 13888.8889 | 41666.6667
| 5 | Dissemination | 500000 | 1 | 1 | 100% | 500000 | 9259.2593 |  |  |  |  | 9259.2593 | 9259.2593 |  |  |  | 9259.2593 | 9259.2593 |  |  |  | 9259.2593 | 9259.2593 | 27777.7778
|  | Subtotal | [7 empty] | 0 | 0 | 650000 | 23148.1481 | 673148.1481 | 648148.1481 | 648148.1481 | 648148.1481 | 23148.1481 | 1967592.5926 | 648148.1481 | 0 | 648148.1481 | 23148.1481 | 1319444.4444 | 3960185.1852
Grand Totals
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 4.3.1 | Setup a research network | [7 empty] | 0 | 51111.1111 | 82777.7778 | 51111.1111 | 185000 | 44166.6667 | 12500 | 44166.6667 | 12500 | 113333.3333 | 45388.8889 | 13722.2222 | 45388.8889 | 13722.2222 | 118222.2222 | 416555.5556
| 4.3.2 | Support research studes on vaccines | [7 empty] | 0 | 0 | 650000 | 23148.1481 | 673148.1481 | 648148.1481 | 648148.1481 | 648148.1481 | 23148.1481 | 1967592.5926 | 648148.1481 | 0 | 648148.1481 | 23148.1481 | 1319444.4444 | 3960185.1852
|  | Grand Totals | [7 empty] | 0 | 51111.1111 | 732777.7778 | 74259.2593 | 858148.1481 | 692314.8148 | 660648.1481 | 692314.8148 | 35648.1481 | 2080925.9259 | 693537.037 | 13722.2222 | 693537.037 | 36870.3704 | 1437666.6667 | 4376740.7407
Budget Assumptions
Biannual Research Meeting
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | Total | USD
International Participation
1 | International Experts or Participants
| a |  | Technical Expert | 4 | 50000 | 3 | 100% | 600000 | 11111.1111
| b | Travel (Related Expenses) | [5 empty] | 0 | 0
|  | Travel |  | 4 | 100000 | 1 | 100% | 400000 | 7407.4074
|  | Local Travel | Lumsum | 4 | 2500 | 3 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 4 | 10000 | 3 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 1150000 | 21296.2963
National Participants
| a | Venue and Hall |  | 20 | 2000 | 2 | 100% | 80000 | 1481.4815
| b | Travel |  | 10 | 20000 | 1 | 100% | 200000 | 3703.7037
| c | Lodging |  | 10 | 10000 | 2 | 100% | 200000 | 3703.7037
| d | Local Travel and DSA | all 40 | 20 | 1000 | 3 | 100% | 60000 | 1111.1111
| h | Miscalleneous |  | 20 | 500 | 2 | 100% | 20000 | 370.3704
|  |  | Sub Total |  |  |  |  | 560000 | 10370.3704
|  |  | Grand Total |  |  |  |  | 1710000 | 31666.6667
Web Platform
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD | Total | USD | Year 1 | Year 2 | Year 3 | Total
Human Resources
| b | Travel (Related Expenses) | [7 empty] | 0 | 0
|  | Coordinator |  | 1 | 100000 | 12 | 100% | 1200000 | 22727.2727 | 1200000 | 22222.2222 | 22222.2222 | 24444.4444 | 26888.8889
|  |  | Sub Total |  |  |  |  | 1200000 | 22727.2727 | 1200000 | 22222.2222 | 22222.2222 | 24444.4444 | 26888.8889 | 73555.5556
National Participants
| a | Website Content and Development |  | 1 | 200000 | 1 | 100% | 200000 | 3787.8788 | 200000 | 3703.7037 | 3703.7037 | 0 | 0
| b | Maintainance |  | 1 | 100000 | 12 | 100% | 1200000 | 22727.2727 | 1200000 | 22222.2222 | 22222.2222 | 24444.4444 | 26888.8889
| c | Computer and IT issues |  | 1 | 100000 | 1 | 100% | 100000 | 1893.9394 | 100000 | 1851.8519 | 1851.8519 | 0 | 0
| d | Logictics |  | 1 | 5000 | 12 | 100% | 60000 | 1136.3636 | 60000 | 1111.1111 | 1111.1111 | 1111.1111 | 1111.1111
|  |  | Sub Total |  |  |  |  | #REF! | #REF! | 1560000 | 28888.8889 | 28888.8889 | 25555.5556 | 28000 | 82444.4444
0
|  |  | Grand Total | [6 empty] | 2760000 | 51111.1111 | 51111.1111 | 50000 | 54888.8889 | 156000

## Secretarial Support
HSS Secretarial Support for the ministry
| Head | Unit | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Year 1 | Year 2 | Year 3 | Total
1 | Secretarial Support to ministry | [7 empty] | 0
| Coordinator | 2 | 152850 | 1 | 12 | 100% | 3668400 | 66698.1818 | 66698.1818 | 73368 | 80704.8 | 220770.9818
| Assistant | 1 | 93354 | 1 | 12 | 100% | 1120248 | 20368.1455 | 20368.1455 | 22404.96 | 24645.456 | 67418.5615
| Subtotal | [5 empty] | 4788648 | 87066.3273 | 87066.3273 | 95772.96 | 105350.256 | 288189.5433
2 | Equipment and Maintainance | [7 empty] | 0
| Computers | 1 | 60000 | 3 | 1 | 100% | 180000 | 3272.7273 | 3272.7273 | 0 | 0 | 3272.7273
| Printers | 1 | 50000 | 1 | 1 | 100% | 50000 | 909.0909 | 909.0909 | 0 | 0 | 909.0909
| Maintainance | 1 | 38000 | 1 | 12 | 100% | 456000 | 8290.9091 | 8290.9091 | 8290.9091 | 8290.9091 | 24872.7273
| Subtotal | [5 empty] | 686000 | 12472.7273 | 12472.7273 | 8290.9091 | 8290.9091 | 29054.5455
3 | Monitoring | [7 empty] | 0
| Travel | 2 | 20000 | 4 | 1 | 100% | 160000 | 2909.0909 | 2909.0909 | 2909.0909 | 2909.0909 | 8727.2727
| DSA | 2 | 11000 | 12 | 1 | 100% | 264000 | 4800 | 4800 | 4800 | 4800 | 14400
| Meetings and organisation | 1 | 12000 | 1 | 8 | 100% | 96000 | 1745.4545 | 1745.4545 | 1745.4545 | 1745.4545 | 5236.3636
| Subtotal | [5 empty] | 424000 | 7709.0909 | 9454.5455 | 9454.5455 | 9454.5455 | 28363.6364
| Total | [7 empty] | 108993.6 | 113518.4145 | 123095.7105 | 345607.7251

## UNICEF
NAME OF PARTNER: UNICEF
Project Title: GAVI HSS
Duration: 2013-2015
Year 1
|  | Funds In US $ Millions |  |  |  | FUNDS ( In US $ Millions)
Activity | Description | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | YR 1 | YR 2 | YR 3 | Total
1.2 | Improve Human Resources to improve cold chain performance
| Establish the NCCVMRC at NIHFW, Delhi and NCCTC at Pune | 0.072222 | 0.072222 | 0.072222 | 0.13055 | 0.34721 | 0.3761 | 0.40788 | 1.1312
| Train and Equip the UIP staff | 0 | 0 | 0 | 0.18085 | 0.18085 | 1.2531 | 0 | 1.434
| Sub Total | 0.072222 | 0.072222 | 0.072222 | 0.3114 | 0.52806 | 1.6292 | 0.40788 | 2.5652
1.3 | Supportive Supervision to ensure quality implementation
| Supportive Supervision | 0.14133 | 0.14133 | 0.21675 | 0.29217 | 0.79158 | 1.2799 | 1.5477 | 3.6193
| Sub Total | 0.14133 | 0.14133 | 0.21675 | 0.29217 | 0.79158 | 1.2799 | 1.5477 | 3.6193
1.4 | Implement EVM improvement plans
| EVMs Conducted and PIPs implemented in Larger states | 0 | 0 | 0.080815 | 0.040519 | 0.12133 | 0.61776 | 1.153 | 1.8921
| Nationwide rollout of the national cold chain MIS | 0 | 0 | 0.051389 | 0.13472 | 0.18611 | 0.28756 | 0.45983 | 0.9335
| Integration of VLM system based on existing models | 0 | 0 | 0.051389 | 0.083333 | 0.13472 | 0.36746 | 0.20422 | 0.70641
| Sub Total | 0 | 0 | 0.18359 | 0.25857 | 0.44217 | 1.2728 | 1.8171 | 3.532
1.5 | Institutional Capacity building to strengthen the cold chain system
| Build Institutional Capacity of the NCCVMRC | 0 | 0 | 0 | 1.9037 | 1.9037 | 0.038889 | 0.044444 | 1.987
| Improve / operationalise existing cold chain equipment & reduce sickness rate. | 0 | 0 | 0.2 | 1.1022 | 1.3022 | 0.2 | 0.2 | 1.7022
| Sub Total | 0 | 0 | 0.2 | 3.0059 | 3.2059 | 0.23889 | 0.24444 | 3.6893
3.1 | Implement Multi pronged national BCC strategy development and operational plans | 0 | 0 | 0.31081 | 0.38852 | 0.69933 | 0.45741 | 0.67963 | 1.8364
| Sub Total | 0 | 0 | 0.31081 | 0.38852 | 0.69933 | 0.45741 | 0.67963 | 1.8364
3.2 | Enhance Infrastructure and HR Capacity to develop and implement BCC strategies | 0.69444 | 0.72754 | 0.9462 | 0.89444 | 3.2626 | 3.5713 | 3.5172 | 10.3512
| Sub Total | 0.69444 | 0.72754 | 0.9462 | 0.89444 | 3.2626 | 3.5713 | 3.5172 | 10.3512
3.3 | Develop and Broadcast immunisation messages through mass media | 0 | 0.58767 | 0.68476 | 0.67656 | 1.949 | 1.9027 | 1.763 | 5.6147
| Sub Total | 0 | 0.58767 | 0.68476 | 0.67656 | 1.949 | 1.9027 | 1.763 | 5.6147
3.4 | Promote advocacy with media for creating an enabling environment for increasing demand for RI services | 0 | 0.307 | 0.35772 | 0.48222 | 1.1469 | 1.1825 | 0.16137 | 2.4908
| Sub Total | 0 | 0.307 | 0.35772 | 0.48222 | 1.1469 | 1.1825 | 0.16137 | 2.4908
| Monitoring and Evaluation | 0.125 | 0.125 | 0.125 | 0.375 | 0.5 | 0.5 | 0.5 | 1.5
| Sub Total | 0.125 | 0.125 | 0.125 | 0.375 | 0.5 | 0.5 | 0.5 | 1.5
| Programme Activities |  |  |  |  | 12.5256 | 12.0347 | 10.6383 | 35.1987
TA | Technical Assistance (Health specialists in 9 States and Delhi) @5% of total cost | 0.1512 | 0.1512 | 0.1512 | 0.1512 | 0.6048 | 0.66528 | 0.73181 | 2.0019
| Sub Total |  |  |  |  | 13.1304 | 12.7 | 11.3702 | 37.2006
| Recovery Charges (@7% of total cost) |  |  |  |  | 0.84592 | 0.93051 | 1.0236 | 2.8
| Grand Total |  |  |  |  | 13.9764 | 13.6305 | 12.3937 | 40.0006

## 1.2
| 1.2 | Improve Human Resources to improve cold chain performance | Year 1 | Year 2 | Year 3 | Total
| 1.2.1 | Establish the NCCVMRC at NIHFW, Delhi and NCCTC at Pune | 347212.963 | 376101.8519 | 407879.6296 | 1131194.4444
| 1.2.2 | Train and Equip the UIP staff | 180851.8519 | 1253111.1111 | 0 | 1433962.963
|  | Sub Total | 528064.8148 | 1629212.963 | 407879.6296 | 2565157.4074
Work Plan
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | 1.2.1 a Establish the NCCVMRC at NIHFW, Delhi and NCCTC at Pune | [8 empty] | X | X | X | X | X | X | X | X
|  | 1.2.1 b Study Tour to WHO Accredited Lab-Center - 7 days (Organised by NCCTC) | [11 empty] | 1 | 1 | 1 | 1 | 3
|  | 1.2.1 c Consultation meetings to develop 1. National Cold Chain Development Plan, 2. National Standards on Cold Chain System and 3. Standard Cold Chain equipment & training modules/ Job-Aids | [11 empty] | 1 | 1 | 1 | 1 | 3
|  | 1.2.2 a National ToT on Effective Cold Chain & Vaccine Logistics Management (ECCVLM) | [11 empty] | 2 | 2 |  |  | 2
|  | 1.2.2 b ECCVLM Training (540 staff-National & state, including Vaccine Logistics managers' Induction) 18 batches in 9 states | [13 empty] | 18
|  | 1.2.2 c Induction training of 320 Cold Chain Technicians (CCT) / Cold Chain Consultants (CCC) in 9 batches | [11 empty] | 1 | 1 | 8 |  | 9
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.1 a Establish the NCCVMRC at NIHFW, Delhi and NCCTC at Pune | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Senior Consultant & NCCTC Coordinator |  | 1 | 150000 | 12 | 1 | 1800000 | 33333.3333 |  | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 33333.3333 | 36666.6667 | 40333.3333 | 110333.3333
| 2 | Consultant- NCCTC |  | 3 | 120000 | 12 | 1 | 4320000 | 80000 |  | 20000 | 20000 | 20000 | 20000 | 80000 | 88000 | 96800 | 264800
| 3 | Programme Assistants |  | 2 | 30000 | 12 | 1 | 720000 | 13333.3333 |  | 3333.3333 | 3333.3333 | 3333.3333 | 3333.3333 | 13333.3333 | 14666.6667 | 16133.3333 | 44133.3333
| 4 | Training Coordinator |  | 1 | 130000 | 12 | 1 | 1560000 | 28888.8889 |  | 7222.2222 | 7222.2222 | 7222.2222 | 7222.2222 | 28888.8889 | 31777.7778 | 34955.5556 | 95622.2222
| 5 | Software Specialists/ Data Analysts |  | 2 | 100000 | 12 | 1 | 2400000 | 44444.4444 |  | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 44444.4444 | 48888.8889 | 53777.7778 | 147111.1111
| 6 | Programme Assistants |  | 1 | 30000 | 12 | 1 | 360000 | 6666.6667 |  | 1666.6667 | 1666.6667 | 1666.6667 | 1666.6667 | 6666.6667 | 7333.3333 | 8066.6667 | 22066.6667
| 7 | Travel costs- National CCC |  | 4 | 50000 | 12 | 1 | 2400000 | 44444.4444 |  | 11111.1111 | 11111.1111 | 11111.1111 | 11111.1111 | 44444.4444 | 48888.8889 | 53777.7778 | 147111.1111
| 8 | Travel costs- Training Coordinator |  | 1 | 50000 | 12 | 1 | 600000 | 11111.1111 |  | 2777.7778 | 2777.7778 | 2777.7778 | 2777.7778 | 11111.1111 | 12222.2222 | 13444.4444 | 36777.7778
| 9 | Travel costs- Software Specialist/ Data Analyst |  | 2 | 50000 | 12 | 1 | 1200000 | 22222.2222 |  | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 22222.2222 | 24444.4444 | 26888.8889 | 73555.5556
| 10 | Miscellaneous/ Stationary/ Communication |  | 10 | 2000 | 12 | 1 | 240000 | 4444.4444 |  | 1111.1111 | 1111.1111 | 1111.1111 | 1111.1111 | 4444.4444 | 4888.8889 | 5377.7778 | 14711.1111
|  | Subtotal | [5 empty] | 15600000 | 288888.8889 |  | 72222.2222 | 72222.2222 | 72222.2222 | 72222.2222 | 288888.8889 | 317777.7778 | 349555.5556 | 956222.2222
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.1 b Study Tour to WHO Accredited Lab-Center - 7 days (Organised by NCCTC) | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | Travel (Related Expenses) | 1 | 20000 | 2 | 1 | 100% | 40000 | 740.7407 |  |  |  |  | 740.7407 | 740.7407 | 740.7407 | 740.7407 | 2222.2222
|  | Travel | 1 | 100000 | 2 | 1 | 100% | 200000 | 3703.7037 |  |  |  |  | 3703.7037 | 3703.7037 | 3703.7037 | 3703.7037 | 11111.1111
|  | Local Travel | 2 | 6500 | 2 | 2 | 100% | 52000 | 962.963 |  |  |  |  | 962.963 | 962.963 | 962.963 | 962.963 | 2888.8889
|  | Lodging+DSA | 1 | 20000 | 2 | 9 | 100% | 360000 | 6666.6667 |  |  |  |  | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 20000
|  | Subtotal | [5 empty] | 652000 | 12074.0741 |  |  |  |  | 12074.0741 | 12074.0741 | 12074.0741 | 12074.0741 | 36222.2222
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.1 c Consultation meetings to develop 1. National Cold Chain Development Plan, 2. National Standards on Cold Chain System and 3. Standard Cold Chain equipment & training modules/ Job-Aids | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | Consultation | 1 | 62437.5 | 40 | 1 | 100% | 2497500 | 46250 |  |  |  |  | 46250 | 46250 | 46250 | 46250 | 138750
|  | Subtotal | [5 empty] | 2497500 | 46250 |  |  |  |  | 46250 | 46250 | 46250 | 46250 | 138750
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.2 a National ToT on Effective Cold Chain & Vaccine Logistics Management (ECCVLM) | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | TOT | 1 | 103250 | 40 | 1 | 100% | 4130000 | 76481.4815 |  |  |  |  | 152962.963 | 152962.963 |  |  | 152962.963
|  | Subtotal | [5 empty] | 4130000 | 76481.4815 |  |  |  |  | 152962.963 | 152962.963 | 0 | 0 | 152962.963
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.2 b ECCVLM Training (540 staff-National & state, including Vaccine Logistics managers' Induction) 18 batches in 9 states | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | ECCVLM Training | 1 | 77250 | 40 | 1 | 100% | 3090000 | 57222.2222 | [5 empty] | 0 | 1030000 |  | 1030000
|  | Subtotal | [5 empty] | 3090000 | 57222.2222 |  |  |  |  | 0 | 0 | 1030000 | 0 | 1030000
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| 1.2.2 c Induction training of 320 Cold Chain Technicians (CCT) / Cold Chain Consultants (CCC) in 9 batches | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | ECCVLM Training | 1 | 37650 | 40 | 1 | 100% | 1506000 | 27888.8889 |  |  |  |  | 27888.8889 | 27888.8889 | 223111.1111 |  | 251000
|  | Subtotal | [5 empty] | 1506000 | 27888.8889 |  |  |  |  | 27888.8889 | 27888.8889 | 223111.1111 | 0 | 251000
| Grand Totals | [9 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1.2.1 | Establish the NCCVMRC at NIHFW, Delhi and NCCTC at Pune | [8 empty] | 72222.2222 | 72222.2222 | 72222.2222 | 130546.2963 | 347212.963 | 376101.8519 | 407879.6296 | 1131194.4444
| 1.2.2 | Train and Equip the UIP staff | [8 empty] | 0 | 0 | 0 | 180851.8519 | 180851.8519 | 1253111.1111 | 0 | 1433962.963
Budget Assumptions
1.2.1 c National Level Consultation - National Standards/ National Cold Chain Plan
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 3 | 15000 | 3 | 100% | 135000 | 2500
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 3 | 100% | 22500 | 416.6667
|  | Lodging+DSA |  | 3 | 10000 | 3 | 100% | 90000 | 1666.6667
|  |  | Sub Total |  |  |  |  | 307500 | 5694.4444
National Participants
| a | Venue and Hall |  | 40 | 2000 | 2 | 100% | 160000 | 2962.963
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 2 | 100% | 90000 | 1666.6667
| f | Sound and Recording |  | 1 | 25000 | 2 | 100% | 50000 | 925.9259
| g | Reporting and printing | Documentation | 1 | 25000 | 2 | 100% | 50000 | 925.9259
| h | Miscellaneous |  | 40 | 500 | 2 | 100% | 40000 | 740.7407
|  |  | Sub Total |  |  |  |  | 2190000 | 40555.5556
|  |  | Grand Total |  |  |  |  | 2497500 | 46250 | 62437.5 | 1156.25
1.2.2 a National Level training of Trainers -ECCVLM
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Master Trainers
| a |  | Technical Expert | 3 | 15000 | 6 | 100% | 270000 | 5000
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 6 | 100% | 45000 | 833.3333
|  | Lodging+DSA |  | 3 | 10000 | 6 | 100% | 180000 | 3333.3333
|  |  | Sub Total |  |  |  |  | 555000 | 10277.7778
National Participants
| a | Venue and Hall |  | 40 | 2000 | 5 | 100% | 400000 | 7407.4074
| b | Travel | Assuming all require | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | all 40 | 40 | 2500 | 5 | 100% | 500000 | 9259.2593
| e | Facilitation |  | 1 | 45000 | 5 | 100% | 225000 | 4166.6667
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 3575000 | 66203.7037
|  |  | Grand Total |  |  |  |  | 4130000 | 76481.4815 | 103250 | 1912.037
1.2.2 b ECCVLM Training (540 staff-National & state, including Vaccine Logistics managers' Induction) 18 batches in 9 states
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 30000 | 6 | 100% | 360000 | 6666.6667
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 25000 | 1 | 100% | 50000 | 925.9259
|  | Local Travel |  | 2 | 2500 | 6 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 2 | 10000 | 6 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 560000 | 10370.3704
State/ district Participants
| a | Venue and Hall |  | 40 | 1000 | 5 | 100% | 200000 | 3703.7037
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 5 | 100% | 300000 | 5555.5556
| e | Facilitation | 1 facilitators | 1 | 10000 | 5 | 100% | 50000 | 925.9259
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 400 | 5 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 2530000 | 46851.8519
|  |  | Grand Total |  |  |  |  | 3090000 | 57222.2222 | 77250 | 1059.6708
1.2.2 c Induction training of 320 Cold Chain Technicians (CCT) / Cold Chain Consultants (CCC) in 9 batches
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 10000 | 6 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses)
|  | Travel |  | 2 | 5000 | 1 | 100% | 10000 | 185.1852
|  | Local Travel |  | 2 | 1500 | 6 | 100% | 18000 | 333.3333
|  | Lodging+DSA |  | 2 | 4000 | 6 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 196000 | 3629.6296
National Participants
| a | Venue and Hall |  | 40 | 750 | 5 | 100% | 150000 | 2777.7778
| b | Travel | Assuming all require | 30 | 1500 | 1 | 100% | 45000 | 833.3333
| c | Lodging | Assuming all require | 30 | 4000 | 6 | 100% | 720000 | 13333.3333
| d | Local Travel and DSA | all 40 | 40 | 1000 | 6 | 100% | 240000 | 4444.4444
| e | Facilitation |  | 0 | 45000 | 0 | 100% | 0 | 0
| f | Sound and Recording | 2 days | 1 | 10000 | 5 | 100% | 50000 | 925.9259
| g | Reporting and printing | Documentation | 1 | 5000 | 5 | 100% | 25000 | 462.963
| h | Miscellaneous |  | 40 | 400 | 5 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 1310000 | 24259.2593
|  |  | Grand Total |  |  |  |  | 1506000 | 27888.8889 | 37650 | 697.2222

## 1.3
| 1.3 | Supportive Supervision to ensure quality implementation | Year 1 | Year 2 | Year 3 | Total
|  | Supportive Supervision | 791583.3333 | 1279950 | 1547720 | 3619253.3333
|  | Sub Total | 791583.3333 | 1279950 | 1547720 | 3619253.3333
Work Plan
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
1.3.1 a Supportive Supervision
| 1 | Consultation & proposal discussion with Med College/ agencies for monitoring and supportive supervision - 1 Event | [10 empty] | 3 | 3 | 6 | 3 |  | 9
| 2 | Orientation and briefing x 9 States (9 Events) | [11 empty] | 3 | 3 | 6 |  | 9
| 3 | Half Yearly review meeting with monitors and sharing (2 times a year x 9 States)- 18 events per year | [13 empty] | 6 | 12 | 18
| 4 | Supportive supervision cum monitoring visits. 12 visits by 10 monitors per year for 2 years in 9 States @ INR 28,500 per visit | [13 empty] | 540 | 1080 | 1620
| 5 | Support capacity building for supportive supervision/ field monitoring through consultants | [8 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| 1.3.1 a Supportive Supervision | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Consultation & proposal discussion with Med College/ agencies for monitoring and supportive supervision - 1 Event |  | 1 | 54300 | 1 | 25 | 1357500 | 25138.8889 |  |  |  | 75416.6667 | 75416.6667 | 150833.3333 | 75416.6667 |  | 226250
| 2 | Orientation and briefing x 9 States (9 Events) |  | 1 | 54300 | 1 | 25 | 1357500 | 25138.8889 |  |  |  |  | 75416.6667 | 75416.6667 | 150833.3333 |  | 226250
| 3 | Half Yearly review meeting with monitors and sharing (2 times a year x 9 States)- 18 events per year |  | 1 | 54300 | 1 | 25 | 1357500 | 25138.8889 | [5 empty] | 0 | 150833.3333 | 301666.6667 | 452500
| 4 | Supportive supervision cum monitoring visits. 12 visits by 10 monitors per year for 2 years in 9 States @ INR 28,500 per visit |  | 1 | 45522000 | 1 | 1 | 45522000 | 843000 | [6 empty] | 281000 | 562000 | 843000
| 5 | support capacity building for supportive supervision/ field monitoring through consultants |  | 12 | 212000 | 12 | 1 | 30528000 | 565333.3333 |  | 141333.3333 | 141333.3333 | 141333.3333 | 141333.3333 | 565333.3333 | 621866.6667 | 684053.3333 | 1871253.3333
|  | Subtotal | [5 empty] | 4072500 | 75416.6667 |  | 141333.3333 | 141333.3333 | 216750 | 292166.6667 | 791583.3333 | 1279950 | 1547720 | 3619253.3333
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| Grand Totals | [9 empty] | Year 1 |  |  |  | 0 | Year 2 | Year 3 | Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1.3 | Supportive Supervision to ensure quality implementation | [8 empty] | 141333.3333 | 141333.3333 | 216750 | 292166.6667 | 791583.3333 | 1279950 | 1547720 | 3619253.3333
Budget Assumptions
1.3.1 b Supportive Supervision
|  | Activity | Unit | Unit Cost INR | Persona | Numbers | Percentage | INR | USD
|  | Travel | 10 | 8000 | 1 | 1 | 100% | 80000 | 1481.4815
|  | Lodging | 10 | 20000 | 1 | 1 | 100% | 200000 | 3703.7037
|  | Misc | 2 | 500 | 1 | 1 | 100% | 1000 | 18.5185
|  | Subtotal | [5 empty] | 281000 | 5203.7037
|  | Grand Total | [5 empty] | 45522000 | 843000
281000
1.3.1 a Supportive Supervision
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 4 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 260000 | 4814.8148
State Participants
| a | Venue and Hall |  | 25 | 1000 | 3 | 100% | 75000 | 1388.8889
| b | Travel | Outstation participants | 20 | 5000 | 1 | 100% | 100000 | 1851.8519
| c | Lodging | Outstation participants | 20 | 10000 | 3 | 100% | 600000 | 11111.1111
| d | Local Travel and DSA | Outstation participants | 25 | 1500 | 3 | 100% | 112500 | 2083.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 25 | 400 | 3 | 100% | 30000 | 555.5556
|  |  | Sub Total |  |  |  |  | 1097500 | 20324.0741
|  |  | Grand Total |  |  |  |  | 1357500 | 25138.8889 | 54300 | 1005.5556

## 1.4
| 1.4 | Implement EVM improvement plans | Year 1 | Year 2 | Year 3 | Total
| 1.4.1 | EVMs Conducted and PIPs implemented in Larger states | 121333.3333 | 617759.2593 | 1153018.5185 | 1892111.1111
| 1.4.2 | Nationwide rollout of the national cold chain MIS | 186111.1111 | 287555.5556 | 459833.3333 | 933500
| 1.4.3 | Integration of VLM system based on existing models | 134722.2222 | 367462.963 | 204222.2222 | 706407.4074
|  | Sub Total | 442166.6667 | 1272777.7778 | 1817074.0741 | 3532018.5185
Work Plan
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
1.4.1 EVMs Conducted and PIPs implemented in Larger states
| 1 | Undertake Effective Vaccine Management (EVM) mission (Training, assessment, supportive supervision during assessment) in 9 States | [10 empty] | 1 |  | 1 | 4 | 4 | 9
| 2 | Undertake one National EVM mission (Training, assessment, supportive supervision during assessment) | [14 empty] | 1 | 1
| 3 | Development of National improvement plan (IP) | [14 empty] | 1 | 1
| 4 | Development of state improvement plans & inclusion in state PIP (9 States) | [11 empty] | 1 | 1 | 4 | 4 | 9
| 5 | Annual review meetings to follow up on progress/ CCL improvements (National) - 2 reviews in 3 years period. | [13 empty] | 1 | 1 | 2
| 6 | Review meetings to follow up on progress/ CCL improvements (9 States) - 12 (2 reviews for 3 states & 1 review for 6 states over a period of 3 years) | [13 empty] | 2 | 10 | 12
1.4.2 Nationwide rollout of the national cold chain MIS
| 1 | Consultation meeting with state/ national staff - 1 event | [11 empty] | 1 | 1 |  |  | 1
| 2 | State level annual review meetings - 18 events (2 Review over 3 years period | [13 empty] | 6 | 12 | 18
| 3 | Development of additional module - One contract | [11 empty] | 1 | 1 |  |  | 1
| 4 | National review meetings 2 Events | [10 empty] | 1 |  | 1 |  | 1 | 2
1.4.3 Integration of VLM system based on existing models
| 1 | Consultation meeting with national & state staff/ experts- 1 national event | [10 empty] | 1 |  | 1 |  |  | 1
| 2 | Develop VLMIS pilot tool and implementation in 1 GMSD/ states/ districts | [11 empty] | 0 |  | 1 |  | 1
| 3 | Review meetings- 3 events, bi-monthly to identify bugs, tweak features, reporting etc | [13 empty] | 3 |  | 3
| 4 | National ToT for 9 States / 4 Government Medical Store Depots (GMSDs) | [13 empty] | 1 |  | 1
| 5 | Organise /review 9 State level trainings | [13 empty] | 3 | 6 | 9
| 6 | National level review meetings - 2 events in 3 years (To be carried out along with NCCMIS reviews)
| 7 | State level half yearly review meetings in 9 States - 18 events (To be jointly carried out with NCCMIS reviews)
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| 1.4.1 EVMs Conducted and PIPs implemented in Larger states | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Undertake Effective Vaccine Management (EVM) mission (Training, assessment, supportive supervision during assessment) in 9 States |  | 1 | 109100 | 1 | 40 | 4364000 | 80814.8148 |  |  |  | 80814.8148 |  | 80814.8148 | 323259.2593 | 323259.2593 | 727333.3333
| 2 | Undertake one National EVM mission (Training, assessment, supportive supervision during assessment) |  | 1 | 8625000 | 1 | 1 | 8625000 | 159722.2222 | [5 empty] | 0 | 0 | 159722.2222 | 159722.2222
| 3 | Development of National improvement plan (IP) |  | 1 | 69375 | 1 | 40 | 2775000 | 51388.8889 | [5 empty] | 0 | 0 | 51388.8889 | 51388.8889
| 4 | Development of state improvement plans & inclusion in state PIP (9 States) |  | 1 | 54700 | 1 | 40 | 2188000 | 40518.5185 |  |  |  |  | 40518.5185 | 40518.5185 | 162074.0741 | 162074.0741 | 364666.6667
| 5 | Annual review meetings to follow up on progress/ CCL improvements (National) - 2 reviews in 3 years period. |  | 1 | 69375 | 1 | 40 | 2775000 | 51388.8889 | [5 empty] | 0 | 51388.8889 | 51388.8889 | 102777.7778
| 6 | Review meetings to follow up on progress/ CCL improvements (9 States) - 12 (2 reviews for 3 states & 1 review for 6 states over a period of 3 years) |  | 1 | 54700 | 1 | 40 | 2188000 | 40518.5185 | [5 empty] | 0 | 81037.037 | 405185.1852 | 486222.2222
|  | Subtotal | [8 empty] | 0 | 0 | 80814.8148 | 40518.5185 | 121333.3333 | 617759.2593 | 1153018.5185 | 1892111.1111
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| 1.4.2 Nationwide rollout of the national cold chain MIS | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Activity | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Consultation meeting with state/ national staff - 1 event |  | 1 | 69375 | 1 | 40 | 2775000 | 51388.8889 |  |  |  |  | 51388.8889 | 51388.8889 |  |  | 51388.8889
| 2 | State level annual review meetings - 18 events (2 Review over 3 years period |  | 1 | 45950 | 1 | 40 | 1838000 | 34037.037 | [5 empty] | 0 | 204222.2222 | 408444.4444 | 612666.6667
| 3 | Development of additional module - One contract |  | 1 | 9000000 | 1 | 1 | 9000000 | 166666.6667 |  |  |  |  | 83333.3333 | 83333.3333 | 83333.3333 |  | 166666.6667
| 4 | National review meetings 2 Events |  | 1 | 69375 | 1 | 40 | 2775000 | 51388.8889 |  |  |  | 51388.8889 |  | 51388.8889 |  | 51388.8889 | 102777.7778
|  | Subtotal | [8 empty] | 0 | 0 | 51388.8889 | 134722.2222 | 186111.1111 | 287555.5556 | 459833.3333 | 933500
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| Integration of VLM system based on existing models | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Consultation meeting with national & state staff/ experts- 1 national event |  | 1 | 69375 | 1 | 40 | 2775000 | 51388.8889 |  |  |  | 51388.8889 |  | 51388.8889 |  |  | 51388.8889
| 2 | Develop VLMIS pilot tool and implementation in 1 GMSD/ states/ districts |  | 1 | 9000000 | 1 | 1 | 9000000 | 166666.6667 |  |  |  |  | 83333.3333 | 83333.3333 | 83333.3333 |  | 166666.6667
| 3 | Review meetings- 3 events, bi-monthly to identify bugs, tweak features, reporting etc |  | 1 | 45950 | 1 | 40 | 1838000 | 34037.037 | [5 empty] | 0 | 102111.1111 |  | 102111.1111
| 4 | National ToT for 9 States / 4 Government Medical Store Depots (GMSDs) |  | 1 | 107875 | 1 | 40 | 4315000 | 79907.4074 | [5 empty] | 0 | 79907.4074 |  | 79907.4074
| 5 | Organise /review 9 State level trainings |  | 1 | 45950 | 1 | 40 | 1838000 | 34037.037 | [5 empty] | 0 | 102111.1111 | 204222.2222 | 306333.3333
| 6 | National level review meetings - 2 events in 3 years (To be carried out along with NCCMIS reviews) | [12 empty] | 0 | 0 | 0 | 0
| 7 | State level half yearly review meetings in 9 States - 18 events (To be jointly carried out with NCCMIS reviews)
|  | Subtotal | [8 empty] | 0 | 0 | 51388.8889 | 83333.3333 | 134722.2222 | 367462.963 | 204222.2222 | 706407.4074
| Grand Totals | [9 empty] | Year 1 |  |  |  | 0 | Year 2 | Year 3 | Total
[11 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1.4.1 | EVMs Conducted and PIPs implemented in Larger states | [8 empty] | 0 | 0 | 80814.8148 | 40518.5185 | 121333.3333 | 617759.2593 | 1153018.5185 | 1892111.1111
| 1.4.2 | Nationwide rollout of the national cold chain MIS | [8 empty] | 0 | 0 | 51388.8889 | 134722.2222 | 186111.1111 | 287555.5556 | 459833.3333 | 933500
| 1.4.3 | Integration of VLM system based on existing models | [8 empty] | 0 | 0 | 51388.8889 | 83333.3333 | 134722.2222 | 367462.963 | 204222.2222 | 706407.4074
Budget Assumptions
Undertake Effective Vaccine Management (EVM) mission (Training, assessment, supportive supervision during assessment) in 9 States
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 6 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 6 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 2 | 10000 | 6 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 370000 | 6851.8519
State Participants
| a | Venue and Hall |  | 40 | 1000 | 5 | 100% | 200000 | 3703.7037
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 5 | 100% | 300000 | 5555.5556
| e | Facilitation | 1 facilitators | 1 | 10000 | 5 | 100% | 50000 | 925.9259
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 400 | 5 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 2530000 | 46851.8519
|  |  | Total for State EVM orientation |  |  |  | 2900000 | 2900000 | 72500
| a | Travel (TAXI) | Assuming all require | 1 | 4000 | 5 | 100% | 20000 | 370.3704
| b | Lodging/ DSA | Assuming all require | 2 | 10000 | 5 | 100% | 100000 | 1851.8519
| d | Miscellaneous |  | 2 | 500 | 2 | 100% | 2000 | 37.037
|  |  | Sub Total |  |  |  |  | 122000 | 2259.2593
|  |  | Total for EVM field work at state level |  |  |  | Total 12 teams | 1464000 | 27111.1111
|  |  | Total for State EVM |  |  | Total |  | 4364000 | 80814.8148 | 109100
State level annual review meetings - 18 events (2 Review over 3 years period
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 5 | 15000 | 6 | 100% | 450000 | 8333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 5 | 20000 | 1 | 100% | 100000 | 1851.8519
|  | Local Travel |  | 5 | 2500 | 6 | 100% | 75000 | 1388.8889
|  | Lodging+DSA |  | 5 | 10000 | 6 | 100% | 300000 | 5555.5556
|  |  | Sub Total |  |  |  |  | 925000 | 17129.6296
National Participants
| a | Venue and Hall |  | 40 | 2000 | 5 | 100% | 400000 | 7407.4074
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | all 40 | 40 | 2500 | 5 | 100% | 500000 | 9259.2593
| e | Facilitation |  | 1 | 45000 | 5 | 100% | 225000 | 4166.6667
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 3575000 | 66203.7037
|  |  | Total for National EVM Training |  |  |  |  | 4500000 | 83333.3333
Field Visit for National EVM (Team of 2, 5 days in the field) |  |  |  | Persons | Unit Cost | Number | %age | INR | USD
| a | Travel (Air) | Assuming all require | 2 | 20000 | 1 | 100% | 40000 | 740.7407
| b | Lodging | Assuming all require | 2 | 10000 | 5 | 100% | 100000 | 1851.8519
| c | Local Travel (Field) |  | 1 | 4000 | 5 | 100% | 20000 | 370.3704
| d | Miscellaneous |  | 2 | 500 | 5 | 100% | 5000 | 92.5926
|  |  | Sub Total |  |  |  |  | 165000 | 3055.5556
|  |  | Total for EVM Field Work |  |  |  | Total 25 teams | 4125000 | 76388.8889
|  |  | Total for National EVM |  |  |  |  | 8625000 | 159722.2222 | 215625 | 3993.0556
Development of National improvement plan (IP)
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 3 | 15000 | 4 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 4 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 3 | 10000 | 4 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 390000 | 7222.2222
National Participants
| a | Venue and Hall |  | 40 | 2000 | 3 | 100% | 240000 | 4444.4444
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 500 | 3 | 100% | 60000 | 1111.1111
|  |  | Sub Total |  |  |  |  | 2385000 | 44166.6667
|  |  | Grand Total |  |  |  |  | 2775000 | 51388.8889 | 69375
State Level Consultation - Improvement Plan / Review Meeting
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 4 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 260000 | 4814.8148
State Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 40 | 5000 | 1 | 100% | 200000 | 3703.7037
| c | Lodging | Assuming all require | 40 | 10000 | 3 | 100% | 1200000 | 22222.2222
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1928000 | 35703.7037
|  |  | Grand Total |  |  |  |  | 2188000 | 40518.5185 | 54700
National Level Consultation - Improvement Plan / Review Meeting
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 3 | 15000 | 4 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 4 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 3 | 10000 | 4 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 390000 | 7222.2222
National Participants
| a | Venue and Hall |  | 40 | 2000 | 3 | 100% | 240000 | 4444.4444
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 500 | 3 | 100% | 60000 | 1111.1111
|  |  | Sub Total |  |  |  |  | 2385000 | 44166.6667
|  |  | Grand Total |  |  |  |  | 2775000 | 51388.8889 | 69375
State Level Annual NCCMIS Review Meeting
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 4 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 260000 | 4814.8148
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1578000 | 29222.2222
|  |  | Grand Total |  |  |  |  | 1838000 | 34037.037 | 45950
1.2.2 a National Level training of Trainers -ECCVLM
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Master Trainers
| a |  | Technical Expert | 3 | 15000 | 6 | 100% | 270000 | 5000
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 6 | 100% | 45000 | 833.3333
|  | Lodging+DSA |  | 3 | 10000 | 6 | 100% | 180000 | 3333.3333
|  |  | Sub Total |  |  |  |  | 555000 | 10277.7778
National Participants
| a | Venue and Hall |  | 40 | 2000 | 5 | 100% | 400000 | 7407.4074
| b | Travel | Assuming all require | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | all 40 | 40 | 2500 | 5 | 100% | 500000 | 9259.2593
| e | Facilitation |  | 1 | 45000 | 5 | 100% | 225000 | 4166.6667
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 3575000 | 66203.7037
|  |  | Grand Total |  |  |  |  | 4130000 | 76481.4815 | 103250 | 1912.037
National IVLMS training of Trainers
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
International Participation
1 | Experts or Master Trainers
| a |  | Technical Expert | 4 | 15000 | 6 | 100% | 360000 | 6666.6667
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 4 | 20000 | 1 | 100% | 80000 | 1481.4815
|  | Local Travel |  | 4 | 2500 | 6 | 100% | 60000 | 1111.1111
|  | Lodging+DSA |  | 4 | 10000 | 6 | 100% | 240000 | 4444.4444
|  |  | Sub Total |  |  |  |  | 740000 | 13703.7037
National Participants
| a | Venue and Hall |  | 40 | 2000 | 5 | 100% | 400000 | 7407.4074
| b | Travel | Assuming all require | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | all 40 | 40 | 2500 | 5 | 100% | 500000 | 9259.2593
| e | Facilitation |  | 1 | 45000 | 5 | 100% | 225000 | 4166.6667
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 3575000 | 66203.7037
|  |  | Grand Total |  |  |  |  | 4315000 | 79907.4074 | 107875

## 1.5
1.5 | Institutional Capacity building to strengthen the cold chain system | Year 1 | Year 2 | Year 3 | Total
1.5.1 | Build Institutional Capacity of the NCCVMRC | 1903703.7037 | 38888.8889 | 44444.4444 | 1987037.037
1.5.2 | Improve / operationalise existing cold chain equipment & reduce sickness rate. | 1302222.2222 | 200000 | 200000 | 1702222.2222
| Sub Total | 3205925.9259 | 238888.8889 | 244444.4444 | 3689259.2593
Work Plan
[9 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
[9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
1.5.1 Build Institutional Capacity of the NCCVMRC
1 | Walk in Cooler (WIC) / Walk in Freezer (WIF) | [10 empty] | 15 | 15 |  |  | 15
2 | Installation cost for WIC/WIF as per UNICEF Long Term Agreement (LTA) @ INR 300,000 each | [12 empty] | 7 | 8 | 15
3 | Ice-Lined Refrigerators (ILRs) / Deep Freezers (DFs) (400) | [10 empty] | 400 | 400 |  |  | 400
4 | Solar Powered ILRs/ Combined units (150) | [10 empty] | 150 | 150 |  |  | 150
5 | Wireless Temperature Monitoring Devices (US$ 100,000) for 50 Cold Rooms. | [10 empty] | 50 | 50 |  |  | 50
6 | Dataloggers (USB, WHO PQS) for assessments and studies. | [10 empty] | 1000 | 1000 |  |  | 1000
1.5.2 Improve / operationalise existing cold chain equipment & reduce sickness rate.
1 | WIC/WIF spares for 3 GMSDs (US@80,000 per GMSD considering increase in price from 2010. 2010 pricelist enclosed) | [10 empty] | 3 |  |  |  | 3
2 | ILR/DF spares for 2 GMSDs (US$200,000 per GMSD considering increase in price from 2010. 2010 pricelist enclosed) | [10 empty] | 2 |  |  |  | 2
3 | Toolkit (District level) for Cold Chain Technicians (List enclosed) | [10 empty] | 100 |  |  |  | 100
4 | Spare parts for solar combined devices (Tentatively, for 3 GMSDs, for charge controllers, panels, battery, compressors, starting device.) | [10 empty] | 3 |  |  |  | 3
5 | Partnership with technical-academic institutes for research & improvement in performance, safety, reliability and energy efficiency of cold chain equipment and system. | [9 empty] | 1 |  | 1 | 1 | 1 | 3
[9 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
1.5.1 Build Institutional Capacity of the NCCVMRC | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Percentage | INR | USD
1 | Walk in Cooler (WIC) / Walk in Freezer (WIF) |  | 1 | 1900000 | 1 | 1 | 1900000 | 35185.1852 |  |  |  | 527777.7778 | 527777.7778 |  |  | 527777.7778
2 | Installation cost for WIC/WIF as per UNICEF Long Term Agreement (LTA) @ INR 300,000 each |  | 1 | 300000 | 1 | 1 | 300000 | 5555.5556 | [5 empty] | 38888.8889 | 44444.4444 | 83333.3333
3 | Ice-Lined Refrigerators (ILRs) / Deep Freezers (DFs) (400) |  | 1 | 37000 | 1 | 1 | 37000 | 685.1852 |  |  |  | 274074.0741 | 274074.0741 |  |  | 548148.1481
4 | Solar Powered ILRs/ Combined units (150) |  | 1 | 350000 | 1 | 1 | 350000 | 6481.4815 |  |  |  | 972222.2222 | 972222.2222 |  |  | 1944444.4444
5 | Wireless Temperature Monitoring Devices (US$ 100,000) for 50 Cold Rooms. |  | 1 | 108000 | 1 | 1 | 108000 | 2000 |  |  |  | 100000 | 100000 |  |  | 200000
6 | Dataloggers (USB, WHO PQS) for assessments and studies. |  | 1 | 1600 | 1 | 1 | 1600 | 29.6296 |  |  |  | 29629.6296 | 29629.6296 |  |  | 29629.6296
| Subtotal | [7 empty] | 0 | 0 | 0 | 1903703.7037 | 1903703.7037 | 38888.8889 | 44444.4444 | 3333333.3333
[9 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
1.5.2 Improve / operationalise existing cold chain equipment & reduce sickness rate. | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
1 | WIC/WIF spares for 3 GMSDs (US@80,000 per GMSD considering increase in price from 2010. 2010 pricelist enclosed) |  | 1 | 4320000 | 1 | 1 | 4320000 | 80000 |  |  |  | 240000 | 240000 |  |  | 240000
2 | ILR/DF spares for 2 GMSDs (US$200,000 per GMSD considering increase in price from 2010. 2010 pricelist enclosed) |  | 1 | 10800000 | 1 | 1 | 10800000 | 200000 |  |  |  | 400000 | 400000 |  |  | 400000
3 | Toolkit (District level) for Cold Chain Technicians (List enclosed) |  | 1 | 120000 | 1 | 1 | 120000 | 2222.2222 |  |  |  | 222222.2222 | 222222.2222 |  |  | 222222.2222
4 | Spare parts for solar combined devices (Tentatively, for 3 GMSDs, for charge controllers, panels, battery, compressors, starting device.) |  | 1 | 4320000 | 1 | 1 | 4320000 | 80000 |  |  |  | 240000 | 240000 |  |  | 240000
5 | Partnership with technical-academic institutes for research & improvement in performance, safety, reliability and energy efficiency of cold chain equipment and system. |  | 1 | 10800000 | 1 | 1 | 10800000 | 200000 |  |  | 200000 |  | 200000 | 200000 | 200000 | 600000
| Subtotal | [7 empty] | 0 | 0 | 200000 | 1102222.2222 | 1302222.2222 | 200000 | 200000 | 1702222.2222
Grand Totals | [8 empty] | Year 1 |  |  |  | 240000 | Year 2 | Year 3 | Total
[9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
1.5.1 | Build Institutional Capacity of the NCCVMRC | [7 empty] | 0 | 0 | 0 | 1903703.7037 | 1903703.7037 | 38888.8889 | 44444.4444 | 3333333.3333
1.5.2 | Improve / operationalise existing cold chain equipment & reduce sickness rate. | [7 empty] | 0 | 0 | 200000 | 1102222.2222 | 1302222.2222 | 200000 | 200000 | 1702222.2222
Budget Assumptions
Cold Chain Equipment and Spares
| Cold Chain Equipment/ Spares | Numbers | Units | Unit price
Cold Chain Equipment
| WIC/ WIFs |  | 1 | 1900000
| WIC/WIF Installations |  | 1 | 300000
| ILRs/ DFs |  | 1 | 37000
| Solar DFs |  | 1 | 350000
| Wireless Temperature Monitoring Devices |  | 1 | 108000
| Dataloggers (USM/PQS) for assessments |  | 1 | 1600
Spares | WIC/WIF spares for 2 GMSDs |  | 1 | 4320000
| ILR/DFs spares for 2 GMSDs |  | 1 | 10800000
| Toolkits for district mechanics |  | 1 | 120000
| Spare parts for solar combined units for 4 GMSDs |  | 1 | 4320000
Total
Partnership and Innovations
| Description |  | Units | Unit price
1 | Partnership with acedemic / technical institutes for research & improvements in technology/ performance/ safety and reliability of cold chain equipment. |  | 1 | 10800000
Total

## 3.1
| 3.1 | Implement Multi pronged national BCC strategy development and operational plans | Year 1 | Year 2 | Year 3 | Total
|  |  | 699333.3333 | 457407.4074 | 679629.6296 | 1836370.3704
|  | Sub Total | 699333.3333 | 457407.4074 | 679629.6296 | 1836370.3704
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
|  | Implement Multi pronged national BCC strategy development and operational plans | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1 | Support 12 states in developing evidence-based communication strategy plans through strategy development workshops
|  | Regional/ State workshops | [9 empty] | 4 | 5 | 9 |  |  | 9
| 2 | State-level review meetings on the progress of planned activities (9) | [12 empty] | 9 | 9 | 18
| 3 | National-level review meetings for lessons learned exchanges | [12 empty] | 1 | 1 | 2
| 4 | Strengthening monitoring and reporting capacity of BCC managers
|  | Regional/ State workshops | [9 empty] | 4 | 5 | 9 |  |  | 9
| 6 | Rapid assessment for evidence gathering in selected states | [12 empty] | 12 | 12 | 24
| 7 | Digital documentation of communication activities in selected states | [13 empty] | 12 | 12
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| Implement Multi pronged national BCC strategy development and operational plans | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Support 12 states in developing evidence-based communication strategy plans through strategy development workshops | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
|  | Regional/ State workshops |  | 1 | 52450 | 1 | 40 | 2098000 | 38851.8519 |  |  | 155407.4074 | 194259.2593 | 349666.6667 |  |  | 349666.6667
| 2 | State-level review meetings on the progress of planned activities (9) |  | 1 | 52450 | 1 | 40 | 2098000 | 38851.8519 |  |  |  |  | 0 | 349666.6667 | 349666.6667 | 699333.3333
| 3 | National-level review meetings for lessons learned exchanges |  | 1 | 72625 | 1 | 40 | 2905000 | 53796.2963 |  |  |  |  | 0 | 53796.2963 | 53796.2963 | 107592.5926
| 4 | Strengthening monitoring and reporting capacity of BCC managers | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
|  | Regional/ State workshops |  | 1 | 52450 | 1 | 40 | 2098000 | 38851.8519 |  |  | 155407.4074 | 194259.2593 | 349666.6667 |  |  | 349666.6667
| 6 | Rapid assessment for evidence gathering in selected states |  | 1 | 242750 | 1 | 1 | 242750 | 4495.3704 | [5 empty] | 53944.4444 | 53944.4444 | 107888.8889
| 7 | Digital documentation of communication activities in selected states |  | 1 | 1000000 | 1 | 1 | 1000000 | 18518.5185 | [6 empty] | 222222.2222 | 222222.2222
0
|  | Subtotal | [7 empty] | 0 | 0 | 310814.8148 | 388518.5185 | 699333.3333 | 457407.4074 | 679629.6296 | 1836370.3704
| Grand Totals | [8 empty] | Year 1 |  |  |  | 349666.6667 | Year 2 | Year 3 | Total
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 3.1 | Implement Multi pronged national BCC strategy development and operational plans | [7 empty] | 0 | 0 | 310814.8148 | 388518.5185 | 699333.3333 | 457407.4074 | 679629.6296 | 1836370.3704
Budget Assumptions
National Level workshop on BCC startegy Development with state participation
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 4 | 15000 | 4 | 100% | 240000 | 4444.4444
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 4 | 20000 | 1 | 100% | 80000 | 1481.4815
|  | Local Travel |  | 4 | 2500 | 4 | 100% | 40000 | 740.7407
|  | Lodging+DSA |  | 4 | 10000 | 4 | 100% | 160000 | 2962.963
|  |  | Sub Total |  |  |  |  | 520000 | 9629.6296
National Participants
| a | Venue and Hall |  | 40 | 2000 | 3 | 100% | 240000 | 4444.4444
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 500 | 3 | 100% | 60000 | 1111.1111
|  |  | Sub Total |  |  |  |  | 2385000 | 44166.6667
|  |  | Grand Total |  |  |  |  | 2905000 | 53796.2963 | 72625
State Level Workshop on Development of Communication Strategy
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 4 | 15000 | 4 | 100% | 240000 | 4444.4444
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 4 | 20000 | 1 | 100% | 80000 | 1481.4815
|  | Local Travel |  | 4 | 2500 | 4 | 100% | 40000 | 740.7407
|  | Lodging+DSA |  | 4 | 10000 | 4 | 100% | 160000 | 2962.963
|  |  | Sub Total |  |  |  |  | 520000 | 9629.6296
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1578000 | 29222.2222
|  |  | Grand Total |  |  |  |  | 2098000 | 38851.8519 | 52450
Contract to external agency [Orientation of Assessors for evidence generation at State Level]
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 1 | 15000 | 1 | 100% | 15000 | 277.7778
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 1 | 20000 | 0 | 100% | 0 | 0
|  | Local Travel |  | 1 | 2500 | 1 | 100% | 2500 | 46.2963
|  | Lodging+DSA |  | 1 | 10000 | 0 | 100% | 0 | 0
|  |  | Sub Total |  |  |  |  | 17500 | 324.0741
State participants
| a | Venue and Hall |  | 15 | 750 | 1 | 100% | 11250 | 208.3333
| b | Travel | Assuming all require | 10 | 1500 | 1 | 100% | 15000 | 277.7778
| c | Lodging | Assuming all require | 10 | 4000 | 1 | 100% | 40000 | 740.7407
| d | Local Travel and DSA | Assuming all require | 15 | 1000 | 1 | 100% | 15000 | 277.7778
| e | Facilitation | 1 facilitators | 1 | 45000 | 0 | 100% | 0 | 0
| f | Sound and Recording |  | 1 | 10000 | 1 | 100% | 10000 | 185.1852
| g | Reporting and printing | Documentation | 1 | 5000 | 1 | 100% | 5000 | 92.5926
| h | Miscellaneous |  | 10 | 400 | 1 | 100% | 4000 | 74.0741
|  |  | Sub Total |  |  |  |  | 100250 | 1856.4815 | 2506.25
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
| a | Travel (Taxi) | 5 teams of two persons | 5 | 4000 | 2 | 100% | 40000 | 740.7407
| b | Lodging/ DSA | Assuming all require | 10 | 4000 | 2 | 100% | 80000 | 1481.4815
| c | Reporting & documentation |  | 1 | 5000 | 1 | 100% | 5000 | 92.5926
|  |  | Sub Total |  |  |  |  | 125000 | 2314.8148
|  |  | Grand Total |  |  |  |  | 242750 | 2180.5556

## 3.2
| 3.2 | Enhance Infrastructure and HR Capacity to develop and implement BCC strategies | Year 1 | Year 2 | Year 3 | Total
|  |  | 3262629.6296 | 3571333.3333 | 3517222.2222 | 10351185.1852
|  | Sub Total | 3262629.6296 | 3571333.3333 | 3517222.2222 | 10351185.1852
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
|  | Enhance Infrastructure and HR Capacity to develop and implement BCC strategies | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1 | Support strengthening of state BCC units/set-ups
|  | Support specialized HR for BCC capacity development and implementation in 9 states | [7 empty] | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
| 2 | Development of BCC tools and dissemination in 9 states (@120000) | [10 empty] | 9 | 9 | 9 | 9 | 9
| 3 | Facilitate inter-state exposure visits for learning and experience sharing of BCC personnel from 11 states in two batches | [8 empty] | 1 | 1 |  | 2
| 4 | Strengthen systems for effective inter personal communication and social mobilization using Polio social mobilization network (7000 x 2500 per month x 3 years /50%) | [7 empty] | X | X | X | X |  | X | X
|  | Support the capacity strengthening of selected CBOs/SHGs/State training agencies for effective IPC and community mobilization especially from underserved areas in 9 states | [9 empty] | 6 |  | 6 | 6 | 6
| 6 | Increase IPC skills capacity of 80% of Trainers of Frontline Workers in 12 states (340 trainers @ 3 trainers per district) | [12 empty] | 8 | 4
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| Enhance Infrastructure and HR Capacity to develop and implement BCC strategies | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 1 | Support strengthening of state BCC units/set-ups | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
|  | Support specialized HR for BCC capacity development and implementation in 9 states |  | 1 | 1250000 | 1 | 1 | 1250000 | 23148.1481 | 208333.3333 | 208333.3333 | 208333.3333 | 208333.3333 | 833333.3333 | 916666.6667 | 1008333.3333 | 2758333.3333
| 2 | Development of BCC tools and dissemination in 9 states (@120000) |  | 1 | 1200000 | 1 | 1 | 1200000 | 22222.2222 |  |  |  | 200000 | 200000 | 200000 | 200000 | 600000
| 3 | Facilitate inter-state exposure visits for learning and experience sharing of BCC personnel from 11 states in two batches |  | 1 | 1787000 | 1 | 1 | 1787000 | 33092.5926 |  | 33092.5926 | 33092.5926 |  | 66185.1852 |  |  | 66185.1852
| 4 | Strengthen systems for effective inter personal communication and social mobilization using Polio social mobilization network (7000 x 2500 per month x 3 years /50%) |  | 7000 | 2500 | 12 | 50% | 105000000 | 1944444.4444 | 486111.1111 | 486111.1111 | 486111.1111 | 486111.1111 | 1944444.4444 | 1944444.4444 | 1944444.4444 | 5833333.3333
|  | Support the capacity strengthening of selected CBOs/SHGs/State training agencies for effective IPC and community mobilization especially from underserved areas in 9 states |  | 1 | 1968000 | 1 | 1 | 1968000 | 36444.4444 |  |  | 218666.6667 |  | 218666.6667 | 218666.6667 | 218666.6667 | 656000
| 6 | Increase IPC skills capacity of 80% of Trainers of Frontline Workers in 12 states (340 trainers @ 3 trainers per district) |  | 1 | 1968000 | 1 | 1 | 1968000 | 36444.4444 | [5 empty] | 291555.5556 | 145777.7778 | 437333.3333
|  | Subtotal | [7 empty] | 694444.4444 | 727537.037 | 946203.7037 | 894444.4444 | 3262629.6296 | 3571333.3333 | 3517222.2222 | 10351185.1852
Budget Assumptions
Capacity building for effective IPC & Community Mobilisation @ state level
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 3 | 15000 | 4 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 4 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 3 | 10000 | 4 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 390000 | 7222.2222
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1578000 | 29222.2222
|  |  | Grand Total |  |  |  |  | 1968000 | 36444.4444
Exchange visits for learning experience followed with one day workshop
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
| b | Travel (Air) | Assuming all require | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 30 | 1500 | 3 | 100% | 135000 | 2500
| h | Miscellaneous |  | 30 | 400 | 3 | 100% | 36000 | 666.6667
|  |  | Sub Total |  |  |  |  | 1671000 | 30944.4444
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
| a | Venue and Hall |  | 40 | 1000 | 1 | 100% | 40000 | 740.7407
| b | Travel | Assuming all require | 30 | 5000 | 0 | 100% | 0 | 0
| c | Lodging | Assuming all require | 30 | 10000 | 0 | 100% | 0 | 0
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 0 | 100% | 0 | 0
| e | Facilitation | 1 facilitators | 1 | 10000 | 1 | 100% | 10000 | 185.1852
| f | Sound and Recording |  | 1 | 25000 | 1 | 100% | 25000 | 462.963
| g | Reporting and printing | Documentation | 1 | 25000 | 1 | 100% | 25000 | 462.963
| h | Miscellaneous |  | 40 | 400 | 1 | 100% | 16000 | 296.2963
|  |  | Sub Total |  |  |  |  | 116000 | 2148.1481
|  |  | Grand Total |  |  |  |  | 1787000 | 33092.5926 | 44675

## 3.3
| 3.3 | Develop and Broadcast immunisation messages through mass media | Year 1 | Year 2 | Year 3 | Total
|  |  | 1948980.5556 | 1902684.2593 | 1763003.7037 | 5614668.5185
|  | Sub Total | 1948980.5556 | 1902684.2593 | 1763003.7037 | 5614668.5185
Work Plan
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
|  | Develop and Broadcast immunisation messages through mass media | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 1 | Produce Two TV and radio PSAs highlighting key messages on RI
|  | Professional agency fee for development of 2 TV and radio PSAs (As per UNICEF LTA rates) | [10 empty] | 1 |  |  | 1
| 2 | Pretesting fees for 2 TV and radio PSAs (Contract to external agency to pretest in 3 states for each of two TV spots) | [10 empty] | 1 |  |  | 1
| 3 | Dubbing, duplication and distribution of 4 PSAs into 4 different Indian languages | [11 empty] | 8 | 8 | 8 |  | 8
| 4 | Media planning and purchase of airtime for PSAs (Two TV and two radio spots braodcasting multiple times in 5 languages across 12 states - Contract to external agency) | [9 empty] | X | X | X |  | X | X
|  | IEC Prototypes will be developed to enable Center and state for public branding of RI (Contract to external agency, as per UNICEF LTA rates) | [13 empty] | 1 |  | 1
| 6 | Pretesting fees | [13 empty] | 6 |  | 6
|  | Support development and organisation of mid-media activities (432 events) in high-focus districts in 12 states (Contract to external agency) | [11 empty] | 48 | 48 | 192 | 192 | 432
|  | Produce an advocacy film (promo) on routine immunization highlighting the milestones achieved so far in RI (2-3 minutes in duration) which can be used on several platforms (Contyract to external agency as per UNICEF LTA) | [11 empty] | 1
[11 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
| Develop and Broadcast immunisation messages through mass media | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  |  | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 3.3.1 | Produce Two TV and radio PSAs highlighting key messages on RI | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 |  | 0
|  | Professional agency fee for development of 2 TV and radio PSAs (As per UNICEF LTA rates) |  | 1 | 5000000 | 1 | 1 | 5000000 | 92592.5926 |  |  |  | 92592.5926 |  | 92592.5926 | 92592.5926 |  | 185185.1852
|  | Pretesting fees for 2 TV and radio PSAs (Contract to external agency to pretest in 3 states for each of two TV spots) |  | 1 | 242750 | 1 | 1 | 242750 | 4495.3704 |  |  |  | 4495.3704 |  | 4495.3704 | 4495.3704 |  | 8990.7407
|  | Dubbing, duplication and distribution of 4 PSAs into 4 different Indian languages |  | 1 | 100000 | 1 | 1 | 100000 | 1851.8519 |  |  |  |  | 14814.8148 | 14814.8148 | 14814.8148 |  | 29629.6296
| 3.3.2 | Media planning and purchase of airtime for PSAs (Two TV and two radio spots braodcasting multiple times in 5 languages across 12 states - Contract to external agency) |  | 1 | 285606600 | 1 | 1 | 285606600 | 5289011.1111 |  |  | 587667.9012 | 587667.9012 | 587667.9012 | 1763003.7037 | 1763003.7037 | 1763003.7037 | 5289011.1111
| 3.3.3 | IEC Prototypes will be developed to enable Center and state for public branding of RI (Contract to external agency, as per UNICEF LTA rates) |  | 1 | 1500000 | 1 | 1 | 1500000 | 27777.7778 | [5 empty] | 0 | 27777.7778 |  | 27777.7778
|  | Pretesting fees |  | 1 | 242750 | 1 | 1 | 242750 | 4495.3704 | [6 empty] | 26972.2222 |  | 26972.2222
| 3.3.4 | Support development and organisation of mid-media activities (432 events) in high-focus districts in 12 states (Contract to external agency) |  | 1 | 10000 | 1 | 1 | 10000 | 185.1852 |  |  |  |  | 8888.8889 | 8888.8889 | 35555.5556 | 35555.5556 | 80000
| 3.3.5 | Produce an advocacy film (promo) on routine immunization highlighting the milestones achieved so far in RI (2-3 minutes in duration) which can be used on several platforms (Contyract to external agency as per UNICEF LTA) |  | 1 | 4000000 | 1 | 1 | 4000000 | 74074.0741 |  |  |  |  | 74074.0741 | 74074.0741 |  |  | 74074.0741
|  | Subtotal | [8 empty] | 0 | 587667.9012 | 684755.8642 | 676556.7901 | 1948980.5556 | 1902684.2593 | 1763003.7037 | 5614668.5185
Budget Assumptions
National Level Consultation Meeting with States/ Review Meetings during pilot implementation
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 3 | 15000 | 4 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 4 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 3 | 10000 | 4 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 390000 | 7222.2222
National Participants
| a | Venue and Hall |  | 40 | 2000 | 3 | 100% | 240000 | 4444.4444
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 500 | 3 | 100% | 60000 | 1111.1111
|  |  | Sub Total |  |  |  |  | 2385000 | 44166.6667
|  |  | Grand Total |  |  |  |  | 2775000 | 51388.8889
State Level Training Programmes
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 4 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 260000 | 4814.8148
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1578000 | 29222.2222
|  |  | Grand Total |  |  |  |  | 1838000 | 34037.037
National training of Trainers
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
International Participation
1 | Experts or Master Trainers
| a |  | Technical Expert | 4 | 15000 | 6 | 100% | 360000 | 6666.6667
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 4 | 20000 | 1 | 100% | 80000 | 1481.4815
|  | Local Travel |  | 4 | 2500 | 6 | 100% | 60000 | 1111.1111
|  | Lodging+DSA |  | 4 | 10000 | 6 | 100% | 240000 | 4444.4444
|  |  | Sub Total |  |  |  |  | 740000 | 13703.7037
National Participants
| a | Venue and Hall |  | 40 | 2000 | 5 | 100% | 400000 | 7407.4074
| b | Travel | Assuming all require | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging | Assuming all require | 30 | 10000 | 5 | 100% | 1500000 | 27777.7778
| d | Local Travel and DSA | all 40 | 40 | 2500 | 5 | 100% | 500000 | 9259.2593
| e | Facilitation |  | 1 | 45000 | 5 | 100% | 225000 | 4166.6667
| f | Sound and Recording |  | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| g | Reporting and printing | Documentation | 1 | 25000 | 5 | 100% | 125000 | 2314.8148
| h | Miscellaneous |  | 40 | 500 | 5 | 100% | 100000 | 1851.8519
|  |  | Sub Total |  |  |  |  | 3575000 | 66203.7037
|  |  | Grand Total |  |  |  |  | 4315000 | 79907.4074
Contract to external agency [Pretesting of PSAs in 3 states]
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 1 | 15000 | 1 | 100% | 15000 | 277.7778
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 1 | 20000 | 0 | 100% | 0 | 0
|  | Local Travel |  | 1 | 2500 | 1 | 100% | 2500 | 46.2963
|  | Lodging+DSA |  | 1 | 10000 | 0 | 100% | 0 | 0
|  |  | Sub Total |  |  |  |  | 17500 | 324.0741
State participants
| a | Venue and Hall |  | 15 | 750 | 1 | 100% | 11250 | 208.3333
| b | Travel | Assuming all require | 10 | 1500 | 1 | 100% | 15000 | 277.7778
| c | Lodging | Assuming all require | 10 | 4000 | 1 | 100% | 40000 | 740.7407
| d | Local Travel and DSA | Assuming all require | 15 | 1000 | 1 | 100% | 15000 | 277.7778
| e | Facilitation | 1 facilitators | 1 | 45000 | 0 | 100% | 0 | 0
| f | Sound and Recording |  | 1 | 10000 | 1 | 100% | 10000 | 185.1852
| g | Reporting and printing | Documentation | 1 | 5000 | 1 | 100% | 5000 | 92.5926
| h | Miscellaneous |  | 10 | 400 | 1 | 100% | 4000 | 74.0741
|  |  | Sub Total |  |  |  |  | 100250 | 1856.4815
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
| a | Travel (Taxi) | 5 teams of two persons | 5 | 4000 | 2 | 100% | 40000 | 740.7407
| b | Lodging/ DSA | Assuming all require | 10 | 4000 | 2 | 100% | 80000 | 1481.4815
| c | Reporting & documentation |  | 1 | 5000 | 1 | 100% | 5000 | 92.5926
|  |  | Sub Total |  |  |  |  | 125000 | 2314.8148
|  |  | Grand Total |  |  |  |  | 242750 | 2180.5556
| Medium | rate per second | Current Clip Seconds | Number | Total | Remarks | Year 1 | Year 2 | Year 3 | Total
| Network TV | 4400 | 40 | 1200 | 211200000 | Telecast Twice a day for 60 days in 10 Networks | 70400000 | 70400000 | 70400000 | 211200000
| Radio | 50 | 40 | 29160 | 58320000 | Telecast 6 times a day, 180 days, 9 states, 3 radio channels | 19440000 | 19440000 | 19440000 | 58320000
| Cinema | 540000 (25 Theatre) - 9 |  | 9 | 4860000 | 25 Theatres, 9 states | 4860000 | 5346000 | 5880600 | 16086600
[6 empty] | Total | 94700000 | 95186000 | 95720600 | 285606600

## 3.4
| 3.4 | Promote advocacy with media for creating an enabling environment for increasing demand for RI services | Year 1 | Year 2 | Year 3 | Total
|  |  | 1146944.4444 | 1182481.4815 | 161370.3704 | 2490796.2963
|  | Sub Total | 1146944.4444 | 1182481.4815 | 161370.3704 | 2490796.2963
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
|  | Promote advocacy with media for creating an enabling environment for increasing demand for RI services | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| 3.4.1 | Hold national and state-level media workshops to sensitize electronic and print media personnel
|  | National workshop | [8 empty] | 1
|  | State workshops in 9 states | [9 empty] | 3 | 3 | 6 | 12 |  | 18
| 3.4.2 | Media monitoring and tracking
|  | Professional fees for development of a media monitoring and tracking framework | [10 empty] | 1
|  | 9 state workshops on media monitoring and tracking framework | [10 empty] | 3 | 3 | 3 | 3 | 9
| 3.4.3 | Advocacy workshops with Parliamentarians/CSOs/Pvt Sec
|  | National workshop | [9 empty] | 1 |  | 1 |  |  | 1
|  | 9 state workshops | [8 empty] | 3 | 3 | 3 | 9 | 9
| 3.4.4 | Media handling Training of AEFI committee members
|  | National AEFI Committee | [8 empty] | 1
|  | AEFI committee members in 9 States | [8 empty] | 3 | 3 | 3 | 9 | 9 |  | 18
| 3.4.5 | Partnership with media institutions/associations for leveraging information for reaching remote areas (Under existing MoU with Indira Gandhi National Open University, raise contract to support the development of modules on Immunisation & communication) | [10 empty] | 1 |  | 1 | 1
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Total
| Promote advocacy with media for creating an enabling environment for increasing demand for RI services | [8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
|  | Name of the Technical position | Remark | Unit | Unit Cost per month | Number of Months | Number of Years | INR | USD
| 3.4.1 | Hold national and state-level media workshops to sensitize electronic and print media personnel | [5 empty] | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
|  | National workshop |  | 1 | 2775000 | 1 | 1 | 2775000 | 51388.8889 |  | 51388.8889 |  |  | 51388.8889 |  |  | 51388.8889
|  | State workshops in 9 states |  | 1 | 1838000 | 1 | 1 | 1838000 | 34037.037 |  |  | 102111.1111 | 102111.1111 | 204222.2222 | 408444.4444 |  | 612666.6667
| 3.4.2 | Media monitoring and tracking |  | 1 |  | 1 | 1 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0
|  | Professional fees for development of a media monitoring and tracking framework |  | 1 | 784000 | 1 | 1 | 784000 | 14518.5185 |  |  |  | 14518.5185 | 14518.5185 |  |  | 14518.5185
|  | 9 state workshops on media monitoring and tracking framework |  | 1 | 1838000 | 1 | 1 | 1838000 | 34037.037 |  |  |  | 102111.1111 | 102111.1111 | 102111.1111 | 102111.1111 | 306333.3333
| 3.4.3 | Advocacy workshops with Parliamentarians/CSOs/Pvt Sec |  | 1 |  | 1 | 1 | 0 | 0 | [7 empty] | 0
|  | National workshop |  | 1 | 2775000 | 1 | 1 | 2775000 | 51388.8889 |  |  | 51388.8889 |  | 51388.8889 |  |  | 51388.8889
|  | 9 state workshops |  | 1 | 1838000 | 1 | 1 | 1838000 | 34037.037 |  | 102111.1111 | 102111.1111 | 102111.1111 | 306333.3333 | 306333.3333 |  | 612666.6667
| 3.4.4 | Media handling Training of AEFI committee members | [11 empty] | 0 |  |  | 0
|  | National AEFI Committee |  | 1 | 2775000 | 1 | 1 | 2775000 | 51388.8889 |  | 51388.8889 |  |  | 51388.8889 |  |  | 51388.8889
|  | AEFI committee members in 9 States |  | 1 | 1838000 | 1 | 1 | 1838000 | 34037.037 |  | 102111.1111 | 102111.1111 | 102111.1111 | 306333.3333 | 306333.3333 |  | 612666.6667
| 3.4.5 | Partnership with media institutions/associations for leveraging information for reaching remote areas (Under existing MoU with Indira Gandhi National Open University, raise contract to support the development of modules on Immunisation & communication) |  | 1 | 3200000 | 1 | 1 | 3200000 | 59259.2593 |  |  |  | 59259.2593 | 59259.2593 | 59259.2593 | 59259.2593 | 177777.7778
|  | Subtotal | [7 empty] | 0 | 307000 | 357722.2222 | 482222.2222 | 1146944.4444 | 1182481.4815 | 161370.3704 | 2490796.2963
Budget Assumptions
National Level Workshop/ Meeting / Consultation
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
Experts Participation
1 | Experts or Participants
| a |  | Technical Expert | 3 | 15000 | 4 | 100% | 180000 | 3333.3333
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 3 | 20000 | 1 | 100% | 60000 | 1111.1111
|  | Local Travel |  | 3 | 2500 | 4 | 100% | 30000 | 555.5556
|  | Lodging+DSA |  | 3 | 10000 | 4 | 100% | 120000 | 2222.2222
|  |  | Sub Total |  |  |  |  | 390000 | 7222.2222
National Participants
| a | Venue and Hall |  | 40 | 2000 | 3 | 100% | 240000 | 4444.4444
| b | Travel |  | 30 | 20000 | 1 | 100% | 600000 | 11111.1111
| c | Lodging |  | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | all 40 | 40 | 2500 | 3 | 100% | 300000 | 5555.5556
| e | Facilitation |  | 1 | 45000 | 3 | 100% | 135000 | 2500
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 500 | 3 | 100% | 60000 | 1111.1111
|  |  | Sub Total |  |  |  |  | 2385000 | 44166.6667
|  |  | Grand Total |  |  |  |  | 2775000 | 51388.8889
State Level Training / Meeting/ Consultation
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 2 | 15000 | 4 | 100% | 120000 | 2222.2222
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  | 2 | 20000 | 1 | 100% | 40000 | 740.7407
|  | Local Travel |  | 2 | 2500 | 4 | 100% | 20000 | 370.3704
|  | Lodging+DSA |  | 2 | 10000 | 4 | 100% | 80000 | 1481.4815
|  |  | Sub Total |  |  |  |  | 260000 | 4814.8148
National Participants
| a | Venue and Hall |  | 40 | 1000 | 3 | 100% | 120000 | 2222.2222
| b | Travel | Assuming all require | 30 | 5000 | 1 | 100% | 150000 | 2777.7778
| c | Lodging | Assuming all require | 30 | 10000 | 3 | 100% | 900000 | 16666.6667
| d | Local Travel and DSA | Assuming all require | 40 | 1500 | 3 | 100% | 180000 | 3333.3333
| e | Facilitation | 1 facilitators | 1 | 10000 | 3 | 100% | 30000 | 555.5556
| f | Sound and Recording |  | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| g | Reporting and printing | Documentation | 1 | 25000 | 3 | 100% | 75000 | 1388.8889
| h | Miscellaneous |  | 40 | 400 | 3 | 100% | 48000 | 888.8889
|  |  | Sub Total |  |  |  |  | 1578000 | 29222.2222
|  |  | Grand Total |  |  |  |  | 1838000 | 34037.037

## TA
TA | Technical assistance- UNICEF | Year 1 | Year 2 | Year 3 |  | Total
| Health Specialists in states and Delhi | 604800 | 665280 | 731808 |  | 2001888
| Sub Total | 604800 | 665280 | 731808 |  | 2001888
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
TA
1 | Health Specialists in states and Delhi | [8 empty] | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 | Year 3 | Grand Total
Technical Assistance - UNICEF | [9 empty] | Q1 | Q2 | Q3 | Q4 | Total | Total | Total
| Name of the Technical position | Remark | Unit | Unit Cost per month | Percentage | Number of Months | Number of Years | INR | USD
1 | Health Specialists in 9 States and Delhi (18 Specialists at 40% of their cost) |  | 18 | 378000 | 40 | 12 | 1 | 32659200 | 604800 | 151200 | 151200 | 151200 | 151200 | 604800 | 665280 | 731808 | 2001888
| Subtotal | [6 empty] | 32659200 | 604800 | 151200 | 151200 | 151200 | 151200 | 604800 | 665280 | 731808 | 2001888

## WHO
NAME OF PARTNER: WHO
Project Title: GAVI HSS
Duration: 2013-2015
Year 1
|  | Funds In US $ Millions |  |  |  | FUNDS (In US $ Millions)
Activity | Description | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | YR 1 | YR 2 | YR 3 | Total
4.1 | Build the capacity of existing institutions at the national, state, district, and block levels in generating and interpreting evidence through measles and other VPD surveillance for improved policy-making
4.1.1 | Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff) | 0.058756 | 0.058756 | 0.058756 | 0.058756 | 0.23502 | 0.25852 | 0.28438 | 0.77792
4.1.2 | Strengthening laboratories for VPD surveillance | 0.11 | 0 | 0 | 0 | 0.11 | 0.158 | 0.2152 | 0.4832
4.1.3 &4 | National/state level trainings workshops | 0 | 0.035185 | 0.062083 | 0 | 0.097269 | 0.107 | 0.11769 | 0.32196
| Operational cost for these activities | 0.1 | 0.1 | 0.1 | 0.1 | 0.4 | 0.35 | 0.35 | 1.1
| Sub Total | 0.26876 | 0.19394 | 0.22084 | 0.15876 | 0.84229 | 0.87352 | 0.96727 | 2.6831
5 | Human resources at national and state level (both technical and support staff)
5a | Human resources at national level (3 technical staff, one program assistant and 3 data support staff) | 0.039678 | 0.039678 | 0.039678 | 0.039678 | 0.15871 | 0.17458 | 0.19204 | 0.52533
5b | Human resources at state and district levels (technical and support staff) | 0.61348 | 0.61348 | 0.61348 | 0.61348 | 2.4539 | 3.2977 | 4.2857 | 10.0373
| Sub Total | 0.65315 | 0.65315 | 0.65315 | 0.65315 | 2.6126 | 3.4723 | 4.4777 | 10.5626
5.1 | Identification and enumeration of high risk populations (no additional cost as human resources budgeted under component 5 shall contribute to this activity) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2 | Intensified RI Monitoring
| Field Monitors | 0.46402 | 0.46402 | 0.46402 | 0.46402 | 1.8561 | 2.0417 | 2.2459 | 6.1436
| Sub Total | 0.46402 | 0.46402 | 0.46402 | 0.46402 | 1.8561 | 2.0417 | 2.2459 | 6.1436
5.3 | AFP surveillance, UIP reviews, Evaluations
5.3a | AFP Surveillance Review | 0 | 0 | 0.020222 | 0 | 0.020222 | 0.022244 | 0.016313 | 0.058779
5.3b | UIP Review | 0 | 0 | 0.0046667 | 0 | 0.0046667 | 0.0051333 | 0.011293 | 0.021093
| Sub Total | 0 | 0 | 0.024889 | 0 | 0.024889 | 0.027378 | 0.027606 | 0.079873
5.4 | SDA Facility management and organization
| Operational Cost | 0.10694 | 0.10694 | 0.10694 | 0.10694 | 0.42775 | 0.44914 | 0.47159 | 1.3485
| Sub Total | 0.10694 | 0.10694 | 0.10694 | 0.10694 | 0.42775 | 0.44914 | 0.47159 | 1.3485
5.5 | Build capacity of frontline workers at state and district levels in high priority states
5.5a | State Medical Officers | 0 | 0.21026 | 0 | 0.21026 | 0.42051 | 0.46256 | 0.50882 | 1.3919
5.5b | District Immunization Officers | 0 | 0.23012 | 0 | 0.23012 | 0.46024 | 0.50627 | 0.5569 | 1.5234
| Sub Total | 0 | 0.44038 | 0 | 0.44038 | 0.88076 | 0.96883 | 1.0657 | 2.9153
| Programme Activities |  |  |  |  | 12.59 | 12.15 | 10.6 | 35.34
| Monitoring and Evaluation | 0.125 | 0.125 | 0.125 | 0.13 | 0.5 | 0.5 | 0.5 | 1.5
| Total Programmable amount |  |  |  |  | 7.1444 | 8.3328 | 9.7558 | 25.233
| Programme Support Cost (@7% of total cost) |  |  |  |  | 0.50011 | 0.5833 | 0.6829 | 1.7663
| Grand Total |  |  |  |  | 7.6445 | 8.9161 | 10.4387 | 26.9993
Total
Recovery Cost (7%)
Total Programme Cost
TA (5%)
Actual Programme Activities
Per activity Deduction
Total
Recovery
5%

## 4.1
| 4.1 | Build the capacity of existing institutions at the national, state, district, and block levels in generating and interpreting evidence through measles and other VPD surveillance for improved policy-making | Year 1 | Year 2 | Year 3 | Total
| 4.1.1 | Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff) | 235022.2222 | 258524.4444 | 284376.8889 | 777923.5556
| 4.1.2 | Strengthening laboratories for VPD surveillance | 110000 | 158000 | 215200 | 483200
| 4.1.3 &4 | National/state level trainings workshops | 97268.5185 | 106995.3704 | 117694.9074 | 321958.7963
|  | Operational cost for these activities | 400000 | 350000 | 350000 | 1100000
|  | Programme Support Cost | 70000 | 60000 | 70000 | 200000
|  | Sub Total | 842290.7407 | 873519.8148 | 967271.7963 | 2683082.3519
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
|  | Activities | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand
| 4.1.1 | Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff)
|  | Technical Officers | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | Programme Assistants | [7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | Data Support Staff | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 4.1.2 | Strengthening laboratories for VPD surveillance
|  | Procurement of Equipment | [7 empty] | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 2 |  |  |  | 2
|  | Consumables | [7 empty] | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6
| 4.1.3 & 4 | National/state level trainings workshops
|  | National Level Workshop | [8 empty] | 1 |  |  | 1 |  | 1 |  |  |  |  | 1
|  | State Level Workshop | [9 empty] | 3 |  |  |  |  | 3 |  |  |  |  | 3
| Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff) | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Head | Unit Cost/monthly remuneration | Number/days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 4.1.1 | Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff)
|  | Technical Officers | 168100 | - | - | 100% | 168100 | 3112.963 |  | 37355.5556 | 37355.5556 | 37355.5556 | 37355.5556 | 149422.2222 | 41091.1111 | 41091.1111 | 41091.1111 | 41091.1111 | 164364.4444 | 45200.2222 | 45200.2222 | 45200.2222 | 45200.2222 | 180800.8889 | 494587.5556
|  | Programme Assistants | 63200 | - | - | 100% | 63200 | 1170.3704 |  | 10533.3333 | 10533.3333 | 10533.3333 | 10533.3333 | 42133.3333 | 11586.6667 | 11586.6667 | 11586.6667 | 11586.6667 | 46346.6667 | 12745.3333 | 12745.3333 | 12745.3333 | 12745.3333 | 50981.3333 | 139461.3333
|  | Data Support Staff | 48900 | - | - | 100% | 48900 | 905.5556 |  | 10866.6667 | 10866.6667 | 10866.6667 | 10866.6667 | 43466.6667 | 11953.3333 | 11953.3333 | 11953.3333 | 11953.3333 | 47813.3333 | 13148.6667 | 13148.6667 | 13148.6667 | 13148.6667 | 52594.6667 | 143874.6667
|  | Subtotal | [7 empty] | 58755.5556 | 58755.5556 | 58755.5556 | 58755.5556 | 235022.2222 | 64631.1111 | 64631.1111 | 64631.1111 | 64631.1111 | 258524.4444 | 71094.2222 | 71094.2222 | 71094.2222 | 71094.2222 | 284376.8889 | 777923.5556
| Strengthening laboratories for VPD surveillance | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Head | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 4.1.2 | Strengthening laboratories for VPD surveillance
|  | Procurement of Equipment | 2700000 | - | - | 70% | 1890000 | 35000 |  | 70000 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 70000 | 210000
|  | Consumables | 1080000 | - | - | 100% | 1080000 | 20000 |  | 40000 |  |  |  | 40000 | 88000 |  | 0 | 0 | 88000 | 145200 |  | 0 | 0 | 145200 | 273200
|  | Subtotal | [7 empty] | 110000 | 0 | 0 | 0 | 110000 | 158000 | 0 | 0 | 0 | 158000 | 215200 | 0 | 0 | 0 | 215200 | 483200
| National/state level trainings workshops | [8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Head | Unit Cost | Number | Days | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 4.1.3 & 4 | National/state level trainings workshops | [11 empty] | 0
|  | National Level Workshop | 23750 | 40 | 2 | 100% | 1900000 | 35185.1852 |  |  | 35185.1852 |  | 0 | 35185.1852 | 0 | 38703.7037 | 0 |  | 38703.7037 | 0 | 42574.0741 |  |  | 42574.0741 | 116462.963
|  | State Level Workshop | 11175 | 50 | 2 | 100% | 1117500 | 20694.4444 |  |  |  | 62083.3333 |  | 62083.3333 | 0 |  | 68291.6667 | 0 | 68291.6667 | 0 |  | 75120.8333 |  | 75120.8333 | 205495.8333
|  | Subtotal |  |  |  |  | 3017500 | 55879.6296 |  | 0 | 35185.1852 | 62083.3333 | 0 | 97268.5185 | 0 | 38703.7037 | 68291.6667 | 0 | 106995.3704 | 0 | 42574.0741 | 75120.8333 | 0 | 117694.9074 | 321958.7963
Grand Totals
[10 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[10 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
| 4.1.1 | Human resources at the National level (4 technical/medical officers at national level; 3 program assistant and 4 data support staff) | [7 empty] | 58755.5556 | 58755.5556 | 58755.5556 | 58755.5556 | 235022.2222 | 64631.1111 | 64631.1111 | 64631.1111 | 64631.1111 | 258524.4444 | 71094.2222 | 71094.2222 | 71094.2222 | 71094.2222 | 284376.8889 | 777923.5556
| 4.1.2 | Strengthening laboratories for VPD surveillance | [7 empty] | 110000 | 0 | 0 | 0 | 110000 | 158000 | 0 | 0 | 0 | 158000 | 215200 | 0 | 0 | 0 | 215200 | 483200
| 4.1.3&4 | National/state level trainings workshops | [7 empty] | 0 | 35185.1852 | 62083.3333 | 0 | 97268.5185 | 0 | 38703.7037 | 68291.6667 | 0 | 106995.3704 | 0 | 42574.0741 | 75120.8333 | 0 | 117694.9074 | 321958.7963
|  | Operational cost for these activities | [7 empty] | 100000 | 100000 | 100000 | 100000 | 400000 | 87500 | 87500 | 87500 | 87500 | 350000 | 87500 | 87500 | 87500 | 87500 | 350000 | 1100000
|  | Grand Totals | [7 empty] | 268755.5556 | 193940.7407 | 220838.8889 | 158755.5556 | 842290.7407 | 310131.1111 | 190834.8148 | 220422.7778 | 152131.1111 | 873519.8148 | 373794.2222 | 201168.2963 | 233715.0556 | 158594.2222 | 967271.7963 | 2683082.3519
Budget Assumptions
Procurement of Equipment
| S.N. | Equipment | Unit Cost (USD) | INR
| 1 | Bio safety cabinet | 9050 | 488700
| 2 | Simple Microscope | 2000 | 108000
| 3 | Incubator | 5887 | 317898
| 4 | Water Bath | 2200 | 118800
| 5 | Centrifuge | 9000 | 486000
| 6 | Electronic Balance | 4000 | 216000
| 7 | pH Meter | 900 | 48600
| 8 | Autoclave | 4000 | 216000
| 9 | Hot air oven | 1000 | 54000
| 10 | Deep Freezer | 1000 | 54000
| 11 | Refrigerator | 1250 | 67500
| 12 | Water purification | 9500 | 513000
| 13 | Magnetic stirrer | 213 | 11502
|  | Total | 50000 | 2700000
|  | 70% | 35000 | 1890000
National Level Consultation or workshop (2 days workshop)
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
International Participation
1 | International Experts or Participants
| a |  | Technical Expert |  | 50000 | 4 | 100% | 0 | 0
| b | Travel (Related Expenses) | [6 empty] | 0
|  | Travel |  |  | 100000 | 1 | 100% | 0 | 0
|  | Local Travel |  |  | 2500 | 4 | 100% | 0 | 0
|  | Lodging+DSA |  |  | 10000 | 4 | 100% | 0 | 0
|  |  | Sub Total |  |  |  |  | 0 | 0
National Participants
| a | Venue and Hall |  | 40 | 1000 | 2 | 100% | 80000 | 1481.4815
| b | Travel |  | 40 | 25000 | 1 | 100% | 1000000 | 18518.5185
| c | Lodging |  | 40 | 5000 | 3 | 100% | 600000 | 11111.1111
| d | Local Travel and DSA (to & fro) |  | 40 | 2500 | 1 | 100% | 100000 | 1851.8519
| e | Facilitation |  | 0 | 0 | 0 | 100% | 0 | 0
| f | Sound and Recording |  |  | 25000 | 1 | 100% | 0 | 0
| g | Reporting and printing | Documentation | 40 | 1000 | 2 | 100% | 80000 | 1481.4815
| h | Miscellaneous |  | 40 | 500 | 2 | 100% | 40000 | 740.7407
|  |  | Sub Total |  |  |  |  | 1900000 | 35185.1852
Unit Cost
|  |  | Grand Total |  |  |  |  | 1900000 | 35185.1852 | 23750
State /District Level training of Trainers workshops (2 days workshop)
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 0 | 30000 | 5 | 100% | 0 | 0
| b | Travel (Related Expenses) |  | 0 |  |  |  |  | 0
|  | Travel |  | 0 | 25000 | 1 | 100% | 0 | 0
|  | Local Travel |  | 0 | 2500 | 5 | 100% | 0 | 0
|  | Lodging+DSA |  | 0 | 10000 | 5 | 100% | 0 | 0
|  |  | Sub Total |  |  |  |  | 0 | 0
National Participants (Including Facilitators)
| a | Venue and Hall |  | 50 | 400 | 2 | 100% | 40000 | 740.7407
| b | Travel | Assuming all require | 50 | 5000 | 1 | 100% | 250000 | 4629.6296
| c | Lodging | Assuming all require | 50 | 5000 | 3 | 100% | 750000 | 13888.8889
| d | Local Travel and DSA (To & Fro) | Assuming all require | 50 | 1000 | 1 | 100% | 50000 | 925.9259
| e | Facilitation | 1 facilitators | 0 | 10000 | 0 | 100% | 0 | 0
| f | Sound and Recording |  | 0 | 25000 | 0 | 100% | 0 | 0
| g | Reporting and printing | Documentation | 50 | 150 | 1 | 100% | 7500 | 138.8889
| h | Miscellaneous |  | 50 | 400 | 1 | 100% | 20000 | 370.3704
|  |  | Sub Total |  |  |  |  | 1117500 | 20694.4444
Unit Cost
|  |  | Grand Total |  |  |  |  | 1117500 | 20694.4444 | 11175

## 5
5 | Human resources at national and state level (both technical and support staff) | Year 1 | Year 2 | Year 3 | Total | [7 empty] | 1895414.4
5a | Human resources at national level (3 technical staff, one program assistant and 3 data support staff) | 158711.1111 | 174582.2222 | 192040.4444 | 525333.7778
5b | Human resources at state and district levels (technical and support staff) | 2453904 | 3297690 | 4285694.16 | 10037288.16
| Sub Total | 2612615.1111 | 3472272.2222 | 4477734.6044 | 10562621.9378
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [6 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
5a | Human resources at national level (3 technical staff, one program assistant and 3 data support staff)
| Technical Staff | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Programme Assistants | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Data Support Staff | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5b | Human resources at state and district levels (technical and support staff)
| Technical Officers District level | [6 empty] | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248 | 248
| Technical Officers State Level | [6 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Support Staff District level | [6 empty] | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444 | 444
Human resources at national level (3 technical staff, one program assistant and 3 data support staff) | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost/monthly remuneration | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5a | Human resources at national level (3 technical staff, one program assistant and 3 data support staff)
| Technical Staff | 168100 | - | - | 100% | 168100 | 3112.963 | 28016.6667 | 28016.6667 | 28016.6667 | 28016.6667 | 112066.6667 | 30818.3333 | 30818.3333 | 30818.3333 | 30818.3333 | 123273.3333 | 33900.1667 | 33900.1667 | 33900.1667 | 33900.1667 | 135600.6667 | 370940.6667
| Programme Assistants | 63200 | - | - | 100% | 63200 | 1170.3704 | 3511.1111 | 3511.1111 | 3511.1111 | 3511.1111 | 14044.4444 | 3862.2222 | 3862.2222 | 3862.2222 | 3862.2222 | 15448.8889 | 4248.4444 | 4248.4444 | 4248.4444 | 4248.4444 | 16993.7778 | 46487.1111
| Data Support Staff | 48900 | - | - | 100% | 48900 | 905.5556 | 8150 | 8150 | 8150 | 8150 | 32600 | 8965 | 8965 | 8965 | 8965 | 35860 | 9861.5 | 9861.5 | 9861.5 | 9861.5 | 39446 | 107906
| Subtotal | [6 empty] | 39677.7778 | 39677.7778 | 39677.7778 | 39677.7778 | 158711.1111 | 43645.5556 | 43645.5556 | 43645.5556 | 43645.5556 | 174582.2222 | 48010.1111 | 48010.1111 | 48010.1111 | 48010.1111 | 192040.4444 | 525333.7778
Human resources at state and district levels (technical and support staff) | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost/monthly remuneration | Number/days | Frequency | Percentage * | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5b | Human resources at state and district levels (technical and support staff)
| Technical Officers District level * | 156330 | - | - | 20% | 31266 | 579 | 430776 | 430776 | 430776 | 430776 | 1723104 | 592317 | 592317 | 592317 | 592317 | 2369268 | 781858.44 | 781858.44 | 781858.44 | 781858.44 | 3127433.76 | 7219805.76
| Technical Officers State Level | 156330 | - | - | 100% | 156330 | 2895 | 69480 | 69480 | 69480 | 69480 | 277920 | 76428 | 76428 | 76428 | 76428 | 305712 | 84070.8 | 84070.8 | 84070.8 | 84070.8 | 336283.2 | 919915.2
| Support Staff District level * | 22950 | - | - | 20% | 4590 | 85 | 113220 | 113220 | 113220 | 113220 | 452880 | 155677.5 | 155677.5 | 155677.5 | 155677.5 | 622710 | 205494.3 | 205494.3 | 205494.3 | 205494.3 | 821977.2 | 1897567.2
| Subtotal | [6 empty] | 613476 | 613476 | 613476 | 613476 | 2453904 | 824422.5 | 824422.5 | 824422.5 | 824422.5 | 3297690 | 1071423.54 | 1071423.54 | 1071423.54 | 1071423.54 | 4285694.16 | 10037288.16
* 20%, 25% and 30% remuneration for year 1,2 and 3 respectively budgeted for supporting GAVI- HSS proposal
Grand Totals
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5a | Human resources at national level (3 technical staff, one program assistant and 3 data support staff) | [6 empty] | 39677.7778 | 39677.7778 | 39677.7778 | 39677.7778 | 158711.1111 | 43645.5556 | 43645.5556 | 43645.5556 | 43645.5556 | 174582.2222 | 48010.1111 | 48010.1111 | 48010.1111 | 48010.1111 | 192040.4444 | 525333.7778
5b | Human resources at state and district levels (technical and support staff) | [6 empty] | 613476 | 613476 | 613476 | 613476 | 2453904 | 824422.5 | 824422.5 | 824422.5 | 824422.5 | 3297690 | 1071423.54 | 1071423.54 | 1071423.54 | 1071423.54 | 4285694.16 | 10037288.16
| Grand Totals | [6 empty] | 653153.7778 | 653153.7778 | 653153.7778 | 653153.7778 | 2612615.1111 | 868068.0556 | 868068.0556 | 868068.0556 | 868068.0556 | 3472272.2222 | 1119433.6511 | 1119433.6511 | 1119433.6511 | 1119433.6511 | 4477734.6044 | 10562621.9378

## 5.2
5.2 | Intensified RI Monitoring | Year 1 | Year 2 | Year 3 | Total
5.2a | Field Monitors | 1708020 | 1878822 | 2066704.2 | 5653546.2
5.2b | External Monitoring in high risk states | 148055.5556 | 162861.1111 | 179147.2222 | 490063.8889
| Sub Total | 1856075.5556 | 2041683.1111 | 2245851.4222 | 6143610.0889
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [6 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
5.2a | Field Monitors
| Field Monitors | [6 empty] | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 972 | 2916
| External Monitoring in high risk states | [6 empty] | 650 | 650 | 650 | 650 | 2600 | 650 | 650 | 650 | 650 | 2600 | 650 | 650 | 650 | 650 | 2600 | 7800
Field Monitors | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost/monthly remuneration / EM day cost** | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5.2a | Field Monitors
| Field Monitors * | 15815 | - | - | 100% | 15815 | 292.8704 | 427005 | 427005 | 427005 | 427005 | 1708020 | 469705.5 | 469705.5 | 469705.5 | 469705.5 | 1878822 | 516676.05 | 516676.05 | 516676.05 | 516676.05 | 2066704.2 | 5653546.2
| External Monitoring in high risk states # | 1025 |  |  | 100% | 1025 | 18.9815 | 37013.8889 | 37013.8889 | 37013.8889 | 37013.8889 | 148055.5556 | 40715.2778 | 40715.2778 | 40715.2778 | 40715.2778 | 162861.1111 | 44786.8056 | 44786.8056 | 44786.8056 | 44786.8056 | 179147.2222 | 490063.8889
| Subtotal | [6 empty] | 464018.8889 | 464018.8889 | 464018.8889 | 464018.8889 | 1856075.5556 | 510420.7778 | 510420.7778 | 510420.7778 | 510420.7778 | 2041683.1111 | 561462.8556 | 561462.8556 | 561462.8556 | 561462.8556 | 2245851.4222 | 6143610.0889
* 972 field monitors will be hired, 50% of their time will be for supporting GAVI - HSS proposal.
** Unit Cost/monthly remuneration is for Field Monitors and per day External monitoring cost in high risk states
# Deployment of External Monitors in high risk states where field monitors are not deployed

## 5.3
5.3 | AFP surveillance, UIP reviews, Evaluations | Year 1 | Year 2 | Year 3 | Total | [7 empty] | 5133.3333
5.3.1 | AFP Surveillance Review | 20222.2222 | 22244.4444 | 16312.5926 | 58779.2593
5.3.2 | UIP Review | 4666.6667 | 5133.3333 | 11293.3333 | 21093.3333
| Sub Total | 24888.8889 | 27377.7778 | 27605.9259 | 79872.5926
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [6 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
5.3.1 | AFP Surveillance Review
| Review Meetings | [8 empty] | 3 |  | 3 |  |  | 3 |  | 3 | 3 |  | 2 |  | 2 | 8
5.3.2 | UIP Review
| Review Meetings | [8 empty] | 1 |  | 1 |  |  | 1 |  | 1 |  |  | 2 |  | 1 | 1
AFP Surveillance Review | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5.3.1 | AFP Surveillance Review
| Review Meetings | 364000 | - | - | 100% | 364000 | 6740.7407 |  |  | 20222.2222 |  | 20222.2222 |  |  | 22244.4444 |  | 22244.4444 |  |  | 16312.5926 |  | 16312.5926 | 58779.2593
| Subtotal | [6 empty] | 0 | 0 | 20222.2222 | 0 | 20222.2222 | 0 | 0 | 22244.4444 | 0 | 22244.4444 | 0 | 0 | 16312.5926 | 0 | 16312.5926 | 58779.2593
UIP Review | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost | Number/days | Frequency | Percentage | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5.3.2 | UIP Review
| Review Meetings | 252000 | - | - | 100% | 252000 | 4666.6667 |  |  | 4666.6667 | 0 | 4666.6667 | 0 | 0 | 5133.3333 |  | 5133.3333 | 0 | 0 | 11293.3333 | 0 | 11293.3333 | 21093.3333
| Subtotal | [6 empty] | 0 | 0 | 4666.6667 | 0 | 4666.6667 | 0 | 0 | 5133.3333 | 0 | 5133.3333 | 0 | 0 | 11293.3333 | 0 | 11293.3333 | 21093.3333
Grand Totals
[8 empty] | Year 1 |  |  |  |  | Year 2 |  |  |  |  | Year 3 |  |  |  |  | Grand Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5.3.1 | AFP Surveillance Review | [6 empty] | 0 | 0 | 20222.2222 | 0 | 20222.2222 | 0 | 0 | 22244.4444 | 0 | 22244.4444 | 0 | 0 | 16312.5926 | 0 | 16312.5926 | 58779.2593
5.3.2 | UIP Review | [6 empty] | 0 | 0 | 4666.6667 | 0 | 4666.6667 | 0 | 0 | 5133.3333 | 0 | 5133.3333 | 0 | 0 | 11293.3333 | 0 | 11293.3333 | 21093.3333
| Grand Totals | [6 empty] | 0 | 0 | 24888.8889 | 0 | 24888.8889 | 0 | 0 | 27377.7778 | 0 | 27377.7778 | 0 | 0 | 27605.9259 | 0 | 27605.9259 | 79872.5926
Budget Assumptions
| AFP Surveillance Review (A) |  |  | Total Cost per state
| Particulars | Cost per reviewer-INR | No. of reviewer/ | Percentage | Total
| Travel cost-INR (to/fro) | 20000 | 6 | 100% | 120000
| Local Travel | 1000 | 6 | 100% | 6000
| Per Diem &refreshment (@INR 5,000/- per night per participant, for 7 nights) | 35000 | 6 | 100% | 210000
| Taxi Hiring (Team of 3 members per taxi) | 14000 | 2 | 100% | 28000
|  |  | Total cost of 1 State |  | 364000
| Particulars | Cost per reviewer-INR | No. of reviewer/ | Percentage | 2013
| Travel cost-INR (to/fro) | 20000 | 4 | 100% | 80000
| Local Travel | 1000 | 4 | 100% | 4000
| Per Diem &refreshment (@INR 5,000/- per night per participant, for 7 nights) | 35000 | 4 | 100% | 140000
| Taxi Hiring (Team of 2 members per taxi) | 14000 | 2 | 100% | 28000
|  |  | Total cost of 1 review |  | 252000

## 5.4
5.4 | SDA Facility management and organization | Year 1 | Year 2 | Year 3 | Total | [7 empty] | #REF!
| Operational Cost | 427750.4 | 449137.92 | 471594.816 | 1348483.136
| Sub Total | 427750.4 | 449137.92 | 471594.816 | 1348483.136
Work Plan
[8 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
| Activities | [6 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
5.4 | Operational Cost | [6 empty] | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 196
Operational Cost | [7 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
| Head | Unit Cost | Number/days | Frequency | Percentage * | Total INR | Total USD | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
5.4 | Operational Cost | 44640 | - | - | 22% | 9820.8 | 181.8667 | 106937.6 | 106937.6 | 106937.6 | 106937.6 | 427750.4 | 112284.48 | 112284.48 | 112284.48 | 112284.48 | 449137.92 | 117898.704 | 117898.704 | 117898.704 | 117898.704 | 471594.816 | 1348483.136
| Subtotal | [6 empty] | 106937.6 | 106937.6 | 106937.6 | 106937.6 | 427750.4 | 112284.48 | 112284.48 | 112284.48 | 112284.48 | 449137.92 | 117898.704 | 117898.704 | 117898.704 | 117898.704 | 471594.816 | 1348483.136
*22% of support services e.g. vehicle running & maintenance and general operating cost (rent, stationery, communication, courier services, housekeeping etc.) will be used to support technical activity for GAVI - HSS proposal. This budget will also contribute to other activities under component 5

## 5.5
| 5.5 | Build capacity of frontline workers at state and district levels in high priority states | Year 1 | Year 2 | Year 3 | Total
| 5.5a | State Medical Officers | 420511.1111 | 462562.2222 | 508818.4444 | 1391891.7778
| 5.5b | District Immunization Officers | 460244.4444 | 506268.8889 | 556895.7778 | 1523409.1111
|  | Sub Total | 880755.5556 | 968831.1111 | 1065714.2222 | 2915300.8889
Work Plan
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3
|  | Activities | [7 empty] | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Grand Total
Build capacity of frontline workers at state and district levels in high priority states
| 5.5 a | State Medical Officers | [8 empty] | 254 |  | 254 | 508 |  | 254 |  | 254 | 254 |  | 254 | 254 |  | 254
| 5.5 b | District Immunization Officers | [8 empty] | 278 |  | 278 | 278 |  | 278 |  | 278 | 278 |  | 278 | 278 |  | 278
[10 empty] | Year 1 |  |  |  | Year 1 | Year 2 |  |  |  | Year 2 | Year 3 |  |  |  | Year 3 | Grand Total
|  | Head | Unit Cost | days | Frequency | Percentage | Total INR | Total USD |  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Build capacity of frontline workers at state and district levels in high priority states
| 5.5 a | State Medical Officers | 11175 | 2 | 2 | 100% | 44700 | 827.7778 |  |  | 210255.5556 |  | 210255.5556 | 420511.1111 | 0 | 231281.1111 | 0 | 231281.1111 | 462562.2222 | 0 | 254409.2222 | 0 | 254409.2222 | 508818.4444 | 1391891.7778
| 5.5 b | District Immunization Officers | 11175 | 2 | 2 | 100% | 44700 | 827.7778 |  |  | 230122.2222 |  | 230122.2222 | 460244.4444 | 0 | 253134.4444 | 0 | 253134.4444 | 506268.8889 | 0 | 278447.8889 | 0 | 278447.8889 | 556895.7778 | 1523409.1111
|  | Subtotal | [7 empty] | 0 | 440377.7778 | 0 | 440377.7778 | 880755.5556 | 0 | 484415.5556 | 0 | 484415.5556 | 968831.1111 | 0 | 532857.1111 | 0 | 532857.1111 | 1065714.2222 | 2915300.8889
Budget Assumptions
State /District Level training of Trainers workshops (2 days workshop)
|  | Activity | Remark | Unit | Unit Cost | Number | Percentage | INR | USD
1 | Experts or Master Trainers
| a |  | Technical Expert | 0 | 30000 | 5 | 100% | 0 | 0
| b | Travel (Related Expenses) |  | 0 |  |  |  |  | 0
|  | Travel |  | 0 | 25000 | 1 | 100% | 0 | 0
|  | Local Travel |  | 0 | 2500 | 5 | 100% | 0 | 0
|  | Lodging+DSA |  | 0 | 10000 | 5 | 100% | 0 | 0
|  |  | Sub Total |  |  |  |  | 0 | 0
National Participants (Including Facilitators)
| a | Venue and Hall |  | 50 | 400 | 2 | 100% | 40000 | 740.7407
| b | Travel | Assuming all require | 50 | 5000 | 1 | 100% | 250000 | 4629.6296
| c | Lodging | Assuming all require | 50 | 5000 | 3 | 100% | 750000 | 13888.8889
| d | Local Travel and DSA (To & Fro) | Assuming all require | 50 | 1000 | 1 | 100% | 50000 | 925.9259
| e | Facilitation | 1 facilitators | 0 | 10000 | 0 | 100% | 0 | 0
| f | Sound and Recording |  | 0 | 25000 | 0 | 100% | 0 | 0
| g | Reporting and printing | Documentation | 50 | 150 | 1 | 100% | 7500 | 138.8889
| h | Miscellaneous |  | 50 | 400 | 1 | 100% | 20000 | 370.3704
|  |  | Sub Total |  |  |  |  | 1117500 | 20694.4444
Unit Cost
|  |  | Grand Total |  |  |  |  | 1117500 | 20694.4444 | 11175