|  |  | [V3.11] |  |
| --- | --- | --- | --- |
| GAVI Alliance Application Form for Country Response To Conditions For Support to: Routine New Vaccines Support Preventive Campaign Support Submitted by The Government of Papua New Guinea Date of submission: 23 January 2014 Deadline for submission: 24 January 2014 Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) Start Year 2011 End Year 2015 Form revised in 2013 (To be used with Guidelines of November 2013) Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public. |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland . The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. Application Specification Please specify for which type of GAVI support you would like to apply to. Type of Support Vaccine Start Year End Year Preferred second presentation[1] Preventive Campaign Support MR, 10 dose(s) per vial, LYOPHILISED 2015 2015 Routine New Vaccines Support Measles second dose, 10 dose(s) per vial, LYOPHILISED 2015 2015 [1] GAVI may not be in a position to accommodate all countries first product preferences, and in such cases, GAVI will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country.

2. Table of Contents 1. Application Specification 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation 4.1.3. Signature Table for the Coordinating Committee for Immunisation 4.2. National Immunization Technical Advisory Group 4.2.1. The NITAG 5. Immunisation Programme Data 5.1 Background information 5.1.1 Lessons learned 5.1.2 Health planning and budgeting 5.1.3 Preparatory activities 5.1.4 Gender and equity 5.1.5 Data quality 5.1.6 MCV Immunisation coverage 5.2. Baseline and Annual Targets (NVS Routine Support) 5.3. Baseline and Annual Targets for Preventive Campaign(s) 5.3.1 Baseline and annual targets (MR campaign) 6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) 6.2 Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED) 6.2.1 Co-financing information 6.2.2 Specifications of vaccinations with new vaccine 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$) 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$) 6.2.5 New and Under-Used Vaccine Introduction Grant 7. NVS Preventive Campains 7.1. Assessment of burden of relevant diseases related to campaigns (if available) 7.1.1 Epidemiology and disease burden for Measles-Rubella 7.2 Request for MR, 10 dose(s) per vial, LYOPHILISED campaign support 7.2.1 Summary for MR campaign support 7.2.2 Grant Support for Operational Costs of the MR Campaign 7.2.3 Evidence of introduction of RCV in routine programme 7.2.4 Introduction planning for RCV 7.2.5 Measles surveillance indicators 7.2.6 Rubella Containing Vaccine introduction Grant 8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine 8.2 Procurement and Management for NVS Preventive Campaign(s) 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign 8.3 Vaccine Management (EVSM/EVM/VMA) 8.4 Waste management 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) 10. List of documents attached to this proposal 11. Annexes Annex 1 - NVS Routine Support Annex 1.1 Measles second dose, 10 dose(s) per vial, LYOPHILISED Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ Table Annex 1.1 C Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED Table Annex 1.1 D Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Annex 2 - NVS Routine – Preferred Second Presentation Annex 3 - NVS Preventive campaign(s) Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking Form

3. Executive Summary Please provide a summary of your country's proposal, including the following the information: l For each specific request, NVS routine support or NVS campaign : ¡ The duration of support ¡ The total amount of funds ¡ Details of the vaccine(s), if applicable, including the reason for the choice of presentation ¡ Projected month and year of introduction of the vaccine l Relevant baseline data, including: ¡ DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) ¡ Birth cohort, targets and immunisation coverage by vaccines l Country preparedness ¡ Summary of EVM assessment and progress on EVM improvement plan l The nature of stakeholders' participation in developing this proposal ¡ Inter-Agency Coordinating Committee ¡ Partners Papua New Guinea has an estimated population of around 7.1 million (2011 census, preliminary figures), 40% of which is under the age of 15. It has more than 800 languages, over 1000 dialects and many ethnic groups, sub-ethnicities, clans and sub-clans spread across its 22 provinces. Health services in Papua New Guinea (PNG) are provided by the Government and church medical services and are primarily financed by public funds. The poor road infrastructure and rugged terrain pose formidable challenges to the effective delivery of health services nationwide. The leading health problems in Papua New Guinea continue to be communicable diseases, with malaria, tuberculosis, diarrhoeal diseases, and acute respiratory disease as major causes of morbidity and mortality. The increased size and mobility of populations, the growth of larger, denser populations in peri-urban communities, and the relative weakening of health services combine to increase the incidence of communicable diseases. The National Department of Health has committed to achieving the goal of measles elimination by 2012 as outlined in its existing cMYP. One of the key activities conducted in PNG was the organization of measles SIA targeting children 9 months – 3 years in 2012, attaining a coverage of 88%, the highest amongst all SIAs conducted until date in PNG. Measles Epidemic in Papua New Guinea: Major measles epidemics have occurred in Papua New Guinea since 1980. Amongst the recent documented epidemics, the 1998 epidemic continued until late 2002 (Mgone et al. 2000). More than half of the hospitalized measles cases were infants <9 months old and fatal cases were reported in infants as young as 4 months (Mgone et al. 2000). The last documented outbreak subsided in 2004-2005. Measles vaccination coverage in PNG; A discussion In its current immunization schedule, measles vaccine is provided at 6 months and 9 months to each infant by one year of age. Measles vaccine has been part of Papua New Guinea’s national Immunization Program since 1982. The 6 month dose of measles that was introduced in the National Immunization schedule in 1992 along with periodic wide-age measles supplementary immunization activities since 2002 had a significant impact in terminating the repeated outbreaks of measles in PNG until the last documented outbreak in 2004-2005. Reported MCV-1 (Measles-9 month dose) coverage and evaluated coverage: A snap shot The official estimates of Measles-9 month for the year 2012 was 67%. The reported coverage estimates for DTP-3 and Measles in Papua New Guinea has been less than 70% for last few years (Ref: NHIS’2012) while the evaluated coverage, Demographic Health Survey and other sub-national surveys conducted in 2011 and 2012 shows a higher evaluated coverage than the reported coverage for the health service areas. In 2011, Oilserach Health Foundation conducted a 16 by 7 cluster survey in Kutubu, Southern Highlands province of 112 children between 12-23 months and the vaccination coverage of Measles – 9 months assessed by card (97.3%) plus history (2.7%) for children 12-23 months was 82.7%. At the time of the survey, 76.8% of children were completely immunised, with 51.8% fully immunised (indicating optimal timing according to the National EPI system). Similar findings were found in Kikori, Gulf province where a 16 by 7 cluster survey was conducted and the evaluated coverage was found to be high than the corresponding reported figures. The above evidences suggest towards under-reporting of administrative figures in PNG. The reasons that can attributed to this includes late reporting to the national health information system by the health centres which are remotely located in the country. A detailed Data Quality Assessment is undergoing at this time to detect the bottlenecks in collecting and collation of quality data by the health system with special reference to immunization system. Verification of recording and reporting practices of MCV-1 in PNG: An initiative The National EPI unit undertook an activity to verify the recording and reporting practices of the health worker of the routine measles vaccine doses. This initiative was conducted in three health centres in three provinces (Milne Bay, National Capital District and Autonomous Region of Bougainville). These health centres were conveniently chosen following discussion with the respective provincial family health coordinators on the criteria that the health facility has robust recording and data reporting system and geographical access with ease of monitoring of the activity in the health facilities by the provincial staffs or other development partners in these provinces. The main objectives of this activity were to: (1) To document the recording and reporting practices of health staffs as for MCV-6 and MCV-9 month doses in NHIS reporting format, (2) To document the age-characteristics of the children receiving different MCV doses and (3) To ascertain the actual coverage level of MCV-9 month from the NHIS with respect to the findings from this study. The national immunization schedule in Papua New Guinea (PNG) provides every child with two doses of measles vaccine before their first birthday. They receive these two doses at 6 and 9 months of life respectively. As for the reporting requirement by the country, the 6 - month dose is never reported in WHO/UNICEF Joint Reporting Format (JRF) while the coverage of 9 - month dose is reported as MCV-1 in the JRF. A study conducted by Mgone in 2008, showed that the average age of children receiving the 6 month dose is around 8 months of age and significant number of children receive the 9 month dose around 11 month and beyond. A total of 1029 infant visited these health centres in the above provinces during the period of initiative. All these infants received a dose of measles as per the national immunization schedule. The health workers recorded the dose either as a 6 month dose, 9 month dose or dose > 1 year according to the age of the child in the NHIS tally sheet. The health worker also recorded the same in a format developed seprately for this initiative format. They recorded for each of the dose whether they were a first dose or second dose for the child. The study showed that out of 751 children aged 9 months who received a dose of measles during the period, in 654 instances the health worker recorded the dose as a 9 month dose in NHIS while in 94 (13%) such instances, the health worker recorded the dose as a 6 month dose. Further analysis of these doses showed that in all the instances these doses were “First dose” for all the children. The findings from the study also showed that out of 278 children aged 10 and 11 months who received a dose of measles during the period, in 226 such instances they were recorded as a 9 month dose in NHIS while in 38 and 14 (total: 19%) such instances they were recorded as 6 month and > 1 year respectively. The above findings clearly indicate that 13% of the reported 6 month and 19% of the reported > 1 Year doses in NHIS should have been recorded as 9 month dose which were received by children between 9-11 months. Based on the study results, the reported coverage of 6 month and 9 month in NHIS for the year 2011 and 2012 was re-adjusted. The table below enumerates the adjusted coverage figures and adjusted % coverage for Measles 9 months (MCV-1) for the country. Yr Reported 6M cov. Adjusted 6M cov. Reported 9M cov. Reported > 1 Yr cov. Adjusted 9M cov. Reported 6M % Adjusted 6M% Reported 9M % Adjusted 9M% ‘11 128473 111772 117601 108735 154962 61 53 56 73 ‘12 142394 123883 130969 191979 185956 68 60 64 89 It is evident from the findings of the study that 13% (CI: 10.34-15.08) of 6M doses are actually 9M doses and 18% (CI: 14.56-23.7) of >1Yr doses are actually 9M doses. Thus, these difference are being added up in the reported 9M coverage and subsequently deducted from the reported 6M and >1 Yr coverage. The adjusted 9M coverage using the findings of the study implicates an increase of 18-25% of the reported coverage in 2011 and 2012 respectively. Measles coverage in Supplementary Immunization Activities in PNG: The April 2012 Measles SIA achieved a national coverage of 88% with 7 provinces (7/20) achieving a coverage of more than 90% while 11 provinces (11/20) achieved of more than 80%. The measles vaccine coverage in PNG during the SIAs had always been around 83-86% in 2008-9 and 2010-11. With the improvement in coverage in April 2012 suggest an improving trend in coverage in SIAs as well. The current two doses of measles in the National Immunization Schedule and the relevance of this request to Measles Second Dose application: The decline in child mortality in Papua New Guinea has been attributed to a range of factors, including the introduction of the national immunization program. Since the inception of the program, there has been a rapid decline in vaccine preventable diseases (VPDs) with attainment of a polio-free status in 2000 and a 98% reduction of measles mortality in 2011; no laboratory confirmed measles cases since 2008. The introduction of hepatitis B vaccine and pentavalent vaccine in the country has extended the potential of the public health system in Papua New Guinea to extend the gains of immunization in support of further immunization related mortality declines, despite the exsiting challenges in service delivery. Measles vaccination has been part of Papua New Guinea’s national Immunization Program since 1982. As per the national immunization schedule, measles vaccine is given to children at 6 months and 9 months of age. Although coverage with 9 M of measles vaccine has steadily risen over the years with considerable variation in coverage both between and within provinces. The 6 month dose of measles that was introduced in the National Immunization schedule in 1992 had a significant impact in terminating the repeated outbreaks of measles in PNG until the last documented outbreak in 2004-2005. The combination of historically low routine vaccination coverage and primary vaccine failure (measles vaccine effectiveness is estimated to be 85% when given at 9 months of age) may result in a substantial number of susceptible children in successive birth cohorts which may fuel measles virus transmission. In order to further stregthen the measles elimination effort in the country and thereby contributing to the Western Pacific region, and to support social development and reduction and elimination of VPDs, the Government of Papua New Guinea is actively seeking the support from the Global Alliance for Vaccines and Immunization (GAVI) to introduce a second dose of measles in second year of life into the routine EPI services from 2015, in support of the Regional Goal of elimination of the disease in the region in the same year. Senn N et al. 2010 in their article “Measles in Papua New Guinea: An age-specific serological survey” concluded that sero-conversion and long term protection rates appeared to be higher when at least one dose of vaccine was provided at or after 12 months of age (though the sample size was small). The paper concluded that infants immunized before 12 months of age were less likely to achieve adequate and long lasting immunity and hence it may be necessary to include at least one additional dose at or after 12 months. In line with the WHO Western Pacific Region goal of achieving measles elimination and technical recommendations from WHO, the introduction of a 2nd dose of measles vaccine is planned for the beginning of 2015. This will replace the need for regular measles supplementary immunization campaigns and ensure that 95% population immunity of each birth cohort is achieved and maintained in every district. While discussions have taken place in the Child Health Advisory Committee on the possible benefits of non-specific effects of an early dose of vaccination (as the 6 months dose in PNG’s national immunization schedule), while decision of withdrawal of the 6-month will be considered in 2014 following the recommendations by the special working group of SAGE on non-specific effects of vaccine. Thus beyond 2014, the national immunization schedule will be adjusted so that the first dose is given at 9 months of age, and the second at 18 months of age. Other strategies to achieve implementation of the measles elimination goal are as follows: Strengthen the existing AFR (Acute, Fever and Rash) surveillance systems and laboratory confirmation of cases to ensure that all suspected cases of measles are detected, investigated, with blood samples taken and tested at Central Public Health Laboratory, an accredited WHO laboratory. Scale up implementation of a Reaching Every District to Reach Every Child Strategy to improve immunization coverage in low-performing districts Supplementation of sub-national measles SIAs in high risk communities with TT SIAs to address the risks with both the first and second dose Planned introduction of school entry checks for children to ensure that they are fully immunized with all antigens. Evidence of rubella in PNG: PNG uses the Acute Fever and Rash (AFR) surveillance to detect cases of rubella in the community. The case investigation form of AFR encompasses the characteristics to identify cases of suspected rubella. Any fever and rash cases which test negative for measles are then tested for rubella. The country however, does not have an established Congenital Rubella Syndrome surveillance to assess the burden the CRS in the country. However, many available evidences exist in the country which points towards the fact that rubella 1. PNG introduced laboratory based Acute Fever and Rash surveillance as part of its Measles Surveillance in 2008. Since its inception of laboratory based surveillance, no cases of measles were detected in PNG. However, increasing cases of rubella have been detected using the system. The rubella positivity in last three years (includes rubella positive and equivocal): 2010: 19%; 2011: 25%; 2012: 32%. Most of these case occurred in children under 15 years old which suggest that rubella virus circulate continuously in children and this group play important role to maintain continuous chains of transmission. 2. Dryden R 1997 in the paper on birth defects in Port Moresby General Hospital detected 1.16 % prevalence of birth defects amongst all births between 1985 and 1986 out of which 27% presented with multiple birth defects and 14% were still born. The paper highlights that the prevalence is an underestimate however, does not determine the causation of the birth defects. 3. Riddell M et al. 2012 in their paper on age – specific immunity strategies for rubella control in Papua New Guinea found that 90% of women more than 15 years of age have acquired natural immunity. The force of infection was highest between 5 – 19 years of age, with an approximate annual risk of infection for susceptible individuals of 23 %. 4. A prospective study was conducted in Autonomous region of Bougainville to assess the outcome of pregnant women infected with rubella with documented rubella outbreak amongst children in the same area. The final assessment of the outcome of the pregnancy testing positive for rubella is awaited. However, 24% of the pregnant women tested positive for IgM rubella in the affected villages. This indicates that the reporting of the rubella cases in the adult population is under-reported in the country, as these cases were detected by active surveillance of the area. 5. The Paediatric Society of PNG supported the National EPI unit to conduct a 5 year retrospective and one year prospective evaluation of the possible congenital rubella syndrome in Port Moresby General Hospital. This involved evaluation of the syndromes of the suspected CRS cases per the case history sheets of the admitted patients and incorporating the available laboratory results from the AFR surveillance from 2008. Although the final results are yet to be shared by the pediatric group, the initial results suggest that a significant number of children would conform to the WHO definition of suspected CRS cases. The preliminary result of cases identified in this study exhibits multiple births defect including: deafness, blindness, heart defects, etc. This is health and social burden for a resource-constrained setting like PNG. The Government of Papua New Guinea (GoPNG) seeks financial assistance from the GAVI Alliance to conduct catch-up campaign using MR vaccine for target population of males and females aged 9 months to 14 years in 2015. Support is requested from GAVI for 3,995,216 doses of MR vaccine; 4,394,737 AD syringes 0.5ML; 439,474 reconstitution disposable syringes 5ML and 48,342 safety boxes; US$ 2,920,000 for operational cost of MR campaign (Although GAVI defined to support US$ 0.65/target population and expects that this would constitute 80% of the operational cost; the operational cost to conduct campaigns in PNG has been around US$ 3.65 million primarily due to cost of transportation to remote locations involving hiring of choppers and boats including shipment of vaccines and logistics. Thus it is requested that GAVI supports 80% of the actual operational cost which the country expends while conducting a campaign and US$ 201,835 for MR vaccine introduction grant (@US$ 0.80/ target birth cohort) with a total value of US$ 3,107,328. The Government of Papua New Guinea (GoPNG) also seeks financial assistance from the GAVI Alliance to introduce the second dose of measles for children aged 18 months of age. The total investment in the procurement of two vaccine schedule for 2015 is estimated at US $ 283,806 for two doses of measles, of which 50% (ie. the second dose) will be funded by GAVI. The Government of PNG procures 100% of its routine vaccines using government fund and the GoPNG already procure two doses of measles for the immunization programme.The Government commits itself to introduce MR vaccine in the routine program for children aged 9 months and at 18 months instead of measles vaccine, after the completion of a wide-age range MR campaign in 2015. Thus, after the completion of the wide-age campaign, the Government of PNG will replace the procurement of the Measles vaccine with the Measles-Rubella vaccine. The national EPI policy of the PNG indicates only WHO pre-qualified vaccines can be used in the national immunization schedule and thus, the GAVI financed vaccines and logistics will be procured and supplied through UNICEF. A detailed catch-up campaign plan has been prepared including training, IEC and surveillance which is enclosed with this application. Considering the climatic scenario in different regions of the country and the cold chain capacity at different levels, the campaign will be conducted in two phases over a period of four months with each phase lasting for two effective working months. The Government commits itself to introduce MR vaccine in the routine program for children aged 9 months and at 18 months instead of measles vaccine, after the completion of this campaign. The Government of PNG procures 100% of its routine vaccines using government fund and the GoPNG already procure two doses of measles for the immunization programme. Thus, after the completion of the wide-age campaign, the Government of PNG will replace the procurement of the Measles vaccine with the Measles-Rubella vaccine. As part of the new vaccine application to GAVI, PNG conducted the Effective Vaccine Management assessment in May 2011. While in September 2008, PNG conducted an internal Effective Vaccine Store Management assessment. The quality issues identified in the EVM exercise in the country including the relevant quality issue in the cold chain system in the country has been implemented by the National EPI unit with support from all development partners which is anticipated to further strengthen the vaccine management in the country. The cold chain capacity in the country at different levels, with possible introduction of pneumococcal vaccine in 2013, is being re-assessed with the possible replacement plan being drafted which will be funded by the Government of PNG. However, the cold chain capacity for conducting routine vaccination both at national and sub-national level is adequate to accomodate the available and the new vaccine. Significant progress has been made in the country since the last EVM to address the quality issues and logistic issues both at the national and provincial levels. A cold chain training manual is being planned in 2014 and detailed training on cold chain management has been incorporated in the district-level EPI training which is being carried out in the country. (Detailed progress on the EVM has been provided as an attachment) Choice of vaccine: The Government of Papua New Guinea plans to introduce 10-dose Measles-Rubella lyophillised combination vaccine in the planned wide age range rubella followed by introduction of the same vaccine in routine vaccination. The Government of Papua New Guinea plans to introduce 10-dose Measles-Rubella lyophillised combination vaccine in the second year of life (18 months) and as such request support from GAVI for the measles component of the second dose of measles planned for introduction of the same in the National Immunization schedule. The Government of PNG will use MR vaccine for both of its doses (first dose at 9-11 months and second dose at 18-24 months) for programmatic ease and will bear the cost of the "R" in the measles second dose vaccine. Summary on coordination with Inter-agency Coordination Committee members and preparedness of the country: The Child Health Advisory Committee and Inter-agency Coordination Committee members in Papua New Guinea represented by all partner organizations and also by civil society organizations were strongly involved during the discussion and preparation of this proposal. Significant support was provided by all ICC members including technical assistance and providing specific input during the review of the documents. The EPI Comprehensive Multi-year plan 2011-15 commits to the introduction of new vaccinces based on available evidences in the country. The introduction of MR will be built on the successful introduction of Hib vaccine in 2008 and Pneumococcal vaccines in 2013. The preparedness of the country can be ascertained from the fact that the national health plan drafted in line with addressing MDG 4 and MDG 5 clearly addresses reduction of child mortality through vaccination as one of the key result areas. Research in Papua New Guinea sufficiently indicates that rubella is a burden for health system in PNG. Research in Papua New Guinea sufficiently indicates that a second dose of measles beyond one year of life will have significant impact in better protecting children. Moreover, the current immunization schedule already encompasses two doses of measles and the government of PNG procures all its traditional vaccines used in the national immunization schedule. In order to establish a simple yet sensitive surveillance system to detect congenital rubella syndrome cases in PNG, the National EPI unit in collaboration with Central Public Health Laboratory, Paediatric Society of PNG, WHO-PNG and US-CDC is planning to start a simplfied surveillance using ocular features in two identified hospitals in the country. The goal of the project is documenting the burden of CRS in PNG based on prospective surveillance prior to country-wide rubella vaccine introduction in 2015. Specific objectives of this project include: 1) initiating comprehensive CRS surveillance based on current World Health Organization standards and an alternate simplified system based on congenital cataract case-finding both at Port Moresby and a provincial hospital that is representative of healthcare/laboratory capacity found elsewhere in the country; 2) generating an estimate of the burden of CRS disease via capture-recapture methods using these two surveillance systems; 3) assessing the cost and feasibility of using congenital cataract detection to monitor CRS incidence; and 4) providing necessary data for designing a sustainable national CRS surveillance system. Accurate country-level estimates of the burden of CRS are necessary for evaluating the post-introduction impact of vaccination and monitoring progress towards CRS elimination. Thus, with view of developing an effective surveillance system for alternative CRS methods feasible in low-resource settings like PNG, this initiative will go a long way. The health system reforms planned in Papua New Guinea; rural health transformation project a joint initiative of Asian Development Bank, AusAID, KOICA with technical support from WHO and UNICEF, which address strengthening of the health system at the community level and these initiatives in Papua New Guinea with also support better reach of the immunization services to the priority group of rural majority and urban poor.

4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation The Government of Papua New Guinea would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests GAVI support for: Measles second dose, 10 dose(s) per vial, LYOPHILISED routine introduction MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns The Government of Papua New Guinea commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 1 and 2 in Section 10. Attachments. Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name Mr. Pascoe Kase Name Mr. Paul Dopsie Date Date Signature Signature This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document): Full name Position Telephone Email Dr. Siddhartha Sankar DATTA Technical Officer-EPI, WHO (675) 325 7827 dattas@wpro.who.int Dr. William LAGANI Manager, Family Health Services (675) 301 3841 william_lagani@health.gov.pg Mr. Gerard Pai SUI National EPI Manager (675) 323 0976 gerard.sui@gmail.com Mr. Pierre SIGNE Chief of Child Survival and Development Programme-UNICEF (675) 308 7368 spierre@unicef.org 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. Profile of the ICC, HSCC, or equivalent committee Name of the committee ICC Year of constitution of the current committee 2006 Organisational structure (e.g., sub-committee, stand-alone) Stand Alone Frequency of meetings Once Every Quarter The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4. Major functions and responsibilities of the ICC/HSCC: The Inter-Agency Coordination Committee on EPI chaired by the Secretary for Health will meet at least quarterly to: 1. Provide overall guidance and direction to immunization services in PNG 2. Coordinate international agencies activities on EPI 3. Assist continuous review and updating of national policy and program on immunization 4. Assist and review implementation of EPI 5. Review necessary information and assist introduction of any new vaccines into immunization systems as appropriate to PNG context 6. Assist development of GAVI and other funding proposals and review their progress of implementation. 7. Review the implementation of annual EPI plan against the set targets and goal Please describe how partners have provided support in preparation of the proposal: All development partners like WHO, UNICEF and AusAID were intricately involved in the preparation of this proposal. Additional support was provided by the Paediatric Society of PNG in providing the essentail data to the Child Health Advisory Committee and the Interagency Coordination Committee members in Papua New Guinea towards the decision making for the introduction of the MR vaccine and the introduction of second dose of measles in the National Immunization Schedule in the country. Significant support was provided by all ICC members including technical assistance and providing specific input during the review of the documents. 4.1.3. Signature Table for the Coordinating Committee for Immunisation We the members of the ICC, HSCC, or equivalent committee [1] met on the 30/08/2013 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 6 (please use the list for signatures in the section below). Please refer to Annex D of the Guidelines for more information on ICCs. Function Title / Organisation Name Please sign below to indicate the attendance at the meeting where the proposal was endorsed Please sign below to indicate the endorsement of the minutes where the proposal was discussed Chair Deputy Secretary for Health / National Department of Health Dr. Paison DAKULALA Secretary Executive Manager, Public Health/ National Department of Health Dr. Sibauk Vivaldo Bieb Members WHO Country Representative/WORLD HELATH ORGANIZATION Dr. William ADUKROW UNICEF Country Representative/ UNICEF Mr. Baba DANBAPPA Programme Director Health / AusAID Dr. Geoff CLARK Assistant Resident Representative / JICA Mr. Noriyuki ITO Paediatrician & Senior Curriculum Development Advisor/ School of Medicine, University of PNG Dr. Paulus RIPA Representative, Churches Medical Council/ PNG Churches Health Services Mr. Joseph SIKA President/ Paediatric Society of PNG Dr. James AMINI Director / Health Sector Improvement Program, NDoH Mr. Paul Dopsie Manager, Family Health Services Dr. William LAGANI By submitting the proposal we confirm that the quorum has been met. Yes The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 7. 4.2. National Immunization Technical Advisory Group Has a NITAG been established in the country ? No

5. Immunisation Programme Data 5.1 Background information Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document. ▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 10. Please attach the cMYP costing tool as DOCUMENT NUMBER 11. ▪ Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12 ▪ Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate. Please use the most recent data available and specify the source and date. Figure Year Source Total population 7,112,628 2011 National Statistical Office, Papua New Guinea Infant mortality rate (per 1000) 57 2007 Demographic Health Survey and Annual Sector Review Surviving infants[1] 205,886 2012 WHO/UNICEF JRF Data GNI per capita (US$) 1,790 2012 World Bank Report Total Health Expenditure (THE) as a percentage of GDP 3 % 2009 WHO National Health Accounts General government expenditure on health (GGHE) as % of General government expenditure 8 % 2009 WHO National Health Accounts [1] Surviving infants = Infants surviving the first 12 months of life 5.1.1 Lessons learned Routine New Vaccines Support If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points or actions taken to address them. Please refer to previous Post Introduction Evaluations (PIE), if applicable. Lessons Learned Action Points PNG successfully introduced DTP-HepB-Hib vaccine in 2008. The major lessons learned included the following: 1. The time lag in introduction of the DTP-HepB-Hib vaccine despite having evidence of disease burden in the country lead to GoPNG to apply for other new vaccines as Pneumococcal vaccine based on available evidences. 2. Introduction of a new vaccine in the immunization schedule led to the transition of vaccine procurement mechanism from HSIP dependent system to 100% funding using government recurrent financial system ensuring regular fund flow to UNICEF to procure the co-financing vaccine doses. This has been a success to the programme financial management. 3. Introduction of DTP-HepB-Hib in 2008 and planned introduction of PCV-13 in 2013 are considered as opportunities to train the health workers on vaccination including re-orientation on routine EPI. 4. Introduction of new vaccines led to re-assess the cold chain and vaccine management system and improving the status from the EVM recommendations. 1. Sharing of research results on other vaccine preventable disease in Papua New Guinea with national decision makers with shortening of time lag between planning and actual introduction of vaccine. 2. PNG will apply subsequently for new vaccines based on available formulation of the vaccines, while research on other possible formulations will be carried out if required. 3. National Department of Health (NDOH) will adhere to co-financing the GoPNG amount from government recurring fund as is done for all routine vaccine while the new vaccine procurement will be included as a line budget item to accommodate the advance payment norms for the co-financing amount 4. Similar process of training of health workers will be conducted and the opportunity of introduction of the new vaccine will be used to sensitize the health workers on technical update on new vaccine and also on routine EPI 5. Formulation of AEFI policy and guidelines on AEFI. Reporting of AEFI will be strengthened Preventive campaign support If campaigns with MR vaccines have already been conducted in your country, please give details of the lessons learned, specifically for: storage capacity, protection from additional freezing, staff training, cold chain, logistics, coverage, wastage rate, etc, and suggest action points to address them in future campaigns. Lessons Learned Action Points 5.1.2 Health planning and budgeting Please provide information on the planning and budgeting cycle in your country The National Health Administration Act (1997) establishes the National Health Plan (NHP) as a national policy. It applies to the entire country including Provincial and Local-Level Governments. The Act provides for the NHP to be approved by the National Executive Council after considering recommendation by the National Health Board. The National Strategic Plan (NSP) 2010-2050 of Government of Papua New Guinea (GoPNG) promises to provide the next forty year vision and framework for long range planning. A Long Term Development Strategy (LTDS) 2010-2030 is being developed to link the principles and focus areas of the NSP and provide policy direction and sectoral interventions with clear objectives, quantitative targets and baseline indicators. To achieve the intended long term goal, the LTDS proposes five broad strategies which will be detailed in four Medium Term Development Plans (MTDP) over the next twenty years. The National Health Plan 2010-2020 forms the basis of all health planning in the country. The main emphasis of the National Health plan in PNG is towards strengthening primary health care for all and improved service delivery for the rural majority and urban disadvantaged. The National health plan clearly addresses Paris declaration on Aid Effectiveness and harmonization. The planning unit under national department of health provides all technical support to the planning of the national health plan while the national health information system in addition to providing the technical support to data collation and analysis provide strategic support to review of the progress by using disease specific and health system indicators. The budget distribution and allocation by the GoPNG is always reviewed in line with the priorities laid down under the national health plan while also addressing the province specific areas of support. Please indicate the name and date of the relevant planning document for health National Health Plan 2011-2020 Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.) Yes, the information herein is aligned to cMYP 2011-15 Please indicate the national planning budgeting cycle for health The Department of Health under the leadership of Secretary for Health with support from all development partners starts the annual national implementation plan preparation from the month of May/June of the preceding year. In this process, each planning and technical unit in national department health involving all program units with technical support from the supporting partners develops the programme specific programme implementation plan. It is always ensured that the programme unit plans are in line with national health plan of the country and all the programmes address the building blocks of the national health plan. The programme unit implementation and budget plans are approved by the respective executive managers. The National department of health submits the plan to ministry of finance and treasury by the month of August / September for review of the budget and fund allocation from the government treasury which contributes to the recurrent expenditure of the department of health. In the month of the November, the consolidated planning, implementation and budget plan is submitted to National Executive Council for approval of the parliament, which when approved and shared with all programme officers in National Department of health for effective implementation. Please indicate the national planning cycle for immunisation The National EPI unit, as part of the national department of Health is the planning unit for the immunization related activities and is the parent unit towards preparing the immunization programme of the country. During the third quarter of the year, the national EPI unit aligns its activities with that of the Provincial Annual Implementation plan and advices the provincial planners towards the national priorities and shares the national plan of action. During the preparation of the annual national EPI plan, the national EPI unit is supported by all partners working in the field of immunization namely WHO, UNICEF, AusAID and JICA and national EPI unit upon costing the annual implementation plan shares the shortfall in terms funding to partners. The national EPI unit, based on the discussion with all partners identifies the specific areas of support by partners to national EPI plan. Based on the alignment of the national Annual Implementation plan with the provincial implementation plan, the national EPI unit submits the same to the department of health for its usual approval process which then becomes part the national planning and budget for health as described in the preceding section.

5.1.3 Preparatory activities Please provide an outline of all preparatory activities for vaccine(s) introduction WHO presented the available evidences to the Child Health Advisory Committee towards the decision making process of the introduction of rubella vaccine and the second dose of measles. Technical consultation with the Paediatricians and Public Health unit of School of Medicine by the National EPI unit on MR vaccine introduction options, costing of the MR vaccine introduction and introduction of second dose of measles beyond one year of life. Resolution at the 2013 Mid-Year meeting of the Paediatric Society of PNG to request the government of PNG to introduce the rubella vaccine along with MCV-2 based on the in-country evidences The Child Health Advisory Committee endorsed the request of the National EPI unit to apply for MR vaccine and MSD introduction with an application to GAVI Assessment of cold chain capacity at all levels to support the introduction of MR vaccine into routine EPI schedule Presentation of GAVI Application outcome will be done in CHAC and ICC meeting after the receipt of the outcome Introduction plans including social mobilization activities, development of training materials and changes in reporting and recording formats will be organized by the National EPI unit Updating of EPI Policy Guidelines including EPI manual for new immunization schedule, printing and distribution of manual and reporting and recording tools to all provinces, district and health centres (Q3 2014) Developing operational National guidelines for the MR campaign (Q3 2014) Coordination meeting and training meeting of all provinces (Q4 2014) Workshop for National and provincial EPI vaccine ordering focal points on the ordering requirements for MR schedule and training on the transition to the new immunization schedule including vaccine estimation forecasts (Q4 2014) Meeting with Procurement unit of the National Department of Health to include procurement of MR vaccine in line with the outcome of the GAVI application for support to second dose of measles in the budgeting process for 2015-16 and beyond (Q3 2014) MR campaign (Q2 & Q3 2015) Estimated delivery of MR vaccine, and initiation of supply through the routine vaccine distribution system in all health facilities by Q4 2015 Introduction of MSD in the National Immunization Schedule in Q4 2015 as MR vaccine 5.1.4 Gender and equity Please describe any barriers in access to immunisation services that are related to geographic, socio-economic and/or gender equity and actions taken to mitigate these barriers. Highlight where these issues are addressed in the vaccine introduction plan(s). The available data in the country does not signify any gender-related barriers in accessing and delivering of the immunization services. The routine immunization coverage data in its present form does not collect sex-disaggregated data. However, the National Health Information System in consultation with all development partners and with technical advice from the Child Health Advisory Committee has started the process to incorporate the reporting of routine vaccine doses by sex of the child. The data when made available by the National Health Information System will be analyzed by the National EPI unit and steps will be taken to address any disparity if any. The National EPI unit in line with the National Health Plan prioritizes the delivery of services to rural majority and urban poor and disadvantaged population. The geo-topographical conditions in the country limit accessing of services by some parts of the population. The plan of the GoPNG to conduct comprehensive EPI/MCH regular outreach to all villages and areas in the country will address the geographical reach of the population to the immunization services. This will be complemented by the GoPNG to fund outreach services of every health centres as one of the minimum priority activities in its financial commitment. This is also being addressed by involving profit and non-for-profit organization health service delivery in their geographical service areas to reach the remote communities. Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s). As the government of Papua New Guinea doesn't place a gender preference to the services provided under the National health services including immunization services, thus children of either sex have will have equal access to immunization services in Papua New Guinea. This includes equity of service delivery to population irrespective of the geographical access and socio-economic status. Social mobilization activities will include activities like radio broadcast including print media, dissemination of information using pamplets & leaflets using business houses, Non-governmental organization and primarily health education of the communities by the health workers of the government system. The Chruch Health Service delivery will be used to reach with the information to all corners of the country using the churches and the health system. Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems. Gender disintegrated coverage figures is recorded at health facility; however, the data is not reported or collated by National Health information system. Is the country currently in a situation of fragility (eg. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities. Not relevant 5.1.5 Data quality Please attach a data quality assessment report, if one has been completed within the previous 36 months (DOCUMENT NUMBER : 13). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER : 14, DOCUMENT NUMBER : 15). 5.1.6 MCV Immunisation coverage Please provide information concerning immunisation coverage related to measle-containing vaccines (MCV) Table 5.1.6: MCV Immunisation coverage Coverage 2005 2006 2007 Administrative(1) WHO/UNICEF(2) Administrative(1) WHO/UNICEF(2) Administrative(1) WHO/UNICEF(2) Measles 1st dose (%) 49 63 64 65 58 58 Measles 2st dose (%) Supplementary Immunisation Activities (SIA) (%) 76 Coverage 2008 2009 2010 Administrative(1) WHO/UNICEF(2) Administrative(1) WHO/UNICEF(2) Administrative(1) WHO/UNICEF(2) Measles 1st dose (%) 58 54 55 55 55 55 Measles 2st dose (%) Supplementary Immunisation Activities (SIA) (%) 86 84 Coverage 2011 2012 Administrative(1) WHO/UNICEF(2) Administrative(1) WHO/UNICEF(2) Measles 1st dose (%) 56 60 64 67 Measles 2st dose (%) Supplementary Immunisation Activities (SIA) (%) 88 Note: (1) National reported Administrative Coverage (2) WHO/UNICEF estimated coverage Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Administrative coverage

5.2. Baseline and Annual Targets (NVS Routine Support) Please refer to cMYP pages to assist in filling-in this section. Number Base Year Baseline and Targets 2012 2015 Total births 215,543 234,160 Total infants’ deaths 9,657 10,481 Total surviving infants 205,886 223,679 Total pregnant women 215,543 234,160 Target population vaccinated with BCG 172,724 203,719 BCG coverage 80 % 87 % Target population vaccinated with OPV3 OPV3 coverage 69 % 80 % Number of infants vaccinated (to be vaccinated) with DTP1 168,527 201,744 Number of infants vaccinated (to be vaccinated) with DTP3 121,051 165,515 DTP3 coverage 59 % 74 % Wastage[1] rate in base-year and planned thereafter (%) for DTP 5 5 Wastage[1] factor in base-year and planned thereafter for DTP 1.05 1.05 Target population vaccinated with 1st dose of Measles 130,969 174,462 Target population vaccinated with 2nd dose of Measles 0 74,560 Measles second dose coverage 0 % 33 % First Presentation: Measles second dose, 10 dose(s) per vial, LYOPHILISED Wastage[1] rate in base-year and planned thereafter (%) {0} 25 25 Wastage[1] factor in base-year and planned thereafter (%) 1.33 1.33 Maximum wastage rate value for Measles second dose, 10 dose(s) per vial, LYOPHILISED 40 % 40 % Pregnant women vaccinated with TT+ 118,699 159,096 TT+ coverage 55 % 68 % Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100 28 % 18 % [1] Number of infants vaccinated out of total births [2] Number of infants vaccinated out of total surviving infants [3] Indicate total number of children vaccinated with either DTP alone or combined [4] Number of pregnant women vaccinated with TT+ out of total pregnant women [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

5.3. Baseline and Annual Targets for Preventive Campaign(s) 5.3.1 Baseline and annual targets (MR campaign) Please specify cohort for rubella-containing vaccines (RCV): RCV Start 9 months RCV End 14 years Cohort population = population 9 months - 14 years old GAVI will only provide support to countries for rubella catch-up campaign by providing MR vaccine for a target population of males and females aged 9 months to 14 years (the exact range in the scope of 9 months to 14 years old will depend on rubella epidemiology in the country. Table 5.3.1 Baseline NVS preventive campaign figures for MR Base Year Baseline and Targets 2012 2015 Total births 215,543 234,160 Total population 9 months - 14 years old 2,757,783 3,003,922 Target population vaccinated with MR 0 3,003,922 MR (campaign) coverage (%) [1] 0 % 100 % Wastage rate (%) for MR (campaign) 0 15 Wastage factor for MR 1 1.18 [1] Number of persons vaccinated out of total target population

6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) Disease Title of the assessment Date Results

6.2. Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED) As reported in the cMYP, the country plans to introduce Measles second dose, using Measles second dose, 10 dose(s) per vial, LYOPHILISED. When is the country planning to conduct this vaccine? September 2015 Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address these issues. Currently the Measles 5-dose vial presentation is not available, but please indicate if the country would prefer this presentation if it becomes available. Yes If the country is introducting measles-rubella (MR) in the routine system, is the country planning to switch the second dose of measles to MR as well, in addition to the first MR dose? No If [YES], when? September 2015 Please note that if the country is planning to switch the routine second dose of measles to MR, the country will be required to finance the rubella component, in addition to financing the routine first dose of MR. 6.2.1. Specifications of vaccinations with new vaccine Data from Year 1 2015 Number of children to be vaccinated with the second dose Table 5.2 # 74,560 Immunisation coverage with the second dose Table 5.2 # 33.33 %

6.2.2. New and Under-Used Vaccine Introduction Grant Calculation of Vaccine Introduction Grant for the Measles second dose, 10 dose(s) per vial, LYOPHILISED Year of New Vaccine Introduction Births (from Table 5.2) Share per Birth in US$ Total in US$ 2015 234,160 0.80 187,328 The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000 Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan). The GAVI Vaccine Introduction Grant will be used to facilitate the development and dissemination of the social mobilization and IEC (Information, Education and Communication) messages to the communities in PNG. The grant will also be used to train the health workers on the new changes in the immunization schedule along with the planned district level training of health workers. Thus, the grant fund will complement the on-going training activities. The grant fund will also be used to strengthen the programme management issues both at the national and provincial level. Please summarise in the table below the full costs of preparing for and introducing the vaccine, and specify which items are expected to be covered with the one-time GAVI grant. Please note that the country will be required to submit a detailed budget for the Vaccine Introduction Grant prior to release of funds. Cost (and finance) to introduce the Measles second dose, 10 dose(s) per vial, LYOPHILISED US$ Cost Category 'Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ Training 100,000 60,000 Social Mobilization, IEC and advocacy 58,000 56,000 Cold Chain Equipment & Maintenance 0 0 Vehicles and Transportation 0 0 Programme Management 250,000 20,000 Surveillance and Monitoring 126,000 18,328 Human Resources 0 0 Waste Management 3,000 3,000 Technical Assistance 30,000 30,000 Other (please specify) Total 567,000 187,328 Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs. The total operational costs for the campiagn will be shared between GAVI funding and the national and provincial government using the ongoing support of the outreach using the minimum priority activity funding to each of the health centre by the national government. The ICC will mobilize fund as required from different development partners as AusAID, WHO, UNICEF as and when required upon approval of the application by GAVI.

7. NVS Preventive Campains 7.1. Assessment of burden of relevant diseases related to campaigns (if available) Disease Title of the assessment Date Results Rubella Assessment of burden of rubella 1997-2013 However, many available evidences exist in the country which points towards the fact that rubella 1. PNG introduced laboratory based Acute Fever and Rash surveillance as part of its Measles Surveillance in 2008. Since its inception of laboratory based surveillance, no cases of measles were detected in PNG. However, increasing cases of rubella have been detected using the system. The rubella positivity in last three years (includes rubella positive and equivocal): 2010: 19%; 2011: 25%; 2012: 32%. Most of these case occurred in children under 15 years old which suggest that rubella virus circulate continuously in children and this group play important role to maintain continuous chains of transmission. 2. Dryden R 1997 in the paper on birth defects in Port Moresby General Hospital detected 1.16 % prevalence of birth defects amongst all births between 1985 and 1986 out of which 27% presented with multiple birth defects and 14% were still born. The paper highlights that the prevalence is an underestimate however, does not determine the causation of the birth defects. 3. Riddell M et al. 2012 in their paper on age – specific immunity strategies for rubella control in Papua New Guinea found that 90% of women more than 15 years of age have acquired natural immunity. The force of infection was highest between 5 – 19 years of age, with an approximate annual risk of infection for susceptible individuals of 23 %. 4. A prospective study was conducted in Autonomous region of Bougainville to assess the outcome of pregnant women infected with rubella with documented rubella outbreak amongst children in the same area. The final assessment of the outcome of the pregnancy testing positive for rubella is awaited. However, 24% of the pregnant women tested positive for IgM rubella in the affected villages. This indicates that the reporting of the rubella cases in the adult population is under-reported in the country, as these cases were detected by active surveillance of the area. 5. The Paediatric Society of PNG supported the National EPI unit to conduct a 5 year retrospective and one year prospective evaluation of the possible congenital rubella syndrome in Port Moresby General Hospital. This involved evaluation of the syndromes of the suspected CRS cases per the case history sheets of the admitted patients and incorporating the available laboratory results from the AFR surveillance from 2008. Although the final results are yet to be shared by the pediatric group, the initial results suggest that a significant number of children would conform to the WHO definition of suspected CRS cases. The preliminary result of cases identified in this study exhibits multiple births defect including: deafness, blindness, heart defects, etc. This is health and social burden for a resource-constrained setting like PNG. 7.1.1 Epidemiology and disease burden for Measles-Rubella Please select at least one of the following information sources to justify RCV diseases burden results: Epidemiological information on burden of disease: þ 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases) o 2 - Rubella seroprevalence surveys þ 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance o 4 - Other

7.2.Request for MR, 10 dose(s) per vial, LYOPHILISED campaign support 7.2.1. Summary for MR campaign support When is the country planning to conduct the MR catchup campaign? April 2015 When is the country planning to introduce MR into routine immunisation? September 2015 Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address this issue. Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED. Outline the key points that informed the decision-making process (data considered etc) and describe the plans for social mobilisation and microplanning, including strategies for insecure or hard-to-reach areas. The existing cMYP of PNG outlines the road-map to improve the routine immunization coverage and also provides a guide to introduction of new vaccines in the routine immunization schedule. Page 23 & 24 of the existing cMYP outlines the need of evidence based decision making for the introduction of the rubella vaccine with technical consultation with the Child Health Advisory Committee. The availability of the following evidences in PNG lead to the decision by the Child Health Advisory Committee to support the introduction of the rubella vaccine in the immunization schedule: PNG introduced laboratory based Acute Fever and Rash surveillance as part of its Measles Surveillance in 2008. Increasing cases of rubella have been detected using the system since then. The rubella positivity in last three years (includes rubella positive and equivocal): 2010: 19%; 2011: 25%; 2012: 32%. Riddell M et al. 2012 in their paper on age – specific immunity strategies for rubella control in Papua New Guinea found that 90% of women more than 15 years of age have acquired natural immunity. The force of infection was highest between 5 – 19 years of age, with an approximate annual risk of infection for susceptible individuals of 23 %. A prospective study was conducted in Autonomous region of Bougainville to assess the outcome of pregnant women infected with rubella with documented rubella outbreak amongst children in the same area. The final assessment of the outcome of the pregnancy testing positive for rubella is awaited. However, 24% of the pregnant women tested positive for IgM rubella in the affected villages. This indicates that the reporting of the rubella cases in the adult population is under-reported in the country, as these cases were detected by active surveillance of the area. The Paediatric Society of PNG supported the National EPI unit to conduct a 5 year retrospective and one year prospective evaluation of the possible congenital rubella syndrome in Port Moresby General Hospital. This involved evaluation of the syndromes of the suspected CRS cases per the case history sheets of the admitted patients and incorporating the available laboratory results from the AFR surveillance from 2008. Although the final results are yet to be shared by the pediatric group, the initial results suggest that a significant number of children would conform to the WHO definition of suspected CRS cases. The preliminary result of cases identified in this study exhibits multiple births defect including: deafness, blindness, heart defects, etc. This is health and social burden for a resource-constrained setting like PNG. Please summarise the cold chain capacity and readiness to accommodate new vaccines, taking into consideration training, cold chain and other logistic requirements. If cold chain expansion is required state how it will be financed, and when it will be in place. Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled. An analysis of the cold chain capacity for the introduction MR was undertaken which found that there was sufficient cold chain storage capacity at all levels of vaccine storage to absorb the requirements of the MR. The national vaccine store has enough excess capacity from the routine schedule, inlcuding with the PCV-13 vaccine introduced (see the EVM report). In all intermediate sores there is also excess capacity (either at +5°C or -20°C) than can be used to store the MR vaccine for the campaign. Moreover, the actual campaign activity will be conducted in two phases, thus the cold chain capacity will be fine for campaign. This will provide sufficient volume to cater for the wide age range target population for the MR campaign. The MR SIA will build on the lessons and success of the 2012 and 2013 Tetanus Toxoid Campaign for around 1.8 million target population which had no demonstrable impact in the shipment plans for routine vaccines Please describe how the campaign activities will contribute to strengthening routine immunisation services. Please refer to specific activities to be undertaken during planning and implementation, to evaluate the implementation of the routine strengthening activities completed during the campaign, and to assess, via an independent survey, the quality and coverage achieved through the campaign. Papua New Guinea uses the opportunities in campaigns to deliver all routine vaccines since 2008. This effort was strengthened during the 2012 measles SIA wherein routine vaccines were delivered to the communities apart from delivering five campaign interventions. This will be continued in any forthcoming campaigns; ensuring that the recording practices of campaign doses and te routine vaccines doses are doen separately. The effort in campaigns is used effectively to reach out to hard-to-reach communities who are usually not reached sufficiently during the routine outreaches. The microplanning activities done in the campaigns also acts as a training activity for the health workers to further enhance their capacity to improve the microplan in their routine activities. The campaign activities as social mobilization and IEC activities provides platform to advocate the routine vaccination in the community and also provides a close contact with policy planners and peoples representatives. The planning process, as development of micro plan during the campaign provides a basis for strengthening the planning process of routine vaccination. The use of Rapid Convenience Monitoring (RCM) institutionalized in 2012 measles SIA will also further strengthens the monitoring and supervision by all levels in the country. Also a probability sampling of households either during the campaign (aligned with planned RCM) or after the campaign with support from the INGOs and FBOs will also support the evaluation of the routine immunization coverage during the campaign and also provide an estimate of coverage in the community of routine immunization services. Please submit relevant documentation to support the estimates of the size of the campaign target population (as DOCUMENT NUMBER : 18). 7.2.2. Grant Support for Operational Costs of the MR Campaign Table 7.2.2: calculation of grant to support the operational costs of the campaigns Year of MR support Target population vaccinated (from Table 5.3) GAVI contribution per target person in US$ Total in US$ 2015 3,003,922 0.65 1,952,549 [1] The Grant will be based on a maximum award of $0.65$ per target person Please describe how the grant will be used to facilitate the preparation and timely and effective delivery of the campaigns to the target population (refer to the cMYP and the Vaccine Introduction Plan). The GAVI Vaccine Introduction Grant will be used to facilitate the development and dissemination of the social mobilization and IEC (Information, Education and Communication) messages to the communities in PNG for the planned campaign. The grant will also be used to train the health workers on the campiagn. The grant will be used to support the operational cost of the provinces to conduct the campaign as per their submitted microplans. Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$ Cost Category 'Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ 2015 2015 Training 178,095 50,000 Social Mobilization, IEC and advocacy 104,000 50,000 Cold Chain Equipment & Maintenance 377,000 75,000 Vehicles and Transportation 1,416,441 700,000 Programme Management 215,000 215,000 Surveillance and Monitoring 50,000 0 Human Resources 1,095,238 732,549 Waste Management 25,000 25,000 Technical Assistance 20,000 0 Planning 100,000 20,000 Volunteer incentives 95,000 85,000 Other (please specify) Additional fund for campaign outlined in excel sheet Post Campaign Coverage Survey 500,000 Total 4,175,774 1,952,549 Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs. The total operational costs for the campiagn will be shared between GAVI funding and the national and provincial government using the ongoing support of the outreach using the minimum priority activity funding to each of the health centre by the national government including additional grant from the Provincial Governors and Administrators. The allocated Provincial and District SIP funds will also be used as and when required. The ICC will mobilize fund as required from different development partners as AusAID, WHO, UNICEF as and when required upon approval of the application by GAVI. 7.2.3 Evidence of introduction of RCV in routine programme Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following: o 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc. o 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated o 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase. In this case, the country must show additional evidence that the country will include MR vaccination in the routine immediately after the campaign. o 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme þ 5 - Other Please attach one or more of these documents AS DOCUMENT NUMBER in Section 10. Attachments Please briefly describe the document used as evidence: A letter of support from the Secretary of Health in line with the cMYP document to introduce the rubella vaccine in the routine programme after the wide-age range campaign. 7.2.4 Introduction planning for RCV Countries should describe their plan for introduction including surveillance activities: Does Papua New Guinea’s cMYP include a plan for the introduction of RCV into the national programme? Yes Please summarise the Introduction Plan for the introduction of RCV into the national programme. Please refer to the instructions described below. Introduction of rubella vaccine is part of the cMYP 2011-15, a document which is approved by the government. Moreover, the Paediatric society of PNG 2013 mid-year resolution including the Child Health Advisory Committee has included inclusion as one of activity as priority for the government. The National EPI unit is further strengthening the surveillance of congenital rubella syndrome in the country. The Government of PNG procures all traditional vaccines for the EPI programme; thus introduction of the vaccine in the national EPI programme is also feasible. It is to note that in the past introduced Hepatitis B without any external support, while after support from GAVI to introduce Pentavalent vaccine in 2008, PNG has contributed more than the required co-financing amount. This indicates the commitment of GoPNG to support to any new vaccine introduced in the national EPI schedule.

INSTRUCTIONS Components of the introduction plan should include: a. Comprehensive vaccination strategy for the introduction of RCV including a description of: i. Initial Measles and rubella (MR) campaign ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs iv. Linkage to the current routine immunisation schedule v. Linkage to measles second dose, if applicable vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs) b. A brief description of the following surveillance activities: i. Integration of Rubella surveillance with case-based measles surveillance ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance iii. Adverse Event Following Immunization (AEFI) surveillance c. Vaccine coverage monitoring and reporting d. The communication strategy for the introduction of RCV 7.2.5 Measles surveillance indicators Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available): Surveillance indicator 2011 2012 Reporting rate at national level (1) 144 66 100,000 100,000 Laboratory confirmation rate (%) (2) 0 0 Note: (1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year (2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage

7.2.6 Rubella Containing Vaccine introduction Grant Has a Rubella Containing vaccine already been introduced nationally on a routine basis? No Calculation of Vaccine Introduction Grant for the MR, 10 dose(s) per vial, LYOPHILISED Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed. Year of New Vaccine Introduction Births (From Table 5.3) Share per Birth in US$ Total in US$ 2015 234,160 0.80 187,328 [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000 Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan). The GAVI Vaccine Introduction Grant will be used to facilitate the development and dissemination of the social mobilization and IEC (Information, Education and Communication) messages to the communities in PNG. The grant will also be used to train the health workers on the new changes in the immunization schedule along with the planned district level training of health workers. Thus, the grant fund will complement the on-going training activities. The grant fund will also be used to strengthen the programme management issues both at the national and provincial level. Please summarise in the table below the full costs of preparing for and conducting the campaign, and specify which items are expected to be covered with the GAVI grant. Please note that the country will be required to submit a detailed budget for the Campaign Operational Support Grant prior to release of funds. Cost (and finance) to introduce the MR, 10 dose(s) per vial, LYOPHILISED US$ Cost Category 'Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ Training 100,000 60,000 Social Mobilization, IEC and advocacy 58,000 56,000 Cold Chain Equipment & Maintenance 0 0 Vehicles and Transportation 0 0 Programme Management 250,000 20,000 Surveillance and Monitoring 125,000 18,328 Human Resources 0 0 Waste Management 3,000 3,000 Technical Assistance 30,000 30,000 Other (please specify) Total 566,000 187,328

8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC). a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF): PNG will prefer procuring of the MR vaccine and injection supplies which is financed by GAVI through the UNICEF supply system for rubella catch-up campaign. As per the EPI policy of the country, the vaccine imported and used in the immunization schedule has to be a WHO pre-qualified vaccine. In view of the transportation and shipment of vaccines to the provinces by the National Vaccine store, it is expected that the MR vaccine to be procured by UNICEF on behalf of GAVI to reach the country by November 2014 to enable PNG to conduct this campaign in October 2013. In addition, the cash grant for operational cost including the vaccine introduction grant will be received in the bank account, the details of which has been provided in this application. The ICC will provide oversight over implementation of rubella catch-up campaign activities and its monitoring and supervision. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document l Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used. l The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality. Not relevant c) Please indicate how funds should be transferred by the GAVI Alliance (if applicable) The funds should be transfered to the HSIP, Port Moresby account, the details of which is furnished here in this application request d) Please indicate how the co-financing amounts will be paid (and who is responsible for this) The National Department of Health is responsible for the payment of the co-financing amount, as required. The fund will be transfered to GAVI using the current system of co-financing for pentavalent vaccine, which is done using UNICEF SD. e) Please describe the financial management procedures that will be applied for the management of the NVS cash support, including procurement. The new vaccine cash support received from GAVI upon the approval of the application will be deposited in the account detail provided in this application. This fund will be managed as a separate ledger account in HSIP at Port Moresby. A separate code will be assigned to this fund. All expenditure will be jointly managed by the HSIP officers in close collaboration and approval from the National EPI manager and Manager of Family Health Services. These funds will be processed for expenditure at the National Level under the overall supervision of the Executive Manager Public Health and Secretary of Health. The fund will be transfered to the Provincial HSIP, if need be, for the activities to be conducted at the provincial level and the usual acquittal mechanism will be emphasized at the provincial level so that acquittal can be done as soon as the campaign is over. An audit of this fund will be carried out as per the usual process of HSIP acquuittal. Any procurement done beyond the support provided by GAVI will be done using the existing temder process of the National Department of Health. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP) The coverage of this new vaccine will be monitored and reported using the established monthly routine immunization report to the National Health Information System. The campaign coverage will be monitored and reported by the National EPI unit. The reporting of the coverage will be done by each district. Rapid Convenience Monitoring of the campaign will be done to assess the quality of the campaign in the provinces and districts. Coverage surveys in future when conducted will include assessment of coverage of this vaccine. g) If applying for measles second dose, does the country wish to have the support in cash or in-kind? Cash 8.2 Procurement and Management for NVS Preventive Campaign(s) 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF): PNG will prefer procuring of the MR vaccine and injection supplies which is financed by GAVI through the UNICEF supply system for rubella catch-up campaign. As per the EPI policy of the country, the vaccine imported and used in the immunization schedule has to be a WHO pre-qualified vaccine. In view of the transportation and shipment of vaccines to the provinces by the National Vaccine store, it is expected that the MR vaccine to be procured by UNICEF on behalf of GAVI to reach the country by November 2014 to enable PNG to conduct this campaign in October 2013. In addition, the cash grant for operational cost including the vaccine introduction grant will be received in the bank account, the details of which has been provided in this application. The ICC will provide oversight over implementation of rubella catch-up campaign activities and its monitoring and supervision. b) Please describe the financial management procedures that will be applied for the management of the preventive campaign cash support, including any procurement to be incurred. The operational fund received from GAVI upon the approval of the application will be deposited in the account detail provided in this application. This fund will be managed as a separate ledger account in HSIP at Port Moresby. A separate code will be assigned to this fund for the operational cost. All expenditure will be jointly managed by the HSIP officers in close collaboration and approval from the National EPI manager and Manager of Family Health Services. These funds will be processed for expenditure at provincial level, under the overall supervision of the Executive Manager Public Health and Secretary of Health. The fund will be transfered to the Provincial HSIP and the usual acquittal mechanism will be emphasized at the provincial level so that acquittal can be done as soon as the campaign is over. An audit of this fund will be carried out as per the usual process of HSIP acquuittal. Any procurement done beyond the support provided by GAVI will be done using the existing temder process of the National Department of Health. c) Please indicate if the campaign is going to be phased, and if so, how this will be done. Phase one: From Apr- June 2015: In 13 provinces covering 1,864, 712 of the target population Phase two: From July – September 2015: In 9 provinces covering 1,139,210 of the target population d) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan) The coverage of this new vaccine will be monitored and reported using the established monthly routine immunization report to the National Health Information System. The campaign coverage will be monitored and reported by the National EPI unit. The reporting of the coverage will be done by each district. Rapid Convenience Monitoring of the campaign will be done to assess the quality of the campaign in the provinces and districts. An independent post-campaign coverage survey using a standardised methodology would be conducted in line with the assessment of the routine immunization coverage. The findings from the survey will be used to strengthen the routine immunization programme and also to identify sub-national areas to target campaigns.

8.3 Vaccine Management (EVSM/EVM/VMA) Under the new guidelines, it is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 36 months. Did the country have Effective Vaccine Management (EVM) in the past? Yes When was the EVM conducted? May 2011 Please attach the most recent EVM report (DOCUMENT NUMBER : 20,21,22), the corresponding EVM improvement plan (DOCUMENT NUMBER : 21) and progress on the EVM improvement plan (DOCUMENT NUMBER : 22). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? No 8.4 Waste management Please describe the country’s waste management plan for immunisation activities (including campaigns). Include details on the safe handling, storage, transportation and disposal of immunisation waste. The sharps are disposed of in incinerator in facilities having one while in other health centres they are buried/burnt. The issue encountered in injection safety disposal is the availability of incinerators in all districts health facilities.

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) Comments and Recommendations from the National Coordinating Body (ICC/HSCC) The ICC concurs with the Government of Papua New Guinea (GoPNG) seeking 80% of the actual operational cost as a financial assistance from the GAVI Alliance to conduct catch-up campaign using MR vaccine for target population of males and females aged 9 months to 14 years in 2015. The support of USD 0.65 is far less than the actual cost per beneficiary in PNG. The operational cost in conducting campaigns in PNG is considerably high due to cost of transportation to remote locations. And as the National EPI unit integrates delivery of other services during the campaign, the investment in this regard is cost-effective. 24.01.2014: The Government of PNG would request a clarification on the comment from IRC on Point 8.4 which outlines discrepancy in the vaccine introduction grant between MR and MSD in the original submitted application. However, on review of the original online application to GAVI from PNG, we found that the requested VIG both for MR and MSD is as per the laid down guidelines and they both equal to US$ 187,328 (Ref. tables under sections 6.2.2 for MSD and 7.2.6 for MR).

10. List of documents attached to this proposal 10.1. List of documents attached to this proposal Document Number Document Section Mandatory File Signature of MOH and MOF.pdf 1 MoH Signature (or delegated authority) of Proposal 4.1.1 File desc: MOH Signature page Date/time: 9/12/2013 6:54:15 PM Size: 63034 Signature of MOH and MOF.pdf 2 MoF Signature (or delegated authority) of Proposal 4.1.1 File desc: MOF Signature page Date/time: 9/12/2013 6:51:11 PM Size: 63034 TOR of ICC .docx 4 Terms of Reference for the ICC 4.1.2 File desc: Date/time: 9/9/2013 12:21:20 AM Size: 16422 ICC Meeting Minutes 02-2013.pdf 5 Minutes of ICC/HSCC meeting endorsing Proposal 4.1.3 File desc: Date/time: 9/9/2013 12:20:15 AM Size: 109776 ICC Signature Page.pdf 6 Signatures of ICC or HSCC or equivalent in Proposal 4.1.3 File desc: ICC Signature page Date/time: 9/12/2013 12:45:25 AM Size: 352762 ICC Minute No 01-2013.pdf 7 Minutes of last three ICC/HSCC meetings 4.1.3 File desc: ICC Meeting minutes 2 Date/time: 8/29/2013 4:24:52 AM Size: 110147 PNG cMYP 2011-2015_FINAL FOR PRINTING.pdf 10 comprehensive Multi Year Plan - cMYP 5.1 File desc: Date/time: 8/29/2013 4:16:50 AM Size: 1246991 PNG cMYP Tables for Costing and Financing (Yoshi - 08May2010AMl) (2).xls 11 cMYP Costing tool for financial analysis 5.1 File desc: Date/time: 8/29/2013 4:17:40 AM Size: 341504 Plan for Introduction of Rubella Vaccine in PNG- Rev 18.10.2013.docx 12 Plan for NVS introduction (if not part of cMYP) 5.1 File desc: Date/time: 10/21/2013 4:20:43 AM Size: 29133 TARGET MR CAMPAIGN ESTIMATE-2015.xlsx 18 Campaign target population documentation 7.x.1 File desc: Date/time: 8/30/2013 2:43:39 AM Size: 19820 Commitment letter from Secretary on Routine Introduction of Rubella.pdf 19 Evidence of introduction of RCV in routine programme 7.3.3 File desc: Letter from Secretary as a commitment Date/time: 9/9/2013 11:54:12 PM Size: 267279 EVM_PNG Report_21.10.2011-Sec Signed.pdf 20 EVM report 8.3 File desc: Date/time: 8/29/2013 4:22:53 AM Size: 862492 EVM_PNG Report_21.10.2011-Sec Signed.pdf 21 Improvement plan based on EVM 8.3 File desc: Date/time: 8/29/2013 4:21:01 AM Size: 862492 STATUS OF IMPROVEMENT PLAN ON EVM RECOMMENDATIONS April 2013.doc 22 EVM improvement plan progress report 8.3 File desc: Date/time: 8/29/2013 4:19:36 AM Size: 83968 GAVI IRC RESPONSE PNG (24.01.2014).docx 23 Summary of response to conditions 3 File desc: Date/time: 1/23/2014 8:17:18 PM Size: 47741

11. Annexes Annex 1 - NVS Routine Support Annex 1.1 - NVS Routine Support (Measles second dose, 10 dose(s) per vial, LYOPHILISED) Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ 2015 Number of vaccine doses # 0 Number of AD syringes # 0 Number of re-constitution syringes # 0 Number of safety boxes # 0 Total value to be co-financed by the Country [1] $ 0 Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ 2015 Number of vaccine doses # 124,100 Number of AD syringes # 110,300 Number of re-constitution syringes # 13,800 Number of safety boxes # 1,400 Total value to be co-financed by GAVI $ 53,000

Table Annex 1.1 C: Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED ID Data from 2015 Number of surviving infants Table 5.2 # 223,679 Number of children to be vaccinated with the first dose Table 5.2 # 174,462 Number of children to be vaccinated with the second dose Table 5.2 # 74,560 Immunisation coverage with the second dose Table 5.2 % 33.00 % Number of doses per child Parameter # 1 Estimated vaccine wastage factor Table 5.2 # 1.33 Number of doses per vial Parameter # 10 AD syringes required Parameter # Yes Reconstitution syringes required Parameter # Yes Safety boxes required Parameter # Yes g Vaccine price per dose Table Annexes 4A $ 0.322 cc Country co-financing per dose Table 6.4.1 $ 0 ca AD syringe price per unit Table Annexes 4A $ 0.0465 cr Reconstitution syringe price per unit Table Annexes 4A $ 0.037 cs Safety box price per unit Table Annexes 4A $ 0.58 fv Freight cost as % of vaccines value Table Annexes 4B % 14.00 % fd Freight cost as % of devices value Parameter % 10.00 %

Table Annex 1.1 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Formula 2015 Total Government GAVI A Country co-finance V 0.00 % B Number of children to be vaccinated with the first dose Table 5.2.1 74,560 0 74,560 C Number of doses per child Vaccine parameter (schedule) 1 D Number of doses needed B x C 74,560 0 74,560 E Estimated vaccine wastage factor Table 5.2.1 1.33 F Number of doses needed including wastage D x E 99,165 0 99,165 G Vaccines buffer stock (F – F of previous year) * 0.25 24,792 0 24,792 I Total vaccine doses needed (((F + G) / Vaccine package size) + 1) * Vaccine package size 124,057 0 124,057 J Number of doses per vial Vaccine parameter 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 110,281 0 110,281 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 13,771 0 13,771 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 1,377 0 1,377 N Cost of vaccines needed I x g 39,947 0 39,947 O Cost of AD syringes needed K x ca 5,129 0 5,129 P Cost of reconstitution syringes needed L x cr 510 0 510 Q Cost of safety boxes needed M x cs 799 0 799 R Freight cost for vaccines needed N x fv 5,593 0 5,593 S Freight cost for devices needed (O+P+Q) x fd 644 0 644 T Total fund needed (N+O+P+Q+R+S) 52,622 0 52,622 U Total country co-financing I x country co-financing per dose (cc) 0 V Country co-financing % of GAVI supported proportion U / T 0.00 %

Annex 2 - NVS Routine – Preferred Second Presentation No NVS Routine – Preferred Second Presentation requested this year

Annex 3 - NVS Preventive campaign(s) Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED) Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED Data from 2015 Total campaign population Table 5.3.1 # 3,003,922 Immunization coverage Table 5.3.1 % 100.00 % Number of persons to be vaccinated Table 5.3.1 # 3,003,922 Number of doses per persons Parameter # 1 Estimated vaccine wastage factor Table 5.3.1 # 1.18 Vaccine stock on 31st December <span style="background-color:#D9D9D9">{0}</span> * (see explanation footnote) Table 5.3.1 # 0 Number of doses per vial Parameter # 10 AD syringes required Parameter # Yes Reconstitution syringes required Parameter # Yes Safety boxes required Parameter # Yes Vaccine price per dose Table Annexes 4A $ 0.578 AD syringe price per unit Table Annexes 4A $ 0.0465 Reconstitution syringe price per unit Table Annexes 4A $ 0.037 Safety box price per unit Table Annexes 4A $ 0.58 Freight cost as % of vaccines value Table Annexes 4B % 13.00 % Freight cost as % of devices value Parameter % 10.00 %

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1) Formula GAVI 2015 B Number of persons to be vaccinated with the first dose Table 5.2.1 3,003,922 C Number of doses per persons 1 D Number of doses needed B x C 3,003,922 E Estimated vaccine wastage factor Table 5.2.1 1.18 F Number of doses needed including wastage D x E 3,544,628 G Vaccines buffer stock (F – F of previous year) * 0.25 0 I Total vaccine doses needed (((F + G) / Vaccine package size) + 1) * Vaccine package size 3,544,728 J Number of doses per vial Vaccine parameter 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 3,334,354 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 393,465 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 41,379 N Cost of vaccines needed I x g 2,048,853 O Cost of AD syringes needed K x ca 155,047.46 P Cost of reconstitution syringes needed L x cr 14,559 Q Cost of safety boxes needed M x cs 24,000 R Freight cost for vaccines needed N x fv 0 S Freight cost for devices needed (O+P+Q) x fd 19,361 T Total fund needed (N+O+P+Q+R+S) 2,261,820.46 Note: There is no cofinancing for NVS preventive campaigns

| Annex 4 Table Annex 4A: Commodities Cost Vaccine Presentation 2015 2016 DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 2.099 2.080 DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 2.099 2.080 DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 2.099 2.080 HPV bivalent, 2 dose(s) per vial, LIQUID 2 4.550 4.500 HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 4.550 4.500 Measles second dose, 10 dose(s) per vial, LYOPHILISED 10 0.322 0.336 Meningococcal type A, 10 dose(s) per vial, LYOPHILISED 10 0.554 0.554 MR, 10 dose(s) per vial, LYOPHILISED 10 0.578 0.606 Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 3.500 3.500 Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 3.500 3.500 Rotavirus, 2-dose schedule 1 2.390 2.390 Rotavirus, 3-dose schedule 1 3.500 3.500 Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 0.880 0.880 Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 0.880 0.880 Supply Form 2015 2016 AD-SYRINGE SYRINGE 0.047 0.047 RECONSTIT-SYRINGE-PENTAVAL SYRINGE 0.037 0.037 RECONSTIT-SYRINGE-YF SYRINGE 0.037 0.037 SAFETY-BOX SAFETYBOX 0.580 0.580 Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised) Table Annex 4B: Freight cost as percentage of value Vaccine Antigen Vaccine Type No Threshold 500,000$ <= > DTP-HepB-Hib HEPBHIB 25.50 % 6.40 % HPV bivalent HPV 3.50 % HPV quadrivalent HPV 3.50 % Measles second dose MEASLES 14.00 % Meningococcal type A MENINACONJUGATE 10.20 % MR MR 13.20 % Pneumococcal (PCV10) PNEUMO 3.00 % Pneumococcal (PCV13) PNEUMO 6.00 % Rotavirus ROTA 5.00 % Yellow Fever YF 7.80 % Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. Vaccine 2015 Measles second dose, 10 dose(s) per vial, LYOPHILISED 0 |  |
| --- | --- |

Table Annex 4D: Wastage rates and factors The following table shows the wastage rates for routine and campaign vaccines, set for 2015. Vaccine dose(s) per vial Maximum Vaccine wastage rate* Benchmark Wastage Rate** DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 5 % DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 25 % 15 % DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 10 % HPV bivalent, 2 dose(s) per vial, LIQUID 2 10 % HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5 % Measles second dose, 10 dose(s) per vial, LYOPHILISED 10 40 % Meningococcal type A, 10 dose(s) per vial, LYOPHILISED 10 10 % MR, 10 dose(s) per vial, LYOPHILISED 10 15 % Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 10 % Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 5 % Rotavirus, 2-dose schedule 1 5 % Rotavirus, 3-dose schedule 1 5 % Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 40 % Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 10 % Comments: * Source - WHO indicative wastage rates ** Source - Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat Note: HPV demonstration project wastage rates are the same as the vaccine Table Annex 4E: Vaccine maximum packed volumes Kindly note that this table is for reference purposes only and includes GAVI- and non GAVI-supported vaccines. Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella freeze dried MR lyophilized SC 1 1 26.1 26.1 Measles-Rubella freeze dried MR lyophilized SC 1 2 13.1 13.1 Measles-Rubella freeze dried MR lyophilized SC 1 5 5.2 7 Measles-Rubella freeze dried MR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP-Hib liquid IM 3 1 32.3 DTP-HepB liquid + Hib freeze-dried DTP-Hib liquid IM 3 10 2.5 DTP-HepB liquid + Hib freeze-dried DTP-HepB+Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB+Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized SC 2 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 3 10 15 Japanese Encephalitis JE_lyo lyophilized SC 3 10 8.1 8.1 Japanese Encephalitis JE_lyo lyophilized SC 3 5 2.5 2.9 Japanese Encephalitis JE_lyo lyophilized SC 3 1 12.6 11.5 Japanese Encephalitis JE_liq liquid SC 3 10 3.4 Rota vaccine Rota_lyo lyophilized Oral 2 1 156 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 PFS 55.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 1 21 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Papilomavirus vaccine HPV liquid IM 3 1 15 Human Papilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5

12. Banking Form In accordance with the decision on financial support made by the GAVI Alliance, the Government of Papua New Guinea hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): HEALTH SECTOR IMPROVEMENT PROGRAM / NATIONAL DEPARTMENT OF HEALTH Address: P.O BOX 807, WAIGANI, NATIONAL CAPITAL DISTRICT, PAPUA NEW GUINEA City Country: NATIONAL CAPITAL DISTRICT, PAPUA NEW GUINEA Telephone no.: (675) 3013691, (675) 3013670 Fax no.: (675) 323 2630 Currency of the bank account: US DOLLAR For credit to: Bank account's title: HEALTH SECTOR IMPROVEMENT PROGRAM US DOLLAR TRUST ACCOUNT Bank account no.: 1001592378 (COCA ACC) Bank's name: BANK SOUTH PACIFIC (BSP) Is the bank account exclusively to be used by this program? True By who is the account audited? RAJA & ASSOCIATES, P.O BOX 3312, BOROKO, NCD PAPUA NEW GUINEA, PH: 3200740, FAX 3200101 Signature of Government's authorizing official Seal Name: MR. PAUL DOPSIE Title: EXECUTIVE MANAGER CORPORATE SERVICES Signature: Date: FINANCIAL INSTITUTION Bank Name: Branch Name: Address: City Country: Swift Code: Sort Code: ABA No.: Telephone No.: FAX No.: CORRESPONDENT BANK (In the United States) I certify that the account No is held by at this banking institution The account is to be signed jointly by at least (number of signatories) of the following authorized signatories: 1 Name: Title: 2 Name: Title: 3 Name: Title: Name of bank's authorizing official Signature: Date: Seal: