|  |  | [V1.3] |  |
| --- | --- | --- | --- |
| GAVI Alliance Application Form for Country Proposals For Support to: Routine New Vaccines Support Submitted by The Government of Rwanda Date of submission: 15 September 2014 Deadline for submission: 17 September 2014 Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) Start Year 2013 End Year 2017 Form revised in 2014 (To be used with Guidelines of April 2014) Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public. |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland . The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. Application Specification Please specify for which type of GAVI support you would like to apply to. Type of Support Vaccine Start Year End Year Preferred second presentation[1] Routine New Vaccines Support Measles second dose, 10 dose(s) per vial, LYOPHILISED 2015 2017 [1] GAVI may not be in a position to accommodate all countries first product preferences, and in such cases, GAVI will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country.

2. Table of Contents 1. Application Specification 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation 4.1.3. Signature Table for the Coordinating Committee for Immunisation 4.2. National Immunization Technical Advisory Group 4.2.1. The NITAG 5. Immunisation Programme Data 5.1 Background information 5.1.1 Lessons learned 5.1.2 Health planning and budgeting 5.1.3 Preparatory activities 5.1.4 Gender and equity 5.1.5 Data quality 5.2. Baseline and Annual Targets (NVS Routine Support) 5.3. Targets for Preventive Campaign(s) 6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) 6.2 Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED) 6.2.1 Specifications of vaccinations with new vaccine 6.2.2 New and Under-Used Vaccine Introduction Grant 6.2.3 Technical assistance 7. NVS Preventive Campains 8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine 8.2 Procurement and Management for NVS Preventive Campaign(s) 8.3 Vaccine Management (EVSM/EVM/VMA) 8.4 Waste management 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) 10. List of documents attached to this proposal 11. Annexes Annex 1 - NVS Routine Support Annex 1.1 Measles second dose, 10 dose(s) per vial, LYOPHILISED Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ Table Annex 1.1 C Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED Table Annex 1.1 D Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Annex 2 - NVS Routine – Preferred Second Presentation Annex 3 - NVS Preventive campaign(s) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking Form

3. Executive Summary Please provide a summary of your country's proposal, including the following the information: l For each specific request, NVS routine support or NVS campaign : ¡ The duration of support ¡ The total amount of funds ¡ Details of the vaccine(s), if applicable, including the reason for the choice of presentation ¡ Projected month and year of introduction of the vaccine l Relevant baseline data, including: ¡ DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) ¡ Birth cohort, targets and immunisation coverage by vaccines l Country preparedness ¡ Summary of EVM assessment and progress on EVM improvement plan l The nature of stakeholders' participation in developing this proposal ¡ Inter-Agency Coordinating Committee ¡ Partners Government of Rwanda is fully committed inachieving the mid decade goals 4 and 5 (MDG 4 and 5) by 2015. For this reason,it takes all the available opportunities to reduce considerably the mortalityand morbidity among the targeted population. Rwanda, through its Vaccine Program, has a goal to contribute to a better child survival byreducing the morbidity and the mortality due to immunization preventablediseases among the children< 5 years old. The Government of Rwandacontributes, to the payment of immunization activity costs both forco-financing with GAVI Alliance and GoR fully pay all costs for traditionalvaccines. From 2002up to now ,Rwanda has successfully introduced six life-saving vaccines(Hepatitis B vaccine, HaemophilusInfluenzae type b, Pneumococcal Conjugate Vaccine, Rotavirus Vaccine,Humanpapilloma Virus Vaccine and Measles & Rubella combined vaccine). All thesevaccines are co-financed both by the Government of Rwand and GAVI Alliance (based on the proportion definedby GAVI for low income countries). In accordance withWHO’s recommendation, last year March2013Rwanda has conducted an immunization campaign to wider group of eligiblechildren for both Measles and Rubella combined vaccine. Sincethen the Government ofRwanda has decided to took advantage ofthe measles platform of two doses of measles vaccine to introducerubella-containing vaccine (RCV) in routine immunization program since January2014 According to the last Routine ImmunizationCoverage Evaluation Survey conducted in March 2013, national first dosecoverage of Measles immunization coverage at national level is 97% and DHS 2010 showed that this coverage was95%. Considering both the small percentage of unimmunized children which rangebetween 3-5% and the vaccine efficacy which is is 85% for all childrenvaccinated, there are a lot of susceptible which need a booster dose to avoid outbreaksof measles and to increase cross protection immunity among total population. Ontop of that measles seconde dose wouldplay an opportunity or chance for those who did not sero-convert with the MCV1and raise the herd immunity Through the opportunity offered by GAVI, Rwandawould like to to introduce a Second Dose of Measles-containing vaccination(MCV2) into its routine immunization Schedule. After guidance fromSAGE, Rwanda will introduce MR vaccine both at 9 months and 15 months to reducewastage rate, to facilitate logistics issues. Rwanda is committed to co-financeRubella component and GAVI to support Measles second dose in full. The Presentationbeing 10dose-vial Lyophilized. Theduration of support The duration of support is for 3years (2015-2017) according to the duration of the cMYP. As the first dose vaccination(MCV1) is administered at 9month of age, the MCV2 will be administered at 15month of age in accordance with ICC recommendation. Birthcohort: 2013 (322079), 2014 (329491), 2015 (336669), 2016 (343733),2017 (350803) These figures are based on 2012 census projection Relevant baseline data (WHO/UNICEF Joint Reporting Form) in 2013: BCG 99% OPV3 100% DTP3 100% Measles 98% Country preparedness: In November 2013 and June2014, EPI Rwanda conducted respectively a comprehensive coldchain assessment to ascertain the cold chain capacity at each level and an EVM assessment and identified areas for improvement as follows: - Reinforce the regular use of the manual temperature records through a monthly temperaturereview process - Increase storage capacity for vaccine storage and transport - Institute planned preventive maintenance and its record - Enhance stock management system by providing computerized stock management tool to all DH. - Reinforce the use of appropriate stock management vouchers - Establish an effective and functional supportive supervision between - Review the EPI supportive supervision and checklists Stakeholders’participation in developing this proposal: The key stakeholders from Ministry of health, UNICEF, WHO and USAID jointly meet as EPI Advisory committee which is part of ICC to develop this proposal and present it to senior ICC members comprising of Minister of health, Ministry of Finance, Heads of agencies and private sectors.

4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation The Government of Rwanda would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests GAVI support for: Measles second dose, 10 dose(s) per vial, LYOPHILISED routine introduction The Government of Rwanda commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 1 and 2 in Section 10. Attachments. Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name Dr Agnes BINAGWAHO Name Amb. Claver GATETE Date Date Signature Signature This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document): Full name Position Telephone Email Mr GATERA Maurice EPI Manager +25075152534 gamaurice2003@gmail.com 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. Profile of the ICC, HSCC, or equivalent committee Name of the committee Inter-Agency Coordinating Committee Year of constitution of the current committee 1996 Organisational structure (e.g., sub-committee, stand-alone) Stand alone committee Frequency of meetings Quarterly The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4. Major functions and responsibilities of the ICC/HSCC: Major functions and responsibilities of the ICC/HSCC: 1. Share technical, financial and logistics information related to immunization services; 2. Coordinate and guide the use of GAVI and partners funds for immunization 3. Coordinate partners' interventions to better support immunization program 4. Support technically and financially the EPI program in order to meet the targeted goals 5. Advocacy and resource mobilization to support the program Please describe how partners have provided support in preparation of the proposal: Firstly, UNICEF, WHOtechnical team have been together with M&E team and Immunization Programdirector to develop this proposal after ICC has been informed about theopportunity of funding MCV2. Ministry of Finance g=has been consulted about theavailability of funds. The Immunization Program developed and for each step the review havebeen made accordingly. Senior management meeting for both RBC and MoH wereinformed and the proposal has been presented before final approval to ICC. 4.1.3. Signature Table for the Coordinating Committee for Immunisation We the members of the ICC, HSCC, or equivalent committee [1] met on the 09/09/2014 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 6 (please use the list for signatures in the section below). Please refer to Annex C of the ‘GAVI HSS and NVS General Guidelines’ for more information on ICCs. Function Title / Organisation Name Please sign below to indicate the attendance at the meeting where the proposal was endorsed Please sign below to indicate the endorsement of the minutes where the proposal was discussed Chair Minister of Health Dr Agnes BINAGWAHO Secretary EPI Manager GATERA Maurice Members Country representative/WHO Martins OVBEREDJO Country representative/UNICEF Noala SKINNER INTERNATIONAL ROTARY CLUB Antoine MUYOMBANO BUFMAR Ernest RWAGASANA USAID Peter MALNAK URUNANA DEVELOPMENT COMMUNICATION George GAHENDA RWANDA RED CROSS KARAMAGA Appolinaire By submitting the proposal we confirm that the quorum has been met. Yes The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 7. 4.2. National Immunization Technical Advisory Group Has a NITAG been established in the country ? Not selected In the absence of a NITAG, countries should clarify the role and functioning of the advisory group and describe plans to establish a NITAG. This document is attached as (Document Number: 9)

5. Immunisation Programme Data 5.1 Background information Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document. ▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 10. Please attach the cMYP costing tool as DOCUMENT NUMBER 11. ▪ Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12 ▪ Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate. Please use the most recent data available and specify the source and date. Figure Year Source Total population 10,738,653 2013 2012 Census projection based on 2.6 % growth rate Infant mortality rate (per 1000) 50 2010 Demographic health Survey 2010 Surviving infants[1] 322,079 2013 Census 2012 population projections GNI per capita (US$) 613 2012 World Bank Branch, 2012 Total Health Expenditure (THE) as a percentage of GDP 48 % 2011 Ministry Of Finance General government expenditure on health (GGHE) as % of General government expenditure 16 % 2011 Ministry Of Finance [1] Surviving infants = Infants surviving the first 12 months of life 5.1.1 Lessons learned Routine New Vaccines Support If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points or actions taken to address them. Please refer to previous Post Introduction Evaluations (PIE), if applicable. If they are included in the Introduction Plan, please cite the section only. Lessons Learned Action Points Cold chain expansion and management are key area to address when planning for new vaccine introduction In 2011, EPI with support from its partners conducted EVM and develop an Improvement plan to prepare the introduction of rotavirus vaccine and HPV vaccine and advocate for cold chain expansion; (2) EPI updated the inventory of cold chain equipment based on the revision of cold chain capacity. Recently, In November 2013 and June 2014, EPI Rwanda conducted respectively a comprehensive cold chain assessment to ascertain the cold chain capacity at each level and an EVM assessment and identified areas for improvement Planning for cold chain storage capacity, transportation and vaccine management is very important when planning for new vaccine introduction. This will help to minimize wastage (vaccine damage by heat and freezing) Additional cold chain monitoring devices was procured by the Government and its Partners (USAID). Training and Supportive supervision was intensified by central EPI staff. New vaccine introduction requires prior training of all personnel participating in vaccination activities, not only for the vaccine in question but also for all technical areas of vaccination to insure quality services. EPI staff, with technical support from partners, adapted training module for new vaccine introduction, trained the trainers and the health workers using a pooled approach. Developing specific key messages to address concerns of parents and of health workers is very important for the acceptation of the new vaccine Key messages were developed, media for transmission of messages identified and used. Revision of recording , reporting tools and of the immunization policy documents (even of immunization data base) is important Partners assisted the program with the revision of EPI management tools (recording, reporting and EPI policy documents) 5.1.2 Health planning and budgeting Please provide information on the planning and budgeting cycle in your country The budgeted annual action plan is prepared based on the health sector’s strategic plan. Planning process is conducted and starting everyyear by April. Developed plans are sent to the MOH for consolidation. MOHintegrates different plans from different divisions and units to have oneHealth Sector annual action plan. EPI action plan is always withdrawn from cMYP (where all the objectives and strategies were defined for specific year ofthe cycle of the cMYP) and then be consolidated together with National Healthsector action plan. Please indicate the name and date of the relevant planning document for health Relevant planning documents and date: 1. Health Sector Strategic Plan III (2012-2018) 2. Comprehensive Multi-Year Plan (cMYP 2013-2017) 3. Annual EPI Plan 2013-2014 4. New & underused vaccine introduction plans (HPV 2014 and MSD/RCV 2013) Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.) Yes but some difference on population figures are observed due to census conducted in 2012. In fact, cMYP has been revised before publication of the results from 2012 census. Please indicate the national planning budgeting cycle for health July-June of proceeding year Please indicate the national planning cycle for immunisation July-June of proceeding year 5.1.3 Preparatory activities Please provide an outline of all preparatory activities for vaccine(s) introduction or campaigns. If they are included in detail the Introduction Plan and/or Plan of Action, please cite the sections only. Preparatory activities for new vaccine introduction: · Assessment of the magnitude of the problem and inform decision makers on new vaccine introduction · Initiate the development of proposal with all the required documents (Updated cMYP, introductionplan) · Call for ICC to endorse the proposal before submission · Submit proposal to GAVI Secretariat If approved by GAVI, the preparation phase stats (advocacy for vaccine introduction support, upgrade cold chain, revision of EPI management tools,training of health workers, surveillance for the disease and AEFI, development of key messages to parents and health workers) 5.1.4 Gender and equity Please describe any barriers in access to immunisation services that are related to geographic, socio-economic and/or gender equity and actions taken to mitigate these barriers. Highlight where these issues are addressed in the vaccine introduction plan(s). Rwanda has more than 500 Health facilities andall of them are doing immunization services, for geographic accessibility,Rwanda is a small country and health services are near the population. Rwanda is planning to build additional health posts across the country and all of themwill be equipped with vaccine and vaccine materials. Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s). Immunization services delivery in Rwanda are providedby either male or female. The social mobilization activities led bycommunityhealth workers team in the community is composed both male and femalewho pray abig role in the immunization program in the community. Both parentsbear the sameresponsibility on their children as far as vaccination isconcerned, butfrequently mothers are the ones accompanying the children at thetime ofimmunization session Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems. The data for sex-disaggregated onimmunization services access in Rwanda is not available simply because apartfrom HPV vaccines which targets adolescent girls, all Rwandan children eligibleto any immunization services would get it without considering whether she/he isfemale or male and therefore there is no discrepancies in reaching Is the country currently in a situation of fragility (eg. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities. No, Rwanda is a stable and secured country with a strong health system. If available, please provide additional information and documents on subnational coverage data, e.g. comparing urban/rural districts or districts with highest/lowest coverage, etc. N/A 5.1.5 Data quality Please attach a data quality assessment report, if one has been completed within the previous 36 months (DOCUMENT NUMBER : 14). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER : 15, DOCUMENT NUMBER : 16). If DQA not available, please briefly describe plans to establish mechanisms for data quality assessment. Brief description plans to establish mechanisms for data quality assessment: - Monthly meeting at central level including partners to analyze administrative data (Routine immunization dataandsurveillance data) and give orientation for improvement - Quarterly coordination meetings between central level and district teams where data quality issues are discussed - Reinforce the supportive supervision to the poorly performing districts andconduct quarterly DQA and share feed back.

5.2. Baseline and Annual Targets (NVS Routine Support) Please refer to cMYP pages to assist in filling-in this section. Number Base Year Baseline and Targets 2013 2015 2016 2017 Total births 338,183 353,502 360,920 368,343 Total infants’ deaths 16,104 16,833 17,187 17,540 Total surviving infants 322,079 336,669 343,733 350,803 Total pregnant women 338,183 353,502 360,920 368,343 Target population vaccinated with OPV3 OPV3 coverage 100 % 100 % 100 % 100 % Number of infants vaccinated (to be vaccinated) with DTP1 327,728 336,669 343,733 350,803 Number of infants vaccinated (to be vaccinated) with DTP3 323,218 336,669 343,733 350,803 DTP3 coverage 100 % 100 % 100 % 100 % Wastage[1] rate in base-year and planned thereafter (%) for DTP 1 1 1 1 Wastage[1] factor in base-year and planned thereafter for DTP 1.01 1.01 1.01 1.01 Target population vaccinated with 1st dose of Measles 316,229 319,836 326,546 333,263 Target population vaccinated with 2nd dose of Measles 0 319,836 326,546 333,263 Measles second dose coverage 0 % 95 % 95 % 95 % First Presentation: Measles second dose, 10 dose(s) per vial, LYOPHILISED Wastage[1] rate in base-year and planned thereafter (%) {0} 1 1 1 1 Wastage[1] factor in base-year and planned thereafter (%) 1.01 1.01 1.01 1.01 Maximum wastage rate value for Measles second dose, 10 dose(s) per vial, LYOPHILISED 40 % 40 % 40 % 40 % Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100 1 % 0 % 0 % 0 % [1] Number of infants vaccinated out of total births [2] Number of infants vaccinated out of total surviving infants [3] Indicate total number of children vaccinated with either DTP alone or combined [4] Number of pregnant women vaccinated with TT+ out of total pregnant women [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period. [1] Number of infants vaccinated out of total births [2] Number of infants vaccinated out of total surviving infants [3] Indicate total number of children vaccinated with either DTP alone or combined [4] Number of pregnant women vaccinated with TT+ out of total pregnant women [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

5.3. Targets for Preventive Campaign(s) No NVS Prevention Campaign Support this year

6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) If already included in detail in the Introduction Plan or Plan of Action, please cite the section only. Disease Title of the assessment Date Results No,the EPI review especially the section related to VPD surveillance is planned before the end of this year. N/A N/A N/A

| 6.2. Requested vaccine (Measles second dose, 10 dose(s) per vial, LYOPHILISED) As reported in the cMYP, the country plans to introduce Measles second dose, using Measles second dose, 10 dose(s) per vial, LYOPHILISED. When is the country planning to introduce this vaccine? January 2015 Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address these issues. Currently the Measles 5-dose vial presentation is not available, but please indicate if the country would prefer this presentation if it becomes available. Yes If the country is introducting measles-rubella (MR) in the routine system, is the country planning to switch the second dose of measles to MR as well, in addition to the first MR dose? No If [YES], when? January 2015 Please note that if the country is planning to switch the routine second dose of measles to MR, the country will be required to finance the rubella component, in addition to financing the routine first dose of MR. 6.2.1. Specifications of vaccinations with new vaccine Data from Year 1 Year 2 Year 3 2015 2016 2017 Number of children to be vaccinated with the second dose Table 5.2 # 319,836 326,546 333,263 Immunisation coverage with the second dose Table 5.2 # 95 % 95 % 95 % |  |
| --- | --- |

6.2.2. New and Under-Used Vaccine Introduction Grant Calculation of Vaccine Introduction Grant for the Measles second dose, 10 dose(s) per vial, LYOPHILISED Year of New Vaccine Introduction Births (from Table 5.2) Share per Birth in US$ Total in US$ 2015 353,502 0.80 282,802 The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000 Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan). The Grant will be transfered to SPIU thendisbursement will be from SPIU to EPI . Some activities to be implemented byDistricts, there will be micro planning with districts before disbursement isdone. ICC will oversee all activities to be done and to approve them. Throughpurchase orders, internal memo and commitment all activities will be done ontime. Please summarise in the table below the full costs of preparing for and introducing the vaccine, and specify which items are expected to be covered with the one-time GAVI grant. Please complete also the ‘Detailed budget for VIG / Operational costs’ template provided by GAVI and attach as a mandatory document in the Attachment section. Detailed budget attached as Document No. 25. Cost (and finance) to introduce the Measles second dose, 10 dose(s) per vial, LYOPHILISED US$ Government support Partners' support* GAVI support Cost Category TOTAL COST US$ Amount US$ Name(s) Amount US$ Amount requested US$ 1 Program management and coordination 6,618 0 0 6618 2 Planning and preparations 24,265 0 0 24265 3 Social mobilization, IEC and advocacy 70,515 0 0 70515 4 Other training and meetings 120,221 0 0 120221 5 Document production 214,779 200,000 0 14779 6 Human resources and incentives 0 0 0 0 7 Cold chain equipment 0 0 0 0 8 Transport for implementation and supervision 0 0 0 0 9 Immunisation session supplies 12,941 0 0 12941 10 Waste management 5,147 0 0 5147 11 Surveillance and monitoring 0 0 0 0 12 Evaluation 13,676 0 0 13676 13 Technical assistance 13,235 0 0 13235 14 Data management 0 0 0 0 Other (please specify) Total 481,397 200,000 0 281397 * If more than one partner is providing financial support to a specific cost category, please list all partners for that category and the amount of support provided. Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs. Exactly GAVI funds will not cover all needs, but there is an opportunity that Government of Rwanda will support the remaining Items to be funded. This includes the production of Data collection tools and Payment of salaries and incentives of Health workers. We have not included the the payment of health workers in above table because the payment of Health workers is continuous and it is done on monthly basis. 6.2.3.Technical assistance Please describe any particular area(s) the Ministry would require technical assistance to support the introduction of Measles second dose. The technical assistance will be needed to carry out the Post Introduction Evaluation (PIE). For introduction as well as the implementation, the technical assistance will not be necessary.

7. NVS Preventive Campains No NVS Prevention Campaign Support this year

8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC). a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF): As in the past, for vaccines and injection supplies, Government of Rwanda will use UNICEF channels for procurement. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document l Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used. l The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality. No alternative mechanism for procurement and delivery of vaccines supply is used in Rwanda. All vaccines and injection supplies are procured through UNICEF channels. c) Please indicate how funds should be transferred by the GAVI Alliance (if applicable) For introduction cash grant, management will bedone according to GAVI principle through SPIU d) Please indicate how the co-financing amounts will be paid (and who is responsible for this) Amount of fund for low income countries forMSDvaccine co-financing for low income countries (as the case for Rwanda withGNIof $ 570 per capita) which is $0.20 per dose has been fixed. Ministry ofHealth in collaboration with Ministry of Finance will transfer fund to UNICEF Copenhagenbased onthe GAVI estimates (secured resource of funding from the Government). e) Please describe the financial management procedures that will be applied for the management of the NVS cash support, including procurement. For the NVS cash support, the Ministry of Healthwill be the lead implementer through Single Project Implementation Unit (SPIU). About procurement of new vaccines and injectionmaterials, GAVI will transfer fundsto UNICEF Copenhagen for vaccines andinjection supplies procurement. UNICEFwill procure vaccines and injectionmaterials and deliver to country. f) Please outline how coverage of the introduced vaccine will be monitored, reported and evaluated (refer to cMYP and Introduction Plan) a) Administratively, coverage will be monitored throughmonthly reports at the health centers to the national level andquarterly thoughreview meetings. b) Annually reports coverage will be reported toGAVI through annual progress reports (APR) using MOH/WHO/UNICEF joint reportingform. g) If applying for measles second dose, does the country wish to have the support in cash or in-kind? In-kind 8.2 Procurement and Management for NVS Preventive Campaign(s) No NVS Prevention Campaign Support this year

8.3 Vaccine Management (EVSM/EVM/VMA) It is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 36 months. When was the EVM conducted? June 2014 Please attach the most recent EVM report (DOCUMENT NUMBER : 22,23,24), the corresponding EVM improvement plan (DOCUMENT NUMBER : 23) and progress on the EVM improvement plan (DOCUMENT NUMBER : 24). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation. When is the next Effective Vaccine Management (EVM) Assessment planned? January Not planned 8.4 Waste management Countries must have a waste management and monitoring plan as appropriate for their immunisation activities (especially for campaigns). This should include details on the safe handling, storage, transportation and disposal of immunisation waste, as part of a healthcare waste management strategy. Please describe in detail, the country’s waste management plan for immunisation activities (including campaigns). All the wastes generated by vaccine, will be collected in safety boxes and incinerated (health centers or at district hospitals).

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

10. List of documents attached to this proposal 10.1. List of documents attached to this proposal Document Number Document Section Mandatory File 1 MoH Signature (or delegated authority) of Proposal 4.1.1 Minister's signature for MSD proposal.pdf File desc: Date/time : 15/09/2014 11:02:54 Size: 336 KB 2 MoF Signature (or delegated authority) of Proposal 4.1.1 Minister's signature for MSD proposal.pdf File desc: Date/time : 15/09/2014 11:03:20 Size: 336 KB 3 MoE signature (or delegated authority) of HPV Proposal 4.1.1 No file loaded 4 Terms of Reference for the ICC 4.1.2 ICC minute of May 13,2014 endorsing ICC ToRs.pdf File desc: Date/time : 15/09/2014 11:14:14 Size: 1 MB 5 Minutes of ICC/HSCC meeting endorsing Proposal 4.1.3 ICC meeting report endorsing the minutes of proposals.pdf File desc: Date/time : 15/09/2014 11:53:18 Size: 1 MB ICC meeting report endorsing the proposal.pdf File desc: Date/time : 15/09/2014 11:31:59 Size: 1 MB 6 Signatures of ICC or HSCC or equivalent in Proposal 4.1.3 Measles application endorsement by ICC members.pdf File desc: Date/time : 15/09/2014 11:18:47 Size: 386 KB 7 Minutes of last three ICC/HSCC meetings 4.1.3 ICC Meeting's report 17-5-2013.pdf File desc: Date/time : 15/09/2014 12:23:11 Size: 2 MB ICC minute of May 13,2014.pdf File desc: Date/time : 15/09/2014 12:08:34 Size: 1 MB ICC minute&attendance list 10Sept2013.pdf File desc: Date/time : 15/09/2014 12:24:11 Size: 2 MB 8 Minutes of NITAG meeting with specific recommendations on the NVS introduction or campaign 4.2 No file loaded 9 Role and functioning of the advisory group, description of plans to establish a NITAG 4.2.1 Role and functioning of the advisory group.doc File desc: Date/time : 15/09/2014 01:08:31 Size: 34 KB 10 comprehensive Multi Year Plan - cMYP 5.1 cMYP signature.pdf File desc: Date/time : 15/09/2014 11:59:39 Size: 321 KB Revised_cMYP_08.12.doc File desc: Date/time : 15/09/2014 11:58:36 Size: 13 MB 11 cMYP Costing tool for financial analysis 5.1 cMYP_Costing_Tool_RWA_En-1.xls File desc: Date/time : 15/09/2014 12:02:04 Size: 3 MB 12 Vaccine introduction plan 5.1 MSD_Introduction plan__RW.doc File desc: Date/time : 15/09/2014 12:03:08 Size: 560 KB 13 Introduction Plan for the introduction of RCV / JE into the national programme 7.x.4 No file loaded 14 Data quality assessment (DQA) report 5.1.5 No file loaded 15 DQA improvement plan 5.1.5 No file loaded 16 Progress report on implementation of DQA improvement plan 5.1.5 No file loaded 17 HPV roadmap or strategy 6.1.1 No file loaded 18 HPV summary of the evaluation methodology 5.1.6 No file loaded 19 Evidence of introduction of RCV / JE / YF in routine programme 7.x.3 No file loaded 20 Campaign target population documentation 7.x.1 No file loaded 21 Roadmap or strategy for strengthening a comprehensinve approach to pneumonia and/or diarrhoea prevention and treatment 6.x.6 No file loaded 22 EVM report 8.3 Rwanda_EVM report 2014_final.doc File desc: Date/time : 15/09/2014 12:04:34 Size: 1 MB 23 Improvement plan based on EVM 8.3 EVM 2014_improvement_plan_Rwanda.xls File desc: Date/time : 15/09/2014 12:05:28 Size: 196 KB 24 EVM improvement plan progress report 8.3 EVM improvement plan progress report.doc File desc: Date/time : 15/09/2014 12:45:31 Size: 34 KB 25 Detailed budget template for VIG / Operational Costs 6.x,7.x.2 Detailed budget attached to MSD Proposal.xls File desc: Date/time : 15/09/2014 12:29:24 Size: 50 KB 26 Risk assessment for Meningitis / Yellow Fever 7.1 No file loaded 27 Plan of Action for campaigns 7.1, 7.x.4 No file loaded Other No file loaded

11. Annexes Annex 1 - NVS Routine Support Annex 1.1 - NVS Routine Support (Measles second dose, 10 dose(s) per vial, LYOPHILISED) Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ 2015 2016 2017 Number of vaccine doses # 0 0 0 Number of AD syringes # 0 0 0 Number of re-constitution syringes # 0 0 0 Number of safety boxes # 0 0 0 Total value to be co-financed by the Country [1] $ 0 0 0 Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ 2015 2016 2017 Number of vaccine doses # 403,800 331,600 338,300 Number of AD syringes # 444,700 364,400 371,900 Number of re-constitution syringes # 44,900 36,900 37,600 Number of safety boxes # 5,450 4,475 4,550 Total value to be co-financed by GAVI $ 146,500 123,500 129,000

Table Annex 1.1 C: Summary table for vaccine Measles second dose, 10 dose(s) per vial, LYOPHILISED ID Data from 2015 2016 2017 Number of surviving infants Table 5.2 # 336,669 343,733 350,803 Number of children to be vaccinated with the first dose Table 5.2 # 319,836 326,546 333,263 Number of children to be vaccinated with the second dose Table 5.2 # 319,836 326,546 333,263 Immunisation coverage with the second dose Table 5.2 % 95 % 95 % 95 % Number of doses per child Parameter # 1 1 1 Estimated vaccine wastage factor Table 5.2 # 1.01 1.01 1.01 Number of doses per vial Parameter # 10 10 10 AD syringes required Parameter # Yes Yes Yes Reconstitution syringes required Parameter # Yes Yes Yes Safety boxes required Parameter # Yes Yes Yes cc Country co-financing per dose Table 6.4.1 $ 0 0 0 ca AD syringe price per unit Table Annexes 4A $ 0.0448 0.0448 0.0448 cr Reconstitution syringe price per unit Table Annexes 4A $ 0.035 0.035 0.035 cs Safety box price per unit Table Annexes 4A $ 0.544 0.544 0.544 fv Freight cost as % of vaccines value Table Annexes 4B % 14.00 % 14.00 % 14.00 % fd Freight cost as % of devices value Parameter % 10.00 % 10.00 % 10.00 % Table Annex 1.1 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Formula 2015 Total Government GAVI A Country co-finance V 0.00 % B Number of children to be vaccinated with the first dose Table 5.2 319,836 0 319,836 C Number of doses per child Vaccine parameter (schedule) 1 D Number of doses needed B x C 319,836 0 319,836 E Estimated vaccine wastage factor Table 5.2 1.01 F Number of doses needed including wastage D x E 323,035 0 323,035 G Vaccines buffer stock Buffer on doses needed = (D - D of previous year) x 25% Buffer on wastages = ((F - D) - (F of previous year - D of previous year)) x 25%, = 0 if negative result G = [buffer on doses needed] + [buffer on wastages] 80,759 0 80,759 I Total vaccine doses needed Round up((F + G) / Vaccine package size) * Vaccine package size 403,800 0 403,800 J Number of doses per vial Vaccine parameter 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 444,661 0 444,661 L Reconstitution syringes (+ 10% wastage) needed (I / J) x 1.11 44,822 0 44,822 M Total of safety boxes (+ 10% of extra need) needed (K + L) / 100 x 1.11 5,434 0 5,434 N Cost of vaccines needed I x vaccine price per dose (g) 104,585 0 104,585 O Cost of AD syringes needed K x AD syringe price per unit (ca) 19,921 0 19,921 P Cost of reconstitution syringes needed L x reconstitution price per unit (cr) 1,569 0 1,569 Q Cost of safety boxes needed M x safety box price per unit (cs) 2,957 0 2,957 R Freight cost for vaccines needed N x freight cost as of % of vaccines value (fv) 14,642 0 14,642 S Freight cost for devices needed (O+P+Q) x freight cost as % of devices value (fd) 2,445 0 2,445 T Total fund needed (N+O+P+Q+R+S) 146,119 0 146,119 U Total country co-financing I x country co-financing per dose (cc) 0 V Country co-financing % of GAVI supported proportion U / (N + R) 0.00 % Table Annex 1.1 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 2) Formula 2016 Total Government GAVI A Country co-finance V 0.00 % B Number of children to be vaccinated with the first dose Table 5.2 326,546 0 326,546 C Number of doses per child Vaccine parameter (schedule) 1 D Number of doses needed B x C 326,546 0 326,546 E Estimated vaccine wastage factor Table 5.2 1.01 F Number of doses needed including wastage D x E 329,812 0 329,812 G Vaccines buffer stock Buffer on doses needed = (D - D of previous year) x 25% Buffer on wastages = ((F - D) - (F of previous year - D of previous year)) x 25%, = 0 if negative result G = [buffer on doses needed] + [buffer on wastages] 1,695 0 1,695 I Total vaccine doses needed Round up((F + G) / Vaccine package size) * Vaccine package size 331,600 0 331,600 J Number of doses per vial Vaccine parameter 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 364,348 0 364,348 L Reconstitution syringes (+ 10% wastage) needed (I / J) x 1.11 36,808 0 36,808 M Total of safety boxes (+ 10% of extra need) needed (K + L) / 100 x 1.11 4,453 0 4,453 N Cost of vaccines needed I x vaccine price per dose (g) 88,942 0 88,942 O Cost of AD syringes needed K x AD syringe price per unit (ca) 16,323 0 16,323 P Cost of reconstitution syringes needed L x reconstitution price per unit (cr) 1,289 0 1,289 Q Cost of safety boxes needed M x safety box price per unit (cs) 2,423 0 2,423 R Freight cost for vaccines needed N x freight cost as of % of vaccines value (fv) 12,452 0 12,452 S Freight cost for devices needed (O+P+Q) x freight cost as % of devices value (fd) 2,004 0 2,004 T Total fund needed (N+O+P+Q+R+S) 123,433 0 123,433 U Total country co-financing I x country co-financing per dose (cc) 0 V Country co-financing % of GAVI supported proportion U / (N + R) 0.00 % Table Annex 1.1 D: Estimated numbers for Measles second dose, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 3) Formula 2017 Total Government GAVI A Country co-finance V 0.00 % B Number of children to be vaccinated with the first dose Table 5.2 333,263 0 333,263 C Number of doses per child Vaccine parameter (schedule) 1 D Number of doses needed B x C 333,263 0 333,263 E Estimated vaccine wastage factor Table 5.2 1.01 F Number of doses needed including wastage D x E 336,596 0 336,596 G Vaccines buffer stock Buffer on doses needed = (D - D of previous year) x 25% Buffer on wastages = ((F - D) - (F of previous year - D of previous year)) x 25%, = 0 if negative result G = [buffer on doses needed] + [buffer on wastages] 1,696 0 1,696 I Total vaccine doses needed Round up((F + G) / Vaccine package size) * Vaccine package size 338,300 0 338,300 J Number of doses per vial Vaccine parameter 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 371,805 0 371,805 L Reconstitution syringes (+ 10% wastage) needed (I / J) x 1.11 37,552 0 37,552 M Total of safety boxes (+ 10% of extra need) needed (K + L) / 100 x 1.11 4,544 0 4,544 N Cost of vaccines needed I x vaccine price per dose (g) 93,162 0 93,162 O Cost of AD syringes needed K x AD syringe price per unit (ca) 16,657 0 16,657 P Cost of reconstitution syringes needed L x reconstitution price per unit (cr) 1,315 0 1,315 Q Cost of safety boxes needed M x safety box price per unit (cs) 2,472 0 2,472 R Freight cost for vaccines needed N x freight cost as of % of vaccines value (fv) 13,043 0 13,043 S Freight cost for devices needed (O+P+Q) x freight cost as % of devices value (fd) 2,045 0 2,045 T Total fund needed (N+O+P+Q+R+S) 128,694 0 128,694 U Total country co-financing I x country co-financing per dose (cc) 0 V Country co-financing % of GAVI supported proportion U / (N + R) 0.00 %

Annex 2 - NVS Routine – Preferred Second Presentation No NVS Routine – Preferred Second Presentation requested this year Annex 3 - NVS Preventive campaign(s) No NVS Prevention Campaign Support this year

| Annex 4 Table Annex 4A: Commodities Cost Estimated prices of supply are not disclosed Table Annex 4B: Freight cost as percentage of value Vaccine Antigen Vaccine Type No Threshold 500,000$ <= > DTP-HepB-Hib HEPBHIB 25.50 % 6.40 % HPV bivalent HPV 3.50 % HPV quadrivalent HPV 3.50 % JE JE 37.00 % Measles second dose MEASLES 14.00 % Meningococcal type A MENINACONJUGATE 10.20 % MR MR 13.20 % Pneumococcal (PCV10) PNEUMO 3.00 % Pneumococcal (PCV13) PNEUMO 6.00 % Rotavirus ROTA 5.00 % Yellow Fever YF 7.80 % Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine. Vaccine 2015 2016 2017 Measles second dose, 10 dose(s) per vial, LYOPHILISED |  |
| --- | --- |

Table Annex 4D: Wastage rates and factors The following table shows the wastage rates for routine and campaign vaccines, set for 2015. Vaccine dose(s) per vial Maximum Vaccine wastage rate* Benchmark Wastage Rate** DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 5 % DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 25 % 15 % DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 10 % HPV bivalent, 2 dose(s) per vial, LIQUID 2 10 % HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5 % JE, 5 dose(s) per vial, LYOPHILISED 5 10 % Measles second dose, 10 dose(s) per vial, LYOPHILISED 10 40 % Meningococcal type A, 10 dose(s) per vial, LYOPHILISED 10 10 % MR, 10 dose(s) per vial, LYOPHILISED 10 15 % Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 10 % Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 5 % Rotavirus, 2-dose schedule 1 5 % Rotavirus, 3-dose schedule 1 5 % Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 40 % Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 10 % Comments: * Source - WHO indicative wastage rates ** Source - Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat Note: HPV demonstration project wastage rates are the same as the vaccine Table Annex 4E: Vaccine maximum packed volumes Kindly note that this table is for reference purposes only and includes GAVI- and non GAVI-supported vaccines. Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella freeze dried MR lyophilized SC 1 1 26.1 26.1 Measles-Rubella freeze dried MR lyophilized SC 1 2 13.1 13.1 Measles-Rubella freeze dried MR lyophilized SC 1 5 5.2 7 Measles-Rubella freeze dried MR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP-Hib liquid IM 3 1 32.3 DTP-HepB liquid + Hib freeze-dried DTP-Hib liquid IM 3 10 2.5 DTP-HepB liquid + Hib freeze-dried DTP-HepB+Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB+Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized SC 2 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 1 5 2.5 2.9 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Papilomavirus vaccine HPV liquid IM 3 1 15 Human Papilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5

12. Banking Form In accordance with the decision on financial support made by the GAVI Alliance, the Government of Rwanda hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): Ministry of Health, Rwanda Address: PO Box 84 City Country: Kigali, Rwanda Telephone no.: +250 785152534 Fax no.: Currency of the bank account: USD For credit to: Bank account's title: MINISANTE GLOBAL ALLIANCE FOR VACCINE AND IMMUNIZATION Bank account no.: 3201097 Bank's name: National Bank of Rwanda Is the bank account exclusively to be used by this program? True By who is the account audited? General Auditor's Office Signature of Government's authorizing official Seal Name: Dr Agnes BINAGWAHO Title: Minister of Health Signature: Date: FINANCIAL INSTITUTION Bank Name: NATIONAL BANK OF RWANDA Branch Name: HEAD OFFICE Address: BNR, AVENUE PAUL VI, 250, KIGALI City Country: KIGALI Swift Code: BNRWRWR Sort Code: ABA No.: Telephone No.: FAX No.: CORRESPONDENT BANK (In the United States) I certify that the account No 3201097 is held by MINISANTE at this banking institution The account is to be signed jointly by at least 2 (number of signatories) of the following authorized signatories: 1 Name: Dr Solange HAKIBA Title: PERMANENT SECRETARY, MINISTRY OF HEALTH 2 Name: Dr Daniel NGAMIJE Title: COORDINATOR, SINGLE PROJECT IMPLEMENTATION UNIT(SPIU) 3 Name: Title: Name of bank's authorizing official Signature: Date: Seal: