Note from the translation team: Pages 41-43 contain a table (5.2) that has large X's in several cells.  The X's are supposed to be removed in this update, but I was unable to remove them.  They seem to be anchored somehow.

Application Form for: BENIN

GAVI Alliance Health System Strengthening (HSS) Support

2009 application deadlines: 1st May and 4th September

An electronic version of this application form is available on the GAVI Alliance website (www.gavialliance.org).

Please send this electronic application with attachments (including the signatures page) to the following email address: proposals@gavialliance.org

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency.  The Proposal and attachments must be submitted in English or French

Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. Proposals received after that date will first be taken into consideration for following review. GAVI will not be responsible for delays or non-delivery of proposals by courier services.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

If hard copies are being submitted please send them to the following address:

New Proposals,

GAVI Alliance Secrétariat,

Chemin de Mines 2.

CH 1202 Geneva,

Switzerland

Table of Contents

Page

Abbreviations and Acronyms	4

Executive Summary	6

Section 1: Application Development Process	10

1.1: The HSCC (or country equivalent)	10

1.2: Overview of application development process	12

1.3: Roles and responsibilities of key partners (HSCC members and others)	16

1.4: Additional comments on the GAVI HSS application development process	18

Section 2: Country Background Information	18

2.1: Current socio-demographic and economic country information	18

2.2: Overview of the National Health Sector Strategic Plan (Document Number ......) and how it links to the cMYP (Document Number......)	21

Section 3: Situation Analysis / Needs Assessment	27

3.1: Recent health system or immunisation assessments	27

3.2: Major barriers to improving immunisation coverage identified in recent assessments	31

3.3: Barriers that are being adequately addressed with existing resources	32

3.4: Barriers not being adequately addressed (in order of highest priority)	33

3.5: Describe specific barriers to civil society and the private sector in delivering immunization services and strengthening health systems or becoming part of the national process to increase immunisation coverage	34

Section 4: Goals and Objectives of GAVI HSS Support	35

4.1: Goals of GAVI HSS support	35

4.2: SMART objectives of GAVI HSS Support	35

*  national average	37

Section 5: GAVI HSS Activities and Implementation Schedule	37

5.1: Sustainability of GAVI HSS support	37

5.2: Major Activities and Implementation Schedule	41

The GAVI Plan will be implemented over three years to remain in compliance with the Program Budget and the Medium-Term Expense Framework (MTEF).	41

5.3: Costed implementation plan for the first year of implementation	44

Section 6: Monitoring, Evaluation and Operational Research	49

6.1: Impact and Outcome Indicators (data should be consistent with other GAVI applications and annual progress reports from the country)	53

6.2: Output Indicators (one per objective)	54

6.3: Process Indicators (one per objective)	54

6.4  Data collection, analysis and use	52

6.5: Strengthening M&E system	58

6.6: Operational Research	60

Section 7: Implementation Arrangements	60

7.1: Management of GAVI HSS support	60

7.2: Roles and responsibilities of key partners (HSCC members and others)	61

7.3: Funding arrangements	65

7.4: Reporting arrangements	68

7.5: Technical assistance requirements	68

Section 8: Budgeting and Funding for GAVI HSS supported activities	69

8.1: Budget for implementing GAVI HSS support	70

8.2: Calculation of GAVI HSS country allocation (this number should be consistent with data used in other GAVI applications and annual progress reports)	74

8.3: Sources of all expected funding for health systems strengthening activities	75

8.4: Describe how GAVI HSS funding will complement other sources of HSS funding	76

Section 9:  Terms and Conditions of GAVI Support	77

Section 10: Endorsement of the Application	80

10.1: Government endorsement	80

10.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent	80

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application and final checklist	82

ANNEX 2 Banking Form	83

# Abbreviations and Acronyms

To the applicant

- Please ensure that all abbreviations and acronyms presented in the application and supporting documents are included here.

| NRA | : | National Regulatory Authorities |
| --- | --- | --- |
| AMP | : | Agency of Preventive Medicine |
| BADEA | : | Arab Bank for Economic Development in Africa |
| BASP 96 |  | Public Health Support Bureau 96 |
| BCG | : | Bacillus Calmette- Guérin |
| CPEM | : | Center for the Purchase of Essential Medicines and Medical Consumables |
| CDEEP | : | Department Committees to monitor Execution and to Evaluate Projects and Programs |
| DHC | : | Department Hospital Center |
| CNEEP | : | National Committee to monitor Execution and to Evaluate Health Sector Projects/Program |
| NUHC | : | National University Hospital Center |
| EXECOM | : | Executive Committee |
| SGC | : | Support Guidelines Committee |
| PNC | : | Prenatal Consultation |
| MEC | : | Monitoring & Evaluation Cell |
| CTB | : | Belgian Technical Co-operation |
| ED | : | Executive Director |
| DDH | : | Department Directorate of Health |
| DZHD | : | Directorate of Health Zone Development |
| DEDTS | : | Directorate of Diagnostic Testing and Blood Transfusion |
| DH | : | Directorate of Hospitals |
| DIEM | : | Directorate of Infrastructures Equipments and Materials |
| NDEPI-PHC | : | National Directorate of the Expanded Program on Immunization and Primary Health Care |
| NDHP | : | National Directorate of Health Protection |
| DPP | : | Directorate of Programming and Planning |
| DFMR | : | Directorate of Financial and Material Resources |
| HRD | : | Human Resources Directorate |
| DHR | : | Directorate of Health Research |
| DFH | : | Directorate of Family Health |
| DNOC | : | Directorate of Nursing and Obstetric Care |
| DTPP | : | Diphtheria Tetanus Pertussis Poliomyelitis |
| DHS III | : | Demographic and Health Survey III |
| STZH | : | Supervisory Teams for Health Zones |
| EDF | : | European Development Fund |
| GAVI |  | Global Alliance for Vaccines and Immunization |
| ZH | : | Zone Hospital |
| INSAE | : | National Institute of Statistics and Economic Analysis |
| HZCP | : | Health Zone Coordinating Physician |
| MoH | : | Ministry of Health |
| MSH | : | Management of Sciences for Health |
| MDG | : | Millenium Development Goals |

| WHO | : | World Health Organization |
| --- | --- | --- |
| NGO | : | Non Governmental Organization |
| EPI | : | Expanded Program on Immunization |
| GDP | : | Gross Domestic Product |
| NHDP | : | National Health Development Plan |
| TFP | : | Technical and Financial Partnership |
| GNI | : | Gross National Income |
| HSS | : | Health Systems Strengthening |
| AS | : | Administrative Secretariat |
| DPMS | : | Department of Planning and Monitoring Studies |
| SGM | : | Secretariat General of the Ministry |
| SNIGS | : | National Health Management Information System |
| UNC | : | Urgent Neonatal Care |
| CUOC | : | Complete Urgent Obstetrical Care |
| UNICEF | : | United Nations Children Fund |
| USAID | : | United States Agency for International Development |
| USD | : | United States Dollar |
| MV | : | Measles Vaccine |

# Executive Summary

To the applicant

- Please provide a summary of the proposal, including the goal and objectives of the GAVI HSS application, the main strategies/activities to be undertaken, the expected results, the duration of support and total amount of funds requested with baseline figures and targets for the priority indicators selected.

Benin is ranked 161 out of 177 in the human development index (UNDP 2005) and approximately 1/3 of its population lives below the poverty level. Its GDP per capita was US$ 555 in 2005, compared to an average of 316 in West Africa. The infant mortality rate is 67 per 1000 live births, and the maternal mortality rate is nearly 397 per 100,000 births according to the DHS III.

Interventions by Benin’s health system revolve around the main strategic arms and guidelines developed in various political and strategic documents prepared by the Ministry of Health and associated Ministries:

- Studies of Long-Term Perspectives, Benin 2025, ALAFIA

- Poverty Reduction, Growth and Strategy Document (PRGSP, 2007-2009)

-National Health Sector Development Plan (2009-2018)

-Three-Year Health Sector Development Plan, for 2009-2011

All of these documents are based on the MDG (4, 5, 6) and emphasize the priorities of the Ministry of Health, which are:

To improve the quality of access to health services; To improve community participation and use of health services; To improve health coverage of the population in general and for the poor and indigent in particular.

In connection with the four documents mentioned above, analysis of the Expanded Program on Immunization situation (cMYP: 2007-2011) shows that it still registers substandard performance in terms of cases and deaths due to vaccine-preventable diseases: 36% of the communes in the country have Penta3 coverage below 90% and 45% have MV coverage below 90%, with continued outbreaks of measles in all of the country’s departments.

The last review of EPI  in December 2008 revealed that only 34% of children in Benin are fully and correctly immunized at 1 year according to the cards. Of the children surveyed for the 3rd dose of the pentavalent, vaccine coverage was 51% and none of the 34 health zones had achieved the card coverage threshold of 80%. Maternal and infant mortality rates remain high (397/100,000; 67/1000).

This situation is primarily due to the poor vaccine coverage seen in certain communes, to weaknesses in the health system, and to inadequacies in the operational implementation of the tested strategies due to the irregularity of advanced strategies that result in high drop-out rates in certain communes, logistics inadequacies (cold chain, means of transport), inadequacies in communication and advocacy activities, weaknesses in integrated and response surveillance, inadequacies in capacity development, and inadequacies in funding for program activities.

A NHDP analysis of the situation and referral to recent assessment results identified the obstacles that have not been sufficiently addressed and that could affect vaccine coverage, in order of priority:

In terms of governance, there was poor capacity for planning and coordinating health sector actions and activities at all levels of the health pyramid; most health agents in the health zones had inadequate planning.

Human resources are inadequate in terms of quantity, quality and motivation to ensure the continuity of care and services necessary for the CUONC (complete urgent obstetrical and neo-natal care) and for fixed station and advanced immunization.

Material resources are characterized by inadequate equipment logistics and maintenance (cold chain, means of transport, ambulance for the reference) and waste management (incinerators);

In terms of health sector funding, the portion of the budget allocated to health went from 7.23% in 2008 to 8.99% in 2009; this remains inadequate to cover all needs.

Likewise, the sector is faced with poor quality of services and poor vaccination performance.

Benin’s national health information system, although operational, registers weaknesses in the collection, analysis and use of health statistics data (publication and feedback) at all levels of the health pyramid, and poor use of operational research. Vaccine coverage data are not disaggregated by sex.

The goal of Benin’s submission to GAVI is to strengthen implementation of NHDP (2009-2018) by “contributing to reducing maternal and infant mortality through immunization and functionality and performance at the three levels of Benin’s health system, with particular emphasis on target health zones, in conjunction with other on-going interventions.”

The support requested from GAVI mainly concerns 4 health zones and two (2) department hospitals in addition to the intermediate and central levels. The selection criteria for Health Zones (HZ) to receive support from the GAVI submission are as follows:

Health zones with poor EPI coverage (Penta3 < 80%)

High maternal and infant mortality rates (greater than 397/100,000 live births; greater than 67 per 1000)

Functionality of the health zone (presence of a zone hospital).

The Department Hospital Centers (DHC) and Department Directorates of Health (DDH) were selected on the basis of geographical location in selected health zones, to optimise the expected effects.

In relation to various constraints, specific objectives were selected for the GAVI submission relative to those of the NHDP. The specific objectives for GAVI support to HSS are:

Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012.

This objective will be assessed by the availability of a work plan coming out of bottom-up planning. This objective will be measured via the following indicators:

-      Number of agents from the DPP, two DDH and four (4) STZH trained in the bottom-up planning process

Number of Target Health Zones that have a smoothly operational three-year work plan

Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 Department Hospitals and the 4 target health zones from 2010 to 2012;

Achievement of this objective will be measured via the following indicators:

Number of target health centers offering CUONC

% of target health zones achieving at least 80% Penta3

Rate of assisted deliveries in target zones

Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 hospitals and 4 health zones targeted from 2010 to 2012

. Two indicators were selected to assess if this objective is achieved:

% of health centers with personnel qualified per standards in target health zones

% of the population indicating that it is satisfied with health care received in the target health zones

To achieve the 3 objectives, 32 concrete activities have been identified; the main ones target institutional strengthening by strengthening the planning, coordination, monitoring and evaluation process; strengthening human, material and miscellaneous equipment resources; and strengthening operational research capacities.

The estimated cost to achieve these 3 objectives is 2,738,068,000 USD.

GAVI support complements efforts by the Government, Technical and Financial Partners (TFP), and Benin communities at the base of mobilizing health sector resources.

This submission was finalized after a long, participative preparation process which included guidelines committee meetings followed by the setting up of thematic groups.

This support is under the authority of the Minister of Health. Implementation will be ensured by the Directorate of Programming and Planning (DPP) in collaboration with the other directorates, with the advisory support of the TFPs.

Funds will be managed according to the management procedures in effect in Benin.

-	At the central (national) level: The Director of Programming and Planning from the Ministry of Health proposes expenditure initiations. The Director of Financial Resources and Materials from the Ministry of Health confirms the initiations and certifies payment of the expenditure with an authorizing signature of the payment order. An account has been opened at the Public Treasury to receive GAVI funds.

The Delegate for the Financial Comptroller to the Ministry of Health verifies that the service has been done and confirms it with an authorizing signature of the payment order.

The Director of Financial Resources and Materials and the Director of Programming and Planning from the Ministry of Health are the two signatories of the account.

-	At the intermediate (departmental) level: The Department Director of Health (DDH), as budget director, coordinates the activities financed by GAVI.

The Division Head of Financial Resources and Materials of the DDH executes the budget allocated to the GAVI funds activities under the supervision of the DDH. He also oversees the management of GAVI funds at the level of the Health Districts (Zones). To that effect, an account will be opened at the Revenue Collections level in the departments involved (deconcentrated structure of the Public Treasury) to receive the GAVI funds. The account signatories are the DDH and the Revenue Officer.

-	at the peripheral level (Health District or Zone): To that effect, the Health Zone Coordinating Physician has an Economic Chargé d’affaires for the Zone to manage the GAVI funds. An account will also be opened at the Revenue Collections level of the commune that hosts the Supervisory Team for the Health Zone. The two account signatories are the Zone Coordinating Physician and the Revenue Officer.

Monitoring mechanisms plan not only for quarterly evaluations, supervisions and controls by the appropriate State bodies, but also for regular audits, both internal and external. Monitoring of GAVI activities will be provided by the Support Guidelines Committee during the quarterly CNEEP sessions, the bi-annual Technical and Financial Partners meetings, and the bi-monthly TFP Health Technical Group. Proceedings and regular reports on the status of implementation progress will be made for the selected indicators.

Regarding sustainability, the appreciable contribution of community funding towards the operation of Health Zones by increased mobilization of additional resources (health mutuals, partnerships, decentralized cooperation, economic operators) is a pledge to sustainable activities. Likewise, setting up a universal insurance program (RAMU) will strengthen health risk coverage, especially for poor and indigent populations.

The adhesion and adoption of the project by Benin’s development partners guarantee their participation and involvement in its implementation and continuity. Intervention by GAVI complements efforts by the Government, the TFP, and Benin communities, which constitute an additional pledge towards the sustainability of the project.

Thus, coordination mechanisms exist within Benin to strengthen governance and to reassure the various actors involved in health development.

The Ministry of Health will collaborate with GAVI procedures to ensure that the policy of transparency and responsibility is met.

# Section 1: Application Development Process

To the applicant: section 1.1

In this section, please describe the process for developing the GAVI HSS application.

- Please begin with a description of your Health Sector Coordinating Committee or equivalent (Table 1.1).

## 1.1: The HSCC (or country equivalent)

Name of HSCC (or equivalent): National Committee to monitor Execution and to Evaluate Health Sector Projects/Program (CNEEP) CNEEP is presided over by the Minister and is composed of: - Chair: Minister of Health or his Representative; - Vice-Chair: Minister of Planning, Development and Assessment of Public Action, or his Representative; - 1st Rapporteur: Minister of Foreign Affairs, African Integration, Francophony and Beninese Abroad, or his Representative; - 2nd Rapporteur: Minister of the Family and National Solidarity. The permanent members are: Ministry of Health structures: - Ministry of Health Cabinet Director; - Ministry of Health Secretary General; - Ministry of Health Technical Advisors; - Central and Technical Directors, or their representatives; - Department Health Directors and their Division Heads of Studies, Planning and Monitoring; - CNEEP sub-committee offices; Private health sector and civil society: - A representative of the Health NGOs Network; - A representative from AMCES; - A representative from the Health Management Committee; - A representative from the National Association of Traditional Medicine Practitioners of Benin; - A representative from the Society of Pharmacists; - A representative from the Society of Physicians; - A representative from the Society of Dental Surgeons; - A representative from the Society of Midwives; - A representative from the Association of Nurses and State-Certified Nurses; - A representative from the Association of Laboratory Technicians; - A representative from the Unions.

Other Ministries - A representative from the Ministry of Economy and Finance; - A representative from the Ministry of National Defense; - A representative from the Ministry of Mines, Energy and Water; - A representative from the Ministry of Primary and Pre-School Education; - A representative from the Ministry of Secondary School Education and Professional Training; - A representative from the Ministry of Higher Education and Scientific Research; - A representative from the Ministry of Agriculture, Animal Husbandry and Fishing; - A representative from the Ministry of the Environment and the Protection of Nature; - A representative from the Ministry of the Interior, Public Safety and Local Communities. (See Order no. 2007-163 of April 16, 2007: pages 2, 3 and 4; the titles of some ministries have been updated.) HSCC operational since: CNEEP, the highest deciding body, was created in 1998 after the health sector Round Table in January 1995. The order regarding its creation was reviewed in 2003 and 2006 to make it much more operational, then again in 1997 to bring it into line with other legal texts. Thus CNEEP is currently ruled by Order no. 2007-163 of April 16, 2007.

Organisational structure (e.g., sub-committee, stand-alone): CNEEP bodies are: - The Plenary Assembly of committee members; - The Permanent Secretariat; - The two Sub-committees, i.e.: - The Monitoring-Evaluation Sub-committee of health pyramid reorganization and sector resource management; - The Monitoring-Evaluation Sub-committee of diseases and family health; - The Department Committees to monitor Execution and to Evaluate Health Sector Projects/Program (CDEEP).

Frequency of meetings: The ordinary sessions of CNEEP are held bi-annually; extraordinary sessions are held as needed. Sub-committees hold their ordinary sessions quarterly. The Department Committees to monitor Execution and to Evaluate Health Sector Projects/Program (CDEEP) also hold their ordinary sessions bi-annually. The GAVI-HSS application was submitted for the last time at the CNEEP meeting on September 2 and 3, 2008.

Overall role and function: CNEEP is charged with: - Validating Ministry of Health program budget; - Supervising the effective implementation of health sector reforms as set forth in the national health policies and strategies; - Overseeing the harmonization and coordination of actions by health development partners; - Approving the new health strategy to be implemented as a result of the expected results; - Studying and approving the bi-annual and annual reports of the CNEEP sub-committees; - Studying and approving the bi-annual and annual reports of the CDEEPs; - Studying and approving the reports on sector project/program beneficiaries’ assessments; - Analyzing the major worrisome issues in the sector; - Making recommendations and assigning tasks to the structures represented within CNEEP. CNEEP will be charged with validating Benin’s application to GAVI.

To the applicant: section 1.2

- In this section, please describe the process your country followed in preparing this GAVI HSS application (Table 1.2)

Note: Without supporting documentation (signed minutes from HSCC meetings) and a thorough outline of the process of preparing the application it will not be possible for the GAVI Independent Review Committee (IRC) to assess the involvement of key stakeholders (civil society, bilateral, private sector and representatives from hard to reach populations) in the process. The signed minutes of the HSCC meetings related to the HSS proposal preparation should be attached (Document Number....) as supporting documentation, together with the signed minutes of the meeting (Document Number....) where the application was endorsed by the HSCC.

## 1.2: Overview of application development process

Who coordinated and provided oversight to the application development process? The Guidelines Committee, created by Ministry of Health Decree no. 3695/MS/DC/SGM/DPP/SA of April 11, 2007 (see copy in the annex), coordinated and supervised the development of the application.

Who led the drafting of the application? Was any technical assistance provided? The ad hoc Committee, created by Ministry of Health Decree no. 3696/MS/DC/SGM/DPP/SA of April 11, 2007 (see copy in the annex), drafted the application to GAVI. It was assisted by an international consultant and two national consultants, and two WHO country experts.

Give a brief time line of activities, meetings and reviews that led to the proposal submission. The members of the ad hoc Drafting Committee were divided by section according to the various competencies to collect and analyze the data. Several drafting workshops of the various sections of the document were organized with financial support from the WHO and the World Bank. The ad hoc Committee in charge of drafting met once per week to assess the progress of work and the problems encountered, with a written report of the meeting addressed to the Guidelines Committee. The Guidelines Committee met three (3) times to examine and amend, in collaboration with development partners, the results of the ad hoc Drafting Committee’s work. May 10 to December 12 2007: Eight (8) Guidelines Committee meetings and fifteen Drafting Committee meetings about drawing up the document September 17, 2007: The draft of the application was submitted to the Executive Committee (EXECOM) of the Ministry of Health, at a partner meeting held to study and amend it. This partner meeting suggested awaiting the conclusions of the health general assembly. November 21 to 24, 2007: Health General Assembly with participation of civil society; conclusions issuing from these audiences enabled the application to be improved. January 7 to 15, 2008: Five (5) meetings of the Drafting Committee to develop and continue the exercise; February 7, 2008: Guidelines Committee meeting for commentary and observations on the Drafting Committee’s work April 8, 2008: Receipt of GAVI Observations April 28 to 29, 2008: Renewed work, taking into consideration the observations and GAVI’s recommendations. This Committee, reinforced by other resource people, was broken down into three sub-groups, which addressed the various observations and recommendations. After the group’s work, it was regularly pooled together to come up with a consensus before the joint meeting with all partners. September 2 and 3, 2008: Organization of an examination session by the National Committee for Monitoring and Evaluating Projects and Programs. November 14, 2008: Joint amendment workshop with decentralized structures from Zou/Collines and Mono/Couffo, bringing together Department Directors of Health, coordinating physicians from health zones, hospital directors, local NGOs, Department Directors in charge of Planning and Development, etc. November 24, 2008: WHO inter-country team mission, Ouagadougou November 28, 2008: Joint amendment workshop with decentralized structures from Atacora/Donga and Borgou/Alibori, bringing together Department Directors of Health, coordinating physicians from health zones, hospital directors, local NGOs, Department Directors in charge of Planning and Development, etc. December 9 to 11, 2008: Participation by Benin’s HSS team in the workshop on development capacities strengthening for GAVI HSS applications in Ouagadougou December 9 to 2008: Delivery of the workshop on development capacities strengthening for GAVI HSS applications in Ouagadougou to members of the Guidelines Committee. February 16 to 20, 2009 in Porto-Novo: Workshop on integrating the recommendations of the December Ouaga workshop by the Drafting Committee. March 17 to 19, 2009: Participation by Benin’s team in the peer review meeting of GAVI HSS applications in Ouagadougou. March 19 to 23, 2009: Integration of peer review amendments from March 17-19, 2009 by workshop participants. March 24, 2009: Delivery and exchange of results from the HSS/GAVI application peer review to the ad hoc Drafting Committee and the Guidelines Committee March 30 to April 1, 2009: Finalization of the application April 6, 2009: Validation of the new application by the Guidelines Committee April 6 to 7, 2009: Integration of Guidelines Committee amendments April 7, 2009: Sending the new application to the TFP April 14, 2009: Organizing a TFP meeting on the new application April 14 to 15, 2009: Integration of Drafting Committee amendments April 15, 2009: Sending Benin’s request to the IST Ouagadougou team for advice April 16 to 17, 2009: Review of the application by an ad hoc committee of partners (WHO, Switzerland, Belgium, UNICEF, FNUAP); April 21, 2009: Finalization of Benin’s request April 23, 2009: Validation of the submission by CNEEP April 24, 2009: Review of the submission by WHO consultants April 27 to 28, 2009: Collecting signatures from authorities and partners April 29, 2009: Obtaining the UNICEF cover letter April 29, 2009: Submission of Benin’s request to GAVI July 20, 2009: Receipt of the conditional letter of approval from GAVI July 22 to August 5, 2009: Drafting of the response items August 17 to 22, 2009: Participation in the peer review meetings in Ouagadougou August 24 to 28, 2009: Continuation of the budget amendment and adjustment work September 2, 2009: Validation of the submission by the expanded extraordinary CNEEP meeting to the Guidelines Committee and the Technical and Financial Partners September 3, 2009: signing by the Ministry of Health and Finance September 4, 2009: Resubmission of Benin’s application to the GAVI Alliance

Who was involved in reviewing the application, and what was the process that was adopted? The various structures and resource people involved in examining the document were: - The central and technical directors of the Ministry of Health, as members of the Guidelines Committee; - The Department Directors of Health; the Directors of Department Health Centers (DHC), coordinating physicians in health zones, managers of local NGOs involved in health; - Health development partners during drafting of and exchanges about the document, as members of the Guidelines Committee and representatives of the Technical and Financial Partners (TFP) group; - Civil society, via: - The representative of the Health Centers Management Committees; - The representative of the Health Non-Governmental Organizations Network; - The representative of the Association of Private, Religious and Social Medical Works; - The representative from the National Association of Traditional Medicine Practitioners of Benin; - The representative from the Society of Pharmacists; - The representative from the Society of Physicians; - The representative from the Association of Midwives, Nurses and State-Certified Nurses; - The representative from the Association of Laboratory Technicians; - The representative of social partners, i.e. unions. - Representatives of other ministries, i.e.: - Ministry of Planning, Development and Assessment of Public Action; - Ministry of Economy and Finance; - Ministry of Higher Education and Scientific Research; - Ministry of Pre-School and Primary Education; - Ministry of Secondary Schools and Professional and Technical Training; - Ministry of the Environment and the Protection of Nature; - Ministry of Foreign Affairs, African Integration, Francophony and Beninese Abroad; - Minister of the Family, Women and Children.

Who approved and endorsed the application before submission to the GAVI Secretariat? The submission application was initially examined during the ordinary CNEEP session of September 2 and 3, 2008. The latest application for re-submission was approved and adopted by: - The TFP on April 14, 2009 - The CNEEP on April 20, 2009 The application was signed by the Minister of Health, the Minister of Finance, and the UNICEF representative. Was funding received form GAVI for HSS proposal development? If so, how much, when was it received, and what was it used for, or what will it be used for? Yes, the amount of 50,000 USD was received through WHO in July 2007 and used to recruit consultants and fund workshops both at the central level and in the departments. Once the various structures for preparing the submission were set up, workshops were held at the central and operation levels (departments and health zones) to gather the opinions and concerns of the future implementation actors. Participating in these workshops were the main Technical and Financial Partners, various socio-professional associations, basic community representatives, NGOs in the health, religious and private sectors, social partners and actors in other sectors, and civil society. These various workshops and gatherings enabled the submission to be drafted from the analysis of the situation to the selection of strategies, activities, and budgeting. This draft was submitted for amendment during several formal and informal meetings with various partners and Ministry structures before being finally adopted by the National Committee to monitor Execution and to Evaluate Health Sector Projects/Program (CNEEP). This submission is part of implementing the 2009-2018 National Health Development Plan and is based on various evaluations of the sector conducted over the past three (3) years, rounded out by the November 2007 conclusions of the Health General Assembly, which included over 600 participants from the three levels of the health pyramid, social partners, actors in associated sectors and other representatives from the population; during audiences of the Health General Assembly emphasis was placed on valuing human resources, among others.

To the applicant: section 1.3

- Please describe the roles and responsibilities of key partners in the development of the GAVI HSS application (Table 1.3).

Note: All key partners should be included in the process: the Ministry of Health, including the planning department and the immunization unit; Ministry of Finance; bilateral and multilateral partners; relevant coordinating committees; NGOs and civil society; and the private health sector. If there has been no involvement of civil society, the private health sector or other key stakeholders in the development of the GAVI HSS application, please explain this below (1.4).

## 1.3: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organisation | HSCC member yes/no | Please list the specific roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| Technical Advisor | Coopération belge | Yes | Support in drafting, amending and adopting the document. Making an international consultant available to the ad hoc drafting committee; submission review |
| Technical Advisor | Coopération Suisse | Yes | Active intervention in orienting, amending and adopting the document. Submission review |
| Technical Advisor | Coopération Française | Yes | Active participation in orienting, drafting, amending and adopting the document. |
| MPN, MAL and EPI Representative | WHO | Yes | Advisory support, active and continuing assistance in clarifying how to fill out the form, drafting, amending and adopting the document. Making available and monitoring the management of GAVI funds for preparing the application; Financial support for organizing workshops at the regional and operational level. Document research and technical support by an international expert (WHO country EPI and two national WHO country experts) |
| Project Leader | WORLD BANK | Yes | Making a consultant available to finalize the application for re-submission; Funding the workshop to incorporate observations from the December 2008 Ouagadougou workshop and the April 2009 CNEEP application validation session |
| Health Program Leader | USAID | Yes | Leader and coordinator of TFP comments and observations to improve the applications; submission review |
| Project Leader | European Union | Yes | Active intervention in orienting, drafting, amending and adopting the document. |
| Representative | UNICEF | Yes | Contribution in finalizing the application and in vaccine coverage improvement measures; submission review |
| Representative | UNFPA | Yes | Contribution in finalizing the application; submission review |
| Network Coordinator | NGO network | Yes | Active participation of the NGO network at each stage of application preparation |
| Chairperson | Health Centers Management Committee | Yes | Contribution with regard to the needs expressed by the beneficiaries (population) |
| Representatives | Civil society (AMCES), religious, traditional medicine and other representatives | Yes | Participation in drafting the sections of the document concerning governance and Ethics |
| Chairpersons | Societies of Physicians, Pharmacists, Midwives, Midwives, Nurses, Laboratory Technicians | Yes | Contribution to the Guidelines Committee for finalizing the application |
|  | Social partners | Yes | Participation in orienting, drafting, amending and adopting the document. |
| Directors | Technical, Central and Department Directors from the Ministry of Health and other Ministries | Yes | Active intervention in orienting, drafting, amending and adopting the document. Coordination and secretariat provided by the Directorate of Programming and Planning (DPP) |
| Representatives | Health Centers Management Committee | Yes | Co-management of the implementation of health institutions activities at the local level |
| Representatives | Ministry of Economy and Finance | Yes | Contribution for drafting aspects concerning the mechanism for using funds; provided advice on financial commitments and signatory to the submission |
| Representatives | Ministry of Planning, Development and Assessment of Public Action | Yes | Contribution to validating statistical data from INSE, guarantor of overall policies to ensure synergy with sector strategies |

To the applicant: section 1.4

- Partners and members of the HSCC are encouraged to provide feedback and let the GAVI secretariat know of any concerns or anticipated issues with implementation, monitoring or financial arrangements.

- If the HSCC wishes to make any additional comments or recommendations on the GAVI HSS application to the GAVI Secretariat and Independent Review Committee, please do so below.

- Please explain if there has been no involvement of civil society or the private sector, and state if they are expected to have a service provision or advocacy role in GAVI HSS support implementation

- If this is a resubmission, please describe what were the main changes introduced for this proposal

- Please describe any lessons learnt or useful practices developed during HSS proposal development

## 1.4: Additional comments on the GAVI HSS application development process

The personal commitment of the Minister of Health and the practical guidelines provided during the renewed work were quite influential throughout the entire preparation process for Benin’s application.

The segregation of EPI data by sex was not documented in the submission because of the lack of specific collection tools. The change in HSS/GAVI forms during the preparation process did not make it easier to fill them out. The peer review meetings organized in Ouagadougou were considered to be highly useful.

# Section 2: Country Background Information

To the applicant: section 2.1

- Please provide the most recent socio-economic and demographic information available for your country. Please specify dates and data sources. (Table 2.1).If these differ from or are inconsistent from those used in other GAVI applications or monitoring, justification should be provided

## 2.1: Current socio-demographic and economic country information

Geographic Information

The Republic of Benin is a western African state located in the Gulf of Benin. It covers an area of 114,763 km2 and extends from the Atlantic Ocean to the Niger River along a length of 700 kilometers. Its width varies from 125 kilometers (along the coast) to 325 kilometers (latitude of Tanguiéta).

Demographic Information

According to the results of the third General Census of Population and Housing (RGPH 3 of 2002), the country has a population of approximately seven million (6 752 569). In 2009 the population is estimated at about eight million six hundred twelve thousand hundred eight /sic/ (8 496 000). The annual demographic growth rate between 1992 and 2002 was 3.2%. The population has a majority of women, at 51.4%.

Socioeconomic Information

Benin is ranked 161 out of 177 in the human development index (UNDP 2005) and approximately 1/3 of its population lives below the poverty level. Its GDP per capita was US$ 555 in 2005, compared to an average of 316 in West Africa. GDP per capita has followed the same trend, going from 311 000 FCFA per capita in 2006 to 323 000 FCFA per capita in 2007.

Disease has been a contributing factor to impoverishing the disadvantaged groups. Cognisant of this situation, the National Studies of Long-Term Perspectives, Benin 2025 made the social well-being of the population a priority, with a particular emphasis on quality health care in all health institutions.

a) Organization of the System of Healthcare and Services

The national health system is structured in a pyramid along territorial lines. It includes three different levels:

- The central or national level:

The Ministry of Health is in charge of implementing health-related policies defined by the Government. As part of this, it initiates health actions and plans, coordinates and controls implementation of resulting activities. The central level is the main responsible party for designing and implementing actions resulting from the previously mentioned policies (refer to Order no.2006–396 of July 31, 2006).

- The intermediate or department level:

This includes Department Directorates of Health (DDH), which number six (6), one per department, per the former territorial division. They are charged with implementing the health policy defined by the government, planning and coordinating all health activities and services in the peripheral areas, and providing epidemiological monitoring in the departments.

- The peripheral level:

The peripheral level is made up of health zones, numbering 34, which are distributed across the entire country. The health zone represents the most decentralized operational entity of the health system.

The end result of the reorganization into health zones is an improvement of social health conditions for a population living in well-defined geographical areas. Its objectives are:

- To improve the quality of basic and first-order health services;

- To improve the viability of social health services;

- To promote decentralization and community participation;

- To develop a partnership with the private sector.

b) Care is also offered at three (3) levels:

The first level, the operational level, is made up of a network of first-contact public services (UVS, maternities and dispensaries only, Health Centers) and private health institutions, which are all supported by a first-order public or private hospital (zone hospital), and which are intended to serve an area comprising between 100,000 and 200,000 inhabitants.

The second level is made up of department hospital centers.

The third level comprises the UHC, the National Blood Transfusion Center, and the National Laboratory.

c)	Evolution of State contributions to health sectors

The evolution of the State’s contributions to health sectors from 2004 to 2009 is as follows:

| Years Categories | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 |
| --- | --- | --- | --- | --- | --- | --- |
| Existing appropriations in the Operating Budget | 28 190 | 30 090 | 29 953 | 30 686 | 32 149 | 48 220 |
| Existing appropriations in the PIP Interior Resources | 9 382 | 9 047 | 9 632 | 11 330 | 19 031 | 34 221 |
| Existing appropriations in the PIP Exterior Resources | 8 098 | 7 718 | 9 332 | 15 650 | 18 475 | 28 974 |
| Existing appropriations in the National Budget (PIP, OPERATIONS) | 37 572 | 39 137 | 39 585 | 42 016 | 51 180 | 82 441 |
| Total existing appropriations (PIP, OPERATIONS) | 45 670 | 46 855 | 48 917 | 64 881 | 73 921 | 111 415 |
| State financial contribution in the Health Sector budget | 82.27% | 83.53% | 80.92% | 64.76% | 69.24% | 73.99% |

The portion of the National Budget in health funding has increased in absolute value from 2004 to 2009. However, in percentage, this portion has regressed, going from 82.27% to 73.99% over the same period. Still there has been an increase in absolute numbers, as indicated in the table above.

The portion of the health sector budget in the National Budget went from 7.23% in 2008 to 8.99% in 2009.

Disease has been a contributing factor to impoverishing the disadvantaged groups. The infant mortality rate is 100.8 per 1000 live births, and the maternal mortality rate remains high at nearly 397 per100,0000 births according to the DHS III.

According to the EPI review to 2008, national vaccine coverage is 51% for DTP3, 49% for MV, 84% for TT, and 34% for fully immunized children.

The main health indicators are summarized in the table below:

| Information | Value | Information | Value |
| --- | --- | --- | --- |
| Population in 2009 | 8 496 000 ** | GNI per capita in 2004 | 350 USD* |
| Annual Birth Cohort in 2009 (projection) | 379 543 **** | Under five mortality rate in 2006 | 125 / 1000* |
| Maternal mortality ratio in 2006 | 397/100 000* live births | Rate of assisted deliveries in 2007 | 82%*** |
| Contraceptive prevalence in 2006 | 6.2%*** | Usage rate of PNC in 2007 | 96%*** |
| Surviving infants* in 2006 | 323 792**** | Infant mortality rate in 2006 | 67/ 1000*** |
| Pentavalent 3 coverage rate in 2008 | 51%***** | Economic growth rate 2006 | 2.9%**, |
| MV coverage rate 2008 | 49%***** | Demographic growth rate | 3,25%** |
| Percentage of GNI allocated to health in 2006 | 8%*** | Neonatal mortality rate in 2006 | 32/1000* |
| Prevalence of chronic malnutrition in 2006 | 43%* | Prevalence of acute malnutrition | 8 .4 %* |

* Surviving infants = Infants surviving the first 12 months of life

Sources

- * : 	DHS III 2006

- ** : 	INSAE

- *** : 	Health statistics (SNIGS) DPP 2006

- ****: 	GAVI 2007 situation report

- ***** : 	EPI review Benin 2008

To the applicant: section 2.2

- Please provide a brief summary of your country’s Health Sector Plan (or equivalent), including the key objectives of the plan, the key strengths and weaknesses that have been identified through health sector analyses, and the priority areas for future development (Table 2.2).

- Please highlight any specific socio economic barriers to accessing immunisation services that may include hard to reach populations or any gender inequities

## 2.2: Overview of the National Health Sector Strategic Plan (Document Number ......) and how it links to the cMYP (Document Number......)

Vision

Benin’s global vision contained in the National Studies of Long-Term Perspectives: Benin ALAFIA 2025 emphasizes social well-being, which rests on the following elements, among others:

- An efficient, high-performing education system;

- Quality health care;

- Potable water, electricity and a healthy housing for all;

- A healthy environment.

This vision will gradually become concrete through the execution of the Millennium Development Goals (MDG), ten-year plans, Poverty Reduction Growth Strategy (PRGS), and various government action plans. Actions targeting the improvement of social health conditions for the population occupy a select position. The Ministry of Health (MoH) is charged with preparing and implementing the health arm.

The National Health Development Plan (NHDP 2009-2018) translates the desires of actors in the Ministry of Health, Technical and Financial Partners, and the Beninese population to provide urgent, effective responses to the health problems of the populations. This plan, the embodiment of a consensus work targeting the major health issues of Benin’s populations, is the result of several workshops on health sector priorities for the next ten years (2009-2018).

The global objectives of the NHDP are:

- To ensure universal access to health services and improved quality of care to achieve the MDG;

- To strengthen the health partnership;

- To improve governance and resource management in the health sector.

The NHDP incorporates a vision that can contribute to strengthening the performance of Benin’s national health system, defined by the Health General Assembly in November 2007:

“In 2025, Benin will have a high-performing health system based on initiatives that are public and private, individual and collective, for the permanent offer and availability of Quality Care that is equitable and accessible to all categories of populations, founded on the values of Solidarity and Risk Sharing, to meet all of the health needs of the people of Benin.”

One of the specific major objectives of the new National Health Development Plan (NHDP 2009-2018) is the development of the country’s 34 health zones.

“To promote the emergence of a high-performing system of quality health service and care to the entire population, the government has reaffirmed the need to strengthen the base of the health pyramid by 2018. This will involve making all health zones operational so that they fully play their role as the drivers behind implementation of this plan at the operational level. In this perspective, the private sector will also be encouraged and strengthened to allow it to also fully play its role in the offer of health care and services. The State plays the role of regulation, policy design, and standards monitoring. This ambition requires the sector to optimize available resources and potentials.” The 2007-2011 cMYP objectives integrate with those of the NHDP.

The table below summarizes the strengths, weaknesses, opportunities and threats from the analysis of the health sector.

Principal strengths and weaknesses identified during the analysis of the health sector

| Plan | Strengths | Weaknesses | Opportunities | Threats |
| --- | --- | --- | --- | --- |
| Governance | Key elements of the health system structure are in place: legislation (including the private sector), health policy, public health service structuring, care facilities network, medicines policy, etc.; Joint action with technical and financial partners is organized (bi-yearly and bi-monthly meetings); Implementation of a decentralized system (health zones) on-going for 12 years, with established structures (Management Committees, Health Committees) to ensure local participation in health system administration; The recent decentralization just conferred specific health-related powers to the communes | Poorly operational health zones: weakness in the planning, coordination, management organization systems; leadership is not properly ensured; Urban health zones are not targeted with one specific approach; Zone hospitals are poorly operational and poorly performing; Inadequacies in the preparation of policies and in the planning process leading to unreliable definition of standards; Problems in applying certain regulatory texts at the intermediate level; Poorly performing monitoring/evaluation mechanism. Management bodies are not operational; Non-existent manuals for administrative, financial, accounting and materials procedures. | Existence of anti-establishment forces (Transparency International, Anti-Corruption Observatory) |  |
| Resources | Availability of human resources: nurses, midwives, and generalist physicians and lab technicians are relatively available; Center for the Procurement of Essential Medicines (CPEM), an autonomous public structure, enables provisioning with generic medicines and medical consumables. | Human resources: Low motivation of human resources; Poor career management of agents; Maladjustment of certain personnel categories; Unequal distribution of personnel between the public and private sectors, between urban and rural areas, and between clinicians and management; Basic training is not adapted to the needs of the field Irregular, inefficient supervision Frequency of illicit practices by personnel Proceedings of the General Assembly pages 61, 65, 73, 76, 77, 78 Material resources; Low level of technical support and inadequate management of technical materials. Inadequate medical-technical and rolling equipment and materials; Inadequate equipment, reagents and medical consumables; Frequent shortages of essential medicines at the CPEM; Monopolizing the CPEM as the only provisioning structure of medicines for health facilities; Weakness in the preventive and curative maintenance system of medical –technical materials and vaccine storage. Proceedings of the General Assembly pages 64, 67 | Health partnerships Political commitment Existence of training schools | Poor motivation for health personnel |
| Funding | Financial planning system enables cost recovery receipts to be retained locally and, since 2004, central credits to be vested in the health zones; Indigent Health Funds operational since 2005 Existence of a secured budget line item for the procurement of vaccines in the Ministry of Health budget. | Household contribution remains high in health sector funding (about 52%) Community funding supports much of the load involving the viability of some health facilities, with a negative effect on funding for preventive actions like immunization. Inadequate health mutuals and health insurance Decrease in the portion of the budget allocated to health compared to the State’s general budget in terms of proportion between 2004 and 2008 | Increase in sector budget to assure sustainability |  |
| Services | Country relatively covered by basic health infrastructure (average of 74%); National Health Management Information Systems (SNIGS) exists and provides information for planning and management; Private sector is varied, and the private socially-oriented sub-sector (religious sector) cooperates with the government; The past five years, maintenance of a 90% overall routine vaccine coverage for the 3rd dose of the pentavalent; | Care offerings remain incomplete, not ensuring continuing services, even where infrastructure exists; Quality of care is barely optimal, with inadequate funding of the quality assurance program; Poor use of services by the population generally in the public sector (0.4 curative contact per person per year and 23% coverage of urgent obstetrical needs); Stagnant health indicators (maternal mortality at 125/1000 and infant mortality at 64.4/1000 in 2006); Malaria-related mortality and morbidity are high, because only 19.7% of pregnant women and 20.2% of children under 5 slept under insecticide-treated mosquito nets during DHS III High prevalence of HIV/AIDS; the weighted prevalence of the infection in 2006 according to SNIGS was estimated to be 2% of the general population and 2.8% in urban areas Poor development of health research Poor vaccine coverage for certain antigens (34% of children in Benin were fully and correctly immunized at 1 year and 58% of mothers were protected against tetanus during the EPI 2008 review) Persistence of pockets of poor coverage in several communes in the north and south are evident in the last DHS III results, which place 47% of children 12-23 months as fully vaccinated. Reluctance in some locales to immunization Inaccessibility of certain targets to immunization services | Institutional and organization reforms |  |
| Health Information | Existence of operational structures to manage health information (SNIGS, INSAE) | Information on vaccine coverage do not account for gender |  |  |

The five (5) priority areas defined in the NHDP are the following:

- Preventing and fighting the main diseases and improving the quality of care;

- Valuing human resources;

- Strengthening partnership in the sector, promoting ethics and medical responsibility;

- Improving the mechanism for sector funding; and

- Strengthening sector management.

# Section 3: Situation Analysis / Needs Assessment

To the applicant: section 3.1

GAVI HSS Support: GAVI HSS support cannot address all health system barriers that impact on immunisation and other child and maternal health services. GAVI HSS support should look for opportunities to complement and leverage other funding for health system strengthening, as well as fill “gaps” in current health system development efforts, without duplication.

- Please provide information on the most recent assessments of the health sector that have identified health system barriers. (Table 3.1)

Note: Assessments can include a recent health sector review (conducted in the last 3 years), a recent report or study on sector constraints, a situation analysis (such as that conducted for the immunisation cMYP), or any combination of these. Please attach the reports of these assessments to the application (with executive summaries, if available).(Document Number....) Please number them and list them in Annex 1.

Note: If there have not been any recent in-depth assessments of the health system (in the last 3 years), at the very least, a desk review identifying and analysing the key health systems bottlenecks will need to be undertaken before applying for GAVI HSS support. This assessment should identify the major strengths and weaknesses in the health system, and identify where capacity needs to be strengthened to achieve and / or sustain increased immunisation coverage.

Note: Issues affecting the specific nature of reaching the hard to reach populations and increasing coverage within assessments or the National Health Plan should be highlighted (such as gender or other socio economic issues)

## 3.1: Recent health system or immunisation assessments

| Title of the assessment | Participating agencies | Main findings in terms of child mortality, immunisation coverage or health systems weaknesses | Dates |
| --- | --- | --- | --- |
| NHDP 2009-2018 (pages 31-32) | Ministry and TFP | - Inadequacies in the planning process at the operational level; - Poor functionality of health zones; - Poor quality of care from inadequate training of human resources and inadequate financial, material and logistics resources, resulting in poor use of services; - Irregular supervision and advanced strategies; - Certain qualified personnel are not available; - Poor use of operational research; - Inadequate quality health data | 2008 |
| Joint WHO/UNICEF report 2008 (sheet 4A-2) | NDEPI-PHC WHO/UNICEF | - Existence of communes with poor vaccine coverage (64% of the country’s communes have Penta3 coverage ≥ 90% and 55% have MV coverage ≥ 90%) - Coverage data not disaggregated by sex | March 2008 |
| Organizational and institutional audit of the Ministry of Health (pages 7-8) | WHO ; CEFA/CAFS; AMCES | - Conflicts of interests and allocations between several directorates - Weakening of the DDHs - Existence of doubles of plans and programs at the Health Zone level - Poor collaboration between the Ministry of Health and the health agent training structures | June 2008 |
| National Strategic Plan for Developing Human Resourced in Health (page 34) | WHO, 8th EDF, UNFPA | - Inadequacy in the strategic vision and development planning of human resources integrating the private sector; - Lack of medical and para-medical personnel, especially medical specialists; - Absence of workforce forecast planning; - Inexistence of qualified personnel for certain sought-after profiles; - Expiration of texts regulating recruitment in the Public Service; - Inadequate credits allocated by the State to recruit personnel; - Unequitable distribution of personnel across the country. | November 2008 |
| Report, Review of the Expanded Program on Immunization, March 2008 (pages no. 55-57; 135-139) | Ministry of Health WHO, UNICEF, USAID, AMP | - Irregular training supervision - Inadequate training of agents involved in EPI management - Inadequate maintenance of cold chain equipment - Inadequate incinerators and poor use of those that exist - Inadequate access by populations to vaccination services, with high drop-out rates ((>10%) - Relative performance of the Expanded Program, only 34% of children in Benin are fully and correctly immunized at 1 year according to the cards and 82% of targets from 12 to 23 months surveyed had received the 3rd dose of the pentavalent, 70% had received the measles vaccine according to cards or history. - 58% of mothers were protected against tetanus at the time of the survey - Existence of pockets of resistance to immunization | October 2008 |
| 2007 performance report (page 38) | Ministry of Health | - Poor programming capacity by sector actors - Problem of credit consumption procedures | December 2007 |
| General Report of the Health General Assembly (pages 14-20) | Ministry of Health WHO, UNFPA, CTB | - Low portion of funding for health - by the State - High maternal and neo-natal mortality rates - Poor quality of services and care - Mismatch between technical support for care structures and the needs of the populations - Poor organization of the reference and counter-reference system - Inadequate training – re-education and supervision of health personnel - Lack of medical and para-medical personnel, especially medical specialists - Inadequacies in the continuity of care/services provision in health facilities - Continual unavailability of medicines, medical consumables and reagents - Inadequate credits allocated by the State to recruit personnel - Salaries and accessories too low - Incentives and compensations provided for by texts not applied | November 2007 |
| Benin’s health care system: Main system characteristics and proposals for strengthening (page 4) | DPP CTB GAVI | Current operations defective in health zones First-level care broken Poorly performing hospitals Absence of true leadership Top-down planning Problematic quality of care Department Directorates of Health off-kilter Inconsistent urban zones Insufficient or worse than bad corrective measures | September 2007 |
| Complete Multiyear Plan for EPI 2007-2011 (pages 34-44) | MoH, UNICEF, WHO, AMP | - Irregular advance strategies result in high drop-out rates in some communes - Logistics inadequacies (cold chain, transport means) - Inadequacies in communication and advocacy activities - Weakness in integrated and response surveillance activities - Inadequate capacity development - Inadequate funding for program activities - Absence of disaggregated data regarding vaccine coverage | October 2006 |
| Rapid assessment of the health system in Benin (page 97-100) | USAID, MoH MSH, MEASURE Evaluation, Quality assurance Project | - Quality of care given is highly variable - Chronic inadequacy of specialist physicians in the public sector - Inexistence of incentive measures to recruit and maintain medical personnel in their positions - Training curricula are not appropriate for the tasks to be assigned to future graduates of training schools - Errors, at times significant, are recorded in the data, which also results in the delayed publication of the statistical yearbook, due to the long time DPP personnel spend correcting errors and validating data - Analysis and use of SNIGS information is practically non-existent at the peripheral health centers At the intermediate level, SNIGS reports are not exploited on a regular basis | June 2006 |
| National Strategies to reduce maternal and neo-natal mortality (page 6-7) | USAID, WHO, UNICEF, FNUAP, ACQUIRE, Ministry of Health | Low proportion of target health centers offering CUONC High neo-natal mortality Proportion of personal with acceptable level of knowledge about strategies for reducing maternal mortality is low Low proportion of health facilities that have CUONC equipment | March 2006 |
| 2007 health statistics yearbook (page 184) | Ministry of Health | Vaccine coverage data are not disaggregated by gender | December 2008 |

To the applicant: section 3.2

- Please provide information on the major health system barriers to improving immunisation coverage that have been identified in recent assessments listed above. (Table 3.1). These could also highlight any socio economic or political reasons as well as men and women’s roles in society, family or among workforce, attitudes towards boys or girls as well as ‘perceptions’ that may affect the immunisation coverage  of specific  ethnic groups or females and males.

## 3.2: Major barriers to improving immunisation coverage identified in recent assessments

Governance

- Poor organization of the reference and counter-reference system;

- Conflicts of interests and allocations between several directorates at the Ministry of Health;

- Weakening of the Department Directorates of Health in the areas of decision-making and activity coordination in the field;

- Poor collaboration between the Ministry of Health and the health agent training institutions;

- Weak intersector action to improve health determinants;

- Undervalued approach to Primary Health Care.

Human resources

- Inadequate capacity development;

- Chronic inadequacy of specialist physicians in the public sector;

- Inexistence of incentive measures to recruit and maintain medical personnel in their positions;

- Training curricula are not appropriate for the tasks to be assigned to future graduates of training schools;

- Poor personnel motivation (salaries and accessories too low);

- Incentives and compensations provided for by texts not applied;

- Lack of medical and para-medical personnel, especially medical specialists;

- Irregular training supervision;

- Inadequate training of agents involved in EPI management;

- Absence of workforce forecast planning;

- Inexistence of qualified personnel for certain sought-after profiles;

- Unequitable distribution of personnel across the country.

Material resources

- Logistics inadequacies (cold chain, transport means);

- Inadequate maintenance of cold chain equipment;

- Inadequate incinerators and poor use of those that exist.

Funding

Low portion of health funding by the State

Services

- Under-performing hospitals;

- Irregular advance strategies resulting in high drop-out rates in some communes;

- Inadequacies in communication and advocacy activities;

- Weakness in integrated and response surveillance activities;

- Inadequacies in the continuity of care/services provision in health facilities;

- Poor quality of care services;

- Mismatch between technical support for care structures and the needs of the populations;

- High maternal and neo-natal mortality rates;

- Inadequate access by populations to vaccination services, with high drop-out rates ((>10%);

- Poor vaccine coverage in some communes (Atlantic-Coast, Ouerne-Plateau);

- Low proportion of health centers offering CUONC and having CUONC equipment, incorporating strategies for reducing maternal mortality;

- High neo-natal mortality;

- Existence of pockets of resistance to immunization.

Health Information

- Errors, at times significant, are recorded in the data, which also results in the delayed publication of the statistical yearbook, due to the long time DPP personnel spend correcting errors and validating data that are prejudicial to data quality;

- Analysis and use of SNIGS information is practically non-existent at the peripheral health centers; At the intermediate level, SNIGS reports are not exploited on a regular basis;

- Vaccine coverage data are not disaggregated by sex.

To the applicant: section 3.3

- Please provide information on those barriers that are being adequately addressed with existing resources (Table 3.3). These could be socio economic, political or related to gender analysis based on social science research.

## 3.3: Barriers that are being adequately addressed with existing resources

There is a series of barriers that have been realized or are in the process of being resolved and funded by other partners

- Chronic inadequacy of specialist physicians (pediatricians, gynecologists, surgeons) in the public sector: training grants are allocated by the Coopération belge;

- Low portion of health funding by the State despite an increase in the national budget obtained for 2009: 08.99% of the State budget versus 7.23% in 2008;

- High neo-natal mortality (taken into consideration by the bilateral cooperations).

To the applicant: section 3.4

- Section 3.4 should outline the most important barriers not being adequately addressed and give reasons why they have been prioritized in terms of those that are not currently funded by other sources, such as those that will have maximum impact or catalyse other activities or for geographic or social reasons. If there is an obvious lack of a national policy that emphasises a human rights based approach to accessing health care (including gender or lack of competencies at different levels of the health system then it should be mentioned here.

## 3.4: Barriers not being adequately addressed (in order of highest priority)

Despite efforts, certain problems persist, such as:

In terms of governance

Poor capacity for planning and coordinating health sector actions and activities, with these consequences:

-	Absence of true leadership for health agents at all levels;

-	Weakening of the DDHs (inadequate technical competencies and coordination of actions in the health zones);

-     Conflicts of interests and allocations between several directorates;

- Current operations defective in health zones;

-     Inadequate planning and coordination at all levels.

In terms of human resources

Human resources are inadequate in terms of quantity, quality, and are poorly motivated, which results in:

- Lack of medical and para-medical personnel, especially medical specialists;

- Irregular training supervision;

- Inadequate training of agents involved in EPI management;

- Inexistence of qualified personnel for certain sought-after profiles.

In terms of material resources

Inadequate equipment logistics and maintenance (cold chain, means of transport) and waste management (incinerators).

In terms of services

Poor quality of service provision linked to

-	Poor organization of the reference and counter-reference system;

-	Under-performing hospitals;

-	Mismatch between technical support for care structures and the needs of the populations;

-	Inadequacies in the continuity of care/services provision in health facilities;

- Low proportion of health centers offering UOC and having UOC equipment, incorporating strategies for reducing maternal mortality;

-	High maternal and neo-natal mortality rates.

Poor vaccination performance linked to

-	Irregular advance strategies resulting in high drop-out rates in some communes;

-	Inadequacies in communication and advocacy activities;

-	Weakness in integrated and response surveillance activities;

-	Inadequate access by populations to vaccination services, with high drop-out rates (>10%);

- Existence of pockets of resistance to immunization.

Health Information

- Weaknesses in the collection, analyses and use of health statistical data (publication and feedback) at all levels of the health pyramid; vaccine coverage data are not disaggregated by sex;

- Weakness in the use of operational research.

To the applicant: section 3.5

- Section 3.5. should outline the barriers to civil society and the private sector in delivering immunization services and strengthening health systems and becoming part of the national process to increase immunisation coverage

## 3.5: Describe specific barriers to civil society and the private sector in delivering immunization services and strengthening health systems or becoming part of the national process to increase immunisation coverage.

All private and religious hospital structures recognized by the State provide immunization only in fixed stations. Private offices, authorized or not, do not provide immunization due to the non-existence of appropriate cold chain equipment and qualified personnel. Similarly, the absence of appropriate support subsidies and strategies for these structures and for civil society is a factor that hinders them from helping to increase vaccine coverage.

# Section 4: Goals and Objectives of GAVI HSS Support

To the applicant: sections 4.1 and 4.2

- Please describe the goals of GAVI HSS support below (Table 4.1).

- Please describe (and number) the objectives of GAVI HSS support (Table 4.2). Please ensure that the chosen objectives are SMART (specific, measurable, achievable, realistic and time-bound).

- This section should demonstrate a) why the proposed HSS objective is expected to sustain immunization coverage and b) how the proposed activities will ensure the achievement of HSS objectives. It is therefore very important to show the links between identified barriers – goals – objectives – activities and indicators. They should follow a logical sequence and distinct outputs, outcomes and processes should be identified.. It should then be evident how the proposed activities will increase or sustain immunization coverage

- Geographic issues: If a discrete sub national area has been selected for intervention, it should be clear how and why the area(s) were selected and the rationale for the geographic specific indicators and criteria

- Any supporting documents or background documents (such as the Human Resource Policy Document Number…., procurement policy Document Number…. or Mid Term Expenditure Framework Document Number….) should be quoted here and references should be precise in terms of sections and page numbers referred to in the application.

## 4.1: Goals of GAVI HSS support

Per the barriers not being covered listed in section 3.4, maternal and infant mortality rates remain high and Penta3 coverage remains low in several health zones in Benin.

Thus the main GAVI HSS support goal is to strengthen implementation of NHDP (2009-2018) by “contributing to reducing maternal and infant mortality through immunization, functionality and performance at the three levels of Benin’s health system, with particular emphasis on target health zones, in conjunction with other on-going interventions.”

This goal will be achieved through the objectives concerning strengthening planning and coordination capacities, CUONC quality, immunization services, and making adequate, motivated human resources available to the structures.

## 4.2: SMART objectives of GAVI HSS Support

The specific objectives for GAVI support to HSS are:

Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012

This objective is linked to the barrier concerning the poor planning, supervision and coordination capacity of health sector actions and activities at all levels, as well as inadequacies in the National Health Information System. To achieve this objective, this application emphasizes activities that target leadership development for health agents, bottom-up planning, public-private joint action, civil society, supervision, strengthening the information system and health research. This objective will be assessed by the availability of a work plan at the end of bottom-up planning. This objective will be measured via the following indicators:

-      Number of agents from the DPP, two DDH and four (4) STZH trained in the bottom-up planning process

- Number of Target Health Zones that have a smoothly operational three-year work plan

II. Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 Department Hospitals and the 4 target health zones from 2010 to 2012;

Objective no. 2 is linked to barriers related to the poor quality of service provision including poor immunization performance in the target zones and inadequate logistics and maintenance of equipment (cold chain, transport means) and waste management (incinerators). In the context of this application this means organizing the reference and counter-reference system, strengthening the technical support center in care structures offering CUONC and immunization services and surveillance, ensuring the continuity of care/services in health facilities, and ensuring communication to support the program. This objective will be measured via the following indicators:

- Number of target health centers offering CUONC

- % of target health zones achieving at least 80% Penta3

- Rate of assisted deliveries in target zones

III. Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 hospitals and 4 health zones targeted from 2010 to 2012

Objective no. 3 is linked to barriers related to human resources that are insufficient in quantity, quality and motivation. Achieving this object will mean recruiting the missing specialist personnel, revising curricula, strengthening the capacities of agents, providing training supervision, and granting performance incentives in the targeted health zones. Two indicators were selected to assess if this objective is achieved:

- % of health centers with personnel qualified per standards in target health zones

- % of the population indicating that it is satisfied with health care received in the target health zones

The support requested from GAVI mainly concerns 4 health zones and two (2) department hospitals in addition to the intermediate and central levels. The selection criteria for Health Zones (HZ) to receive support from the GAVI submission are as follows:

1.	Health zones with poor EPI coverage (Penta3 < 80%)

2.	High maternal and infant mortality rates (greater than 397/100,000 live births; greater than 67 per 1000)

3.	Functionality of the health zone (presence of a zone hospital).

The Department Hospital Centers (DHC) and Department Directorates of Health (DDH) were selected on the basis of geographical location in selected health zones, to optimise the expected effects.

| Departments (DDH and DHC) | Health Zones | Penta 3 | Maternal mortality rate | Infant mortality rate | Presence of zone hospital |
| --- | --- | --- | --- | --- | --- |
| Borgou / Alibori | Malanville/Karimama | 21% | 397/100 000* | 86 per 1000 | Yes |
|  | Tchaourou | 29% |  | 78 per 1000 | Yes |
|  | Adjohoun / Bonou / Dangbo | 44% |  | 73 per 1000 | Yes |
|  | Sakété / Ifangni | 39% |  | 75 per 1000 | Yes |

# *  national average

# Section 5: GAVI HSS Activities and Implementation Schedule

To the applicant: section 5.1

- Please identify below how it is intended to sustain, both technically and financially, the impact achieved with GAVI HSS support (5.1) when GAVI HSS resources are no longer available.

Note: Mechanisms for the technical and financial sustainability should be carefully outlined especially for GAVI support related to infrastructure, equipment, transport and human resources development efforts. This should include how these investments will be sustained after GAVI HSS support has finished. Reference should be made to the Infrastructure, Procurement or Human Resources Development strategies or policy documents (Document Number ....), if they exist.

Note: GAVI recommends that GAVI HSS supports a few prioritised objectives and activities only. It should be possible to implement, monitor and evaluate the activities over the life of the GAVI HSS support.

- For each SMART objective identified in Table 4.2, detail the major activities that will be undertaken to achieve that objective. Include the implementation schedule (duration, annual milestones, and end point if any) for each of these activities.

- Ensure timing of activity duration in table 5.2 is consistent with the timing of expenditures for each activity shown in table 5.3

## 5.1: Sustainability of GAVI HSS support

The political will that is increasingly displayed to support the health sector through the effective application of the decision to ensure the no-cost (underwritten by the State) provision of care to children under 5 and caesareans to pregnant women by its nature ensures the sustainability of GAVI support. The government has committed to yearly increases in the portion of the budget allocated to the health sector to 10% of the general State budget by 2010.

In addition to the motivation and incentive policy conducted beginning in 2008, the Government has opted to gradually recruit specialists and other qualified agents for the benefit of health centers and hospitals. In this way the effort has continued in 2009, with a significant increase in payroll, which increased from 8 billion in 2008 to 24 billion in 2009.

Also to sustain the underwriting of specialists in remote zones, the Ministry of Health is negotiating with stakeholders (communes, hospitals and partners involved in the locale) to ensure that motivational incentives are underwritten (one-third by the actors).

Strengthening the management capacity of Health Zone Supervisory Team managers will enable the effective, efficient use of the resources allocated by the State and development partners to the health sector.

The appreciable contribution of community funding towards the operation of Health Zones by increased mobilization of additional resources (health mutuals, partnerships, decentralized cooperation, economic operators) is a pledge to sustain activities. Likewise, setting up a universal insurance program (RAMU) will strengthen health risk coverage, especially for poor and indigent populations.

The adhesion and adoption of the project by Benin’s development partners guarantee their participation and involvement in its implementation and continuity. Intervention by GAVI complements efforts by the Government, the TFP, and Benin communities, which constitute an additional pledge towards the sustainability of the project.

Thus, coordination mechanisms exist within Benin to strengthen governance and to reassure the various actors involved in health development.

National Committee to monitor Execution and to Evaluate Health Sector Projects/Program (CNEEP)

CNEEP bodies are: (1) Plenary Assembly of committee members; (2) The Permanent Secretariat; (3) The two sub-committees (the monitoring-evaluation sub-committee of health pyramid reorganization and sector resource management; the monitoring-evaluation Sub-committee of diseases and family health); (4) The Department Committees to monitor Execution and to Evaluate Projects/Program (CDEEP).

Bi-annual meeting of sector development partners

This meeting brings together the sector’s Technical and Financial Partners, members of the Minister’s cabinet, technical and central directors from the Ministry of Health.

Joint annual performance review of the health sector

This brings together the government, Technical and Financial Partners, and civil society on the performance of the health sector to take stock of actions conducted during the past year and to give guidelines for the future.

National Coordination Committee (NCC) for projects/programs financed by the Global Fund

This provides technical support to the development of requests and monitoring the implementation of projects financed by the Global Fund. It has a technical cell that meets four times per year and on request. The NCC itself meets two times per year.

Inter-Agency Coordinating Committee (IACC)

The IACC is charged with political and strategic guidelines in immunization matters. It meets three times per year.

Roll Back Malaria facilitation group

This is an arrangement of national partners to support the national program to fight malaria in analysing the situation, planning, implementation and resource mobilization. It meets four times per year.

Ministry Executive Committee (EXECOM)

This meets every Monday in ordinary session, and upon the request of the Minister in extraordinary session. It can be expanded as needed at the intermediate level depending on the subjects to be discussed. It takes stock of weekly activities, provides guidelines on activities to plan for the coming week, and consultative advice on the main files listed in the agenda.

Mechanism for monitoring-evaluation, control and internal verification

The sector has:

- At the national level, a monitoring-evaluation cell within the Directorate of Programming and Planning, focal points within other central and technical directorates, and priority sector projects, a General Inspection of the Minister and Financial Control Delegations;

- At the intermediate level, Divisions of Studies, Planning and Monitoring

- Management committees exist at the health zone level and in other health facilities to support health personnel in implementing the guidelines in the NHDP at the decentralized level.

Other mechanisms for transparency in management

As part of a more rational management of State resources (internal and external), Benin has available several tools, including:

- Anti-corruption observatory;

- Transparency International Benin;

- State Inspection General (SIG);

- Social Watch;

- Finance Inspection General (FIG).

The Ministry of Health will collaborate with GAVI procedures to ensure that the policy of transparency and responsibility in Benin meets the stated criteria.

To the applicant: section 5.2

- Note: Please add (or delete) rows so that Table 5.2 contains the correct number of objectives for your GAVI HSS application, and the correct number of activities for each of your core objectives.

- Note: Please add (or delete) years so that Table 5.2 reflects duration of your GAVI HSS application

- Note: The budget for the first year should demonstrate the use of unit costs and a budget breakdown. This will add to the soundness and sense of realism of the proposal; especially for any activities that may include major training or procurement components.  Budgets should be based on real costs and not based on contingency cost.

- For each objective identified in Table 4.2, please give details of the major activities that will be undertaken in order to achieve the stated objective and the implementation schedule for each of these activities over the duration of the GAVI HSS support.

## 5.2: Major Activities and Implementation Schedule

To achieve objective no. 1, scheduled activities concern capacities, creation of a joint framework with community representatives, supervision, acquisition of technical, rolling, and computer materials, and monitoring-evaluation. The selected activities also incorporate findings; realizing these activities will enable governance and leadership in the targeted zones to be improved.

To achieve objective no. 2, the scheduled activities concern the acquisition of medical-technical materials, medical consumables, rolling stock, cold chain equipment, and the construction of incinerators. Execution of these activities will enable the quality of care and immunization services to be improved for remote targets, and thus maternal and infant mortality to be reduced.

Objective no. 3, in order to make personnel available and ensure the continuity and availability of care 24 hours a day, envisions recruitment of qualified health agents and specialist physicians, strengthening of STZH supervision by the intermediate level, and granting of performance incentives.

## The GAVI Plan will be implemented over three years to remain in compliance with the Program Budget and the Medium-Term Expense Framework (MTEF).

| PRINCIPAL ACTIVITIES | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 |  |  |  | 2011 |  |  |  | 2012 |  |  |  |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012 |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1: Train 42 STZH and DDH agents in the bottom-up planning process, budgeting and resource allocation over 3 days in two sessions (1 in the south and 1 in the north) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2: Develop, by pyramid level, a three-year work plan through a bottom-up planning process with 24 participants over 3 days (3 STZH members per zone, 1 COGEC per zone, 1 per DHC, 1 per DDH targeted and 4 managers at the central level) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3: Train the STZH of 4 target health zones in the techniques of training supervision for 40 members of the STZH and 4 trainers (one session in the north and one session in the south) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4: Organize the annual workshop on validating SNIGS data at the level of the 2 departments (1 in the south and 1 in the north) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5: Create and make operational a joint action group (health agents, health committees, local elected officials, traditional practitioners and civil society) to involve them in the preparation, implementation and monitoring of activities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6: Train DPP agents in results-focused management tools |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.7: Acquire 8 computers and accessories (2 at the SNIGS in the DDH; 2 for the 2 DHC and 4 for the four (4) target Health Centers for improved management of EPI data) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.8: Set up a mechanism for controlling SNIGS data quality |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.9: Perform bi-annual monitoring of GAVI funds activities by the Guidelines Committee acting through the DPP and the DFMR |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.10: Have health zones supervised by the intermediate level (DDH) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.11: Have the STZH supervise activities in the 4 health zones (HZ) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.12: Produce annual bulletins of SNIGS feedback at the targeted and national zones levels |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.13: Have a consultant conduct a limited midterm evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.14: Conduct an internal financial audit every year |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.15: Train 40 STZH members for the 4 targeted health zones in operational research in two sessions (1 in the south and 1 in the north) with 4 trainers at the central level |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.16: Conduct a study on the factors associated with demotivation of personnel in the target zones |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.17: Have 2 consultants (1 national and 1 international) conduct the final evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 departmental hospitals and the 4 health zones targeted from 2010 to 2012; |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1: Acquire medical consumables and reagents for laboratories involved in the epidemiological surveillance of diseases targeted by EPI |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2: Acquire 2 supervision vehicles for the 2 family health services of the 2 DDHs |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3: Acquire 32 motorcycles for advanced strategy immunization in the four (4) targeted health areas |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.4: Acquire medical-technical materials for the 2 DHC and 4 health zone hospitals targeted (manual vacuum aspiration, suction cups, caesarean boxes, newborn resuscitation materials) for the CUONC; automatic serology devices, microbiology hoods for the 2 hospitals |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.5: Acquire 10 refrigerators to store vaccines in health centers |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.6: Acquire 3 supervision vehicles (the DZHD, the DPP and the NDEPI) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.7: Acquire 2 ambulances for the Adjohoun-Bonou-Dangbo and Sakété-Ifangni Health Zones |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.8: Construct 3 incinerators in the health centers and hospitals that don’t have one |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.9: Provide upkeep and maintenance for all medical-technical equipment and materials in the 4 HZs and 2 DHCs targeted |  |  |  |  |  |  |  |  |  |  |  |  |

| Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 departmental hospitals and 4 health zones targeted from 2010 to 2012 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 3.1: Strengthen the capacities of 50 midwives and maternity nurse in the following areas: Obstetric nursing care: PCIME, SOU, UNC |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2: Train/recycle 100 midwives and maternity nurses in the following areas: Obstetric nursing care; PCIME, SOU, UNC |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3: Recruit 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology, obstetrics, pediatrics, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.4: Monitor activities in the 4 health zones (HZs) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.5: Grant motivational incentives to teams (physicians, midwives, nurses, lab technicians and administrators) in the 4 and 2 targeted DHC zones based on results. |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.6: Pay salaries of the 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology-obstetrics, pediatrics, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |

To the applicant: section 5.3

Note: The first year’s implementation plan should be outlined in section 5.3, giving details of timelines, inputs, outputs and processes to be monitored, with details of  costs (and unit costs at least for the first year implementation).

## 5.3: Costed implementation plan for the first year of implementation

1st YEAR IMPLEMENTATION PLAN

| Program Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Signature date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Effective start date: |  |  |  |  |  |  |  |  |  |  | CNEEP approval: |  |  |  |  |
| Ending date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |
|  | Activities |  | RESPONSIBLE STRUCTURES |  | RESULTS INDICATOR |  | COST (IN 000 OF USD) | EXECUTION PERIOD: |  |  |  | LOCATION in 2010 |  |  |  |
|  |  |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | DEPARTEMENT | HEALTH ZONES |  |  |
|  | Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012 |  |  |  |  |  | 153,017 |  |  |  |  |  |  |  |  |
|  | Activity 1.1 Train 42 STZH and DDH agents in the bottom-up planning process, budgeting and resource allocation over 3 days in two sessions (1 in the south and 1 in the north) |  | DPP |  | % of personnel trained |  | 29,398 |  |  |  |  | 2 Departments | 4 Targeted zones |  |  |
|  | Activity 1.2 Develop, by pyramid level, annual three-year work plan through a bottom-up planning process with 24 participants over 3 days (3 STZH members per zone, 1 COGEC per zone, 1 per DHC, 2 per DDH targeted and 4 managers at the central level) |  | DPP and other directorates |  | Plan developed |  | 8,385 |  |  |  |  | 2 Departments | 2 Departments and national level |  |  |
|  | Activity 1.3 Train the STZH of 4 target health zones in the techniques of training supervision for 40 members of the STZH and 4 trainers (one session in the north and one session in the south) |  | DDH |  | % of personnel trained |  | 24,471 |  |  |  |  | 2 Departments | 4 Targeted zones |  |  |
|  | Activity 1.4: Activity 1.4: Organize the annual workshop on validating SNIGS data at the level of the 2 departments (1 in the south and 1 in the north) |  | DPP |  | Workshop report |  | 27,679 |  |  |  |  | 2 Departments | 2 DDHs |  |  |
|  | Activity 1.5: Create and make operational a joint action group (health agents, health committees, local elected officials, traditional practitioners and civil society) to involve them in the preparation, implementation and monitoring of activities. |  | DDH |  | Joint action report |  | 13,222 |  |  |  |  | 2 Departments | Two DDHs |  |  |
|  | Activity 1.6: Train DPP agents in results-focused management tools |  | DPP |  | Training report |  | 13,293 |  |  |  |  | DPP | Central level |  |  |
|  | Activity 1.7: Acquire 8 computers and accessories (2 at the SNIGS in the DDH; 2 for the 2 DHC and 4 for the four (4) target Health Centers for improved management of EPI data) |  | DPP/DFMR |  | Delivery receipt |  | 26,667 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 1.8 Set up a mechanism for controlling SNIGS data quality |  | DPP |  | Control report |  | 887 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 1.9: Perform bi-annual monitoring of GAVI funds activities by the Guidelines Committee acting through the DPP and the DFMR |  | Guidelines Committee/DPP |  | Monitoring report |  | 4,664 |  |  |  |  | National level | 6 HZ |  |  |
|  | Activity 1.10: Have health zones supervised by the intermediate level (DDH) |  | DDH |  | Supervision report |  | 2,176 |  |  |  |  | 2 Departments |  |  |  |
|  | Activity 1.11: Have the STZH supervise activities in the 4 health zones (HZ) |  | HZCP |  | Supervision report |  | 2,176 |  |  |  |  | 4 HZs | HZCP |  |  |
|  | Activity 1.12 Produce annual bulletins of SNIGS feedback at the targeted and national zones levels |  | DPP/DDH |  | Bulletin produced |  | 0 |  |  |  |  | 2 Departments | 4 HZs and national level |  |  |
|  | Activity 1.13 Have a consultant conduct a limited midterm evaluation |  |  |  |  |  | 0 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 1.14: Conduct an internal financial audit every year |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | Activity 1.15: Train 40 STZH members for the 4 targeted health zones in operational research in two sessions (1 in the south and 1 in the north) with 4 trainers at the central level |  |  |  |  |  | 0 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 1.16: Conduct a study on the factors associated with demotivation of personnel in the target zones |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | Activity 1.17: Have 2 consultants (1 national and 1 international) conduct the final evaluation |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 departmental hospitals and the 4 health zones targeted from 2010 to 2012; |  |  |  |  |  | 391,632 |  |  |  |  |  |  |  |  |
|  | Activity 2.1: Acquire medical consumables and reagents for laboratories involved in the epidemiological surveillance of diseases targeted by EPI |  | DPP/DFMR |  | No. received |  | 41,572 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 2.2: Acquire 2 supervision vehicles (for the two department family health services of the two DDHs |  | DPP/DFMR |  | No. received |  | 66,667 |  |  |  |  | 2 Departments | 2 DDH central level |  |  |
|  | Activity 2.3: Acquire 32 motorcycles for advanced strategy immunization in the four (4) targeted health areas |  | DPP/DFMR |  | No. of motorcycles delivered |  | 64,000 |  |  |  |  | 2 Departments | 4 HZ |  |  |
|  | Activity 2.4: Acquire medical-technical materials for the 2 DHC and 4 health zone hospitals targeted (manual vacuum aspiration, suction cups, caesarean boxes, newborn resuscitation materials) for the CUONC; automatic serology devices, microbiology hoods for the 2 hospitals |  | DPP/DFMR |  | No. of materials received |  | 181,333 |  |  |  |  | 2 Departments | 4 HZs and 2 DHCs |  |  |
|  | Activity 2.5: Acquire 10 refrigerators to store vaccines in health centers |  | DPP{/DFMR |  | No. of materials received |  | 26,660 |  |  |  |  | 2 Departments | 4 HZs |  |  |
|  | Activity 2.6: Acquire 3 supervision vehicles (the DZHD, the DPP and the NDEPI) |  |  |  |  |  | 0 |  |  |  |  | 2 Departments | DPP, DZHD, NDEPI |  |  |
|  | Activity 2.7: Acquire 2 ambulances for the Adjohoun-Bonou-Dangbo and Sakété-Ifangni Health Zones |  |  |  |  |  | 0 |  |  |  | X | 1 Department | 2 HZs |  |  |
|  | Activity 2.8: Construct 3 incinerators in the health centers and hospitals that don’t have one |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | Activity 2.9: Provide upkeep and maintenance for all medical-technical equipment and materials in the 4 HZs and 2 DHCs targeted |  | DIEM/DDH |  | Maintenance report |  | 11,400 |  |  |  |  | 2 Departments | 4 HZs and 2 DHCs |  |  |
|  | Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 departmental hospitals and 4 health zones targeted from 2010 to 2012 |  |  |  |  |  | 341,844 |  |  |  |  |  |  |  |  |
|  | Activity 3.1: Strengthen the capacities of 50 midwives and maternity nurses in the following areas: Obstetric nursing care: PCIME, SOU, UNC |  | DFH/ HZCP |  | Number trained |  | 29,693 |  |  |  |  | 2 Departments | 4 HzS |  |  |
|  | Activity 3.2: Train/recycle 100 midwives and maternity nurses in the following areas: Obstetric nursing care; PCIME, SOU, UNC |  | DFH/HZCP |  | Number trained |  | 0 |  |  |  |  |  |  |  |  |
|  | Activity 3.3: Recruit 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology, obstetrics, pediatrics, etc.) |  | DPP |  | Number recruited |  | 305,329 |  |  |  |  | 2 DHCs | 4 HZs |  |  |
|  | Activity 3.4: Monitor activities in the 4 health zones (HZs) |  | DDH |  | Monitoring report |  | 6,822 |  |  |  |  | 2 Departments | 4 HZs |  |  |
|  | Activity 3.5: Grant motivational incentives to teams (physicians, midwives, nurses, lab technicians and administrators) in the 4 and 2 targeted DHC zones based on results. |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | Activity 3.6: Pay salaries of the 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology-obstetrics, pediatrics, etc.) |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 886,493 |  |  |  |  |  |  |  |  |

BALANCE SHEET

| Signature date: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ending date: |  |  |  | Responsible structure: |  |  |  |  |
|  |  |  |  | Date: |  |  |  |  |

| Activities | RESULTS INDICATOR | Physical % of execution rate | Financial execution in millions of F CFA |  |  | Location | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | P3 | R4 | TAUX5 |  |  |
| Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012 |  |  | 153,017 |  |  |  |  |
| Activity 1.1 Train 42 STZH and DDH agents in the bottom-up planning process, budgeting and resource allocation over 3 days in two sessions (1 in the south and 1 in the north) | % of personnel trained |  | 29,398 |  |  | 4 Targeted zones |  |
| Activity 1.2 Develop, by pyramid level, annual three-year work plan through a bottom-up planning process with 24 participants over 3 days (3 STZH members per zone, 1 COGEC per zone, 1 per DHC, 1 per DDH targeted and 4 managers at the central level) | Plan developed |  | 3,385 |  |  | 2 departments and national level |  |
| Activity 1.3 Train the STZH of 4 target health zones in the techniques of training supervision for 40 members of the STZH and 4 trainers (one session in the north and one session in the south) | % of personnel trained |  | 24,471 |  |  | 4 Targeted zones |  |
| Activity 1.4: Organize the annual workshop on validating SNIGS data at the level of the 2 departments (1 in the south and 1 in the north) | Workshop report |  | 27,679 |  |  | Two DDHs |  |
| Activity 1.5: Create and make operational a joint action group (health agents, health committees, local elected officials, traditional practitioners and civil society) to involve them in the preparation, implementation and monitoring of activities. | Joint action report |  | 13,222 |  |  | Two DDHs |  |
| Activity 1.6: Train DPP agents in results-focused management tools | Training report |  | 13,293 |  |  | Central level |  |
| Activity 1.7: Acquire 8 computers and accessories (2 at the SNIGS in the DDH; 2 for the 2 DHC and 4 for the four (4) target Health Centers for improved management of EPI data) | Delivery receipt |  | 26,667 |  |  | 4HZs |  |
| Activity 1.8: Set up a mechanism for controlling SNIGS data quality | Control report |  | 887 |  |  | 4 HZs |  |
| Activity 1.9: Perform bi-annual monitoring of GAVI funds activities by the Guidelines Committee acting through the DPP and the DFMR | Monitoring report |  | 4,664 |  |  | DPP DFMR |  |
| Activity 1.10: Have health zones supervised by the intermediate level (DDH) | Supervision report |  | 2,176 |  |  | 2 DDHs |  |
| Activity 1.11: Have the STZH supervise activities in the 4 health zones (HZ) | Supervision report |  | 2,176 |  |  | HZCP |  |
| Activity 1.12: Produce annual bulletins of SNIGS feedback at the targeted and national zones levels | Bulletin produced |  | 0 |  |  | 4 HZs and national level |  |
| Activity 1.13: Have a consultant conduct a limited midterm evaluation |  |  | 0 |  |  | 4 HZs |  |
| Activity 1.14: Conduct an internal financial audit every year |  |  | 0 |  |  |  |  |
| Activity 1.15: Train 40 STZH members for the 4 targeted health zones in operational research in two sessions (1 in the south and 1 in the north) with 4 trainers at the central level |  |  | 0 |  |  | 4 HZs |  |
| Activity 1.16: Conduct a study on the factors associated with demotivation of personnel in the target zones |  |  | 0 |  |  |  |  |
| Activity 1.17: Have 2 consultants (1 national and 1 international) conduct the final evaluation |  |  | 0 |  |  |  |  |
| Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 departmental hospitals and the 4 health zones targeted from 2010 to 2012; |  |  | 391,632 |  |  |  |  |
| Activity 2.1: Acquire medical consumables and reagents for laboratories involved in the epidemiological surveillance of diseases targeted by EPI | Number received |  | 41,572 |  |  | 4 HZs |  |
| Activity 2.2: Acquire 2 supervision vehicles (for the 2 family health services of the two DDH | Number received |  | 66,667 |  |  | 2 DDHs |  |
| Activity 2.3: Acquire 32 motorcycles for advanced strategy immunization in the four (4) targeted health areas | Number of motorcycles delivered |  | 84,000 |  |  | 4 HZs |  |
| Activity 2.4: Acquire medical-technical materials for the 2 DHC and 4 health zone hospitals targeted (manual vacuum aspiration, suction cups, caesarean boxes, newborn resuscitation materials) for the CUONC; automatic serology devices, microbiology hoods for the 2 hospitals | Number of materials received |  | 181,333 |  |  | 4 HZs and 2 DHCs |  |
| Activity 2.5: Acquire 10 refrigerators to store vaccines in health centers | Number of materials received |  | 26,660 |  |  | 4 HZs |  |
| Activity 2.6: Acquire 3 supervision vehicles (the DZHD, the DPP and the NDEPI) |  |  | 0 |  |  | DPP DZHD NDEPI |  |
| Activity 2.7: Acquire 2 ambulances for the Adjohoun-Bonou-Dangbo and Sakété-Ifangni Health Zones |  |  | 0 |  |  | 2 HZs |  |
| Activity 2.8: Construct 3 incinerators in the health centers and hospitals that don’t have one |  |  | 0 |  |  |  |  |
| Activity 2.9: Provide upkeep and maintenance for all medical-technical equipment and materials in the 4 HZs and 2 DHCs targeted | Maintenance report |  | 11,400 |  |  | 4 HZs and 2 DHCs |  |
| Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 hospitals and 4 departmental health zones targeted from 2010 to 2012 |  |  | 341,844 |  |  |  |  |
| Activity 3.1: Strengthen the capacities of 50 midwives and maternity nurses in the following areas: Obstetric nursing care: PCIME, SOU, UNC | Number trained |  | 29,693 |  |  | 4 HZs |  |
| Activity 3.2: Train/recycle 100 midwives and maternity nurses in the following areas: Obstetric nursing care; PCIME, SOU, UNC | Number trained |  | 0 |  |  |  |  |
| Activity 3.3: Recruit 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology, obstetrics, pediatrics, etc.) | Number recruited |  | 305,329 |  |  | 4 HZs |  |
| Activity 3.4: Monitor activities in the 4 health zones (HZs) | Monitoring report |  | 6,822 |  |  | 4 HZs |  |
| Activity 3.5: Grant motivational incentives to teams (physicians, midwives, nurses, lab technicians and administrators) in the 4 and 2 targeted DHC zones based on results. |  |  | 0 |  |  |  |  |
| Activity 3.6: Pay salaries of the 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology-obstetrics, pediatrics, etc.) |  |  | 0 |  |  |  |  |
|  |  |  | 886,493 |  |  |  |  |

# Section 6: Monitoring, Evaluation and Operational Research

To the applicant: Sections 6.1, 6.2 and 6.3

Note: It is strongly recommended that the chosen indicators are linked with proposal objectives and not necessarily with activities. Where possible, sex disaggregated and age specific data should be used and made available.

- For all indicators, please give a data source, the baseline value of the indicator and date, and a target level and date. Some indicators may have more than one data source (Table 6.1).

Note: The chosen indicators should be drawn from those used for monitoring the National Health Sector Plan (or equivalent) or cMYP and ideally be measured already (i.e. not a new indicator identified specifically for the GAVI HSS support). Examples of additional impact and outcome indicators are given in the tables below. It is recommended that when activities are implemented primarily at sub-national level that indicators are monitored, to the extent possible, at sub-nationally as well.

- All the presented data in this application form should be consistent with other GAVI proposals and reports and with other official health reports and documents. Any discrepancies between these data and those presented in this proposal or the GAVI Annual Progress Reports should be fully explained and justified. This is especially important for the birth cohort, target populations and coverage rates.

- All applications should identify a nominated focal point in Government service who oversees the monitoring and evaluation of the GAVI HSS proposal

- All applications must include the three main GAVI HSS impact / outcome indicators:

- National DTP3 coverage rate (%)

- Number / % of districts achieving ≥ 80% DTP3 coverage

- Under five mortality rate (per 1000)

- Please identify three additional impact / outcome indicators that can be used to assess the impact / outcome of the GAVI HSS support in improving immunisation and other child and maternal health services in Table 6.1 below.

- Please list up to 6 output and process indicators in Table 6.2 & 6.3 below.

- For all indicators, please give a data source, the baseline value of the indicator and date, a target level and date, as well as a numerator and denominator. Some indicators may have more than one data source.

- Baseline values should be noted for all indicators and there should be a process indicator for each objective

Note: Definitions of impact, outcome, and output can be found at the following website: www.unep.org/Terminology.pdf. A monitoring HSS toolkit is available on the WHO website http://www.who.int/healthinfo/statistics/toolkit_hss/EN_PDF_Toolkit_HSS_Introduction.pdf

Note: Examples of outcome, output and process indicators are shown below. Existing sources of information should be used to collect the information on the selected indicators wherever possible. In some countries there may be a need to carry out health facility surveys, household surveys, or establish demographic surveillance. If extra funds are required for these activities, they should be included in this application.

Examples of Outcome Indicators – related to GAVI HSS Objectives (note these are only examples)

| Objective | Possible indicators |
| --- | --- |
| Improve access to MCH services | % measles coverage (children less than 2 years); % births attended by a skilled birth attendants; % contraceptive use among women 15-44 years of age; % of children under 5 sleeping under ITNs |
| Improve the quality of health services | % of the population reporting they received health services of good quality; DTP3-DTP1 drop-out rate; |
| Improve equity of coverage of PHC services | DTP3 coverage rates in % by income quintile |

Examples of Output Indicators (note these are only examples)

| Strategy | Indicator | Numerator | Denominator | Data Source |
| --- | --- | --- | --- | --- |
| Advocacy for greater health expenditure for primary health care | General government health expenditure as a proportion of total government expenditure | The sum of all government health expenditures | Total government expenditure | Government budget |
| Strengthen the national HMIS | % of districts that submit timely, complete, accurate reports to national level | The number of districts that submit timely, complete, accurate reports to national level | The total number of districts | Health Information System |
| Strengthening supervision of community health nurses | Systematic Supervision | Number of health centres visited at least 6 times in the last year using a quantified checklist | Total number of health centres | Health facility survey |
| Strengthened human resource capacity | Knowledge of Health Workers | Mean score of health workers in public and NGO health centres on verbal knowledge test including case scenarios |  | Health facility survey |
| Strengthen stock management and logistics systems | % of facilities that have all tracer medicines and commodities in stock: on the day of visit, and in the last three months | The number of facilities with the selected tracer drugs in stock (present and non-expired) on the day of visit /during a specified reference period (last three months). | The total number of facilities | Health Information System & Health facility survey |

Examples of Process Indicators (note these are only examples)

| Activity | Possible indicators |
| --- | --- |
| Construct 280 health posts in rural areas | Number of health posts constructed |
| Procure 1000 motorcycles for community health nurses | Number of motorcycles procured |
| Train health workers on family planning methods | Number of health workers trained |
| Procure safe delivery kits | Number of safe delivery kits procured and delivered |

## 6.1: Impact and Outcome Indicators (data should be consistent with other GAVI applications and annual progress reports from the country)

| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. National pentavalent 3 coverage (%) | NDEPI/MoH | 51% | EPI review | 2008 | 80% | 2012 |  |
| 2. Mortality rate for children under five (per 1000) | INSAE | 125‰ | DHS III | 2006 | 115‰ | 2012 |  |
| 3. Health zones achieving penta3 coverage >= 80% | NDEPI/MoH | 0% | EPI review | 2008 | 50% | 2012 |  |
| 4. Rate of deliveries assisted by medical or paramedical personnel | SNIGS | 80% | Health Statistics Yearbook | 2007 | 90% | 2012 |  |
| 5. Caesarean rate | SNIGS | 4% | 2007 Statistics Yearbook | 2007 | 5% | 2012 |  |
| 6. Measles vaccine coverage | NDEPI/MoH | 49% | EPI review report | 2008 | 60% | 2012 |  |

## 6.2: Output Indicators (one per objective)

| Indicator | Numerator | Denominator | Data Source | Baseline ValueError: Reference source not found | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Proportion of supervisions conducted by the STZH | No. of public health facilities visited at least 4 times in the year by the STZH | Total no. of public health facilities | Health Zones supervision report | 10% | DDH/HZ | 2008 | 80% | 2012 |
| 2. Proportion of targeted health facilities offering CUONC | No. of health facilities offering CUONC | Total no. of health facilities | NHDP | 25% | DFH/ DH | 2008 | 80% | 2012 |
| 3. % of health training ensuring continuity of maternity and emergency services | No. of hospitals providing continuity of maternity service | All zone and DHC hospitals targeted | Hospitals activity report | 25% | DH | 2008 | 75% | 2012 |

## 6.3: Process Indicators (one per objective)

| Activities | Indicators | Observations |
| --- | --- | --- |
| - Train 42 STZH and DDH (DPMS) agents in the bottom-up planning process | No. of agents trained |  |
| 2. Acquire 32 motorcycles for advanced strategy immunization in the four (4) targeted health areas | No. of motorcycles procured and made available to targeted health centers |  |
| 3. Recruit 14 specialist physicians for 4 HZs and for 2 DHCs (surgery, gynecology-obstetrics, pediatrics, etc.) | No. of specialist physicians recruited for the 4 HZs and 2 DHCs targeted (surgery, gynecology-obstetrics, pediatrics, etc.) |  |

To the applicant: section 6.4

- Please describe how the data for the identified indicators will be collected, analyzed and used. Existing data collection and analysis methods should be used wherever possible. Please indicate how data will be used at local levels and ways of sharing with other stakeholders in the last column of Table 6.4 below.

- Data collection: the level data is collected at and whose responsibly it is to collect it

- Data Use: the level this data is analysed at in disaggregated form, and who is responsible at local and central levels for ensuring the data is assessed and analysed

- Use of data: how will this indicator’s data be used in assessing performance, and in revising or developing plans  and strategies

6.4: Data collection, analysis and use

| Indicator | Data collection | Data analysis | Use of data |
| --- | --- | --- | --- |
| Impact and outcome |  |  |  |
| 1. National DTP3 coverage rate (%) | Data are collected monthly in the health facilities from notebooks, registers and tally cards. This information is input at the Health Zones and is sent via computer means to department and national teams. | Data analysis starts at the commune level for all levels of the health pyramid (health zone, department, national). | The information thus obtained is used in the monitoring meetings by the zone supervisory teams (ZST), in the CDEEP by department health teams, and in the EXECOM and CNEEP by the national level. This enables decision-making, feedback, and planning. It immediately prepares corrective action in the field at the communal level. |
| 2. Under five mortality rate (per 1000) | - The data are collected from registers and hospitalisation forms in the health facilities. - Information also comes from censuses and specific household surveys (RGPH, DHSB) | - Analysis is performed at all levels of the health pyramid (commune, health zone, department, and national) - - Analysis of census/survey data and demographic projections is performed by INSAE | The information helps better monitor fatal diseases, improves management of these diseases and advocates for resources to be directed properly by Government and partners. It enables decision-making, feedback, and monitoring to achieve the MDG. |
| 3. Number / % of Zones/health districts achieving ≥80% DTP3 coverage | Data are collected monthly in the health facilities from notebooks, registers and tally cards. This information is input at the Health Zones and is sent via computer means to department and national teams. | Data analysis starts at the commune level for all levels of the health pyramid (health zone, department, national). | The information thus obtained is used in the monitoring meetings by the zone supervisory teams (ZST), in the CDEEP by department health teams, and in the EXECOM and CNEEP by the national level. This enables decision-making, feedback, and planning. It immediately prepares corrective action in the field at the communal level. |
| 4. Rate of deliveries assisted by medical or paramedical personnel | Data are collected monthly in the health facilities from notebooks, registers and cards. This information is input at the Health Zones and is sent via computer means to department and national teams. | Data analysis starts at the commune level and is performed all levels of the health pyramid: health zone, department, national (DFH, DPP). | The information thus obtained is used in the monitoring meetings by the zone supervisory teams (ZST), in the CDEEP by department health teams, and in the EXECOM and CNEEP by the national level. The information is used to raise awareness of personnel and women in outlying areas. This enables decision-making, feedback, and planning. |
| 5. Caesarean rate | The data are collected monthly in health zone hospitals and DHC from registers and hospitalisation forms. This information is input at the Health Zones and is sent via computer means to department and national teams. | Data analysis starts at the zone level and is performed all levels of the health pyramid: health zone, department, national (DFH, DPP). | The information thus obtained is used in the monitoring meetings by the zone supervisory teams (ZST) and the DHC Directions Committee in the CDEEP by department health teams. The information is used to raise awareness of personnel and women in outlying areas. This enables decision-making, feedback, and planning. |
| 6. Measles vaccine coverage | Data are collected monthly in the health facilities from notebooks, registers and tally cards. This information is input at the Health Zones and is sent via computer means to department and national teams. | Data analysis starts at the commune level for all levels of the health pyramid (health zone, department, national). | The information thus obtained is used in the monitoring meetings by the zone supervisory teams (ZST), in the CDEEP by department health teams, and in the EXECOM and CNEEP by the national level. This enables decision-making, feedback, and planning. It immediately prepares corrective action in the field at the communal level. |
| Output | Data collection | Data analysis | Use of data |
| 1. Proportion of supervisions conducted by the STZH | Data obtained by surveying health structures | Analysis will be performed at the department and national levels. | The information is used to assess the performance of the various health zones and departments, as well as the quality of work performed. Enables decision-making during CDEEP and CNEEP. |
| 2. Proportion of targeted health facilities offering CUONC | Data are collected annually via self-evaluation reports from hospitals These data are also available in the DDH reports. | Analysis is performed at the department and national levels. | The information is used to assess the performance of the various hospitals. Enables decision-making at the local level. |
| 3. % of health training ensuring continuity of maternity and emergency services | Data are collected every six months via self-evaluation reports from zone hospitals and DHC. | Analysis is performed at the health zone, DHC, DDH and national levels. | The information is used to assess the performance of the various health zones and departments, as well as the quality of work performed in the field. |
| Process |  |  |  |
| - Number of STZH and DPMS agents trained in the bottom-up planning process | Data obtained after training agents | Analysis will be performed at the department and national levels. | To justify conducting training |
| 2. Number of motorcycles acquired for advanced strategy immunization in the four (4) targeted health areas | Data obtained from delivery receipts | Analysis will be performed at the department and national levels. | To assess that the activity is occurring |
| 3. No. of specialist physicians recruited for the 4 HZ and 2 DHC targeted (surgery, gynecology-obstetrics, pediatrics, etc.) | Data obtained by surveying health structures | Analysis will be performed at the department and national levels. | To assess the level of technical support |

To the applicant: section 6.5

- Please indicate if the Monitoring & Evaluation (M&E) system needs to be strengthened to measure the listed indicators and if so describe which areas of the M&E system specifically needs strengthening. (Table 6.5).

Note: GAVI HSS resources may be used to strengthen the Health Information System itself. If the country chooses, the investment should be harmonised with the support from other donors (such as the Global Fund for AIDS, HIV and TB and others). Countries can seek GAVI HSS support for including relevant sex disaggregated data in their Health Information System.

## 6.5: Strengthening M&E system

The Monitoring & Evaluation system was put in place by Decree under the National Committee to monitor Execution and to Evaluate Health Sector Projects/Program (CNEEP) ; the Chairperson is the Minister of Health. Sub-committees at the central level and department committees serve as relays or antennae of the CNEEP. In operational and technical terms, the Monitoring & Evaluation system is provided by the Directorate of Programming and Planning, which coordinates all M&E activities through its technical departments, especially the Monitoring & Evaluation Cell, the Programming department, the Statistics and Documentation department, and the Planning Studies department; the 3 levels of the health pyramid via the department focal points and leaders of central level M&E programs, the head of Planning at Monitoring Studies at the intermediate level, and the Zone Supervisory Teams at the peripheral level.

The M&E system is based on the National Health Management Information System (SNIGS) and other studies and surveys.

Benin’s health information system has encountered several problems, summarized below:

- SNIGS health coverage is inadequate, especially for private health facilities, so the information provided by SNIGs is not exhaustive

- The completeness rate is generally low

- Lack of qualified human resources

- Some information needed to implement the application is not always available in a timely manner (current state of infrastructure and health facility equipment, etc.)

- Non-use of data by the health pyramid at the operational level

Thus the current SNIGS performance need to be strengthened in order to provide better monitoring and evaluation of the HSS/GAVI application. This would enable the M&E system to have the information needed to implement, monitor and evaluate the application at its disposal. Some of these actions will be undertaken, e.g.:

- Training on information management in the department of care providers is in progress. This same training will be integrated into the training curriculum for future promotions;

- Providing health structures (borough health centers, commune health centers, Zone Hospitals, national hospitals) with data collecting materials;

- Making the computer tools necessary to manage data available in the zones, department level and central level health directorates;

- Strengthening the capacities of those responsible for managing the data for the targeted Department Health Directorates and Health Zones (HZ) in using and mastering computer data management applications;

- Strengthening the technical and functional capacities of actors in the M&E chain (MEC/DPP, SSD/DPP, focal points/technical and central directorates, DPMS, DDH, DHC and ZH) in M&E and management focusing on the results and organizing techniques of specific surveys.

A survey will be conducted at the start of the HSS/GAVI application implementation and again at the end. At the start, this survey will help generate information not currently available (baseline data for certain indicators, information concerning infrastructure, equipment in the health infrastructures that will be targeted). Lessons will be drawn from the results to adapt the strategy for strengthening the health system, and the standards and directives to prepare future National Health Plans. Monitoring tools will be developed for this purpose. At the end of the implementation, the survey will enable the results and impact of the project on the health system and on health of communities to be assessed.

Publishing quarterly bulletins of health data from health districts, publishing bi-annual reviews of health statistics in health regions, and publishing the health statistics yearbook at the national level will provide indicators on: (i) health resources, (ii) service coverage, and (iii) the incidence and activities for monitoring and evaluating actions undertaken with funding from GAVI and other partners. These publications will promote feedback at all levels of the health system, to ensure more effective implementation of health interventions.

The progress made by implementing the GAVI support will be broadly spread across the country and across other health sector partners.

To the applicant: section 6.6

- Please indicate if the GAVI HSS application includes elements of operational research that address some of the health systems barriers to better inform the decision making processes. (Table 6.6).

Note: GAVI HSS Support can be used for operational research such as analysis of reasons why populations are not able to access immunisation services (whether this be due to social, economic, political or gender), with overall equity in access being the ultimate goal. This funding could also be used to test/examine of specific strategies to see which might work best.

## 6.6: Operational Research

To better make decisions and solve some of the health problems the country faces, it was agreed to develop operational research, especially the training of personnel in health research methodology in certain areas, including:

- The study of factors associated with demotivation of personnel in the target zones;

# Section 7: Implementation Arrangements

To the applicant: sections 7.1 and 7.2

- Please describe how the GAVI HSS support will be managed (Table 7.1).  Please also indicate the roles and responsibilities of all key partners in implementing the GAVI HSS support (Table 7.2).

Note: GAVI encourages countries to align the implementation arrangements for the GAVI HSS support with existing country mechanisms. Applicants are strongly discouraged from establishing a project management unit (PMU) for the GAVI HSS support. The establishment of PMUs will only be funded under exceptional circumstances, based on a strong rationale.

## 7.1: Management of GAVI HSS support

| Management mechanism | Description |
| --- | --- |
| Name of lead individual / unit responsible for managing GAVI HSS implementation / M&E etc. | The Directorate of Programming and Planning (Ministry of Health) will be responsible for managing GAVI HSS support and for the M&E of the application in Benin. |
| Steering committee role in GAVI support | The steering committee is charged with: - Developing proposals for strengthening the health system - Developing annual action plans for strengthening the health system - Accounting for the progress of action plan implementation to CNEEP; - Implementing the guidelines ordered by CNEEP; - Proposing disbursement plans for the application, monitoring execution of the budget, and proposing solutions as needed to any problems related to execution of the action plans; - Making activities reports to CNEEP. |
| The HSCC in Benin is the CNEEP. Role of HSCC (or equivalent) in implementation of GAVI HSS and M&E | Among other duties, CNEEP is charged with: - Validating the Ministry’s program budget including the three-year and yearly GAVI work plan; - Monitoring execution of funds allocated by GAVI; - Approving the disbursement plans for the application; - Supervising the effective implementation of health sector reforms as set forth in the development plans; - Studying and adopting the reports of GAVI-funded activities and the audit and evaluation reports; - Initiating audits on the management of HSS-GAVI financial resources; - Initiating annual, midterm and end-of-project evaluations of application implementation at times. |
| Mechanism for coordinating GAVI HSS support with other health system strengthening activities and programs | GAVI support will be integrated into the activities contained in the health sector’s Program Budget and Annual Work Plan. The mechanism for coordinating GAVI HSS support with other interventions consists of organizing: - Quarterly meetings with all actors, jointly presided over by the Leader of the partners and the Minister of Health, to discuss the consistency and pertinence of interventions in relation to sector strategy and to follow the work plan; - Bi-monthly meetings by the health technical group of health sector development partners; - Annual reviews of the sector to evaluate the implementation of all interventions and to decide the future guidelines needed to improve performances; Extraordinary meetings of the steering committee and CNEEP will be organized as needed. |

## 7.2: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organization | HSCC member yes/no | Please list the specific roles and responsibilities of this partner in the GAVI HSS implementation |
| --- | --- | --- | --- |
| Ministry of Health Cabinet Director | Ministry of Health | Yes | Chairperson of the Support Guidelines Committee (SGC) Orientation, monitoring, studying and adopting reports |
| Director of Programming and Planning | Ministry of Health | Yes | Coordinator of the SGC Technical Team for the HSS Orientation, monitoring, execution, coordination, development of reports |
| National Director of the Expanded Program on Immunization | Ministry of Health | Yes | Second Rapporteur of the SGC for the HSS Orientation, monitoring and development of reports on immunization and primary health care activities |
| Director of Family Health | Ministry of Health | Yes | Member of the SGC for the HSS Orientation, monitoring and development of reports, especially those for reproductive health |
| Budget Director | Ministry of Finance and the Economy | Yes | Member of the SGC for the HSS Resource mobilization, studying and adopting financial reports |
| Director of External Resource Mobilization | Ministry of Development, Planning and Assessment of Public Actions | Yes | Member of the SGC for the HSS Resource mobilization, studying and adopting reports |
| Representative of the Association of Private, Religious and Social Medical Works (AMCES) | Private sector | Yes | Member of CNEEP Participate in various validation and adoption sessions |
| Representative of the association of traditional practitioners | Civil society | Yes | Member of CNEEP Participation in various workshops |
| Union representative | Health section union | Yes | Member of CNEEP Participation in various workshops |
| Representative of the Network of Beninese NGOs for health | Civil society | Yes | Member of CNEEP Participation in various validation sessions |
| Resident WHO representative | WHO - Benin | No | Technical support and advice on mobilization, and making financial, human, material and logistics resources available. Participates in monitoring activities during statutory meetings |
| Resident UNICEF representative | UNICEF - Benin | No | Technical support and advice on mobilization, and making financial, human, material and logistics resources available Strategic support in maternal, newborn and child survival strategies Participates in monitoring activities during statutory meetings |
| Resident UNFPA representative | UNFPA | No | Technical support and advice on implementing the Reproductive Health Program Participates in monitoring activities during statutory meetings |
| UNAIDS | UNAIDS | No | Technical Financial support and advice on fighting AIDS (alignment and harmonization with implementation of the 2007-2011 national strategy to fight AIDS) |
| Belgian Technical Cooperation | Belgian embassy | No | Technical and Financial support in strengthening the health system Participates in monitoring activities during statutory meetings |
| Head of the Development, Environment and Regional Cooperation Division | European Commission delegation | No | Technical support and advice on implementing the national strategy Participates in monitoring activities during statutory meetings |
| USAID | US embassy | No | Technical and Financial support for the Integrated Program for Family Health to extend the use of family health services, products and preventive measures in a politically-favorable environment Leader of technical and financial partners |
| Coopération Suisse | Swiss embassy | No | Technical and Financial support in strengthening the health system Promoting and developing health mutuals |

To the applicant: section 7.3

Please provide information on the financial management of GAVI HSS support in table 7.3

Note: Applications will not be reviewed or approved by the Independent Review Committee (IRC) if the required documentation on the financial arrangements are not submitted together with the completed application form

Note: The GAVI Alliance adopted a Transparency and Accountability Policy (TAP) for cash-based support, including GAVI HSS support, which took effect as of 1 January 2009.

Note: The TAP policy outlines a set of minimum requirements for the financial management of GAVI HSS support:

- Funding should be used for objectives stated within a proposal.

- Funds must be managed in a transparent manner, and accurate and verifiable financial reports should be provided on a regular basis, as specified by individual funding arrangements.

- Funds must be managed within accounts that meet national legal requirements for auditing, accounting and procurement.

Note: Besides the above minimum financial management requirements:

- Funds should be reflected in the national budget (be on budget).

- Funds should be additional to the government allocation to the health sector, as well as to the contributions of other partners: i.e. no funding should be diverted away from the health sector if HSS funds are received.

Note: It is also a GAVI Alliance requirement that all countries receiving HSS support will need to go through a GAVI Financial Management Assessments (FMA) prior to the release of the first years support.

## 7.3: Funding arrangements

| Mechanism / procedure | Status / Description |
| --- | --- |
| Has a GAVI FMA been conducted: yes / no | No |
| When was the last FMA conducted: mm/yyyy | Not applicable |
| If yes: Has an Aide Memoire been signed: yes / no (Document Number.....) | Not applicable |
| If yes: Will the present Aide Memoire govern the financial management of the GAVI HSS funds: yes / no | Not applicable |
| If no: Reasons for not following all the agreements in the last Aide Memoire | Not applicable |
| Next FMA scheduled for: mm/yyyy | Not applicable |
| Has a joint financing mechanism been established for the health sector: yes / no | No |
| If yes: Will this joint financing mechanism be used for managing GAVI HSS funds: yes / no (Document Number.....) | Not applicable |
| If no: Reasons for not using the joint financing mechanism | Not applicable |
| Please provide a detailed description of the financing mechanism proposed for the management of GAVI HSS funds if all the agreements in the last Aide Memoire is not followed or a FMA has yet to be conducted. | GAVI HSS support funds will be transferred to the country by bank transfer to the Benin Ministry of Health. An independent account is opened by express exemption of the Ministry of the Economy and Finance to the General Directorate of the Public Treasury to house the GAVI funds for strengthening the health system. This account has two signatures: The Director of Financial Resources and Materials from the Ministry and the Director of Programming and Planning from the Ministry of Health. The funds will be managed according to the management procedures in effect in Benin. At the central (national) level: The Director of Programming and Planning from the Ministry of Health proposes expenditure initiations. The Director of Financial Resources and Materials from the Ministry of Health confirms the initiations and certifies payment of the expenditure with an authorizing signature of the payment order. The Government Contracts Cell of the Ministry of Health will be involved in the materials procurement process. An account has been opened at the Public Treasury to receive the GAVI funds. The Delegate for the Financial Comptroller to the Ministry of Health verifies that the service has been done and confirms it with an authorizing signature of the payment order. The Director of Financial Resources and Materials and the Director of Programming and Planning from the Ministry of Health are the two account signatories. At the intermediate (departmental) level: The Department Director of Health (DDH), as budget director, coordinates the activities financed by GAVI. The Division Head of Financial Resources and Materials of the DDH executes the budget allocated to the GAVI funds activities under the supervision of the DDH. He also oversees the management of GAVI funds at the level of the Health Districts (Zones). To that effect, an account will be opened at the Revenue Collections level in the departments involved (deconcentrated structure of the Public Treasury) to receive the GAVI funds. The account signatories are the DDH and the Revenue Officer. At the peripheral level (Health District or Zone): To that effect, the Health Zone Coordinating Physician has an Economic Chargé d’affaires for the Zone to manage the GAVI funds. An account will also be opened at the Revenue Collections level of the commune that hosts the Supervisory Team for the Health Zone. The two account signatories are the Zone Coordinating Physician and the Revenue Officer. |
| Title(s) of document(s) governing the annual budgeting process for the use GAVI HSS funds (Document Number.....) | The appropriations law of the Republic of Benin. |
| Title(s) of document(s) governing the audit of the GAVI HSS funds (Document Number.....) | Not applicable |
| Frequency of internal audits planned for GAVI HSS funds? | After the annual action plan has been executed, an internal financial audit will be order to certify the accounts. This audit will be conducted by the DFMR and the Inspection General of the Ministry, and the audit reports will be sent to the steering committee for adoption. |
| Frequency of external audit planned for GAVI HSS funds? | In addition to the internal audit, which is a self-regulation of the mechanism, it is absolutely necessary that there be two external audits, one at the midpoint and one at the end of the project, conducted by an independent audit firm designated for this purpose. |
| Title(s) of document(s) governing procurement procedures for GAVI HSS funds (Document Number.....) | Government contracts code |

To the applicant: section 7.4

- Please describe arrangements for reporting on the GAVI HSS funds, including the responsible Government Official who will be responsible for compiling the Annual Progress report (APR).

Note: Implementation of GAVI HSS supported activities will be reported to the GAVI Alliance through the Annual Progress Report (APR). The report will provide information on progress in reaching targets set in the GAVI HSS Application Form.  The APR will also provide financial management information on the use of GAVI HSS funds.

Note: The deadline for the submission of the Annual Progress Report for the previous calendar year is 15 May of each year. All countries should submit an APR, even if the GAVI HSS support was received towards the end of the previous year.

## 7.4: Reporting arrangements

To account for progress that has been made, records and reports of quarterly activities (three months) will be developed by the Directorate of Programming and Planning and sent on a regular basis to the steering committee. It will also summarize activities reports, which it will present to the CNEEP every six (6) months.

The Director of Programming and Planning issues the situation report every year. This report is validated by the Steering Committee and the CNEEP, then sent to GAVI by its technical secretariat before the deadline of 15 May in the year following the budget year in question.

The situation report incorporates planned activities, activities realized, the planned budget and the executed budget. This report is accompanied by the report of the financial audit, meeting minutes from the steering committee, and CNEEP meeting minutes.

To the applicant: section 7.5

- Please identify what technical assistance will be required during the life of GAVI HSS support, as well as the anticipated source of technical assistance if known (Table 7.5).

Note: The GAVI Alliance Secretariat can provide countries with one-time financial support to assist with the application process. The procedures for this support are described in the GAVI HSS Guidelines under Technical Support.

Note: Request for resources for technical support to implement and monitor the GAVI HSS support should be made using table 7.5 below.

## 7.5: Technical assistance requirements

| Activities requiring technical assistance | Anticipated duration | Anticipated timing (year, quarter) | Anticipated source (local, partner etc.) |
| --- | --- | --- | --- |
| 1. Conduct a study on the factors associated with demotivation of personnel in the target zones | 45 days | 1st quarter 2012 | local |
| 2. Mid-way evaluation | 20 days | 3rd quarter 2011 | local |
| 3. Final evaluation | 30 days | 4th quarter 2012 | Partner local |
| 4. Internal audit (annual and end-of-project) | 20 days | 1st quarter 2nd and 3rd year | Partner and Local |

# Section 8: Budgeting and Funding for GAVI HSS supported activities

To the applicant: section 8.1

- Please prepare a budget for all major activities for the duration of the GAVI HSS support. Please add or delete rows / columns to give the right number of objectives, activities and years. (Table 8.1)

Note: Please ensure that all costs for the implementation of GAVI HSS support, including technical assistance, are included in the budget. Please convert all budget figures to US$ (at the current exchange rate), and ensure that GAVI deflators are used for future costs (see guidelines on the GAVI website: www.gavialliance.org).

Note: The amount requested in table 8.1 should not exceed the amount specified in table 8.2.

Note: Management costs should be kept to a minimum. All management costs should be detailed in the budget and whether the management is through partners; including cost of having other partners responsible for managing part of the implementation of the GAVI supported activities.

Note: Unit costs and calculations should be attached in a spreadsheet.

For each subsequent year, provide the estimated expenditure (using unit costs) for each activity. Please carefully check that the totals of columns (expenditure by year) are consistent with the totals by Row (for activity and SMART Objective). Calculation errors are a frequent source of delays, as the IRC will ask for clarifications

Ensure the total budget for the entire HSS proposal does not exceed the country allocation calculated in Section 8.2 below

## 8.1: Budget for implementing GAVI HSS support

| Area for support |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Unit cost, if applicable (appended) | Year 1 of implementation | Year 2 of implementation |  | Year 3 of implementation |  |  |  |  | TOTAL COSTS |  |
|  |  | 2010 | 2011 |  | 2012 |  |  |  |  |  |  |
| Objective 1: Strengthen planning, coordination and monitoring/evaluation capacities of DPP agents, 2 DDH and 4 health zones from 2010 to 2012 |  | 153,017 | 72,572 |  | 120,524 |  |  |  |  | 346,113 |  |
| Activity 1.1 Train 42 STZH and DDH agents in the bottom-up planning process, budgeting and resource allocation over 3 days in two sessions (1 in the south and 1 in the north) |  | 29,398 | 0 |  | 0 |  |  |  |  | 29,398 |  |
| Activity 1.2 Develop, by pyramid level, annual three-year work plan through a bottom-up planning process with 24 participants over 3 days (3 STZH members per zone, 1 COGEC per zone, 1 per DHC, 1 per DDH targeted and 4 managers at the central level) |  | 8,385 | 0 |  | 0 |  |  |  |  | 8,385 |  |
| Activity 1.3: Train the STZH of 4 target health zones in the techniques of training supervision for 40 members of the STZH and 4 trainers (one session in the north and one session in the south) |  | 24,471 | 0 |  | 0 |  |  |  |  | 24,471 |  |
| Activity 1.4: Organize the annual workshop on validating SNIGS data at the level of the 2 departments (1 in the so |  | 27,679 | 27,679 |  | 28,507 |  |  |  |  | 83,865 |  |
| Activity 1.5: Create and make operational a joint action group (health agents, health committees, local elected officials, traditional practitioners and civil society) to involve them in the preparation, implementation and monitoring of activities. |  | 13,222 |  | 13,222 |  |  | 13,244 |  | 39,688 |  |  |
| Activity 1.6: Train DPP agents in results-focused management tools |  | 13,293 |  | 0 |  |  | 0 |  | 13,293 |  |  |
| Activity 1.7: Acquire 8 computers and accessories (2 at the SNIGS in the DDH; 2 for the 2 DHC and 4 for the four (4) target Health Centers for improved management of EPI data) |  | 26,667 |  | 0 |  |  | 0 |  | 26,667 |  |  |
| Activity 1.8: Set up a mechanism for controlling SNIGS data quality |  | 887 |  | 887 |  |  | 887 |  | 2,661 |  |  |
| Activity 1.9: Perform bi-annual monitoring of GAVI funds activities by the Guidelines Committee acting through the DPP and the DFMR |  | 4,664 |  | 4,664 |  |  | 4,664 |  | 13,992 |  |  |
| Activity 1.10: Have health zones supervised by the intermediate level (DDH) |  | 2,176 |  | 2,176 |  |  | 2,176 |  | 6,528 |  |  |
| Activity 1.11: Have the STZH supervise activities in the 4 health zones (HZ) |  | 2,176 |  | 2,176 |  |  | 2,176 |  | 6,528 |  |  |
| Activity 1.12: Produce annual bulletins of SNIGS feedback at the targeted and national zones levels |  | 0 |  | 6,000 |  |  | 6,000 |  | 12,000 |  |  |
| Activity 1.13: Have a consultant conduct a limited midterm evaluation |  | 0 |  | 9,769 |  |  | 0 |  | 9,769 |  |  |
| Activity 1.14: Conduct an internal financial audit every year |  | 0 |  | 6,000 |  |  | 6,000 |  | 12,000 |  |  |
| Activity 1.15: Train 40 STZH members for the 4 targeted health zones in operational research in two sessions (1 in the south and 1 in the north) with 4 trainers at the central level |  | 0 |  | 0 |  |  | 24,693 |  | 24,693 |  |  |
| Activity 1.16: Conduct a study on the factors associated with demotivation of personnel in the target zones |  | 0 |  | 0 |  |  | 16,089 |  | 16,089 |  |  |
| Activity 1.17: Have 2 consultants (1 national and 1 international) conduct the final evaluation |  | 0 |  | 0 |  |  | 16,089 |  | 16,089 |  |  |
| Objective 2: Provide the integrated package of essential quality services accounting for immunization and Complete Urgent Obstetrical and Neo-natal Care (CUONC) in the 2 departmental hospitals and the 4 health zones targeted from 2010 to 2012; |  | 391,632 |  | 465,262 |  | 390,544 |  | 1,247,438 |  |  |  |
| Activity 2.1: Acquire medical consumables and reagents for laboratories involved in the epidemiological surveillance of diseases targeted by EPI |  | 41,572 |  | 15,751 |  | 164,544 |  | 221,867 |  |  |  |
| Activity 2.2: Acquire 2 supervision vehicles (for the two family health services of the two DDHs |  | 66,667 |  | 0 |  | 0 |  | 66,667 |  |  |  |
| Activity 2.3: Acquire 32 motorcycles for advanced strategy immunization in the four (4) targeted health areas |  | 64,000 |  | 0 |  | 0 |  | 64,000 |  |  |  |
| Activity 2.4: Acquire medical-technical materials for the 2 DHC and 4 health zone hospitals targeted (manual vacuum aspiration, suction cups, caesarean boxes, newborn resuscitation materials) for the CUONC; automatic serology devices, microbiology hoods for the 2 hospitals |  | 181,333 |  | 94,444 |  | 174,444 |  | 450,221 |  |  |  |
| Activity 2.5: Acquire 10 refrigerators to store vaccines in health centers |  | 26,660 |  | 0 |  | 0 |  | 26,660 |  |  |  |
| Activity 2.6: Acquire 3 supervision vehicles (the DZHD, the DPP and the NDEPI) |  | 0 |  | 100,000 |  | 0 |  | 100,000 |  |  |  |
| Activity 2.7: Acquire 2 ambulances for the Adjohoun-Bonou-Dangbo and Sakété-Ifangni Health Zones |  | 0 |  | 200,000 |  | 0 |  | 200,000 |  |  |  |
| Activity 2.8: Construct 3 incinerators in the health centers and hospitals that don’t have one |  | 0 |  | 33,333 |  | 0 |  | 33,333 |  |  |  |
| Activity 2.9: Provide upkeep and maintenance for all medical-technical equipment and materials in the 4 HZs and 2 DHCs targeted |  | 11,400 |  | 21,733 |  | 51,556 |  | 84,689 |  |  |  |
| Objective 3: Make health personnel available in accordance with national standards for continuity of services in the 2 departmental hospitals and 4 health zones targeted from 2010 to 2012 |  | 341,844 |  | 374,599 |  | 428,078 |  | 1,144,521 |  |  |  |
| Activity 3.1: Strengthen the capacities of 50 midwives and maternity nurses in the following areas: Obstetric nursing care: PCIME, SOU, UNC |  | 29,693 |  | 0 |  | 0 |  | 29,693 |  |  |  |
| Activity 3.2: Train/recycle 100 midwives and maternity nurses in the following areas: Obstetric nursing care; PCIME, SOU, UNC |  | 0 |  | 0 |  | 55,927 |  | 55,927 |  |  |  |
| Activity 3.3: Recruit 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology, obstetrics, pediatrics, etc.) |  | 305,329 |  | 0 |  | 0 |  | 305,329 |  |  |  |
| Activity 3.4: Monitor activities in the 4 health zones (HZs) |  | 6,822 |  | 6,822 |  | 6,822 |  | 20,466 |  |  |  |
| Activity 3.5: Grant motivational incentives to teams (physicians, midwives, nurses, lab technicians and administrators) in the 4 and 2 targeted DHC zones based on results. |  | 0 |  | 66,667 |  | 66,667 |  | 133,334 |  |  |  |
| Activity 3.6: Pay salaries of the 14 physician specialists for 4 HZs and 2 DHCs (surgery, gynecology-obstetrics, pediatrics, etc.) |  | 0 |  | 298,662 |  | 298,662 |  | 597,324 |  |  |  |
| Activity 3.7: Monitor activities in the 4 health zones (HZs) |  | 0 |  | 2,448 |  | 0 |  | 2,448 |  |  |  |
| TOTAL |  | 886,493 |  | 912,433 |  | 939,146 |  | 2,738,072 |  |  |  |

To the applicant: section 8.2

- Please calculate the amount of funds available per year from GAVI for the proposed GAVI HSS activities, based on the annual number of births and GNI per capita as follows (Table 8.2):

- If GNI < $365 per capita, country is eligible to receive up to $5 per new born

- If GNI > $365 per capita, country is eligible to receive up to $2.5 per new born

Note: The following example assumes the birth cohort in the year of GAVI application is 100,000, and gives the total fund allocations if the GNI < $365 per capita and if the GNI > $365 per capita.

Examples: GAVI HSS country allocation calculation (note these are examples only)

## 8.2: Calculation of GAVI HSS country allocation (this number should be consistent with data used in other GAVI applications and annual progress reports)

| GAVI HSS Allocation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Year of GAVI application |  | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | TOTAL FUNDS |
|  | 2009 |  | 2010 | 2011 | 2012 |  |
| Birth cohort (number) |  |  | 354,599 | 364,973 | 375,659 |  |
| Allocation per newborn ($) |  |  | 2.5 USD | 2.5 USD | 2.5 USD |  |
| Annual allocation ($) |  |  | $886,497.5 | $912,432.5 | $939,447.5 | 2,738,077.5 |

Birth cohort:	354,599

Source:	Annual Situation Report for the year 2008

To the applicant: section 8.3

- Please summarize the overall available funding for the Heath System Strengthening efforts related to improving the immunization coverage and the coverage of other child health services.

- Immediately following the table, please provide a concise explanation to demonstrate how the proposed GAVI HSS funding will be used to complement these existing and/or planned efforts to strengthen health systems capacity.

Note: GAVI HSS funds must be additional to the government’s health budget – and the funds should not displace resources allocated to the health sector.

Note: Please specify the contributions from the Government, GAVI and the main funding partners or agencies. If there are more than four main contributors, please insert more rows. Please indicate the names of the partners in the table, and group together all remaining expected contributions.  Please indicate the source of the data (Public Expenditure Review, MTEF, donor reports etc).

## 8.3: Sources of all expected funding for health systems strengthening activities

| Funding Sources |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | TOTAL FUNDS | Observations |
|  | 2009 | 2010 | 2011 | 2012 | (in 000 of $) |  |
| GAVI (HSS application) |  | 886,493 | 912,433 | 939,146 | 2,738,072 |  |
| GOVERNMENT | 17 382 | 19 194 | 21 881 |  | 36 576 |  |
| EDF | 0 | 1 800 | 2 000 |  | 38 00 | Increase |
| SWITZERLAND | 960 | 298 | 1 000 |  | 2258 | Renewal |
| BELGIUM | 800 | 800 | - |  | 1600 |  |
| BADEA | 1 400 | - | - |  | 1400 | End in 2009 |
| BAD | 8 074 | 10 974 | - |  | 19 048 |  |
| WHO | 1 402 | 1 816 | 2 070 |  | 5288 |  |
| UNICEF | 662 | 507 | 578 |  | 1747 |  |
| UNFPA | 1 600 | 1 600 | 1 824 |  | 5024 |  |
| TOTAL | 32 280 | 40 245 | 8 721 |  | 81246 |  |
| Total needs for health systems strengthening | 42 132 | 42 132 | 42 132 |  | 126 396 |  |

Source of information on funding sources:

GAVI:	(Benin’s application to GAVI)

Government: (program budget)

Donor 1: EDF

Donor 2. SWITZERLAND:

Donor 3. BELGIUM:

Donor 4. BADEA:

Donor 5. BAD

Donor 6. WHO:

Donor 7. UNICEF

Donor 8. UNFPA:

Total others:

To the applicant: section 8.4

- Please provide a concise explanation to demonstrate how the proposed GAVI HSS funding will be used to complement these existing and/or planned efforts to strengthen health systems capacity.

## 8.4: Describe how GAVI HSS funding will complement other sources of HSS funding

Three main sources currently contribute to funding coverage for health expenses in Benin, including the area of health system strengthening funding. These are the national budget, community funding, and contributions from development and other partners (Telethon, local collective, others).

Note that health system strengthening is suffering from under-funding despite the multiple funding from existing partners. This is why, as part of achieving the Millennium Development Goals and the goals in the NHDP, we would like to experiment with setting up a high-performing zone in four (4) zones and two DDHs with GAVI funding.

Benin has also committed with the Technical and Financial Partners to have a single and shared Three-Year Development Plan and a single and shared Monitoring & Evaluation mechanism, and discussions are ongoing to harmonize the funding mechanisms so that Benin can move towards a SWAp (Benin, Belgium, World Bank, European Union, UNICEF) between now and the end of 2009.

There are oversight and exchange devices within Benin’s health sector, including:

- Coordination of bilateral and multilateral lenders with a harmonization and alignment agenda lead by USAID;

- Quarterly joint meeting of Partners presided over by the Ministry of Health;

- Joint annual performance review of the sector.

The zones and DHC selected as part of this request complement the structures already being supported by other partners, including:

- Belgian Coopération

Health zone support project in the departments of Atacora/Donga and Mono/Couffo.

- USAID

Integrated Family Health Project in the departments of Zou/Collines

- European Union (9th EDF)

Support for research action in four (4) health zones, one per department

- PADS

Health Sector Development Support Project (PADS) in the departments of Borgou and Collines

All of these projects are monitored and evaluated by the CNEEP, which will also be in charge of monitoring the HSS/GAVI project.

# Section 9:  Terms and Conditions of GAVI Support

To the applicant:

- This Section sets out the terms and conditions for GAVI HSS support. By signing and endorsing this application form, you confirm you have read and agree to GAVI’s terms and conditions for HSS support.

GAVI ALLIANCE

TERMS AND CONDITIONS

FUNDING USED SOLELY FOR APPROVED PROGRAMMES

The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance for this application will be used and applied for the sole purpose of fulfilling the programme(s) described in this application.  Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance.  All funding decisions for this application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.

AMENDMENT TO THIS PROPOSAL

The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in this application.  The GAVI Alliance will document any change approved by the GAVI Alliance, and this application will be amended.

RETURN OF FUNDS

The Country agrees to reimburse to the GAVI Alliance, all funding amounts that are not used for the programme(s) described in this application.   The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.

SUSPENSION TERMINATION

The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in this application , or any GAVI Alliance-approved amendment to this application.  The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in this application if a misuse of GAVI Alliance funds is confirmed.

ANTICORRUPTION

The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with this application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.

AUDITS AND RECORDS

The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.

The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds.  If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final.   The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this proposal is accurate and correct and forms a legally binding obligation on the Country, under the Country’s law, to perform the programmes described in this application.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY

The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and will comply with its requirements.

ARBITRATION

Any dispute between the Country and the GAVI Alliance arising out of or relating to this application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English.

For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance.  For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.

The GAVI Alliance will not be liable to the Country for any claim or loss relating to the programmes described in this application , including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death.  Country is solely responsible for all aspects of managing and implementing the programmes described in this application.

# Section 10: Endorsement of the Application

To the applicant: sections 4.1, 4.2, 4.3 and 4.4

- The GAVI HSS proposal cannot be reviewed without the necessary signatures and endorsement from the Minister of Health and Minister of Finance, the Chair and members of the Health Sector Coordinating Committee (HSCC)

- All HSCC members should sign the minutes of the meeting where the GAVI HSS application was endorsed. This should be submitted with the application and any issues identified during the meeting that may affect the proposal’s implementation or monitoring should be highlighted by HSCC members (numbered and listed in Annex 1).

- Please give the name and contact details of the person for GAVI to contact if there are queries.

Note: The signature of HSCC members represents their agreement with the information and plans provided in this application, as well as their support for the implementation of the plans. It does not imply any financial or legal commitment on the part of the partner agency or individual.

## 10.1: Government endorsement

The Government of Benin commits itself to providing immunisation and other child and maternal health services on a sustainable basis. Performance on strengthening health systems will be reviewed annually through a transparent monitoring system. The Government requests that the GAVI Alliance funding partners contribute financial assistance to support the strengthening of health systems as outlined in this application.

| Minister of Health: | Minister of Finance: |
| --- | --- |
| Name: Doctor Dorothée YEVIDE | Name: Mathias N. HOUNDONOUGBO |
| Titre/ Position: Cabinet Director of the Minister of Health | Title / Position: Deputy Cabinet Director of the Minister of the Economy and Finance |
| Signature: | Signature: |
| Date: | Date: |

## 10.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent

Members of the Health Sector Coordination Committee or equivalent endorsed this application at a meeting on September 2, 2009.…………………………………... ………...

The signed minutes are attached as Annex 1.

| Chair of HSCC (or equivalent): |  |
| --- | --- |
| Name: Doctor Dorothée YEVIDE | Post / Organisation: Cabinet Director of the Minister of Health |
| Signature: | Date: |

10.3: Government official to contact in case of programmatic enquiries:

Name: Pascal KORA BATA                Title: Director of Programming and Planning

Tel. Nº:     21 33 49 06                        Address: 01 BP 882 RB

Fax Nº:     21 33 04 64

e-mail: serokbp@yahoo.fr

10.4: Government official who is the focal point for overseeing the financial management of GAVI HSS funds:

Name: Béatrice RADJI                                  Title: Director of Financial Resources and Materials

Tel. Nº:   21 33 52 58                                   Address : 01 BP 882 RB

Fax Nº: 21 33 04 64

e-mail: rabededo@yahoo.fr

# ANNEX 1 Documents Submitted in Support of the GAVI HSS Application and final checklist

To the applicant:

- Please number and list in the table below all the documents submitted with this application. Please be consistent with the title and number of the background / supporting document when referring to it in the proposal.

Note: The Proposal and attachments must be submitted in English or French, and be accompanied with soft copies of the submitted documents.

| Document (with equivalent name used in-country) | Available (Yes/No) | Duration | Attachment Number |
| --- | --- | --- | --- |
| National Health Sector Strategic Plan (or equivalent) |  |  |  |
| National Health Sector Development Plan (NHDP) 2009-2018 | Yes | 2008 | 01 |
| CDMT 2009-2011 | Yes | October 2008 | 02 |
| DSCRP | Yes | March 2007 | 03 |
| Rapid assessment of the health system in Benin | Yes | June 2006 | 04 |
| Complete Multiyear Plan for EPI 2007-2011 | Yes | January 2007 | 05 |
| General Report of the Health General Assembly | Yes | November 2007 | 06 |
| Benin’s health care system: Main system characteristics and proposals for strengthening | Yes | September 2007 | 07 |
| National strategies to reduce maternal and neo-natal mortality | Yes | March 2006 | 08 |
| Minutes of the CNEEP adoption meeting, signed by the Chair of CNEEP | Yes | April 2009 | 09 |
| Minutes of the Guidelines Committee adoption meeting | Yes | April 2009 | 10 |
| Decree regarding the appointment, composition and operations of the CNEEP | Yes | April 2007 | 11 |
| Order regarding the creation, appointment and composition of the Application Guidelines Committee | Yes | Sent at the 1st and 2nd submission | 12 |
| Order regarding the creation, appointment and composition of the Application Drafting Committee | Yes | Sent at the 1st and 2nd submission | 13 |
| Reports from peer workshops in Ouagadougou | Yes | December 2008 | 14 |
| SNIGS 2007 | Yes | October 2008 | 15 |
| Report of the organizational audit of the Ministry of Health | Yes | June 2008 | 16 |
| Report of the EPI review | Yes | March 2009 | 17 |
| Human Resources Strategic Plan | Yes | December 2008 | 18 |

ANNEX 2 Banking Form

Note: It cannot be stressed enough that without a banking form that contains complete, accurate banking details (IBAN, SWIFT code, corresponding US bank and account details) it is impossible to transfer funds. Lack of full and correct information in this section WILL cause many unnecessary delays. This needs to be endorsed by UNICEF country representative on letter headed paper.

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNISATION |  |  |  |  |  | Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunisation dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| Address: |  |  |  |  |  |  |  |  |  |  |
| City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| Is the bank account exclusively to be used by this program? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  | Seal: |  |
| Title: |  |  |  |  |  |  |  |  |  |  |
| Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . Is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

TO:

GAVI Alliance Secretariat,

Att. Dr Julian Lob-Levyt

Executive Secretary

Chemin de Mines 2.

CH 1202 Geneva,

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

EPI review report: pages 49- 50-74; March 2009.

NHDP 2009-2018: pages 31 and 32

A (to be reviewed)

2009-2018 Health Sector Human Resources Development Strategic Plan, pages 21-22

Minutes from HSCC meetings related to the HSS proposal preparation should be attached as supporting documentation, together with the minutes of the meeting where the application was endorsed by the HSCC. The minutes should be signed by the HSCC Chair. The minutes of the meeting endorsing this GAVI HSS application should be signed by all members of the HSCC.

Made available by the Belgian Technical Cooperation

Recruited with support funds upon drafting the GAVI

If the application identifies activities that are to be undertaken at a sub-national level, sub-national data will need to be provided where it is available. This will be in addition to the national data requested.

Rapport revue EPI : pages 49- 50-74 ; mars 2009

Within the last 3 years.

2009-2018 Health Sector Human Resources Development Strategic Plan, pages 21-22

Source : EPI review 2008

Source : DHS III, 2006

Source : DHS III, 2006

If number of districts is provided than the total number of districts in the country must also be provided.

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

Please submit a copy of the Aide Memoire

Please submit a copy of the agreement/memorandum of understanding, which governs the joint financing mechanism and a copy of the document which describes how the joint financing mechanism is currently functioning.

Please note that the mechanism selected must comply with the minimum requirements of GAVI’s Transparency & Accountability Policy

Please submit a copy of the procedures and legislation, which applies to the annual budgeting process for the use of GAVI HSS funds and documentation, which describes how the budgeting process for GAVI HSS funds would be conducted

Please submit a copy of the procedures, which apply to the external audit of GAVI HSS funds and documentation, which describes how the external audit of GAVI HSS funds would be conducted

“External audit” defined as the audit conducted by the Government’s Supreme Auditing Agency.

Please submit a copy of the procurement  procedures for GAVI HSS funds and documentation, which describes how the procurement would be processed

See GAVI HSS Guidelines for countries respective funding levels under Allocation