Central African Republic

Support Project for the Health System Strengthening Strategy of the Central African Republic

October   2007

An electronic version of this document is available at the GAVI Alliance web site (www.gavialliance.org) and in CD form. It is highly recommended that applications be submitted via e-mail, including the scanned documents with the required signatures. Please send the application to :

Mr Craig Burgess

Senior Program Officer, HSS

GAVI Alliance Secretariat

c/o l’UNICEF, Palais des Nations

1211 Geneva 10, Switzerland

e-mail : cburgess@gavialliance.org

Thank you for making sure that the application was properly received by the GAVI Secretariat by the indicated date. Applications that are received after this date shall not be taken into consideration for this review calendar period. GAVI shall not be responsible for lateness in delivery or problems with the delivery of the applications by courier services.

All documents and annexes must be submitten in English or French. All the required information must be included in the application forms. The GAVI Secretariat shall not accept any separate document as part of the application. The GAVI Secretariat is not prepared to return the documents or annexes thus submitted to the country they were sent from. Unless otherwise specified, the documents may be brought to the attention of GAVI Alliance partners, their staff and to public attention.

All questions must be addressed to:

Mr Craig Burgess  (cburgess@gavialliance.org) or to the representatives of a GAVI partner institution.

Contents

Page

Abbreviations and acronyms	4

Overview of the Proposal	6

Section 1: Process for Preparing the Application	10

Section 2: Country Background Information	15

Section 3: Situation Analysis / Needs Assessment	19

Section 4: Goals and Objectives of GAVI HSS Support	36

Section 5: GAVI HSS Activities and Implementation Schedule	36

Brief summary of the activities that led to this proposal.	41

Section 6: Monitoring , Evaluation et Operational Research	45

Section 7: Implementation Arrangements	58

Section 8: Cost and financing for GAVI HSS Support	64

Section 9: Endorsement of the application	70

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application	73

ANNEX 2 Bank Form	75

# Abbreviations and acronyms

AFD                            : French Development Agency

ARV			: Anti-Retro Viral Drugs

CHW			: Community Health Worker

ASSOMESCA	: Association des Oeuvres Médicales pour la Santé en Centrafrique

ABEDA                       :Arab Bank for Economic Development in Africa

BCG			: Bacillus Calmette-Guérin

KB			: Koch’s Bacillus

CAB			: Ministerial Cabinet

CEMAC		: Economic and Monetary Community of Central Africa

ICRC			: International Committee of the Red Cross

CNTS			: National Blood Transfusion Center

COGES	 	: Management Council and Committee

COOPI		            : Italian Development and Aid (NGO)

CPN		            : Prenatal Consultation

CS                               : Health Center

CSLP 		            : Poverty Reduction Strategy Program

DGSPP		: Department of Public Health and Population

DRP		            : Department of Research and Planning

DOTS			: Directly Observed Treatment (english acronym)

DPM			: Pharmacy and Medicine Office

DR			: Resources Office

DTP			: Diphteria – Tetanus – Pertussis

DS                               : Health District

DSRP                          : Poverty Reduction Strategy Paper

ED 		            : Demographic Survey

EDS 		            : Demographic and Health Survey

DMT			: District Management Team

RMT                            : Regional Program Team

EIBC 		            : General Household Spending Survey

EDF                             : European Development Funds

FAO			: United Nations Food and Agriculture Organization

IMF			: International Monetary Fund

FOSA		            : Health Clinics

GAVI			: Global Alliance for Vaccines and Immunization

HDH                            : Health District Hospital

HCR			: High Commissioner for Refugees

IADE 		            : State Certified Obstretrics-Nurse

IB 		        	: Bamako Initiative

IDA			: International Development Agency

IDE 		            : State Certified Nurse

HDI			: Human Development Index

IEC 		            : Information, Education et Communication

HPI			: Human Poverty Index

HIPCI                          : Heavily Indebted Poor Countries Initiative

ARI		            : Accute Respiratory Infection

TFR			: Total Fertility Rate

STI 		            : Sexually Transmitted Infections

JNSE                           : National Child Survival Day

LMD 		            : Diarrheal Disease Control Program

LNBCSP		: National Clinical Biology and Public Health Laboratory

MEG 	                        : Essential Generic Drugs

MEPCI  		: Ministry of Economy, Planning and International Development

MICS 		            : Multiple Indicator Cluster Survey

ITN			: Insecticide-Treated Mosquito Nets

MNT			: Non-Communicable Diseases

MSF			: Doctors Without Borders

MPHP 			: Ministry of Public Health and Population

MSR	 		: Risk-Free Pregnancy

MST			: Sexually Transmitted Illnesses

NEPAD		: New Partnership for Africa’s Development

OAC			: Community-Based Organiations

OAPI			: African Intellectual Property Organization

OEV			: Orphans and Other Vulnerable Children

OMD			: Millenium Development Goals

WHO 			: World Health Organization

ONG 			: Non Governmental Organization

UNAIDS		: United National Joint Programme on HIV/AIDS

OPEC			: Organization of Petroleum Exporting Countries

WFP			: World Food Program

LDC			: Least Developed Countries

SAP			: Structural Adjustment Policies/Programs

UNDP			: United Nations Development Program

PS                                : Health Post

PVHIV		: Persons Living with HIV

CAP                            : Complimentary Activities Package

IMCI 			: Integrated Management of Childhood Illnesses

EPI 			: Expanded Program on Immunization

FP 		 	: Family Planning

GDP			: Gross Domestic Product

IHP 			: Interim Health Plan

MAP 			: Minimum Activities Package

NDPH			: National Development Plan for Health

NPRH			: National Plan for Reproductive Health

cMYP                          : comprehensive Multi-Year Plans for Immunization

HIPC			: Heavily Indebted Poor Countries

PCTP			: Parent-Child HIV Transmission Prevention

CAR			: Central African Republic

GHPC			: General Housing and Population Census

HRHC			: Human Resources in Health Care

GDI                             : Gross Domestic Income

HSS                             : Health System Strengthening

HR (1,2,…7)		: Health Region N° (1,2,…,7)

SFDE 			: Certified Midwife

SG			: Secretariat General of the Ministry

AIDS 			: Auto-Immune Deficiency Syndrome

CMH 			: Child/Mother Health

NSHI	 		: National System for Health Care Information

OCNE			: Obstetric Care and Neonate Emergencies

SR			: Reproductive Health

SSP 			: Primary Care Services

AHT			: African Human Trypanosomias

ALT 			: Advanced Laboratory Technician

AHT 			: Advanced Health Technician

MPU 			: State Medical Procurement Unit

EU 			: European Union

UNFPA            	: United National Population Fund

UNICEF		: United Nations Children’s Fund

YFV			: Yellow Fever Vaccine

MV			: Measles Vaccine

TV			: Tetanus Vaccine

VPO			: Polio Vaccine

HIV 			: Human Immunodeficiency Vaccine

To the applicant

- Please ensure that all abbreviations and acronyms presented in the application and supporting documents are included here..

# Executive Summary of the Proposal

To the applicant

- Please provide a summary of the proposal which comprises the goal and objectives for the proposal for winning the support of the HSS by GAVI, with the strategies and main activities to be undertaken, the expected results, the duration of the support and the total amount of funds requested, as well as the baseline figures and targets for the priority indicators that have been included.

- Please identify the person(s) responsible for the preparation of the GAVI HSS application, indicating the role and nature of the HSCC (or equivalent) as well as the stakeholder participating in the preparation of the application.

The evaluation of the first National Development Plan for Health (NDPH I) of the Central African Republic has demonstrated the importance of reforming the national health system in order to improve performance. This reform is included in the priority areas established in the second National Development Plan for Health (NDPH II) covering the years 2006-2015. In order to enact this plan, the Ministry of Public Health and Population (MPHP), in conjunction with its partners, has drafted the National Strengthening Plan for its Health System. In the process of documenting this plan, in view of preparing an HSS proposal for the CAR, several bottlenecks have been detected in the provision of basic health services among which vaccination. It concerns (i) the poor operational capacity of the Health Districts (HD), (ii) the general problems affecting the management of health services and vaccination in particular, (iii) problems related to financing Health Care and, (iv), the motivational strain apparent among human resouces active in healthcare. The poor operational capacity of the HDs is essentially due to the poor health coverage available therein, the lack of sufficient numbers of, and sufficiently qualified human resources active in Health Care at the district level, and the complexity of the task of organizing health services in peripheral areas, especially among the many categories of Health Centers (five categories, not including the Health Posts) which not only brings little value to the system but also make the quality provision of health care services more difficult (effectiveness, follow-up, efficiency, etc.). The problems that are faced at the District level are to a certain extent a reflection of the poor leadership that is apparent in the CAR health system in general. This is what comes to attention for example in the absence of organizational norms for functioning, noted at different levels of the health system. As an example, it is apparent that there is a lack of clarity in the sharing of jurisdictions and the tasks among the different participants in the health care system. Among the other barriers faced by the Comprehensive Multi-Year Immunization Plan that were noted, one was the fact that staff supervision is erratic and sometimes nonexistant at all levels. The management of resources, especially of financial resources, is very centralized in CAR. Unfortunately, this state of affairs makes for very long disbursement delays. This has reached a stage where the benefiting facilities receive their equipment, supplies and materials with a signficant delay, sometimes in the course of the budget year following the budget year in question. These disbursement delays have unavoidable consequences on the implementation of Health Care projects, including vaccination. Indeed, among the budget for the Health Sector Coordination Committees (HSCC) for the health clinics (FOSA) there is the planned purchase of fuel and various items needed for the proper functioning of the cold chain as well as the layouts for operational costs for frontline strategies. If certain HSCC have acted responsibly regarding their duties, others, due to delays and insufficiency of the credits granted by the Government, have opted for renewing materials and consumables for medical care rather than the purchase of fuel for the cold chain, thus exposing the Health Centers to depleted stocks of products necessary for vaccination. The salaries of civil servants (which include Health Care human resources) are several months in arrears. This situation contributes to a drop in motivation among medical personnel and makes quality Health Care service provision rather random. The proposal for Health System Strengthening (HSS) in CAR, which is the topic of this document, is part of the goal to bring about reform in order to increase service provision and the use of quality health care services including vaccination. It thereby proposes to contribute to the achievement of the target set out by the Ministry for Public Health and Population in NDPH II. This target consists in the improvement of the health of CAR’s people, in particular those who are the most vulnerable and the poorest. A single specific target is pursued, which is to contribute to the reduction of infant- juvenile and maternal mortality rates in CAR by increasing the availability of health care services and the use of quality services in the Health Regions 2 & 4 from now through 2011. In order to reach this goal, three areas of operation have been identified : Making the Health Districts (HD) operational ; Assistance to the normalization and support process for development of the HDs in the Target Regions (Steering of the Health System), Rationalization of Health Care financing Making the Health Districts Operational The results that are expected from this program area are the following : The 5 HDs shall be rendered operational, each one counting several functional HCs and HPs. The distances that the population must cover in order to have access to care are to be reduced because of increased Health Care coverage. The HCs and HPs shall have qualified and motivated personnel, with sufficient stock products and who can therefore offer consistent and sustained vaccination services (Strengthening of routine EPI) and other quality health care services to populations that they cover. The Health District Hospitals (HDH) assist the development of services in peripheral health centers (HCs and HPs) and offer referral services thereby reducing the incidence of maternal and infant mortality. The activities are planned as part of the operational area which has targeted 5 HDs of the 24 in the country : The reinforcement of managerial skills in the District Management Teams (DMT), The expansion of health coverage with the construction/upgrade of 60 Health Centers, along with their equipment and the supply of basic medicine and specific stock products, and the contracting of external services, especially faith-based ones, The mobilization of Health Care human resources so as to favor the rural HD by hiring contract staff and, On- work training of human resources in the HDs. Operational assistance to the 5 targeted HDs A research study shall be carried out in two of the five targeted HD in order to generate a model for a standard HD and to thereby reduce the existing complexity in HD management throughout CAR by establishing a two-tier health care system, in which one shall offer the Minimum Package of Activities (MPA) and the other the Complimentary Package of Activities (CPA). Assistance to the normalization and support process for HD development in the Target Regions The expected results in this area are : A new national health plan for CAR which shall indicate a new definition for HD on the basis of Health Care criteria (access to quality Health Care). Each HD shall henceforth have two levels of complimentary care cross linked through a referral and counter referral system. The management and operational norms for each level of the health care system is formalized, which will transfer a greater share of oversight and jurisdiction to the DMTs in their growing responsibility. A development plan for HHR is prepared and implemented, which will make it possible to resolve staff shortage and qualitative problems at the HD level. The DMTs have greater jurisdiction and have enough resources to assist the HD in their development In order to reach these goals, a certain number of normalization activities that are usually performed by a centralized administration and upon which depends the success in making the HD operational, shall be performed at the peripheral level and shall receive due support in the context of this plan. This is the case of the preparation of a certain number of standard documents including the new version of the health plan, the human resource development plan, the management and operational norms at each level of the health care system, operational research, etc. The same shall be applied to certain activities at the intermediary level (Health Regions) which the HDs depend on, even as they benefit from GAVI-HSS support (planning, supervision, information management, monitoring & evaluation of the HDs, etc.) Rationalization of Health Care financing Here are the results expected in this area: A basket fund is established in each of the targeted Health Regions (2&4) and it is progressively helped by other financing sources, The resources needed for the development and operational preparedness of the HDs in order offer quality Health Care are available from this source. The Health Sector Coordination Committees (HSCC) of the health clinics raise funds for the purchase of specific stock products necessary for vaccination, The basket fund shall be under the responsibility of the Provincial Steering Committee for Sector Strategy. It shall be the starting point for developping the sector specific approach in the Health Care field in CAR. Targets In terms of improving the state of health in communities, the HSS proposal made by CAR shall help increase coverage of DTC3 to 80% and thus help contribute to the reduction of infant juvenile mortality rates from 176 to 140 deaths per 1000 live births in the targeted HD. It shall also contribute to increase the rate of assisted childbirth from 53.4% to 70% in the presence of qualified personnel, which shall make it possible to reduce maternal mortality rates by 20%. Target population, budget and period of coverage The proposal covers a population which is estimated at 1 094 790 inhabitants (26 % of the total population) living in the HDs of Nana Mambéré, Mambéré Kadéi, Sangha Mbaéré in Health Region 2, the HDs of Kémo and Ouaka in Health Region 4. The total budget is 3 161 960 USD of which 2 379 000 USD, or 73%, are designated for the peripheral level (Health District). It is part of the planning cycle of the comprehensive Multi-Year Plan for Immunization (CMYP) and shall therefore be implemented between January 2008 and December 2011.

# Section 1 : Process for Preparing the Application

To the applicant

In this section, please describe the process for preparing the GAVI HSS application.

- Please begin with a description of your Health Sector Coordinating Committe or its equivalent (Table 1.1).

## 1.1: The HSCC (or the equivalent in your country)

Name of the HCSS (or its equivalent) : Technical Steering Committee for the Reform of the Health Care System in the Central African Republic

The HCSS has been active carrying out its mission since : The Technical Steering Committee for the Reform of the Health Care System in the Central African Republic has been active since the month of July with the creation of a technical operations core in charge of preparing a strategic plan for strengthening the health care system and the HSS proposal of CAR.

Organizational structure (e.g., sub-committees, stand-alone) : The Technical Steering Committee for the Reform of the Health Care System in CAR includes a Technical Secretariat. It aims to establish ad hoc commissions for addressing specific questions. It can also call on external experts if required.

Frequency of meetings: The Technical Steering Committee for the Reform of the Health Care System in CAR meets on a quarterly basis. It may also be summoned in an extraordinary session if required.

Overall role and function : The role of the Technical Steering Committee for the Reform of the Health Care System is : to define and ensure proper monitoring of new policies and strategies that are part of the reform of the health care system National Development Plan for Health Care (NDPH) and the Poverty Reduction Strategy Paper (PRSP); to monitor the implementation of the NDPH and the PRSP to mobilize internal and external resources (multilateral and bilateral partners) needed for the financing of the health sector ; to ensure coordination, matching and harmonization in the Health Care sector; to countercheck the results of the technical Secretariat ; to organize the annual reviews of the Health Care sector ; to examine and approve the plans and annual reports of the Health Care sector ;

To the applicant

Next, please describe the process your country followed to develop the GAVI HSS application (Table 1.2)

## 1.2: Overview of the application preparation process

Who coordinated and provided oversight to the application preparation process? It was the Technical Steering Committee for the Reform of the Health Care System which coordinated and provided oversight of the application preparation process through the offices of its Technical Secretariat.

Who led the drafting of the application and was any technical assistance provided? The Department Research and Planning of the Ministry of Health which is the organism in charge of coordianting the Technical Secretariat and which led the drafting of the application. In January 2007, the WHO has sent an international consultant to the Ministry of Health and Population to assist the application preparation process. Furthermore, as of July, the WHO has sent a national consultant to help finalize the strategic plan for health care system strengthening and the HSS proposal made by CAR. UNICEF has sent an international consultant to the Ministry of Public Health and Population (MPHP) to assist the country team in the preparation of their submission. The participation of NGOs and officials from key international organizations in this process must be noted with regard to their contribution to assisting the health care system.

Give a brief time line of activities, meetings and reviews in preparation of the application submission. The application preparation process by the CAR started with the preparation of a work schedule which was done on the occasion of a workshop organized in the month of April at Libreville concerning the Health Care System Strengthening. In July 2007, a technical team was enlisted composed of the Director of Research and Planning Office, the Director of the Expanded Program for Immunization, a UNICEF representative and a Policy Official from the Ministry of Health Care and Population. This Committee had the following goal : (i) to check and confirm the work schedule prepared at Libreville, (ii) to finalize the strategic plan for Health Care System Strengthening and, (iii) preparing the HSS application of CAR; In August 2007, a workshop was organized in Boali (a town 100 Km from Bangui) for the finalization of the Strategic Plan for Health Care System Strengthening. It was on the occasion of this workshop that the process for completing the application form was started. This workshop met with the participation of the MPHP, the Ministry of Finance, the WHO, UNICEF and a delegation from the European Commission’s Health Directorate General, and one from ASSOMESCA (NGO). At the end of August 2007 the first draft of the HSS application from CAR became available and was sent for review to the partners in the Health Care sector towards mid September. Between September 20 and 24, 2007, a workshop was organized at Boali for the finalization of the HSS application from CAR. On the occasion of the workshop, a small group was enlisted in order to make a digest of the different observations ; The version of the application drafted at Boali was again sent to the partners of the Health Care sector for review on Friday September 28, 2007. A control meeting regarding the application took place on Tuesday October 2, 2007 ; The signing ceremony (approval) by the Government (Ministry of Public Health and Population and the Ministry of Finance) as well as the members of the National Committee on the Reform of the Health Care Sector was organized on Wednesday October 3, 2007;

Who was involved in reviewing the application, and what was the process that was endorsed? The organizations which took part in the review of the HSS application from CAR are : The World Health Organization (country bureau) The United Nations Children’s Fund (country bureau) The UNFPA The delegation from the European Commission Health Directorate General The ‘Association des Oeuvres Médicales pour la Santé en Centrafrique’ (ASSOMESCA) The review process for the HSS application from CAR was the following : Once a draft of the document was prepared, it was sent on to the organizations in charge of review, accompanied with a request to review the document and to propose corrections or possible observations. This step was undertaken twice. Once prior to the Boali workshop and the second time following Boali. After forwarding the document for review by the different organizations, a workshop was organized to permit the various parties to bring the amendments they deemed necessary to the document. The last workshop of this kind was the one organized on October2, 2007. On the occasion of this workshop the last draft of the document was prepared.

Who approved and endorsed the application prior to submission to the GAVI secretariat? Prior to its submission to the GAVI Secretariat, the application from CAR was approved by: The Ministry of Public Health and Population The Ministry of Finance and Budgeting The WHO, country bureau UNICEF, country bureau The European Commission and, The Association des Oeuvres Médicales pour la Santé en Centrafrique (ASSOMESCA) The UNFPA.

To the applicant

- Please describe overleaf the roles and responsibilities of key partners in the development of the GAVI HSS application (Table 1.3)

Note: Please ensure that all key partners are included; the Ministry of Health; Ministry of Finance; Immunisation Program; bilateral and multilateral partners; relevant coordinating committees; NGOs and civil society; and private sector contributors. If there has been no involvement of civil society or the private sector in the development of the GAVI HSS application, please explain this below (1.4).

## 1.3: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organization | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| Director of the Research and Planning Office | Ministry of Public Health and Population | Yes/Member of the Technical Secretariat of the Steering Committee | Providing direction to the entire HSS application preparation process from CAR |
| Director of the Expanded Program on Immunization | Ministry of Public Health and Population | Yes/ Member of the Technical Secretariat of the Steering Committee | Technical support for the preparation of the application |
| Director of the Budget for the Ministry of Finance | Ministry of Finance | Yes/ Member of the Technical Secretariat of the Steering Committee | Technical support for the preparation of the application |
| Health care system advisor (MPN/WHO/CAR) | World Health Organization | Yes/ Member of the Technical Secretariat of the Steering Committee | Technical support for the preparation of the HSS application from CAR |
| Head of the Health Care department/ UNICEF | United Nations Children’s Fund | Yes/ Member of the Technical Secretariat of the Steering Committee | Review of the GAVI HSS application prior to submission to the GAVI Alliance Staffing with an international Consultant |
| Head of the Health Care DG for the European Commission | European Commission | Yes/Member of the National Steering Committee for Sector Strategy | Review of the GAVI HSS application prior to submission to the GAVI Alliance |
| International Consultant | Ministry of Public Health for the Democratic Republic of Congo | No | Technical support for the preparation of the HSS application from CAR |
| Policy Official in charge of monitoring NDPH II | MPHP | Yes/ Member of the National Steering Committee for Sector Strategy | Drafting of the Strategic Plan for Health Care System Strengthening |

A l’attention du proposant

- If the HSCC wishes to make any additional comments or recommendations on the GAVI HSS application to the GAVI Secretariat and Independent Review Committee, please do so below.:

- Please explain if there has been no involvement of civil society or the private sector, and state if they are expected to have a service provision or advocacy role in GAVI HSS implementation.

## 1.4: Additional comments on the GAVI HSS application development process

All of the partners in the Health Care sector (bilateral and multilateral cooperation and from the United Nations system and civil society) were involved in one way or the other in the process of preparing the application from CAR. However, the schedules of the various participants didn’t make it possible for them to participate in all the steps involved in the process as described here above.

# Section 2: Country Background Information

To the applicant

- Please provide the most recent socio-economic and demographic information available for your country. Please specify dates and data sources. (Table 2.1).

## 2.1: Current socio-demographic and economic country information

| Information | Value | Information | Value |
| --- | --- | --- | --- |
| Population | 4 216 666 | GDP per capita (2005) | USD331 |
| Annual Births (2006) | 144655 | Child Mortality Rate below 5 years (2006) | 176/ 1000 |
| Surviving Infants | 128187 | Child Mortality Rate (2006) | 106/ 1000 |
| Percentage of GDI allocated to health (en 2006) | 1.19 | Percentage of Government expenditure on health (en 2006) | 7.07 |

To the applicant

- Please provide a brief summary of your country’s Health Sector Plan (or equivalent), including the key objectives of the plan, the key strengths and weaknesses that have been identified through health sector analyses, and the priority areas for future development (Table 2.2).

## 2.2: Overview of the National Health Sector Strategic Plan

The Ministry of Public Health and Population has a National Health Care Development Plan II (NHDP II) which covers to the period 2006-2015. The National Health Care Development Plan is part of the implementation of the National Health Policy of the Central African Republic and is therefore based on a long-term program (10 years) which thus comprises all of the priority areas for this sector. The plan describes the health situation of the national population while underscoring the the areas which hinder health system performance and meets these challenges with innovative strategies which enable citizens to have access to a better state of health. Taking its bearing from the millenium development goals, it is an action plan for the provision of universal health care in the African Region in the 21st century, also modeling its programs on Agenda 2020, and other regional and subregional strategies. The NHDP advocates equality and social justice for all Central Africans. The health indicators are indeed alarming. Indeed, over the last twenty years, the life expectancy at birth of the Central African population has regressed to 40 years for men and 45.7 for women according to the results from the General Census on Population and Households (GCPH) of 2003. Regarding mortality, the general mortality rate went from 26% to 17% from 1959 to 1988. It’s only in the 1990s that an upward trend has been observed. The Acquired Immuno-Deficiency Syndrom (AIDS) in CAR, combined with a severe deterioration in living conditions of the population, explains the high present overall mortality rate, reaching 20.1%. Child Mortality Rate went from 97% in 1995 to 130.6% in 2000, and 132% in 2003. The mortality rate for children under 5 years is 176 per thousand live births as of 2007 (MICS3). This rate is far above those in most countries in the subregion. (64 per thousand in Gabon). As for the maternal mortality rate, it has gone from 683 to 948 per 100,000 live births in between 1988 and 1995. According to the GCPH 2003, this rate is 1355 per 100 000 live births in contrast to 420 per 100 000 live births in Gabon, a country in the subregion. Death rates are mainly caused by the following groups of diseases : Endemic illnesses among which is HIV/AIDS (with a 6% prevalence rate according to the MICS3), malaria, which accounts for nearly 40% of all medical consultations, and tuberculosis, with 9016 cases recorded in 2004, African Human Trypanosomias (AHT), onchocerciasis, etc. Diseases that affect the survival of children under 5 years: diarrheal diseases (25.7% of medical visits in 2000); acute respiratory infections (17.45% in 2003) ; protein-calorie malnutrition both severe and moderate as well as micronutrient deficiency; DTP illnesses (measles, whooping cough, neonatal tetanus) whose prevalence is closely linked to the poor immunization coverage. Efforts to eradicate polio suffered a setback in 2004 due to a widespread epidemic (30 cases of full-blown polio virus were recorded). In 2006, no case of full-blown polio was registered in the country. Other than the problems related to the population’s state of health described above, the analysis of the health situation and the evaluation of past strategies and policies underscore the main problems listed below: poor performance of the health system ; insufficient and poor condition of infrastructure and equipment; outages in the stock of medicines and vaccines; insufficient quality and quantity of human resources as well as their poor distribution; insufficient and poor management of financial resources, and a general environment that is not conducive to good health. Taking into account the strengths, weaknesses, opportunities and risks inherent in this sector, the strategy and policy lines are defined as follows: (i) strengthening the capacity of the institutional framework (reform of the health system) and partnerships; (ii) combatting illnesses and managing emergency or catastrophic situations; (iii) promoting reproductive health to the public; (iv) promoting an environment that is conducive to good health. The stengthening of the institutional framework meets a requirement that was identified during the final evaluation of the NHDP I which recognized the need to redefine the present institutional framework of the Ministry of Health and to improve its performance. Among other things, this reform should consist in the preparation of a new organizational arrangement of human resources that is less top heavy and has less services, with a regrouping of programs for a more rational use of resources and a redefinition of Health Districts that takes into account real health concerns as opposed to administrative needs. The NHDP II has made this reform into a priority area for success in all the actions needed to improve the state of health among communities. It is in this context that the Ministry of Health resolved to prepare a sector-wide strategy to strengthen its health care system. This strategy has defined five lines of work in the pursuit of an improved health service provision, to reach the targets set out by the Millenium Development Goal for Development linked to health (goals 4, 5, & 6) by reinforcing the health system in CAR. The main strategic lines are the following : Strengthening the institutional framework for the MPHP; The development of the Health Care human resource base; The mobilization and rationalization of financing for the Health Care sector; Strengthening intra and intersectorial collaboration. Improved availability and access to quality medicine. Strengthening the institutional framework of the MPHP.- the central level will focus on improving the way the health care system is steered, especially in the development of norms and directives, the strengthening of capacities regarding all aspects of planning and supervision as well as information management, the strengthening of coordination within the Health Care sector, modification of the health plan, the preparation, endorsement and promotion of a Public Health Code. A new organizational arrangement or workflow process for human resources shall be created. It shall promote a more flexible structure that is more coherent at the central level and which will results in a new map of Health Care provision, organizational and operational norms affecting all levels of the Health Care hierarchy, and all other standardization documents required, including those involving hospital reform. In the peripheral sphere, the Ministry of Health resolves to redefine the Health Districts (HD). The concept involves establishing HDs at the periphery defined on the basis of health provision criteria which are based on providing quality services to the greatest number of people in need. This will involve establishing a two-tiered health care system where the first tier shall offer Health Care which reflects the services of the Minimum Activity Package (MAP) and the second tier shall offer the Complimentary Activity Package (CAP). The first tier shall comprise the Health Posts and the current C, D & E Centers. The second tier is the primary referral center comprising prefecture Hospitals and HD hospitals (HDH) as well as the current Health Centers A & B. The two tiers shall be linked by a referral and counter referral system. Each HD shall be managed by a District Management Team (DMT) trained to provide primary care management and which shall be in charge of the development of the HD. The DMT shall at once be responsible for clinical matters in the HDHs and also for developing the periphery services of the HD (HC and HP). The development at this level of provision shall be gradual and reflect the HD coverage plans being offered. It shall reflect the nature of resources available. The intermediate level shall be strengthened so that it can effectively play a support role in HD development. The development of Health Care human resources. – In order to implement the actions that have been described above, the availability of human resources will be necessary in order to provide sufficient quality healthcare. Refresher courses will be organized for all managerial positions before they return to the posts they have been assigned to. The training shall take place in the HDHs and in the Health Clinics where the operational level is deemed satisfcatory. The on-the-job training shall be regularly scheduled for all levels of the health care system. The quantitative insufficiency shall be filled, at first, by contracting the unemployed national Health Care workers before looking to more lasting solutions (hiring personnel by the civil service, etc.) The human resources shall be deployed in such a way as to favor rural areas. The country has started out on a process of developing a Strategic Development plan for Human Resources in Health Care in the 2007-2015 period. The analysis of the situation was carried out in 2006 and the conclusions presented above were drawn from thereof. It is now the time to develop the needs forecast for the period covered under this plan, and to prepare a career plan for health workers, to establish national and infrastructure standards. Mobilization and rationalization of the sector’s financial resources.- An important mobilization of financial resources for the Health Care sector is necessary in order to permit CAR to improve its performance as it carries out the Millenium Development Goals (MDG). However, the rationalization of financing for the field of health care (decentralizing health financing, improving management and efficiency in the distribution of resources) is an essential step to take in order to increase the effectiveness of Health Care delivery. An intra and inter-sector collaboration. – The MPHP must make sure that it strengthens intra and intersector collaboration. This means that private Health Care workers in the field, especially those who are employed by faith-based organizations, must be involved in the Health Care plans of the Government. This could be effectuated by contracting them, which would lead to a greater level of quality service provision over the long-term. At the inter-sectorial level, actions will be undertaken with the aim of promoting healthier behavior. It will also be necessary to strengthen the collaboration with the Ministry of secondary and universitary education, in charge of training health workers, as well as the Ministries in charge of Planning and Finance to reinforce their involvement in the planning process, the distribution of resources and budgetary monitoring, with the Ministry responsible for the water supply, communications, etc. Improving the availability of essential and quality medicine and its accessibility. – Making essential quality medicine available to the population at a reduced cost is an important policy line for the national health care system. That is why special attention must be given to a homologation system in order to grant proper authorizations to put products on the market. To accomplish this, it is necessary to computerize the homologation system within the Health Department. The improvement in the availability of essential medicines requires strengthening of the acquisition capacity, the storage and distribution by the Medical Procurement Unit (MPU) and by other distributors at the clinic level.

## Section 3: Situation Analysis / Needs Assessment

To the applicant

GAVI HSS Support: GAVI HSS support cannot address all health system barriers that impact on immunisation and other child and maternal health services. GAVI HSS support should complement and not duplicate or compete with existing (or planned) efforts to strengthen the health system. GAVI HSS support should target “gaps” in current health system development efforts.

- Please provide information on the most recent assessments of the health sector that have identified health system barriers. (Table 3.1)

Note: Assessments can include a recent health sector review (conducted in the last 3 years), a recent report or study on sector constraints, a situation analysis (such as that conducted for the cMYP), or any combination of these. Please attach the reports of these assessments to the application (with executive summaries, if available). Please number them and list them in Annex 1.

Note : If there have not been any recent in-depth assessments of the health system (in the last 3 years), at the very least, a desk review identifying and analysing the key health systems bottlenecks will need to be undertaken before applying for GAVI HSS support. This assessment should identify the major strengths and weaknesses in the health system, and identify where capacity needs to be strengthened to achieve and / or sustain increased immunization coverage.

## 3.1: Recent health system assessments

| Title of the evaluation | Institutions involved | Areas / topics covered | Dates |
| --- | --- | --- | --- |
| Expense framework over the mid-term | Ministry of the Economy, Planning and International Cooperation, Ministry of Finance and Budget, The International Monetary Fund | National macroeconomic affairs Policy for sector-specific expenses Macroeconomic framework 2009-2011 Government development targets Presentation of the macroeconomic model | September 2007 |
| Map of health care services distribution in CAR | Health Ministry, WHO/CAR | Establishment of country-wide health service net | 2007 |
| Poverty Reduction Strategy Paper | All the Ministries with the support of all the development partners | Poverty Reduction Strategy | 2007 |
| Action plan for country programs - 2010 between CAR and UNFPA | Government of CAR and UNFPA | Reproductive Health Care | February 2007 |
| Rapid evaluation of capacities in Health Districts Health Districts (prefecture ealth facilities) and proper scaling of priority health operations | Ministry of Public Health and Population(MPHP) et World Health Organization | Operational capacity of prefecture health facilities Health Care infrastructure Human resources for Health Care provision Basic equipment for health clinics Coverage of health care per district. | May 2007 |
| Complete Multi-Year Immunization Plan | Inter Agency Coordination Committee(IACC), the Ministry for Budgeting, The Ministry of the Economy, the Ministry for and International Cooperation | Analysis of the external and internal vaccination environment; Long-term view and national Expanded Program on Immunization (EPI) ; Analysis and cost for financing the EPI | April 2007 |
| Cross sector emergency support to the health, education and anti HIV/AIDS sectors. | Ministry of Public Health and Population , National Anti VHI/AIDS CommitteeVHI/AIDS, Ministry of Education and the World Bank | Assistance to the National Anti HIV/AIDS Program Assistance for meeting urgent needs in the health sector Assistance for meeting urgent needs in the education sector Support to the financial management and contracting unit | April 2007 |
| Preliminary report with multiple indicators for monitoring the status of children and women (MICS3) | Ministry of the Economy, Planning and International Cooperation, CAR Statistics Institute, WHO, UNICEF, UNDP, UNFPA, UNAIDS | The status of the child in CAR, The status of women in CAR, Rates of HIV seropositivy | March 2007 |
| Interim report of the support mission for the preparation of the HSS proposal of the CAR. | Université libre de Bruxelles, the WHO and the Ministry of Health | Proposal for the process for preparing CAR application for GAVI-HSS | January 2007 |
| National Development Plan for Health Care2006-2015 of CAR | National Committee for the Coordination of Primary Health Care, WHO, European Union | Analysis of the status of the Health Care sector, strategic planning and action priorities of the Ministry of Health for the period 2006-2015 | 2006 |
| The National Helath Policy program of the CAR | Ministry of Health and WHO | Analysis of the sector status Political orientations | 2004 |
| Final report on the feasibility study for a health care program in the CAR financed by the 9th EDF | Ministry of Public Health and Population and European Union | Analysis of the health care program strategy for Regions 1 & 6 (improvement of primary care provision and performance-award contracts) | 2006 |
| Mission of the Arab Bank for Economic Development in Africa (ABEDA) in CAR | Ministry of Public Health and Population and ABEDA | Construction of 22 maternity wards in 6 Health Regions | April 2006 |
| National Plan for the Development of Human Resources in Health Care (NPDHR) | Ministry of Health and the WHO | Analysis of the human resources status in Health Care provision | 2006 |
| Final report on the feasibility study for the health project of CAR, volume I | French Development Agency and the MPHP | Analysis of the general context in the country | January 2005 |
| Final report on the feasibility study for the health project of CAR, volume II | French Development Agency and the MPHP | Analysis of the specific context of the various health care areas. | January 2005 |
| Final report on the feasibility study for the health project of CAR, volume III | French Development Agency and the MPHP | Proposal for care provision (improvement of the quality and accessibility to basic health care services in Bangui, improvement of the epidemiological surveillance and consolidation of the national pharmaceutical policy and the Medical Procurement Unit) | January 2005 |

To the applicant

- Please provide information on the major health system barriers to improving immunisation coverage that have been identified in recent assessments listed above. (Table 3.2)

- Please provide information on those barriers that are being adequately addressed with existing resources (Table 3.3).

- Please provide information  on those barriers that are not being adequately addressed and that require additional support through GAVI HSS (Table 3.4).

3.2: Major barriers to improving immunisation coverage identified in recent assessments

The obstacles to immunization services were identified in the complete Multi-Year Immunization Plan (CMYP) and other recent evaluations of the health sector. They can be grouped into four categories, which are: (a) the poor operational capacity of the Health Districts in the implementation of essential health care service provision, (b) the general health service management problems in general and those linked to immunization in particular, (c) the problems linked to the financing of Health Care and the lack of motivation on the part of medical staff. Poor Operational capacity in the Health Districts Three problems explain the poor operational capacity observed at the HD level, which are: (1) the poor health coverage in the HDs, (2) both qualitative and quantitative lack of human resources in Health Care, and (3) the over-complexity of the HD organization. Poor health care coverage in the CAR There are still significant problems linked to Health Care geographic accessibility to general health care and to immunization in particular. At least 25% of the population is over 10 Km from a health care facility, most of which are lacking proper equipment, first aid material and human resources. Given this situation, only 22% of the population has access to quality health care. The interim report on the rapid evaluation of the HDs which was undertaken by the Ministry of Public Health and Population and the WHO in May 2007 shows that around 76% of the health clinics counsel pregnant women on HIV/AIDS, 18% propose nevirapine or AZT to prevent mother child transmission of HIV, 62.3% have a Parent-Child HIV Transmission Prevention (PCTP) screening facility, 11.6% of the clinics have adopted the Integrated Management of Childhood Diseases (IMCD) and 64.9% do the screening and treatment for Malaria. Only 37.3% of the health clinics including all categories carry out routine vaccination. This situation explains to a large extent the poor coverage by routine vaccination that was observed prior to the routine EPI which was carried out in 2006 on the occasion of the national child survival day (NCSD). Indeed, between 2002 and 2005, the coverage by immunization of DTP3 has jumped between 23 and 47% for the country as a whole as is shown in the following figure: Figure 1: Change in immunization coverage (DTP3) in the CAR since 2002. It is therefore due to the campaign to accelerate immunization coverage that was organized in 2006 on the occasion of the national childhood survival day (NCSD) that there was increase in coverage, for all antibodies, in 2006. The poor health provision coverage in the country is worsened by the advanced state of disrepair of the infrastructure due to the armed conflicts that have taken place in the country. According to the interim report on the rapid evaluation of HD capacities in implementing basic services, there are a large number of imbalances regarding infrastructure and equipment that are favorable to central hospitals, while there is also a large deficit in the interior of the country in comparison with Bangui, the Capital. Quantitative and qualitative insufficiency of human resources for health care provision (HRH) in clinical facilities. According to the CMYP of the CAR, there is an insufficiency that is both quantitative and qualitative, in terms of personnel for immunization. The majority of workers doing the EPI are community Health Care workers (first aid nurses and midwives). There aren’t any personnel that are trained for maintenance of cold chain products at either the intermediary or peripheral levels. The supervision of personnel at all levels is uneven and in some cases completely absent. The health care human resources lack motivation due to accumulated arrears in salaries owed to civil servants and in the absence of other forms of motivation (regular supervision, appreciation letters, courses and retraining, career plans, awards, etc). Some community Health Care workers (those who vaccinate) work on a nearly voluntary basis and often in very unsanitary conditions. At the start of the year 2007, 4 of 24 Health Districts (prefectures and health precincts) didn’t have any doctors working for the public services. 3 HDs only had one doctor working for the public services. Along the same lines, the rapid evaluation that was performed in May of 2007, shows that of 16 Health Districts (not including those in Bangui), there is less than one Registered Nurse and/or midwife per 100 000 inhabitants in 3 HDs, one for 100 000 inhabitants in 10 HDs and more than 2 per 100 000 inhabitants in 2 HDs. The same study shows that only 13 registered nurses and 18 Assistant Midwives worked in the 330 Health Posts that were studied which are ambulatory care type centers and which only reach up to 2/3 of the rural population (each center may service a population of up to 5000 inhabitants) In most other cases, it is the community Health Care workers (first aid workers, midwives, sanitary workers or even social workers) who fill the role. Furthermore, the personnel working for the MPHP is aging. In general, a qualitative and quantitative lack of personnel is evident in the peripheral clinics. At the same time, one must take note of the fact that 1000 civil servants and health workers (of whom 70 are doctors) are unemployed in CAR due to the suspension of all hires. This measure was undertaken by the Government as a result of policies backed by the Bretton Wood institutions in order to avoid the excessive burden of salaries on public spending. Only quota replacements are allowed. This measure explains the relative dearth of human resources that has been observed in several sectors of national life, among which is Health Care. The MPHP has encouraged the Management Committees to hire contract personnel but due to lack of funding (which reflects the general impoverishment of the population, which can’t afford to pay health care costs), the Management Committees and Managing Boards of the peripherals clinics are not always able to hire the human resources that they need. Complexity of the organization of the HDs in the CAR. The peripheral level that is the operational focus of national Health Care policies is made up of 16 health prefectures and 8 precincts which are part of the Health Care prefectures in the city of Bangui, or a total of 24 prefectures and precincts or Health Districts (HD). This operational level also includes a Prefecture Hospital or Health District Hospital (HDH), Health Centers (HC) and Health Posts (HP). This level comprises a large variety of primary care services (Health Centers whose categories go from A to E) as well as Health Posts. The subdivision of health prefectures or Health Districts (HD) and the establishment of Centers and Posts reflects an administrative division of responsibilities but not a Health related one... As a consequence, most HDs are very large and half of those outside Bangui, the Capital, have a population which goes from 250 000 to 450 000 inhabitants. The distances people must travel and the precarious state of the roads are such that most users have to travel long distances to reach the health care services, on the one hand, and on the other, the supervision, referral and counter-referral system that is an essential component of quality service, especially with regard to continued provision of services, is very expensive and thus difficult to implement. All of the evaluations that have been done in the last few years recognized that the multiplication of categories of health centers contributes no added value to the organization and functioning of the clinics, but it does make it difficult to establish norms as much regarding resources (human, material and infrastructure) as regarding activities and for this reasons has had a negative impact on quality service provision including vaccination. Health service management problems for general services and for immunization in particular The problems that are linked to the institutional framework and the provision of steering for the health system of the CAR are considered as the major obstacles and challenges if there is to be an improvement in results regarding these services. The guidance for health services in general and vaccination services in particular are enormous challenges to the CAR. Among the main obstacles that are mentioned in the Complete Multi-Year Immunization Plan, there is the fact that the supervision of personnel at all levels of service provision is uneven and in some cases completely lacking. The absence of organizational and operational norms applicable throughout the entire health care system is at the root of the weaknesses that are observed in health service management. As an example, one may look to the poor delineation of jurisdiction and responsibility among the different actors at work in the health care services, especially: Among the heads of the MPHP, the heads of the Health Regions and the Health Prefectures. Among the regulatory powers (the heads of the MPHP, the heads of Health Regions and of the Health Districts) and the care providers (HC, HP, HDH) both public and private, with a resulting handicap in the development of the latter in their capacity to act autonomously, a factor upon which the improvement of quality health care provision and vaccination depends. The conflicts between the clinic managers and the Management Committees contribute to the frustration and the lack of motivation in the personnel and the community. At the level of the Ministry of Health, one observes a certain lack in the ability to steer the health care system due to the onerous human resource workflow process in the current system. The structure of the institutions administering Health Care are complex and could be an obstacle to decision-making given the barriers to the flow of information and the breakdown of decision-making mechanisms for matters of common concern. Furthermore, the optimal functioning of such a structure is a budget drain. This level alone takes up 41% of the state budget devoted to Health Care (of which 17% are for the central administration) while only 2% are spent on the intermediary level (the 7 Regional Health Offices) in charge of lending technical assistance to the periphery. As a result the intermediary level of the health care system doesn’t have the resources necessary to fulfill its mission, which is to bring technical assistance to the development of the Health Districts. The absence of organizational and functional norms leads to a situation where the intermediary level takes the place of the periphery especially in matters concerning the training of Health Care personnel in the HDs and the supervision of the peripheral clinics. At the peripheral level, for example, there is a lack of norms clearly defining the number of persons and the qualifications which they must possess in order to join the District Management Team (DMT). It has reached a point where in certain DMTs there is demonstrable lack of qualifications that are necessary to be part of a District Management Team. The members of the DMT haven’t received proper training to perform their tasks. The roles and responsibilities of the DMT members are not clearly delineated. The training and supervision of the HD activities are executed along vertical management lines by a group of program heads that are posted at the regional management level, even if they are sometimes accompanied by a member of the DMTs. This shows the degree to which the division of responsibilities between the intermediary level and the HD is not clear. Problems in Health Care financing The management of resources and especially financial resources is very centralized in the CAR. All of the resources are administered by the Resource Office which, after negotiating the credits, receives the material and the supplies which it then endeavors to distribute to the outlying centers. Unfortunately, this process is quite long. Things have reached a stage where certain beneficiaries receive their equipment, supplies and materials with significant delays, sometimes in the course of the financial year following the financial year for which the budget was attributed. In order to meet their operational costs, the heads of the clinics tend to compensate by increasing the cost of their services in the public clinics which mostly depend on the financial contribution of households (community financing). This situation leads to the following consequences: (i) increased cost of health services which puts service access beyond the means of most people, (ii) problems with Health Care service quality due to insufficient resources including medicine (iii) worsened poverty among the population (iv) a tendency of the health staff and the Management Committees to favor the financing of treatment since this brings in more income to the detriment of preventive care and information campaigns. Indeed, among the expenses of the Management Committees (COGES), there is a budget for the purchase of fuel and cold chain accessories as well as the financing of advanced strategy operations costs. If certain COGES accept their responsibility in this matter, others, due to delays and insufficient credit from the State, give preference to the renewal of materials and consumables going to treatments instead of devoting money to the purchase of fuel meant for the cold chain, thereby exposing the HD to depleted stocks of vaccination products. Finally, it is important to highlight the fact that many Management Committees are either not functional or else are in conflict with the heads of clinics and in most cases they haven’t been trained in the ways of good management and thus don’t have the proper tools for performing. This situation makes the rational use of existing financial resources even more difficult. The near absence of State financing for Health Care facilities and the wide divergences in the disbursement schedule of external resources brought in by the development partners have reached an impasse. The authorities in this sector, especially the DMT, don’t know what resources they will be able to count on to plan the service provision that is necessary at the start of their budget year. This situation makes all efforts difficult, even random in view of the need for an integrated development of the HDs. Lack of motivation among health service human resources in the CAR. As witnessed in nearly all the recent evaluations of the Health Care sector (including the cMYP), the successive Governments have all accumulated several months and even years of arrears in salary disbursement. This current Government has tried to bring this situation under control but this has met cash flow problems. Besides the arrears that have accumulated under past Governments, the total count comes to about 6 months of unpaid salaries. The last disbursement was made in July of 2007, which was for December 2006 payments. This situation is at the source of the low motivation of personnel, and the tendency to devote more means to medical treatment which can generate some form of revenue and their survival to the detriment of ‘free’ vaccination services as described here above.

3.3: Barriers that are being adequately addressed with existing resources

Several projects of the health sector in the CAR that have been financed by donors and the Government are either in the process of being carried out or else are set to start in the following months. These projects, such as those which will receive backing from the European Union in the context of the 9th European Development Fund (EDF) and the French Cooperation Agency in the context of the ‘health program for the CAR’ and others still, shall play a part in the areas that have been marked as barriers to the delivery of vaccination services and other health services. Given that most of these activities (which target the identified barriers) have yet to start, it is difficult to render a judgment regarding their effectiveness on the one hand, and on the other, the different projects will not cover the entire country. This makes it possible to look to the GAVI HSS application from the CAR as a means to implement the activities mentioned over a wider geographical area in order to overcome barriers to vaccination and other health services. The input that is expected from these projects designed to overcome the present barriers is described in point 3.4a. The barriers to vaccination which will not benefit from any substantial activities in the following years are reviewed in point 3.4b and the contribution that is expected from GAVI HSS to confront these barriers is described in point 3.4 c.

## 3.4a: Expected contributions from the declared resources aimed at overcoming barriers to vaccination.

Overview of the assistance projects to the health system in the CAR The following paragraphs are an overview of the programs meant to impact the areas identified as obstacles to vaccination service and to other health services. This makes it possible to show (point 3.4c) the way in which financial resources solicited from GAVI for the Health System Strengthening shall be complimentary to those that already exist or which are projected throughout the country. In general the FDA programs and those of the EU are geographically located, respectively, in Region 7 and in Region 1 & 6 while those of the World Bank the Arab Bank for Economic Development in Africa and the organisms of the United Nations system shall be carried out throughout the whole country. The health project from the 9th European Development Fund will create programs with a budget of 9 500 000 euros and the health program from the CAR shall be financed by French Development Assistance through the French Development Agency (FDA) with a total of 6 000 000 euros. The World Bank’s will contribute to the health sector with 1 973 000 $ US. This amount is essentially meant to stock several health centers with insecticide-treated mosquito nets (ITN) and will also finance emergency care services for the years 2008 and 2009 in several HDs. The Arab Bank for Economic Development in Africa (ABEDA) shall contribute 3 330 000 $ US to the health sector. This financing is meant for the construction of 22 maternity wards in 6 Health Regions, which will contribute to an increase in service provision for maternal and child health needs. The organisms of the United Nations, in the context of the cooperation programs with the Government, have set aside funds to strengthen the health care system. This is the case of WHO which shall finance the health system with USD 1 146 480 for the 2008 – 2011 period, while UNICEF will bring USD 3 780 000 for the 2008 to 2011 period. The financing by UNICEF is meant to strengthen the Integrated Childhood Management of Childhood Illness (ICMI) activities in several HDs. The UNFPA will strengthen the services for Reproductive health in several clinics with USD 6 566 743 for the 2008 to 2011 period. These funds include HIV/AIDS programs. Programs aimed at the identified barriers The specific programs of the different projects that address the identified barriers are described in the paragraphs below. A. Barrier related to the poor operational capacity of the HDs. 1. Poor health coverage in the CAR. In order to improve health coverage throughout the country, significant upgrade and equipping of Health Care infrastructure are being planned as part of the Poverty Reduction Strategy Paper in the CAR. Furthermore, the European Union and French Development Assistance through the French Development Agency (FDA) shall be active over the coming months to improve the qualitative and quantitative provision of health care services. The part played by the European Union shall take place in the context of the Health Program of the 9th European Development Fund (HP9EDF) and shall be carried out in Health Region 1 & 6 as of next year. The total amount budgeted for the improvement of health coverage in the area of responsibility of this project (health region 1 & 6) is 2,954,109 euros. Another fund shall be set aside to bring to completion some projects which were started during the implementation of the health program of the 8th European Development Fund in Health Region 2. The French Cooperation Agency, through the French Development Agency (FDA) shall take part in the plans to improve the health provision in the capital Bangui. The budget for this project shall be € 2,087,559. The ABEDA shall contribute to the improvement of services by constructing and equipping the clinics and staff housing in several HDs. The World Bank shall finance the equipping of 12 hospitals throughout the country in the context a program for emergency care provision. 2. Qualitative and quantitative insufficiency in human resources for health care services All of the support projects for the Health Care sector especially those that have been mentioned in the previous point, have training provisions for personnel working in the Health Districts which will be beneficiaries of these actions. The training is meant to improve the skills of the human resources working in peripheral areas. The health project shall be financed by French Cooperation Agency through the FDA and is planning to contract health workers from among those who are currently unemployed in Bangui as a result of a freeze on hiring by the Government. The project has set aside a €77,531 fund for training purposes. The Government aims to hire, before the end of the current year, a limited number of managers to try to meet the gaps in services across all areas. In the health sector, 190 managers will be hired and integrated into the public service. 3. Complexity of the organization of the HDs in the CAR The Ministry of Public Health and Population has just prepared a Strategy to strengthen its health care system. This strategy comes as a result of the recognition that the health care system of the CAR is in need of reorganization, as witnessed in the 2006-2015 National Development Plan for Health Care, where it is cited as a basic condition for having success in all health programs being implemented in the country. In the periphery the Strategy has redefined the operational units of the Ministry of Health. Indeed, the Health District shall henceforth have a two-tiered health provision system. The first tier is the front-line contact with the population, carried out by the current Health Posts and the category C & D Health Centers. These area clinics shall each provide for a population of about 5000 people and shall offer a Minimum Activity Package (MAP). The second tier shall be the services provided upon referral. This tier shall provide care which is part of activities complimentary to those offered by the MAP and which shall require a higher technical input and it shall be constituted by the prefecture hospitals and the current A & B Health Centers. A new services map shall therefore be produced as a result of this new outlook with each HD preparing a health coverage plan whose implementation should make it possible to project for quality health provision for the entire population. Significant financing shall be required to implement the cartography map which shall result from this new outlook. The Strategy of the Ministry includes a gradual implementation in accordance with the availability of funds. The HP9PDF shall work towards making this outlook a concrete reality (two-tier healthcare system) in Health Regions 1&6. Barriers regarding the management of health services in general and vaccination in particular The European Union, in the health program for the 9th European Development Fund (HP9EDF) of the CAR, is planning to provide assistance to the steering functions, especially those regarding central level regulation and the development support for HDs in the 1&6 HDs. The total amount set aside for this area is €638 816. In the Health Program of the French Cooperation Agency, there are also plans to provide assistance to some aspects of health service management. This involves the improvement of the health service providers at the central level in the Health Region of Bangui (HR 7) and at the periphery. These actions shall consist in training for planning, monitoring & evaluation and their implementation. The budget provided for this action is €1 050 700. Furthermore, this program shall also help to improve actions regarding the regulatory framework and control in the MPHP with regards to the pharmaceutical sector. The budget for this program, focused on regulation and control, is €76 184. Barriers due to the lack of motivation of Health Care personnel in the CAR. The health program of the 9th European Development Fund shall introduce for the first time in the CAR, performance-based contracts. These performance contracts shall be cosigned between the National Public Health Units on the one hand, and the two Health Regions that are supported by the Organisms in charge of channeling funds, the DMT and the creditors. The total amount that will be budgeted for these performance contracts shall be € 1 794 800. This provision of services shall help increase the revenues of health care human resources concerned and therefore contribute to boost the motivation of the staff, which should really help to improve the cash flow for health care as well as the quality of its provision. The health program of the CAR that is financed by the French Cooperation Agency shall receive €224 003 for bonuses meant to make up for their low motivational level. Finally, the different support programs to the health sector and financing by development backers will contribute to the general improvement of the health sector and lower the barriers mentioned above to health care provision in general and vaccination in particular. However, the magnitude of the challenges is such that the programs that are foreseen shall not be able to lower all the barriers in the country as a whole. The problem of low health coverage shall be addressed in the city of Bangui in the context of the health program that is being financed by French Cooperation Agency through the FDA and in the Health Program of the 9th European Development Fund in the 1 & 6 Regions. The GAVI HSS proposal of the CAR shall therefore extend its actions in the targeted Regions and HDs (Regions 2&4). The two projects mentioned above shall also target some of the steering responsibilities in support of the central organization in addition to strengthening the Regional Management Teams (RMT) for the planning, monitoring & evaluation plans in their Region. The GAVI HSS application of the CAR seeks to support the normalization process and to disseminate the strengthening capacity for the RMTs and the DMTs in the respective Regions or HDs where they operate. The incentives that are meant to improve the motivation of personnel in the context of the GAVI HSS proposal shall basically be oriented towards the periphery (HD).

# 3.4b: Barriers not being adequately addressed that require additional support from GAVI HSS

Barriers regarding the Health Care provision financing problems The barriers which aren’t being adequately addressed are those related to Health Care provision financing. Indeed, the disbursement rate of the State budget devoted to health is quite low (about 50%), and the funds that have been disbursed are mostly for the salaries of staff. Furthermore, the central level of the Ministry of Health accounts for a large part of this budget, 41%. If the funds for the programs financed by the donors and the United Nations organisms (UNICEF, UNFPA, World Bank, etc.) do not raise any liquidity problems for the periphery of the health care system, they are nevertheless disbursed according to a vertical administration of funds (which does raise some serious issues regarding the efficiency with which these funds are distributed) and their procedures and disbursement schedules do not favor a more integrated development of the HDs. The problems faced by management structures and their operational capacities in the DMT still remain as before in most of the HDs.

## 3.4c: The contribution expected from the GAVI-HSS application from the CAR in addressing the vaccination barriers.

The Central African Republic proposes two groups of impact areas to be derived from the GAVI-HSS support addressing the current barriers to vaccination. These are : Barriers which will be addressed or are already addressed by the assistance from Government or other donors, but for which there needs to be an extension accorded to other Health Regions as is the case for barriers relating to the poor operational capacity of the Health Districts (HD) and the health provision management or steering issues, especially those that involve the standardization of functions and support to the development of the HDs. Barriers which are not being addressed in a satisfactory manner because they do not receive substantial attention, which is the case of the problems that are related to Health Care financing. In this sense, the GAVI-HSS application from the CAR shall have three areas of impact, which are: Support to the operational level of the Health Districts ; Support to the standardization and support functions for the HDs in the Target Regions (Steering of the Health System) The rationalization of financing for health The support to the operational level of the Health Districts is the main area of impact and the principal strategy of this application. The other two impact areas (support to the standardization and support functions to the development of the HDs as well as the rationalization of Health Care financing) are support strategies for the first area. Indeed, the development of the HDs is only possible when the intermediary health care system in charge of providing technical support to the HDs and the level of standardization have a minimal degree of functionality and the financial resources and other resources are available in a timely fashion at the peripheral level. 1. Support to the operational level of the Health Districts. The actions that are planned in the framework of this impact area, are : strengthening the management capacity of the District Management Teams (DMT)), the extension of health coverage by renovating the Centers and Posts, along with their equipment and basic medical supplies as well as specific products, the contracting of private service providers, especially faith-based ones, the mobilization of Health Care human resources for the benefit of the HDs in rural areas by hiring contracted personnel, the on-the-job training of human resources in the HDs. Support to the operation of the targeted District Hospitals, The Strengthening of the management capacities of the community participation associations including the Management Committees (COGES). Furthermore, two HDs among those which shall benefit from the planning shall receive support for functioning as per the model recently proposed by the MPHP which is in line with the classic HD model as defined by the WHO. This action aims to put an end to the complexity in the health care structure which makes health management difficult and compromises its quality (follow-up, efficiency, effectiveness, etc.). The experience shall be documented and evaluated before being generalized throughout other HDs depending on available funds. The extension of health coverage and the availability of quality human resources in the HDs shall bring about an increase in service provision in general and in vaccination in particular, which shall make it possible to improve routine vaccination coverage. Selecting Health Districts to be targeted by the GAVI-HSS application from the CAR Based on the vaccination results over the last three years (2003, 2004, 2005) as is shown in figure 1, it is possible to see that all of the regions, and therefore all the HDs, have had poor performance indicators in matters in vaccination. The year 2006 wasn’t taken into account since it already received an accelerated DTP campaign. These results show that all of the regions, and therefore all the HDs, are to a great extent affected in the same way by the barriers to vaccination service provision in the country. However, a certain number of them have received development assistance which has gone towards helping relieve the bottleneck in vaccination provision and in other health services as described under point 3.4a. As a result, the criteria that have been selected for choosing the HDs to benefit from support with the GAVI-HSS resources are: (i) absence of development assistance and, (i) absence of an insecure environment. However, the number of HDs to receive support must be in relation to the available budget, considerint that an average rate of $3 per inhabitant per year is acceptable for the region. The HDs of the Health Regions 1 & 6 shall receive support from the European Union and this support shall make it possible to lower a certain number of barriers, among which are poor health coverage in the targeted HDs. Health Region 7 (Bangui) shall receive the support of the French Cooperation Agency through the FDA. The regions which don’t currently receive development assistance are therefore regions 2, 3, 4 & 5. However, the security situation which is extant in regions 3&5 categorize them as being in a state of emergency. This is also the case for the HD of Nan Gribizi in Health Region 4. Therefore, only the HDs in Health Region 2 (Nana Mambéré, Mambéré Kadéi and Sangha Mambéré) and two HDs in Health Region 4 (Kémo and Ouaka) meet the two criteria that were identified (absence of support for development and absence of a poor security environment). The total population in these HDs is 1 094 790 inhabitants or about 26 % of the total population. Therefore the HDs targeted by the GAVI-HSS application from the CAR and the populations thereof are listed in the following chart: Regions Health Districts Population Health Region 2 Nana Mambéré 233 795 Mambéré Kadei 364 795 Sanga Mbaéré 101 070 Health Region 4 Kemo 118 420 Ouaka 276 710 Total Population 1 094 790 By applying the average of $3 per inhabitant and per year it is possible to conclude that the financial resources expected from GAVI-HSS are not sufficient for complete assistance to the five HDs that have been listed. Even if one includes the support provided by the other donors mentioned here above, one still falls short of the rate of $3 per inhabitant per year. Therefore, the choice was made to focus the resources provided by GAVI to the level of service provision where the main health problems of the community are addressed, which is also the level that takes charge of vaccination activities, that is to say, the HPs and HCs. The development of peripheral health services is highly dependent on the managerial skills of the District Management Team (DMT). Indeed, it is the DMTs who must lead the process for preparing the coverage plans for the districts that are needed to provide increased coverage, ensure the quality of care through proper supervision, and train the HC and HP personnel. The rapid evaluation performed by the MPHP with the support of the WHO shows that not all of the DMTs had received previous training on primary Health Care provision management. The supported DMTs shall receive such training. Healthcare human resources shall be mobilized in favor of the HDs targeted in the application. This will involve hiring personnel under contract among which there will be those who are currently unemployed in the country and to assign them to the clinics which lack HHR. On-the- job training is planned for the improvement of the HHR’s job performance. The Health District Hospitals (HDH) that are targeted shall receive a minimum assistance to allow them to play their part in the operational duties of the HDH. This minimum support to the HDHs is justified as per the following: the HDHs in the CAR offer vaccination services, they play an important technical support role in the development of decentralized services especially with regard to the HCs and HPs (training of the personnel in the HCs and the HPs, quality assurance for health services provided in the HCs and HPs, etc.) They often have an important role to play in the reduction of child and maternal mortality rates by offering referral services for more specialized care. Choosing the Health Districts to develop according to the classic WHO model The HDs that are to be developed as pilot centers must meet a certain number of conditions: (i) have dimensions and population near that of a classic HD (100 000 to 150 000 inhabitants), (ii) have infrastructure which makes it possible to develop one true Health Care pool if it has about 100 000 to 150 000 inhabitants or two true pools if it has more than 250 000 inhabitants, (iii) be close to Bangui in order to reduce costs related to monitoring visits on behalf of the central level of the MPHP which must be frequent enough. The HD of Kémo in Health Region 4, and of Mambéré Kadéi in Health Region 2, are the only ones which meet these conditions. 2. Support to the standardization and assistance functions for the development of the Health Districts (steering the health care system) The poor levels of performance that have been noted in the HDs are partly explained by the fact that the central and intermediate levels of the health care system don’t always properly carry out their missions. This is the case of all problems related to the production of the Health Care cartography map (the current one only considers administrative criteria), the difficulty of establishing applicable norms for each level of the health system, the assistance which some HDs benefit from at the intermediary level and which isn’t always appropriate, etc. As such, a certain number of centralized functions relating to standardization, upon which rests the success in making the HDs more operational in the periphery, shall be assisted in the framework of this application. This is the case, for example, in the preparation of a certain number of standardized documents including the updated health plan, the development plan for human resources, the organizational and operational norms for each level of health care, etc. The same applies to certain functions at the intermediary level (Health Regions) which the HDs that are to benefit from GAVI-HSS support depend on (planning, supervision, monitoring & evaluation of the HDs, training, etc.) 3. Rationalization of Health Care financing The rationalization of Health Care financing is a requirement if the service offer for quality Health Care in the HDs is to be proposed. Besides the strengthening capacity of the DMT managers and the functionality of the Management Committees (COGES) that are planned for areas that aim to make the HDs more operational, the rationalization of Health Care financing to increase the development of quality services (integrated, effective and efficient, etc.) at the peripheral level (HDs) shall require the establishment of a ‘basket fund’ for the targeted Regions. This ‘basket fund’ shall be financed over the long-term by all the financial sources that are allocated to the targeted provinces including the State budget for Health Care provision. The establishment of the ‘basket fund’ presents the following advantages: decentralize the financing of Health Care thus improving the availability of financial resources for better HD development, more oversight sharing with Health Care authorities in the periphery areas on questions relating to the choice of areas to finance ; the improvement of financial management in general and in the efficient allocation of these resources in particular. The course taken by the ‘basket fund’ shall be documented and evaluated before being implemented in other Health Regions. This ‘basket fund’ shall be the starting point for a sector-wide approach once the national status quo shall so permit it especially with regard to carrying out the reforms in this sector.

Section 4: Goals and Objectives of GAVI HSS Support

To the applicant

- Please describe the goals of GAVI HSS support below (Table 4.1).

- Please describe (and number) the objectives of GAVI HSS support (Table 4.2). Please ensure that the chosen objectives are specific, measurable, achievable, realistic and time-bound.

## 4.1: Goals of GAVI HSS support

The GAVI-HSS application from the CAR is part of the implementation of the National Development Plan for Health Care whose goal is to contribute to the improvement in the health of the Central African population, in particular of those strata of society that are most vulnerable, including the poor.

## 4.2: Objectives of GAVI HSS Support

A single specific objective is the focus of the GAVI HSS application from the CAR : To contribute to the reduction in infant, juvenile and maternal mortality in the Central African Republic by increasing the availability of health services and the use of quality health care services in Health Regions 2 & 4 until 2011

Section 5: GAVI HSS Activities and Implementation Schedule

To the applicant

- For each objective identified in Table 4.2, please give details of the major activities that will be undertaken in order to achieve the stated objective and the implementation schedule for each of these activities over the duration of the GAVI HSS support (Table 5.2 overleaf).

Note: GAVI recommends that GAVI HSS supports a few prioritized objectives and activities only. It should be possible to implement, monitor and evaluate the activities over the life of the GAVI HSS support.

Note: Please add (or delete) rows so that Table 5.2 contains the correct number of objectives for your GAVI HSS application, and the correct number of activities for each of your core objectives. .

Note: Please add (or delete) years so that Table 5.2 reflects duration of your GAVI HSS application

To the applicant

- Please identify below how you intend to sustain, both technically and financially, the impact achieved with GAVI HSS support (5.1) when GAVI HSS resources are no longer available.

## 5.1: Sustainability of GAVI HSS support

The Central African Republic is a country which is emerging from a long period of armed conflict which has had real consequences on the social and economic fabric of the country. The return of peace as well as the different reforms that the Government is currently implementing will assist in improving its tax revenue base and therefore contribute to increasing the public investment in Health Care, which is currently around 7%. The country is part of the Heavily Indebted Poor Countries Initiative (HIPCI). In fact, it will reach the completion point of this initiative by the end of this year. This will allow it to free up substantial resources that will increase the part of the budget that the state devotes to Health Care. Once this initiative matures, the funds proceeding from debt forgiveness shall allow the country to contribute to help perpetuate the gains that are expected from GAVI HSS in the Health Regions 2 & 4. In the meantime, other donors have already started working on a long-term plan. The European Commission has studied the possibility of identifying a new Health Care program for its 10th EDF while the 9th EDF is being announced as starting in the coming months. Finally, the Government’s own resources shall be healthier thanks to an improved management approach to taxation, as well as the HIPCI funds which will come from debt forgiveness once the country has reached the completion point of the HIPCI initiative, in addition to the external resources which are expected from donors such as the EU and the French Cooperation Agency. These are long-term investments which will make it possible to perpetuate the programs to be implemented as a result of financing from the GAVI/HSS application from the CAR.

5.2: Major Activities and Implementation Schedule

| Major Activities | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 (2011) |
| --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1st Program Area : Support to Operational Capacity Building for Health Districts |  |  |  |  |
| A. Distribution of the Health Care coverage of the CAR |  |
| Activity 1.1 : Situation report on the Health Care status in Regions 2 & 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2 : Upgrade of the HCs and HPs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3 : Provision of the HCs and HPs with stock material |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4 : Provision of the HCs that have been built or upgraded with cold chain supplies |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5 : Provision of the HCs and HPs with medicine and specific products |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6: Training/freshener courses for the personnel of the HCs and HPs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.7: Contracting of private faith-based parties |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Strengthening of the capacities of the HD management teams |  |
| Activity 1.8: Training of the management teams of the Health Districts in the management of primary Health Care. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.9 : Training /retraining of the DMTs for the ‘pilot’ HDs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.10 : Supervisory assistance to the DMTs for the supervision of the HCs and HPs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C. Mobilization of Health Care human resources favoring the rural HDs |  |
| Activity 1.11 : Hiring and paying of subcontracted health workers favoring the supported HDs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.12 : Payment of performance bonuses in the supported HDs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D. Support to the operational capacity of the Health Districts Hospitals |  |
| Activity 1.13 : Provisioning of the 5 HDs with essential medicines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.14 : Provisioning of HDHs with medical supplies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.15 : Training the personnel of the HDHs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2nd Program Area : Strenthening the functions of normalization and of technical suppord to HDs |  |  |  |  |
| Activity 2.1 : Preparing a plan for developing Health Care human resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2 : Preparing/updating the health plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3 : Defining the organizational and functional norms for each level of the health care system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.4 : Organizing meetings of the National Steering Committee for Sector-wide Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.5: Training of the Regional Management Teams for planning, monitoring, evaluation and information management. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.6 : Supervisory assistance of activities in the HDs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.7 : Nation-wide consultation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.8 : International consultation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.9 : Organizing the annual review of the sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3rd Program Area : Decentralization of Health Care financing |  |  |  |  |
| Activity 3.1 : Establishment of a ‘basket fund’ in the Target Regions |  |  |  |  |  |  |  |  |  |  |

Short remarks on the main activities endorsed in this application. The activities are presented according to their respective Program Area. The results that are expected for each program are also presented. A. Operational capacity building in the Health Districts Expected results The 5 HDs are operational and each one has several functional HCs and HPs. The distance that the population must travel in order to have access to Health Care is reduced due to the increase in service coverage. The HCs and HPs have qualified and motivated personnel, with stores of stock products and can therefore offer on-going vaccination services (strengthening of routine EPI) and other quality health care services to the populations they cover. The HDHs support decentralized development of services (HS and HP) and offer referral services that are necessary for the reduction of maternal and infant mortality rates. The activities that are planned for these Program Areas, are: 1. Activities related to the wider distribution of Health Care coverage Situation report of the status in the target HDs. - a survey shall be carried out in the target HDs at the start of the proposal implementation. It will target both household and clinics. Its aim is to: - obtain baseline values which are not available for certain indicators: - update the data on infrastructure and the availability of facilities in view of the damage that was inflicted throughout the years of armed conflict, and: - generate information for better targeting of actions during the preparation of the action plan for the first implementation year of the proposal. Another survey shall be carried out at the end of the program based on the indicators that were used during the initial survey. It shall aim to evaluate the results obtained in terms of the effect and improvement of health among the population. Upgrade of the Health Centers and the Health Posts. –In order to have a wider distribution of health coverage, several Health Care Centers (HC) and Health Posts (HP) shall be upgraded in the target HDs. An average of 12 HC and/or HPs are to be upgraded in each targeted HD, which gives a total of 60 HCs and/or HPs. The exact number of HCs and HPs to be upgraded per HD shall be determined during the initial situation report inspection which is to be performed at the beginning of the project. This action should make it possible to for a population of about 500 000 inhabitants (or 12% of the total country population) to have access to quality Health Care provision within a 5 Km radius. Provision of the HCs and HPs with stock material. – All of the upgraded HCs and HPs shall be equipped with basic medical supplies (consultation equipment, laboratory equipment, especially a microscope and accessories that are necessary for using it, two or three childbirth kits, medical supplies, etc.). Provision of the HCs and HPs with essential medicine. – All of the HCs and HPs that are upgraded shall be provided with essential medicine and specific products. This supply shall be made using credit lines to be opened in the name of the targeted HC or HP in the proposal submitted by the Medical Procurement Unit (MPU). Contracting private faith-based parties. - The integration of private parties into the Health Care map of the HDs shall help with the rapid improvement of coverage distribution. This action shall target the clinics that belong to religious groups that are associated within the NGO ASSOMESCA. This shall be done via a contract with the Health Region or the HD. These shall commit themselves to offer the population what is proper for their category of health care provision, either the Minimum Activities Package or the Complimentary Activity Package. In return they can use the stock products such as medicine and materials (with a credit line from the MPUs); their personnel will have access to training, etc. Activities that are part of the strengthening of the capacities of the HD Management Teams Training of the management teams in the management of primary health care services. - The members of the DMTs shall be trained in primary Health Care management techniques. The total number of persons to be trained shall be 20 (or, on average, from 3 to 4 managers per HD including the 2nd development pool from the Mambere Kadei HD). This training shall be done in workshops, each lasting 4 weeks. This is required so that the DMTs can get the skills that are necessary to manage an HD, especially with regard to planning, monitoring & evaluation, supervision, information management, resource management, etc, which are areas in which the basic training for doctors does not expend much resources. The improvement of skills among the DMTs shall allow them to include as part of the rationalization plan the HCs and HPs on their mandate that are also supported by other donors and by the Government. This shall help to widen the distribution of health coverage beyond the areas covered by the HCs and HPs targeted in the GAVI HSS financial provision. Supervision of activities in the HCs and HPs. - A quarterly supervision of the HCs and HPs shall be carried out by the DMTs. On average, each HC and HP shall receive supervision 4 times per year. This supervision shall concern all the HC/HP in the target HDs including those supported by the Government and the other development partners. A vehicle fleet (4-wheel drives) shall be made available to the DMTs for their supervision of the HCs and HPs. Mobilization of Health Care human resources favoring the HDs Hiring and paying health workers under contracts favoring the supported HDs. – sixty registered nurses and/or midwives shall be hired as contracted personnel for the HCs and/or HPs of the target HDs. These personnel shall be paid from the financial provisions offered by GAVI HSS that will be allocated. A monthly bonus of USD 100 shall be paid per registered nurse under contract. The payment of this bonus shall be made during the implementation period of the proposal. It shall be part of a performance-award contract. The personnel that are hired shall become part of the civil service at the earliest possible date. Payment of bonuses based on performance to personnel working in the clinics.- performance bonuses shall also be paid to personnel that are currently working in the clinics on the basis of a list of activity indicators and the relevant results which are listed in point 6.1 & 6.2 of this proposal. The performance-aware contracts shall be developed during the preparation of the proposal implementation. Nearly fifty bonuses linked to performance shall be paid to existing personnel in the clinics. The purpose is to stem the low motivation of the Health Care workers whose salary is already several months in arrears. The performance shall be evaluated on a quarterly basis by the health authority that is hierarchically above the level the bonuses are being paid out to. On-the-job training of human resources in the HDs Training/retraining of Health Care workers in the HCs and HPS. – The paramedical personnel (nurses, midwives and Assistant midwives and, if necessary, community health workers) that are employed in the Health Centers that are to be upgraded, and those who will be hired under contract, shall be trained and/or retrained. This training is justified by the fact that the current personnel in the clinics rarely have the opportunity for continued on-the-job training and also, because the personnel to be hired have long been unemployed. A renewal of skills is thus necessary. This training is centered on the Minimum Package of Activities (MPA) which includes at the same time medical care, preventive and public awareness activities. Three workers shall be trained for each targeted HC or PH in a Prefecture Hospital with a good operational level, for a total of 100 agents to be trained. Training of the personnel in the HDHs. – the personnel working in the HDHs shall also be trained/retrained. Indeed, most of the persons working in the HDHs haven’t received any training/retraining over the last few years. The few training programs that are arranged in the country are organized according to special programs that the HDHs do not partake of. This training and retraining shall take the form of internships in the hospitals of other HDs with a good operational level. Ten workers shall be trained per HDH on average. Initial training of the medical personnel. - A program for initial training of young doctors who have just been hired shall be arranged. This training shall take place in the HDHs or in the prefecture hospitals that already have a good operational level and it shall last for three months. This training shall only commence in the second year, in order to identify and prepare the HDHs to receive the young doctors. All of the young doctors who have just been hired shall have access to this training before they return to their assigned posting. In the context of this proposal, 10 young doctors shall have access to this training. Support for the operational capacity of the HDs. Support for the operational capacity of the HDHs shall be done through two main activities, which are: (i) the training of personnel and, (ii) the provision of essential medicine, specific products and medical supplies Training of the personnel of the HDHs.- (see the preceding Program Area) Provision of the HDHS with essential medicine. - all of the 5 HDHs shall be supplied with essential medicine with the aim of improving the quality of the referral health services which they are mandated to provide. In addition to these HDHs, there is also the Health Center of the HD of Mambéré Kadéi which shall have to ensure provision of the complementary activity package (referral services). As for the HC/HPs, this medicine shall be granted to the HDs in the form of a line of credit to be registered at the Medical Procurement Unit, which is the national organism in charge of supplying essential and generic medicine. Provision of the HDHs with medical supplies. – minimum supplies are required for the HDHs to address the health issues which call for referral or specialty health services. The 5 HDHs and the HC of the HD of Mambéré Kadéi which was mentioned in the previous paragraph shall thus be supplied with consultation material, laboratory and surgery supplies. The identification of the exact type of material that the different HDHs shall require shall be decided on the occasion of the analysis of the initial situation report. Strengthening of the standardization procedure and technical support for the HDs. Expected results A new national Health Care plan for the CAR shall be developed, with the HDs being redefined on the basis of Health Care criteria (access to quality healthcare). The HDs shall henceforth have a two-tier level of care provision linked through a system of referrals and counter referrals. The organizational and functional norms for each level of the health care system shall be made explicit, which transfers more responsibility and jurisdiction to the DMTs over the development of these tiers. A development plan for the development of Health Care Human Resources (HHR) shall be prepared and implemented, which makes it possible to resolve the qualitative and quantitative insufficiency at the HD level. The RMTs shall have a wider mandate and have sufficient resources to assist the HDs in their development. The activities that are planned in this Program Area are: The preparation of a development plan for human resources for health. – A national policy paper on resource development shall be prepared. This policy shall give a far reaching orientation regarding career planning for health workers, especially with regard to hiring procedures, on the job training, early training opportunities, etc. The preparation of a national policy for developing human resources will require nation-wide and international participation. A workshop to validate this policy shall be organized. This workshop shall be residential and will involve 50 people, lasting 5 days. Finalization of the national health plan. The reform of the health sector engaged by the Ministry through its Sector-wide Strategy shall require a redefinition of the national health plan. This action is in the course of being implemented by the Ministry of Health and Population. However, it will have to be reoriented depending on the new outlook by the Ministry concerning the organization of the HDs. A national consultation shall be necessary to prepare a preliminary plan. An international consultancy will help to improve the quality of the work before it is validated on the occasion of the national 5-day workshop. Preparation of the organizational and functional norms of each level of the health care system. – the organizational and functional norms for the peripheral, intermediary and central levels shall be developed. As for the Development Plan for the HHR, three validation workshops for the norm-setting documents shall be organized (one workshop per level). A national and international consultancy shall also be necessary. Organization of the meetings of the National Steering Committee. – a meeting of the National Steering Committee for the Sector-wide Strategy shall be organized every two months during the first year and every three months the other years of implementation of the proposal. Training of the Regional Management Teams. – four members of the Regional Management Teams (RMT) shall be trained in matters relating to planning, monitoring & evaluation, health information management and supervision of the HD activities in each of the Health Regions, for a total of 8 people to train for the two targeted Health Regions. This training shall be extended to three other RMTs where there is the highest need for training, which amounts to a total of 20 people in the program (5 RMTs to train with 4 people in each of them). This training shall be done in a workshop moderated by central level managers and supported by international consultants as the need may be. Supervisory support to the HD activities. – the 5 HDs targeted in the proposal shall be supervised two times per year by the Regional Management Teams in the Health Regions in question. In total, the number of such supervisory visits shall be 40 during the implementation of the proposal. Organization of the annual reviews of the sector. - an annual review of the Health Care sector shall be organized during the first trimester of each year. They shall serve as the context in which to draw lessons from the programmed actions in the sector (by the MPHP and its partners) in the course of the previous year. They shall bring together participants from the Ministry of Health from the central, regional and peripheral levels. These reviews shall be an opportunity to evaluate the implementation of the activities of the CAR’s GAVI-HSS proposal as well as that of other programs that have been financed either by the Government, or else by donors. They shall take place in residential workshops lasting 5 days. Rationalization of Health Care financing Expected results A basket fund is established in each of the targeted Health Regions (2 & 4), and it is progressively added to by the different financial backers (Government, donors including the Global Fund to Fight Aids, Tuberculosis and Malaria). The resources that are required for the development and operation of the HDs so as to offer quality health services (effective, integrated, universal, efficient, etc.) are available from this source. The Management Committees (COGES) become proficient in management and produce funds for the purchase of stock materials for vaccination including fuel. Since the area related to building the operational capacity of the HDs already covers the strengthening of the DMT capacities in questions of management, and of the operational capacity of the COGES, there is only a single activity that is planned as part of the rationalization of Health Care financing. This is the establishment of a ‘basket fund’ for each of the targeted regions. This activity shall require assistance from international technical advisors over the short-term to determine the status of these ‘Basket funds’ as well as the manner in which they are managed.

# Section 6: Monitoring, Evaluation and Operational Research

To the applicant

- All applications must include the three main GAVI HSS impact / outcome indicators:

- National DTP3 coverage (%)

- Number / % of districts achieving ≥ 80% DTP3 coverage

- Under five mortality rate (per 1000)

- Please list up to three more impact / outcome indicators that can be used to assess the impact of GAVI HSS on improving immunization and other child and maternal health services.

Note: It is strongly suggested that the chosen indicators are linked with proposal objectives and not necessarily with activities.

- For all indicators, please give a data source, the baseline value of the indicator and date, and a target level and date. Some indicators may have more than one data source (Table 6.1).

Note: The chosen indicators should be drawn from those used for monitoring the National Health Sector Plan (or equivalent) and ideally be measured already (i.e. not an extra burden to measure). They do not have to be GAVI HSS specific. Examples of additional impact and outcome indicators are given in the tables below. It is recommended that when activities are implemented primarily at sub-national level that indicators are monitored, to the extent possible, at sub-nationally as well.

Examples of impact indicators

- Maternal mortality rate

Example of outcome indicators

- National measles coverage

- Proportion of districts with coverage at 80% or above

- Hib coverage

- HepB coverage, BCG coverage

- DTP1-DTP3 drop-out rate

- Proportion of births attended by skilled health personnel

- Antenatal care use

- Vitamin A supplementation rate

| Intervention | Possible indicators |
| --- | --- |
| Immunization | National measles coverage; proportion of districts with coverage at 80% or above; BCG coverage; Polio 3 coverage; Hib coverage; HepB3 coverage |
| Maternity care | Antenatal care use; skilled birth attendance; tetanus toxoid 2 or more doses; caesarean section rate; postnatal care |
| Family planning | Contraceptive use among women |
| Treatment of sick children | oral rehydration therapy and continued feeding for children with diarrhoea; Care seeking for pneumonia; Antibiotic treatment for pneumonia |
| Nutrition | Breastfeeding rate; (start on first day, exclusive at 0-3 montsh, supplements at 6-9 montsh); vitamin A supplementation rate to children 6-59 montsh (within last 6 montsh) and postpartum to mother within 8 weeks |
| Water/sanitation | Access to safe water source; adequate sanitary facilities |
| Tuberculosis | DOTS treatment coverage (treatment success rate times case detection rate) |
| Malaria | Children with fever receiving anti-malarials; children sleeping under ITN |
| AIDS | % of HIV-positive pregnant women receiving ARVs; PMTCT among pregnant women |

To the applicant

- Please list up to 6 output indicators based on the selected activities in section 5. (Table 6.2).

- For all indicators, please give a data source, the baseline value of the indicator and date, a target level and date, as well as a numerator and denominator. Some indicators may have more than one data source (Table 6.1).

Note: Examples of output indicators that could be used, with the related numerator, denominator (if applicable) and data source are shown below. Existing sources of information should be used to collect the information on the selected indicators wherever possible. In some countries there may be a need to carry out health facility surveys, household surveys, or establish demographic surveillance. If extra funds are required for these activities, they should be included.

Examples of output indicators

| Indicator | Numerator | Denominator | Data Source |
| --- | --- | --- | --- |
| Systematic Supervision | Number of health centres visited at least 6 times in the last year using a quantified checklist | Total number of health centers | Health facility inventory |
| Knowledge of Health Care Workers | Mean score of health workers in public and NGO health centres on verbal knowledge test including case scenarios |  | Health facility inventory |
| Drug availability index | Average number of ten selected essential drugs that are in stock in sampled health centres |  | HMIS & and Health Care facility inventory |

## 6.1: Impact and Outcome Indicators

| Indicator | Data Source | Baseline value | Source | Date of Baseline | Target | Target Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National DTP3 coverage (%) | EPI annual report | 45.6% | EPI annual report | 2005 | 80% | 2011 |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | EPI annual report | 5 | EPI annual report | 2005 | 100% | 2011 |
| 3. Under five mortality rate (per 1000) | Multi-indicator survey (MICS3) | 176 | Multi-indicator survey (MICS3) | March 2007 | 140 | 2013 |
| 4. Rate for childbirth assisted by qualified personnel | Multi-indicator survey (MICS3) | 53.4% | Multi-indicator survey (MICS3) | March 2007 | 70% | 2011 |
| 5. Number of HDs where at least 70% of the population has access to health care services within a 5 Km radius. | Situation report for the targeted HDs | Not available | Situation report for the targeted HDs | 2008 | 5, or 100% | 2011 |
| 6. Maternal mortality rate (per 100 000 live births) | General population and household census. | 1355 | General population and household census. | December 2003 | A 20 % reduction relative to the value to be published in the final MICS3 report | 2013 |

## 6.2: Activity indicators

| Indicators | Numerator | Denominator | Data source | Baseline value | Source | Date of Baseline | Target | Target date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. % of Health Centers that have been upgrade and/or built | Number of HCs and HPs that have been upgraded and/or built | Number of HCs and HPs that have been upgraded and/or built | Annual report on the implementation of the proposal |  |  |  | 60 HC/HPs were upgraded and/or built | 2011 |
| 2. Number of persons who received training in the Health Centers | Number of persons who received training in the Health Centers | Number of persons who received training in the Health Centers | Annual report on the implementation of the proposal |  |  |  | 100 Health Care workers received training | End of 2008 |
| 3. Number of HD managers to have received training in primary care management | Number of HD managers to have received training in primary care management | Number of HD managers to have received training in primary care management | Annual report on the implementation of the proposal |  |  |  | 20 HD Managers received training | End of first quarter 2008 |
| 4. Proportion of Health Centers who have received at least 6 official visits in the course of the past year, in which a quantified control checklist was used | Number of Health Centers who have received at least 6 official visits in the course of the past year, in which a quantified control checklist was used | Number of Health Centers who have received at least 6 official visits in the course of the past year, in which a quantified control checklist was used | Annual report on the implementation of the proposal |  |  |  | All of the Healthcare Centers in the supported HDs are supervised 4 times per year. | 2011 |
| 5. % of persons hired as Health Care workers under contract for the HCs and HPs | Number of persons hired and paid | Number of persons to be hired | Annual report on the implementation of the proposal |  |  |  | 60 Health Care workers are hired and paid | 2008 |
| 6. % of District Hospitals receive regular supplies of essential medicines | Number of HDHs listed for receiving essential medical supplies | Number of HDHs receiving regular supplies of essential medicines | Annual report on the implementation of the proposal |  |  |  | 5 HDHs have not recorded stock depletion for medication | End of 2011 |

To the applicant

- Please describe how the data will be collected, analyzed and used. Existing data collection and analysis methods should be used wherever possible. Please indicate how data will be used at local levels and ways of sharing with other stakeholders in the last column (Table 6.3).

6.3: Data collection, analysis and use

| Indicators | Data collection | Data analysis | Use of data |
| --- | --- | --- | --- |
| Impact and outcome |  |  |  |
| 1. National DTP3 coverage (%) | Data collection shall be made with the standard information system | The data shall be analyzed by comparing the national figures to the expected results. This analysis shall be repeated for each level of the health care system. | After the analysis of each level, decisions shall be taken and actions undertaken to improve the situation if so required, after which the data shall be sent to the next echelon. Half-yearly reviews shall be organized for an analysis of the situation at the national level with proper lines of actions analyzed. |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | Data collection shall be made with the standard information system | Data for this indicator shall be analyzed at the provincial and national level. The results for the HDs shall be compared to the national figures on the one hand, and on the other, the HDs shall be compared to each other. These data shall be discussed on the occasion of the IACC meetings and the semester EPI reviews. | Once the HDs with problems have been identified, the factors which pertain to the situation at hand shall be the object of research and possible solutions shall be identified and applied where possible. |
| Under five mortality rate (per 1000) | Data collection for this indicator shall use a household survey such as MICS, the Demographic and Health Survey (DHS) or the General and Household Census. The preliminary report for the MICS3 survey shall be performed in 5 years, or one year after the end of the implementation of the GAVI-HSS proposal of the CAR, an ideal period of time for measuring this indicator | The data shall be analyzed using traditional epidemiological data analysis software, such as Epi info, SPSS, etc. | Concerning the HSS proposal from the CAR, the MICS3 and MICS4 data (in 5 years) shall be compared to evaluate the impact of the project on childhood health in the targeted HRs and HDs. . |
| 4. Rate for childbirth assisted by qualified personnel | Data collection for this indicator shall use a household survey such as MICS, the Demographic and Health Survey (DHS) or the General and Household Census. | The data shall be analyzed using traditional epidemiological data analysis software, such as Epi info, SPSS, etc. | Concerning the HSS proposal from the CAR, the MICS3 and MICS4 data (in 5 years) shall be compared to evaluate the impact of the project on maternal health in the targeted HDs. |
| 5. Number of HDs where 70% of the population with access to quality Health Care within a 5 Km radius. | Data collection shall be performed by a survey targeting both the clinics and the households. | The data shall be analyzed using traditional epidemiological data analysis software, as with other indicators measured in the course of this project | The data relating to these indicators, like those of other indicators to be measured, shall first help to better focus the different annual plans for implementing the proposal which will then be used as a reference for the final evaluation. |
| Rate of maternal mortality | Data collection for this indicator shall use a household survey such as MICS, the Demographic and Health Survey (DHS) or the General and Household Census. The preliminary report for the MICS3 survey shall be performed in 5 years, or one year after the end of the implementation of the GAVI-HSS proposal of the CAR, an ideal period of time for measuring this indicator | The data shall be analyzed using traditional epidemiological data analysis software, such as Epi info, SPSS, etc. Once the analysis is finished, the results shall be distributed in a survey report. | Concerning the HSS proposal from the CAR, the MICS3 and MICS4 data (in 5 years) shall be compared to evaluate the impact of the project on maternal health in the targeted HDs. This will make it possible to better match the programs for better performance results in the future. |
| Activity |  |  |  |
| 1. % of Health Centers upgraded and/or built | Data collection relating to this activity shall make use of the standard information system | The analysis shall be made by comparison with the data relative to this activity as set out in this proposal. | The data shall be used to evaluate the work performance and, if required, to program further tasks. |
| 2. Number of persons trained in the Health Centers and Health Posts. | Data collection relating to this activity shall make use of the standard information system | The analysis shall compare the operational goals of the project and the performance thereof | In the course of the year, monthly data shall help to better monitor the evolution of the project and to contribute modifications of the activities if so required. At the end of each year, the data shall be used to evaluate the proposal implementation with regard to the annual action plan, which should help to better orient the actions for the following year’s operational plan. |
| 3. Number of HD managers to have received training in primary care management. | Data collection relating to this activity shall make use of the standard information system | The analysis shall compare the operational goals of the project and the performance thereof | In the course of the year, the monthly data shall help to better monitor the evolution of the project and to contribute modifications of the activities if so required. At the end of each year, the data shall be used to evaluate the proposal implementation with regard to the annual action plan, which should help to better orient the actions for the following year’s operational plan. |
| 4. Number of Health Centers who have received at least 6 official visits in the course of the past year, in which a quantified control checklist was used | Data collection relating to this activity shall make use of the standard information system | The analysis shall compare the operational goals of the project and the performance thereof | In the course of the year, the monthly data shall help to better monitor the evolution of the project and to contribute modifications of the activities if so required. At the end of each year, the data shall be used to evaluate the proposal implementation with regard to the annual action plan, which should help to better orient the actions for the following year’s operational plan. |
| 5. % of persons hired as contracted Health Care worked for the HCs and HPs | Data collection relating to this activity shall make use of the standard information system | The analysis shall compare the operational goals of the project and the performance thereof | In the course of the year, the monthly data shall help to better monitor the evolution of the project and to contribute modifications of the activities if so required. At the end of each year, the data shall be used to evaluate the proposal implementation with regard to the annual action plan, which should help to better orient the actions for the following year’s operational plan. |
| 6. % of District Hospitals receive regular supplies of essential medicines | Data collection relating to this activity shall make use of the standard information system | The analysis shall compare the operational goals of the project and the performance thereof | In the course of the year, the monthly data shall help to better monitor the evolution of the project and to contribute modifications of the activities if so required. At the end of each year, the data shall be used to evaluate the proposal implementation with regard to the annual action plan, which should help to better orient the actions for the following year’s operational plan. |

To the applicant

- Please indicate if the M&E system needs to be strengthened to measure the listed indicators and if so describe which indicators specifically need strengthening. (Table 6.4).

- Please indicate if the GAVI HSS application includes elements of operational research that address some of the health systems barriers to better inform the decision making processes or and to obtain better knowledge of the impact on Health Care.  (tableau 6.5).

6.4: Strengthening M&E system

The health care information system for the CAR present several problems, which can be summarized as follows, taking into account the present context:: The completion rate is generally low. Indeed, in 2004, the completion rate of NSHI reports was 54.6%. The data provided by the NSHI are not always taken into account in the decision-making process in the health care system. Some information that is necessary for the implementation of the proposal is not available (current status of infrastructure and equipment in health clinics, etc.). Therefore the actual performance of the NSHI doesn’t allow for an improved monitoring and proper evaluation of the HSS proposal. To improve this situation and to make the information necessary for implementation, monitoring and evaluation of the proposal available, four actions shall be undertaken: training for information management shall be included in the training programs for the DMTs on managing primary care, as well as that of the RMTs (planning, monitoring, evaluation, supervision and information management) and furthermore, in the different training programs for local Health Care workers (HCs and HPs). Furnishing the necessary tools for information management in the clinics and the DMTs; The organization of annual health sector reviews during which the progress being made regarding barriers in the provision of health care services in general and immunization in particular. Indeed, the review of the programs which are currently being organized in the country only seldom consider questions related to Health Care systems; A survey shall be undertaken at the start and at the end of the GAVI HSS implementation. At the start, the survey shall help generate information that is not currently available (data bases for certain indicators, information concerning infrastructure, equipment in the targeted health clinics). At the end of this implementation, the outcome of the survey shall be the evaluation of the results obtained and the impact of the project on the health care system and the health status in the communities. Among the impact/result indicators that are listed in the proposal, it is worth mentioning the one relating to the ‘number of HDs where at lest 70% of the population has access to quality Health Care within a 5 Km radius’ and for which there is currently no updated data base.

6.5: Operational Research

Development of Pilot Health Districts The organization of HDs in the CAR raises several issues: - the HDs are defined on the basis of administrative criteria as opposed to Health Care, and as a consequence, the country has very spread-out HDs with significant populations contained therein, - the HDs in the CAR have several categories of Health Centers (a total of 5) and Health Posts, which leads to several levels of Health Care provision making referral and counter referral services quite complex and hindering follow-up treatment - the distances that must be covered to supervise the HCs and HPs as well as the number of categories into which they can be separated, make the allocation of resources inefficient from the very start. All of these problems have as a consequence the existing level of operational capacity, which is quite poor in most HDs, leading to the lack, for a substantial part of the population, of quality Health Care provision including immunization. The MPHP has decided to undertake a health care system reform which shall establish a model ‘Health District’ for covering a population of 100 000 to 150 000 inhabitants with a two-tiered system that is linked together through a functional system of referrals and counter-referrals. In order to carry this out, a course of research shall be undertaken in the context of the GAVI HSS proposal from the CAR. This research shall consist in developing two ‘pilot HDs’ out of the 5 targeted in the proposal according to the model determined in the HSS strategic plan. These HDs shall therefore receive a supplementary number of activities relating to this research on operational processes. These initiatives include: - redefining the role and the composition of the DMTs and the purpose of the HDH s, the HCs and HPs, close and frequent monitoring of these HDs by those mandated to carry out the research and also responsible for primary Health Care at the central level of the MPHP, - a national consultation to document this process, - a short-term yearly international consultation to support this process. The variables to be monitored are: the operational capacity of the HDs (including referral and counter referral), the access by the population to quality Health Care, the cost of implementing the findings, the improvement of coverage indicators, the relevance of the research mission and of the current Regional Team, etc. The expected results are: - the average size of the population in relation to the optimal operational capacity of the HDs shall be defined, - the mission of the DMT, the HDH and the HC/HP shall also be redefined, - the relations which need to be fostered between the Health Care institutions in the HD shall be described, - the resources required for the proper operation of the HDs are identified, - the community-based organizations that are required for the proper operation of the HDs are described, - the type of intermediary level support (Regional) which the HDs require for their development shall be know. As we have seen here above, the HDs that are involved in this study are those of Kémo and Mambéré Kadéi. These results shall be used for the preparation/updating of the policies, standards & national strategies.

# Section 7: Implementation Arrangements

To the applicant

- Please describe how the GAVI HSS support will be managed (Table 7.1).  Please also indicate the roles and responsibilities of all key partners in GAVI HSS implementation (Table 7.2).

Note: GAVI encourages aligning GAVI HSS with existing country mechanisms. Applicants are strongly discouraged from establishing a project management unit (PMU) for GAVI HSS. Support for PMUs will only be considered under exceptional circumstances, based on a strong rationale.

## 7.1: Management of GAVI HSS support

| Management mechanism | Description |
| --- | --- |
| Name of lead individual / unit responsible for managing GAVI HSS implementation / M&E etc. | The Director of the Research and Planning Office (DRP) shall be in charge of coordinating GAVI support for the HSS/M&E of the proposal from the CAR. |
| Role of HSCC (or equivalent) in implementation of GAVI HSS and M&E | The National Steering Committee shall be in charge of: Approving the annual implementation plans for the GAVI-HSS proposal from the CAR; Approving the disbursement plans detailed in the proposal ; Ensuring the monitoring of the implement of the proposal during its monthly or bi-monthly meetings, as required; The annual evaluation of the proposal implementation during its annual sector reviews, which it is in charge of organizing; Initiating the audits on the management of financial resources of GAVI-HSS ; Initiating the final evaluation of the GAVI-HSS proposal from the CAR |
| Mechanism for coordinating GAVI HSS with other system activities and programs | The coordination mechanism for GAVI-HSS support with other programs, which shall involve: Organizing bi-monthly meetings during the first year, and quarterly meetings in the second year involving all the health sector stakeholders in order to discuss questions of coherence and relevance with relation to the sector-wide strategy, Organizing the annual reviews of all programs and deciding which future orientation are most necessary to improve performance. Extraordinary meetings of the National Steering Committee shall be organized if required. |

7.2: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organization | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS implementation |
| --- | --- | --- | --- |
| Chief of Cabinet in the Health Ministry | Ministry of Public Health and Population | Yes | 1. Chairs the meetings of the National Steering Committee in the absence of the Minister of Health 2. Organizes the annual health sector reviews, 3. Initiates the annual audits planned as part of this proposal |
| UNICEF Official | United Nations Children’s Fund | Yes | 1. Provides technical and financial support for the activities relating to child survival as contained in this proposal 2. Carrie out financial audits and the same regarding the quality of data about child survival. |
| WHO Official | World Health Organization | Yes | 1. Provides technical support for the preparation of the annual plans for the implementation of the proposal, 2. Support the central level in the preparation of standardized documents required for reform of the Health Care sector 3. Provides technical support during the different evaluation processes of the proposal. |
| UNFPA Official | United Nations Population Fund | Yes | 1. Provides technical support and complimentary financial assistance for the reproductive health activities. 2. Performs audits on the quality of the data relating to reproductive health. |
| Health sector Official | European Commission | Yes | 1. Provides technical support (as an international consultant) for resolving technical problems related to the implementation of the proposal. |
| Health sector Official | French Development Agency | Yes | 1. Provides technical support (as an international consultant) for resolving technical problems related to the implementation of the proposal. |

To the applicant

- Please give the financial management arrangements for GAVI HSS support. GAVI encourages funds to be managed ‘on-budget’. Please describe how this will be achieved (Table 7.3).

- Please describe any procurement mechanisms that will be used for GAVI HSS (Table 7.4).

## 7.3: Financial management of GAVI HSS support

| Mechanism / procedure | Description |
| --- | --- |
| Mechanism for channeling GAVI HSS funds into the country | The funds for the GAVI HSS proposal shall be transferred to the country by a bank wire. An account shall be opened to receive the GAVI-HSS financing in the CAR. IT shall be cosigned by the Ministry of Health and the WHO Representative in the CAR. |
| Mechanism for channeling GAVI HSS funds from central level to the periphery | The funds shall be transferred from the central level towards the periphery by bank transfer. The supported Health Regions and HDs shall have bank accounts for the GAVI HSS support. These accounts shall be endorsed by the representatives of the United Nations organisms at the intermediary level, or else by the representatives of the local community associations that participate in the proposal. |
| Mechanism (and responsibility) for budget use and approval | The mechanisms for employing the budget funds and their authorization are described in the paragraphs below. |
| Mechanism for disbursement of GAVI HSS funds | The operational plans shall be prepared by the HDs receiving the GAVI HSS funds. These plans shall be multi-donor plans in which the activity to receive financing shall clearly be designated as per each donor (including GAVI HSS). They shall be drawn up by the immediate superior in Management. At the Regional level, a financial inventory of financing expected from the Government and all of the development partners shall be drawn up (involving all the partners). The harmonization of these activities shall be conducted thereby and the complete budget for the sector shall be prepared including the costs of activities, the resources and the budget gap. The disbursement schedule on all sides shall be discussed. The provincial planning shall be drawn up by the Department of Research and Planning (DRP) for an annual plan. The resulting operating plan must be approved by the National Committee on Sector-wide Strategy. On this basis, there will be a disbursement plan to be established by the DRP and approved in turn by the National Steering Committee. As mentioned above, two signatures shall be necessary for the disbursement of GAVI-HSS funds from the CAR. These are the signatures of the Minister of Health and the WHO representative. Once the budgets have been approved, the funds shall be disbursed for the Health Care institutions that are tasked with implementing the activities contained in the proposal (Health Regions, Health Districts, etc.) The HD of Ouaka may not have a bank account. The funds shall be transferred by an intermediary organism still to be identified. This may be the diocese. Purchases (of medical supplies, computer material, vehicles etc.) shall be the task of UNICEF, which will make bulk purchases. Concerning medication, there will be lines of credit opened for Health Care institutions registered in the Medical Purchasing Unit. It will be responsible for supplying the clinics that are beneficiaries. As regards upgrades and construction, the funds shall be sent to the accounts of the contractors who have won bids. This shall be carried out as per national procedures. The funds that are meant for activities at the central level shall be paid into the account of the National Public Health unit that is to be established with the 9th European Development Fund. |
| Auditing procedures | The audits shall be initiated by the National Steering Committee upon request by one or several members of its offices. The Executive Secretariat of GAVI may also initiate an audit if it deems it necessary. Whatever the organization which has initiated the audit, the results shall be discussed by the Steering Committee for useful resolution thereof. |

## 7.4: Procurement mechanisms

The purchase of medicines, specific products and light material shall be the responsibility of the Medical Purchasing Unit (MPU) which is a buying syndicate. The clinics that shall receive GAVI-HSS support shall have open lines of credit at the MPU and the amounts corresponding to these lines of credit shall be paid to the Syndicate, which shall contribute markedly to the strengthening of its capacity by increasing its turnover rate. The MPU shall announce a public tender for each order. The Health Care institutions shall stock themselves with supplies from the MPU. The different orders incoming from the clinics shall be collected and examined by a member of the DMT with the appropriate expertise. It shall then be approved by the Management Committee (COGES) before being sent on to the MPU. The DMT shall be able to monitor and to rationalize the use of medicines in the clinics. The purchase of medical supplies, computer equipment and a vehicle fleet shall be made via an aggregate order sent on to UNICEF given their expertise in purchasing. On the one hand this will make it possible to negotiate better prices, due to the scale of the orders, ,and on the other, it will ensure the timely delivery of supplies. The supply of material ordered by UNICEF to the clinics shall be made by the traditional supply channels familiar to UNICEF.

To the applicant

- Please describe arrangements for reporting on the progress in implementing and using GAVI HSS funds, including the responsible entity for preparing the APR. (Table 7.5)

Note: The GAVI Annual Progress Report, due annually on 15 May, should demonstrate: proof of appropriate accountability for use of GAVI HSS funds, financial audit and proper procurement (in line with national regulations or via UNICEF); efficient and effective disbursement (from national to sub-national levels; in the context of a Swap mechanism, if applicable); and evidence on progress on whether expected annual output targets and longer term outcome targets are being achieved.

## 7.5: Reporting arrangements

The performance report on the activities of the GAVI-HSS proposal shall come in two parts. The first shall be of a technical nature and the second one financial. On the technical level, each institution that is responsible for the implementation of the activities of the proposal shall prepare a technical report about the activities undertaken in the course of the year. Each report shall be made on the basis of goals that are listed in the annual action plan as approved by the National Steering Committee on the occasion of its health sector annual review meetings. The different reports shall be put together by the Technical Secretariat of the Steering Committee. On the financial level, each institution that is responsible for managing the funds derived from the GAVI-HSS proposal (the central and intermediary levels of MPHP, the organism that channels the funds, the Medical Purchasing Unit, UNICEF, the companies who will have been contracted to undertake work on upgrades and construction, etc.) shall be expected to justify the use of the funds that have been made available to them. The annual reviews shall be held in February and March of each year to allow sufficient time to the Technical Secretariat of the National Steering Committee to prepare the necessary data before the end of April. This should make it possible to distribute the annual report on the implementation of activities contained in the GAVI proposal before May 15, each year. The different reports shall cover the period running from January 1 to December 31. Once the financial and technical reports have been approved by the National Steering Committee for sector-wide strategy, they shall be sent on to the GAVI Alliance by the Minister of Health and Population.

To the applicant

- Some countries will require technical assistance to implement GAVI HSS support. Please identify what technical assistance will be required during the life of GAVI HSS support, as well as the anticipated source of technical assistance if known (Table 7.6).

## 7.6: Technical assistance requirements

| Activities requiring technical assistance | Anticipated duration | Anticipated timing (year, quarter) | Anticipated source (local, partner etc.) |
| --- | --- | --- | --- |
| 1. Drafting of a situation report to define the baselines and for the final evaluation of the proposal implementation | The initial two months at the start of the project and the final two months of its implementation | January and February 2008 November and December 2011 | International Consultation |
| 2. Preparation of a development plan for Health Care human resources | One month | First trimester of 2008 | National/International Consultation |
| 3. Preparation of the organizational and functional norms for each level of the health care system | One month | First trimester of 2008 | National/International Consultation |
| 4. Preparation of the national health plan | One month | First trimester of 2008 | National/International Consultation |
| 5. Establishment of a Health District based on the model defined by the MPHP | Two on-month periods per year | Every 2nd and 4th trimester of the year | International Consultation |
| 6. Establishment of a basket fund for the two targeted provinces | One month per consultation | Two to three short-term consultations in the first year and one consultation the 3rd and 4th year. | International Consultation |

# Section 8: Costs and Funding for GAVI HSS assistance

To the applicant

- Please calculate the costs of all activities for the duration of the GAVI HSS support. Please add or delete rows / columns to give the right number of objectives, activities and years. (Table 8.1)

Note: Please ensure that all support costs for management, M&E, and technical assistance are included. Please convert all costs to US$ (at the current exchange rate), and ensure that GAVI deflators are used for future costs (see guidelines on the GAVI website: www.gavialliance.org).

Note: The overall total request for GAVI HSS funds in table 8.1 should not exceed the overall total of GAVI HSS funds allocated in table 8.2. Funds may be requested in annual trenches according to estimated annual activity costs. These may vary annually from the allocation figures in table 8.2.

8.1: Cost of implementing GAVI HSS support activities

| Area of support | Cost per year in USD |
| --- | --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | Year 5 of implementation | TOTAL COSTS |
|  | 2007 | 2008 | 2009 | 2010 | 2011 |  |  |
| Activity costs |  |  |  |  |  |  |  |
| Program Area I |
| Construction and/or upgrade of the HCs and HPs |  | 210 000 | 140 000 | 70 000 |  |  | 420 000 |
| Furnishing the HCs and HPs with medical supplies and a cold chain |  | 180 000 | 120 000 | 60 000 |  |  | 360 000 |
| Supplying the HCs and HPs with essential medicine and specific products |  | 80 000 | 40 000 |  |  |  | 120 000 |
| Organizing the training/refresher courses of Health Care personnel in the clinics |  | 28 000 | 14 000 | 28 000 |  |  | 70 000 |
| Training the HD managers in HD management |  | 90 000 |  |  |  |  | 90 000 |
| Organizing the training/refresher courses of the DMTs for the pilot HDs |  | 30 000 |  |  |  |  | 30 000 |
| Organizing the training/refresher courses of personnel in the HDHs |  | 42 000 |  |  |  |  | 42 000 |
| Supplying the HDs with a vehicle fleet (4-wheel drives) |  | 150 000 |  |  |  |  | 150 000 |
| Supplying the HDs with computer equipment |  | 15 000 |  |  |  |  | 15 000 |
| Hiring and paying the subcontracted Health Care workers in the HCs and HPs |  | 60 000 | 60 000 | 60 000 | 60 000 |  | 240 000 |
| Supervising the activities in the HCs and HPs |  | 48 000 | 48 000 | 48 000 | 48 000 |  | 192 000 |
| Supplying the HDHs with essential medicine |  | 240 000 |  |  |  |  | 240 000 |
| Supplying the HDHs with medical supplies |  | 300 000 |  |  |  |  | 300 000 |
| Paying performance-award bonuses to active medical personnel |  | 45 000 | 45 000 | 45 000 | 45 000 |  | 190 000 |
| Program Area I subtotal |  | 1 518 000 | 467 000 | 241 000 | 153 000 |  | 2 379 000 |
| Program Area II |
| Preparing a situation report of the sector for the targeted regions |  | 50 000 |  |  | 50 000 |  | 100 000 |
| Preparing a development plan for the HHR |  | 20 000 |  |  |  |  | 20 000 |
| Updating /developing a national health plan |  | 20 000 |  |  |  |  | 20 000 |
| Drafting the organizational and functional norms for each level of the health care system |  | 20 000 |  |  |  |  | 20 000 |
| Organizing the NSC meetings on sector-wide strategy |  | 2 000 | 2 000 | 2 000 | 2 000 |  | 8 000 |
| Organizing the training of the RMTs in planning, monitoring, evaluation & supervision |  | 20 000 |  |  |  |  | 20 000 |
| Support to the supervision of the HDs |  | 20 000 | 20 000 | 20 000 | 20 000 |  | 80 000 |
| Organizing the annual reviews of the Health Care sector |  | 25 000 | 25 000 | 25 000 | 25 000 |  | 100 000 |
| Program Area II subtotal |  | 175 000 | 47 000 | 47 000 | 97 000 |  | 366 000 |
| Program Area III |
| Establishing a ‘basket fund’ for the targeted Regions |  |  |  |  |  |  |  |
| Support costs |  |  |  |  |  |  | 616 960 |
| Management costs |  | 147 760 | 30 720 | 44 800 | 23 680 |  | 246 960 |
| M&E support costs |  | 75 000 | 25 000 | 25 000 | 75 000 |  | 200 000 |
| External audit |  |  | 20 000 | 20 000 | 20 000 |  | 60 000 |
| Technical support |  | 52 000 | 26 000 | 6 000 | 26 000 |  | 110 000 |
| TOTAL COSTS |  | 1 892 760 | 590 720 | 358 800 | 319 680 |  | 3 161 960 |

The cost of establishing the ‘Basket Funds’ is integrated into the costs of international consultation. The management fees shall mainly be used for the Ministry of Health and Population in its management capacity as the monitoring agency for the implementation of the proposal (the Office of Research and Planning at the central level, and the intermediate level in the targeted Health Regions). Among their other tasks, they shall help to strengthen these facilities.

The monitoring & evaluation costs include the annual review and the initial situation report (ex ante evaluation) in addition to the final evaluation (ex post evaluation) which shall be undertaken. This cost is already included among the activities relating to the providing guidance to the health care system.

To the applicant Please calculate the amount of funds available per year from GAVI for the proposed GAVI HSS activities, based on the annual number of births and GDI per capita as follows (Table 8.2): If GDI < $365 per capita, country is eligible to receive up to $5 per capita If GDI > $365 per capita, country is eligible to receive up to $2.5 per capita Note: The following example assumes the birth cohort in the year of GAVI application is 100,000, and gives the total fund allocations if the GDI < $365 per capita and if the GDI > $365 per capita.

Examples: GAVI HSS country allocation calculation

| GAVI HSS Allocation (GDI < $365 per capita) | Allocation per Year (USD) |
| --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100 000 | 102 000 | 104 000 | 106 000 |  |
| Allocation per newborn | 5 USD | 5 USD | 5 USD | 5 USD |  |
| Annual allocation | 500 000 USD | 510 000 USD | 520 000 USD | 530 000 USD | 2 060 000 USD |

| GAVI HSS Allocation (GDI > $365 per capita) | Allocation par Year (USD) |
| --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100 000 | 102 000 | 104 000 | 106 000 |  |
| Allocation per newborn | 2,5 USD | 2,5 USD | 2,5 USD | 2,5 USD |  |
| Annual allocation | 250 000 USD | 255 000 USD | 260 000 USD | 265 000 USD | 1 030 000 USD |

## 8.2: Calculation of GAVI HSS country allocation

| GAVI HSS Allocation | Allocation par Year (USD) |
| --- | --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | Year 5 of implementation | TOTAL FUNDS |
|  | 2007… | 2008… | 2009… | 2010… | 2011… | 20… |  |
| Birth cohort | 147582 | 150583 | 153650 | 156780 | 159978 |  |  |
| Allocation per newborn |  | 5 USD | 5 USD | 5 USD | 5 USD |  |  |
| Annual allocation |  | 752915 | 768250 | 783900 | 799890 |  | 3 104 955 |

Source and date of GDI and birth cohort information.

GDI:	USD 33I per inhabitant and per year

Birth cohort: sources; Complete Multi-Year Immunization Plan 2007-2011

All other:

To the applicant

Note: Table 8.3 is not a compulsory table.

- Please endeavor to identify the total amount of all expected health system strengthening related spending in the country during the life of the GAVI HSS application (Table 8.3).

Note: Please specify the contributions from the Government, GAVI and the main funding partners or agencies. If there are more than four main contributors, please insert more rows. Please indicate the names of the partners in the table, and group together all remaining expected contributions.  Please indicate the source of the data (Public Expenditure Review, MTEF, donor reports etc).

8.3: Sources of all expected funding for health systems strengthening activities

| Funding Sources | Allocation per Year (USD) |
| --- | --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | Year 5 of implementation | TOTAL FUNDS |
|  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |  |
| GAVI Alliance |  | 1 892 760 | 590 720 | 358 800 | 319 680 |  | 3 161 960 |
| Government |  | 10 719 500 | 15 450 200 | 20 763 200 | 26 474 800 |  | 73 407 700 |
| WHO |  | 281 000 | 281 000 | 292 240 | 292 240 |  | 1 146 480 |
| European Union (9th EDF) |  | 3 182 500 | 3 182 500 | 3 182 500 | 3 182 500 |  | 12 730 000 |
| UNICEF |  | 945 000 | 945 000 | 945 000 | 945 000 |  | 3 780 000 |
| UNFPA |  | 2 067 143 | 2 142 000 | 1 195 286 | 1 184 314 |  | 6 588 743 |
| World Bank |  | 869 000 | 1 104 000 |  |  |  | 1 973 000 |
| French Development Agency |  | 6 488 454 | 962 669 | 461 692 |  |  | 7 911 816 |
| Arab Bank for Economic Development in Africa |  | 1 665 000 | 1 665 000 |  |  |  | 3 330 000 |
| All Others |  |  |  |  |  |  |  |
| TOTAL FINANCING |  | 28 110 357 | 26 323 089 | 27 198 718 | 32 398 534 |  | 114 030 698 |

Source of information on funding sources:

| Donors | Sources of information |
| --- | --- |
| GAVI Alliance | HSS application from the CAR |
| Government | Public budget for health and mid-term expenditure framework |
| WHO | Cooperation strategy WHO-CAR 2008-2013 |
| European Union (9th EDF) | Final report on the feasibility study on the 9th EDF Health Care program |
| UNICEF | Annual action plan of UNICEF |
| French Development Agency | Final report on the feasibility study – CAR Health Program DP N° AFD/TDH/SAN 2005/01, volume 3 |
| Arab Bank for Economic Development in Africa | Loan agreement between the CAR and ABEDA, June 2007 |
| World Bank | Agreement regarding the modifications and redrafting of the development credit agreement between the CAR and the International Development Association, June 2007 |
| UNFPA | Action Plan for the 2007- 2010 Country Program between the CAR and the UNFPA |

# Section 9: Endorsement of the Application

To the applicant

- Representatives of the Ministry of Health and Ministry of Finance, and the Chair of the Health Sector Coordinating Committee (HSCC), or equivalent, should sign the GAVI HSS application.

- All HSCC members should sign the minutes of the meeting where the GAVI HSS application was endorsed. This should be submitted with the application (numbered and listed in Annex 1).

- Please give the name and contact details of the person for GAVI to contact if there are queries.

Note: The signature of HSCC members represents their agreement with the information and plans provided in this application, as well as their support for the implementation of the plans. It does not imply any financial or legal commitment on the part of the partner agency or individual.

Section 9.1: Endorsement by the Government

The Government of the Central African Republic promises to provide vaccination services as well as long-term mother and child health care services.  The effectiveness of the health care system strengthening shall receive a yearly evaluation that is transparent. The Government solicits from the partners of the GAVI Alliance to contribute financial aid in support of the health care system strengthening as it is described in this application.

| Minister of Health | Minister of Finance |
| --- | --- |
| Name: Dr. Bernard LALA | Lieutenant Colonel Sylvain NDOUTINGAI |
| Title/Position: Minister of Public Health and Population | Title/Position: Minister of Finance, Mines, Energy and Hydraulic Resources |
| Signature: NT: ministerial stamp y signature | Signature: NT: ministerial stamp y signature |
| Date: October 3, 2007 | Date: October 3, 2007 |

9.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent

Members of the Health Sector Coordination Committee or equivalent endorsed this application at a meeting on October 3, 2007. The signed minutes are attached as Annex 6.

| Members of the National Steering Committee for the Reform of the Health Care System (Names) | Position / Organization | Signature |
| --- | --- | --- |
| Dr Valentin Goana | Chief of Cabinet of the Ministry of Public Health and Population | NT Signed; dated October 3, 2007 |
| Mahimbo Mdoe | Representative of UNICEF/CAR | NT Signed; dated October 3, 2007 |
| Dr Leódégal Bazira | Representative of the WHO/CAR | NT Signed; dated October 3, 2007 |
| Dr Pierre-Yves Lambert | Representative of the European Commission in the CAR | NT Signed; dated October 3, 2007 |
| Dr Michel Kosh Komba | Representative of ASSOMESCA | NT Signed; dated October 3, 2007 |
| Basile O. Tambashe | Representative of UNFPA | NT Signed; dated October 3, 2007 |

9.3: Person to contact in case of enquiries:

Name:   Philemon Mbessan  			Title: Director of Research and Planning

Tel No:  00 236  04  71  90			Address: BP 883 Bangui CAR

Fax No.

Email: mbessanp@yahoo.fr

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application

To the applicant:

- Please number and list in the table below all the documents submitted with this application.

Note: All supporting documentation should be available in English or French, as electronic copies wherever possible. Only documents specifically referred to in the application should be submitted.

| Document (with equivalent name used in-country) | Available (Yes/No) | Duration | Attachment Number |
| --- | --- | --- | --- |
| National Development Plan for Health Care in the CAR 2006-2015 | Yes | 2006-2015 | 1 |
| Strategic Plan for Strengthening the Health Care System | Yes |  | 2 |
| Complete Multi-Year Immunization Plan | Yes | 2007-2011 | 3 |
| Mid-Term Expense Framework | Yes | 2008- 2010 | 4 |
| Poverty Reduction Strategy Paper8 | Yes | 2007- 2015 | 5 |
| Minutes of the HCSS Meeting, signed by the President of the HCSS | Yes |  | 6 |
| Map of Health Service Provision in the CAR | Yes |  | 7 |
| Action Plan for Country Programs 2007- 2010 between the CAR and UNFPA | Yes |  | 8 |
| Rapid evaluation of the capacities of the Health Districts (Health Care prefecture) for full-scale implementation of Health Care needs | Yes |  | 9 |
| Cross-sector emergency assistance to the Health Care, education and HIV/AIDS sector | Yes |  | 10 |
| Preliminary Report of the multiple-indicator Survey on the monitoring of children of women (MICS3) | Yes |  | 11 |
| Interim Report of the mission to support the preparation of the HSS proposal of the CAR. | Yes |  | 12 |
| National Health Care Policy project of the CAR | Yes |  | 13 |
| Final report on the feasibility study regarding actions targeting the Health Care sector in the CAR with financing from the 9th EDF | Yes |  | 14 |
| Mission of the Arab Bank for Economic Development in Africa (ABEDA) in the CAR | Yes |  | 15 |
| Final report on the feasibility study of the Health Care program of the CAR, volume I | Yes |  | 16 |
| Final report on the feasibility study of the Health Care program of the CAR, volume II | Yes |  | 17 |
| Final report on the feasibility study of the Health Care program of the CAR, volume III | Yes |  | 18 |

# Footnotes

The minutes of the HSCC meeting about assistance from HSS, including the minutes  on the meeting during which the proposal was endorsed, must be joined to the application, as support documents. The minutes must be signed by the president of the HSCC. The minutes detailing the adoption of this proposal for GAVI assistance to the HSS must be signed by all members of the HSCC.

If the proposal identified activities that are to be implemented at the subnational level, data on these subnational criteria must be provided if they are available. These data must be provided in addition to national data.

Population Projection according to the General Survey on Population and Households, 2003

Estimated GDP for the month of August 2007 instead of the Gross Domestic Income which is not available. The GDP is documented in the report on the Mid-Term Expense Framework.

MICS3, 2007.

Ministry of Health, Complete Multi-Year Immunization Plan, April 2007

Budget forecast for 2006

In the course of the last three years.

The map showing distribution of health care services exists in draft form. Its completion shall be undertaken with GAVI financial support.

Ministry of Public Health and Population2004, Projet de Politique Nationale de Santé de la CAR

Ministry of Health 2007, Strategic Health System Strengthening plan

Ministry of Public Health and Population 2007, Interim report on the evaluation of the capacity of Health Districts in carrying out large scale priority health care provision, page 23

Ministry of Public Health and Population, 2007, complete Multi-Year Plan for Immunization, page 17

Ministry of Public Health and Population, 2007, complete Multi-Year Plan for Immunization, page 20

Interim report on the assistance mission to the rapid development of the HSS proposal for the CAR, Université Libre de Bruxelles.

The NHDP, the cMYP, the Interim report on the evaluation of the capacity of Health Districts in carrying out cMYPI, the interim report on the evaluation of the capacity of the HDs in carrying out priority leath care provision and the report on the mission undertaken by Jean Macq  (Université Libre de Bruxelles) in January of 2007 to prepare the evaluation of the GAVI-HSS proposal for the CAR recognize that the complexity of the peripheral health system in the CAR has no added value regarding its capacity to provide health care to the population.

Ministry of Public Health and Population 2006, NDPH of the CAR, page, 38

Ministry of Pubic Health and Population 2007, complete Multi-Year Plan for Immunization, page 20

Final report on the feasibility study for the Health Care project in the CAR, general context, Volume 1, page 14

Ministry of Public Health and Population, 2006, National Development Plan for Health Services (NDPH),  page 36

Ministry of Public Health and Population 2006, National Health Care Development Plan 2006-2015, page 41

Ministry of Public Health and Population 2007, Health System Strengthening Strategy, CAR

Ministry of Health, National Health Care Development Plan 2006- 2015, page 34.

Ministry of Public Health and Population2006, Health System Strengthening Strategy of the CAR

‘Assistance for the development of a HD’ means assitance which aims to improve the total service base for basic services. It is different from vertical services which seek to manage a single disease.

Final feasibility report on a health sector program in the CAR financed by the 9th EDF

Results from the General Population and Household Census, December 2003.

The country has a service provision map which shall be completed on the occasion of the  implementation of the GAVI HSS application from the CAR.

We have preferred to work with the concept of a ‘Program Area’ rather than with objectives, because the proposal we have submitted only contain one specific objective and therefore all the activities contribute to its development.

Si le nombre de districts est fourni, alors le nombre total de districts dans le pays doit être fourni aussi.

if the baseline data is not available, please indicate whether it is intended to collect such data and when this will be undertaken.

This information is important for providing easier access to data and to check it against the records.

The target date for measuring the impact indicators is set for 2013, or two years following the date set for the end of the project in 2011. For indicators obtained from the results the target date is the same as the project end date (proposition GAVI-RSS).

The data relating to this indicator are the same as for routine EPI, the baseline values are those for 2005 given that 2006 a program for accelerated routine EPI improved all immunization coverage data. The monitoring of this indicator in the context of this proposal shall only take into account the data relating to routine immunization. In addition to the values listed in this table are national, while in the framework for the proposal the targets shall be broken down into HDs, each one of them being targeted for a 80% child DTP3 immunization rate.

Ibid point 26.

The preliminary report of the 3rd multi-indicator survey (MICS3) has just been distributed as of the month of March of the current year.

There are no recent data corresponding to this indicator, 2000 being the year of the last available data. A sector-wide situation report in the targeted HDs shall be undertaken before the initiation of the activities implementation of the proposal to get the current baseline data for certain indicators, including the one relating to the access to quality Health Care.

A sector-wide situation report in the targeted HDs shall be undertaken before the implementation of the proposal in order to determine the baseline data of a certain number of indicators and at the end of the projet to evaluate the results obtained from the implementation of the proposal.

The preliminary report on the 3rd multi-indicator survey has not yet included the data related to maternal mortality rate. The data listed in tshi proposal were collected in 2003 (General Population and Household Census).

In table 6.2, given that it lists the indicators pertaining to activities or outcome, the reference baseline value is not extant because the activities will not start until the implementation of the project.  The columns listing values and reference dates are filled with the outcome and impact indicators (tableau 6.1).

if the baseline data is not available, please indicate whether it is intended to collect such data and when this will be undertaken.

The quality standard for health care shall be determined at the central level taking into account, and in the context of, the national situation.

This indicator shall be measured in the initial situation report (determiniation of the baselines) and during the final evaluation.

The amount that the EU allocated to Health Care  via the 0th  EDF is € 7 405 341.It was converted into USD at an exchange rate of 1euro for USD 1.34. An annual avergae was calculated in order to simplify the completion of the table herein.

The UNFPA funds allocated to the health care system especially with regard to reprodcutvei Health Care includes funds allocated for the right against HIV/AIDS not including the health care system. It hasn’t been possible to derive a separate figure for these allocations as yet.

The funds that the French Development Agency shall allocate to the Health Care sector are given in euros. The total amount is for €7 405 341. In order to complete the table, the funds that are to be allocated for the fight against HIV/AIDS especially those for caring for AIDS orphans were deducted from the total budgeted amount, and furthermore, the remaining sum was converted into USD at a rate of 1 euro for 1.34 USD.

If available, please provide the National immunization plan and the financial feasibility plan.

If available, please send us the pages on the Strengthening of the Health Care System and this application for GAVI support to HSS

The map of the health care services is in draft form. Its final publication shall be resumed as per GAVI financing.

# Text boxes

ADMINISTRATIVE AND HEALTH CARE ZONES IN THE CAR

NANA

MAMBERE

OUHAM

PENDDE

OUHAM

MAMBERE

KADEI

SANGHA

MBAERE

VAKAGA

OMBELLA

MPOKO

KEMO

NANA

GREBIZI

HAUTE

KOTTO

HAUT

MBOMOU

BASSE

KOTTO

BAMINGUI

BANGORAN

MBOMOU

OUAKA

LOBAYE

BANGUI

7

CHAD

SUDAN

CAMEROON

DEMOCRATIC REPUBLIC OF CONGO

CONGO

2

1

3

6

4

5

BAMBARI