Application Form for: NIGERIA

GAVI Alliance Health System Strengthening (HSS) Applications

September 2007

An electronic version of this document is available on the GAVI Alliance website (www.gavialliance.org) and provided on CD. Email submissions are highly recommended, including scanned documents containing the required signatures. Please send the completed application to:

Dr Craig Burgess

Senior Programme Officer, HSS

GAVI Alliance Secretariat

c/o UNICEF, Palais des Nations

1211 Geneva 10, Switzerland

Email: cburgess@gavialliance.org

Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. Proposals received after that date will not be taken into consideration for that review round. GAVI will not be responsible for delays or non-delivery of proposals by courier services.

All documents and attachments should be in English or French.  All required information should be included in this application form. No separate proposal documents will be accepted by the GAVI Secretariat. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents may be shared with the GAVI Alliance partners, collaborators and the general public.

Please direct all enquiries to:

Dr Craig Burgess (cburgess@gavialliance.org) or representatives of a GAVI partner agency.

Table of Contents

Page

Abbreviations and Acronyms	3

Application for GAVI Alliance Health System Strengthening Applications

Executive Summary	5

Section 1: Application Development Process	8

Section 2: Country Background Information	14

Section 3: Situation Analysis / Needs Assessment	17

Section 4: Goals and Objectives of GAVI HSS Support	21

Section 5: GAVI HSS Activities and Implementation Schedule	23

Section 6: Monitoring, Evaluation and Operational Research	28

Section 7: Implementation Arrangements	37

Section 8: Costs and Funding for GAVI HSS	43

Section 9: Endorsement of the Application	52

Annexes

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application	54

ANNEX 2 Banking Form	56

# Abbreviations and Acronyms

To the applicant

- Please ensure that all abbreviations and acronyms presented in the application and supporting documents are included here.

ALGON 	Association of Local Governments of NigeriaHH

APR		 Annual Progress Report

ARI 		Acute Respiratory Infection

cMYP 	Comprehensive Multi-Year Plan for Immunisation

CSO 		Civil Society Organisation

DAC 		Development Assistance Committee

DFID 		Department for International Development

DTP 		Diphtheria Tetanus and Pertussis

FMOH		Federal Ministry of Health

GAVI 		Global Alliance for Vaccines and Immunisation

GNI 		Gross National Income

HERFON	Health Reform Foundation of Nigeria

HMN 		Health Metrics Network

HPCC		Health Partners Coordinating Committee

HPR		Health Planning and Research

HSCC 	Health Sector Coordination Committee

HSF		HEALTH SYSTEM FORUM

HSS		Health Systems Strengthening

HSS 		Health System Strengthening

ICC 		Inter-Agency Coordinating Committee for Immunisation

IRC 		Independent Review Committee

ISS 		Immunisation Services Support

JRF		WHO - UNICEF Joint Reporting Form

LEEDS	LGA Economic Empowerment and Development Strategy

LGA 		Local Government Authority

M&E 		Monitoring and Evaluation

MDG 		Millennium Development Goal

MOF 		Ministry of Finance

MOH 		Ministry of Health

MTEF 		Medium Term Expenditure Framework

NACA		National Agency for Control of AIDS

NDHS		National Demographic Health Survey

NEEDS	National Economic Empowerment and Development Strategy

NGO 		Non Governmental Organisation

NHMIS 	Health Management Information System

NICS		National Immunization Coverage Survey

NPHCDA	National Primary Health Care Development Agency

OECD 	Organisation for Economic Co-operation and Development

PHC		Primary Health Care

PHC		PRIMARY HEALTH CARE

PMU 		Project Management Unit

PRSP 	Poverty Reduction Strategy Paper

RED 		Reach Every District

SEEDS	State Economic Empowerment and Development Strategy

SMOH	State Ministry of Health

SOWC	State of the World’s Children

SWAp 	Sector Wide Approach

UNICEF 	United Nations Children’s Fund

USAID 	United States Agency for International Development

WB 		World Bank

WDC		Ward Development Committee

WHO 		World Health Organisation

WHS		Ward health System

# Executive Summary

To the applicant

- Please provide a summary of the proposal, including the goal and objectives of the GAVI HSS application, the main strategies/activities to be undertaken, the expected results, the duration of support and total amount of funds requested and the baseline figures and targets for the priority indicators selected.

- Please identify who took overall responsibility for preparing the GAVI HSS application, the role and nature of the HSCC (or equivalent), and the stakeholders participating in developing the application.

Nigeria is the most populous country in Africa with a population of approximately 140 million inhabitants (Census, 2006). The population is predominantly young with approximately 45% under 15 years of age, 20% under 5years while women of child bearing age (15-49 years) account for 22% of the total population. With a per capita GNI of US$640, Nigeria has about 57% of its population living below $1 per day.

The performance of Nigeria’s health system declined appreciably in the closing decade of the last century resulting in poor health outcomes however, recent assessments have shown that maternal mortality ratio has improved from 948/100,000 in 2003 to 800/100,000 in 2006. However under five mortality rate has shown marginal improvement from 230/1000 live births in 1990 to 194/1000 live births in 2005 and infant mortality rate has improved from 120/1000 live births in 1990 to 100/1000 live births in 2005.(UNICEF State of the world children 2007).  There is also a remarkable improvement in the DPT3 coverage from 37.5% in 2005, to 77% in 2006. (JRF 2005 & 2006) This remarkable improvement in DPT3 coverage is as a result of a combination of the Immunization Plus Days (IPDs) and the acceleration of the reach every ward (REW).

In spite of these modest achievements, the health system still faces major challenges such as inadequate funding, shortage and mal-distribution of human resource for health, general infrastructural decay, lack of harmonized and efficient logistics system and a weak national health management information system as well as inefficient health programme management.

The health sector reform programme of 2004 – 2007 was designed to address the weak health system in order to meet the MDGs. In spite of the increase in government funding and support from development partners, funding gap remains a major challenge.

The Goal of the GAVI HSS application is to strengthen the National health system and reposition it to deliver effective, efficient and sustainable health services.

The General objective is to develop the Ward Health System in 960 wards to deliver PHC services based on minimum health care package by 2010.

Specific objectives include:

- To re-vitalise the Ward Development Committees in the selected 960 wards

- To rehabilitate and equip 960 health facilities (1/ward) to deliver PHC minimum health package

,

    - To train and retrain PHC workers in those 960 wards on managerial capacity, and technical skills for integrated service delivery by 2010.

    - To strengthen the NHMIS for programme monitoring and management in 100 LGAs by 2010.

    - To strengthen the logistics system and infrastructure at the National/State/LGA/Ward levels by the end of 2010

The following strategies will be used to achieve the above objectives:

- Infrastructural development to support the ward health system

- Capacity building to deliver quality PHC services

- Data management for informed decision making

- Harmonization of health commodities distribution.

The scope of the activities will cover 960 wards (10% of total wards in the country) which will be selected by a combination of high performing wards (low proportion of un- immunized children) and low performing wards (high proportion of un- immunized children)

The expected result will be as follows:

- Improved access to and utilization of PHC services in targeted wards

- Increased technical and managerial capacity of PHC workers to deliver quality health service

- Improved data management and use of data for planning, programme monitoring and decision making

- A unified effective and efficient health commodity procurement and distribution system established

| Indicator | Data Source | Baseline Value | Target by 2010 |
| --- | --- | --- | --- |
| 1. National DTP3 coverage (%) | NICS (2006) | 36.3% | 80% |
| 2. Number / % of LGAs achieving ≥80% DTP3 coverage | JRF 2006 | 310(40%) | 620(80%) |
| 3. Under five mortality rate (per 1000) | State of the world’s children report ( UNICEF 2007) | 194/1000 | 185/1000 |
| 4.Proportion of birth attended by skilled Health personnel | NDHS(2003) | 36.3% | 60% |
| 5.Antenatal care up take/proportion of women attending antenatal clinic | UNICEF State of the world children(2007);women &children | 58% | 70% |
| 6.T.T 2+ coverage | UNICEF state of the world children (2007) | 51% | 65% |

This proposal which covers a period of 3yrs from 2008 – 2010 has been developed to be consistent with the comprehensive multi-year plan 2006 - 2010. The cost of achieving the above objectives over the stated period is US$44,703,365 with Baseline assessment cost of US$158,731

The proposal was developed by a Committee made up of FMOH, FMOF and development partners set up by the Honourable Minister of Health. The Committee was chaired by the Head, Health Planning Research and Statistics Department of the Federal Ministry of Health. It was reviewed severally by the Health Sector Forum (HSF) and has been formally endorsed by the Health Partners Coordinating Committee (HPCC) for submission.

# Section 1: Application Development Process

To the applicant

In this section, please describe the process for developing the GAVI HSS application.

- Please begin with a description of your Health Sector Coordinating Committee or equivalent (Table 1.1).

## 1.1: The HSCC (or country equivalent)

Name of HSCC (or equivalent): Health Partners Coordinating Committee (HPCC) …………………………………………………………………………………………………………………

HPCC operational since: 1999

Organisational structure (e.g., sub-committee, stand-alone): Stand alone committee headed by the Honourable Minister of Health. It has Subcommittees that coordinates health programmes such as Immunization, HIV/AIDS, Roll Back Malaria, Tb/Leprosy, Avian Influenza and Health system forum

Frequency of meetings: Quarterly. (Pls attach all minutes of previous meetings)

Overall role and function: Coordinates the roles and activities of Government and Development Partners active in specific programmes within the health sector e.g. Immunization, Malaria, HIV/AIDS, TB, Onchocerciasis, IMNCH, Guinea worm etc Review reports of priority health programme performance at all levels of the health sector and takes decisions that will be jointly implemented

To the applicant

- Next, please describe the process your country followed to develop the GAVI HSS application (Table 1.2)

## 1.2: Overview of application development process

Who coordinated and provided oversight to the application development process? FMOH, Department of Health Planning, Research and Statistics (HPRS)

Who led the drafting of the application and was any technical assistance provided? The Head, Department of HPRS, FMOH as the Chairman of the proposal development committee.

Give a brief time line of activities, meetings and reviews that led to the proposal submission. July 2006 : Honourable Minister of Health constituted the HSS proposal drafting committee sequel to ICC recommendation August 2006 : WHO HQ and AFRO gave technical assistance to the committee for 1 week to assist in reformatting the NPI 2006-2010 strategic plan into a cMYP 2006 – 2010 January 2007 : ICC approved the timeline proposed by the drafting committee February 2007: HSF Reviewed the initial draft and recommended that FMOH should assume leadership of the drafting committee with support from all the HSF partner agencies in line with GAVI guidelines. . February 2007 : FMOH (Department of HPRS) formally assumed the leadership of the HSS drafting committee February 2007 : Received inputs from USAID/IMMUNIZATIONbasics Washington DC March 2007 : Committee had a one week retreat with the support of WHO and draft 1 was produced March 2007 : Draft proposal reviewed at HPCC and endorsed for submission to GAVI after corrections and input from HSF March 2007: Review of draft 1 at WHO regional workshop in Ouagadougou. Observations and suggestions arising from the review necessitated more inputs and change in submission date to October 2007 April 2007: Review of new timeline for submission of application. June 2007: Review of HSS Plan of Action for the development of a new draft using the new application form and guidelines. July 2007: Committee held a ten day retreat with technical assistance by a health systems consultant. September 6th 2007: Committee held a meeting in which decisions were taken on urgent steps to get inputs from CSOs, LGAs, States and stakeholders in the HSS application draft. September 16th 2007: Committee reviewed draft proposal and distributed draft to HSF for review on the 21st of September 2007 September 21st 2007 : HSF Reviewed the proposal and made further comments and observations September 24th 2007 : A select group of the Committee had a 5 day sitting and incorporated comments and observations of the HSF into the proposal document for review in their next meeting September 28th 2007 : Final review of draft by HSF October 2nd – 4th 2007: Endorsement of the proposal by the Hon. Ministers of Health and Finance. October 4th 2007: Submission of the proposal to GAVI Secretariat. Pls provide documents to support all meeting and activities listed above

Who was involved in reviewing the application, and what was the process that was adopted? ICC, HSF, HPCC were involved in the review of the proposal at various stages of development. The process that was adopted involved draft copies sent to members for comments and inputs. Such comments and inputs were thereafter discussed at plenary sessions of meetings. Feedback was sent to the HSS proposal drafting committee members for incorporation into the proposal. Review of draft proposal was also carried out by USAID/IMMUNIZATIONbasics, Washington DC through Technical cooperation.

Who approved and endorsed the application before submission to the GAVI Secretariat? Honourable Minister of Health on behalf of the HPCC

To the applicant

- Please describe overleaf the roles and responsibilities of key partners in the development of the GAVI HSS application (Table 1.3).

Note: Please ensure that all key partners are included; the Ministry of Health; Ministry of Finance; Immunisation Program; bilateral and multilateral partners; relevant coordinating committees; NGOs and civil society; and private sector contributors. If there has been no involvement of civil society or the private sector in the development of the GAVI HSS application, please explain this below (1.4).

## 1.3: Roles and responsibilities of key partners (HPCC members and others)

| Title / Post | Organisation | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| Hon. Minister | Federal Ministry of Health | Yes | Inaugurated the proposal drafting Committee. Chairs the Health Partners Coordination Committee. Gives final endorsement of the proposal before submission |
| Hon. Minister | Federal Ministry of Finance | NO | Sent a technical person that was involved in the proposal drafting committee. Endorses the final proposal |
| Director Health Planning and Research | Federal Ministry of Health | Yes | Headed and coordinated the activities of the proposal drafting committee. |
| Hon. Minister/Deputy Chairman | National Planning Commission | YES | Member of the HPCC |
| Executive Director | National Primary Health Care Development Agency | Yes | Provided technical staff that participated in the drafting of the proposal Facilitated proposal drafting by providing required logistics support to the Committee. Provided secretarial support to the proposal drafting Committee Member of the HPCC and HSF that reviewed the proposal |
| WHO Representative in Nigeria | Wold Health Organisation | Yes | Provided technical support to the proposal drafting committee on all health matters. Provided logistics support to the Committee Member of the HPCC and HSF that reviewed the proposal |
| Country Representative | UNICEF | Yes | Provided technical support to the proposal drafting Committee. Member of the HPCC and HSF that reviewed the proposal |
| Country Director | World Bank | Yes | Technical support in the area of statistics/demographic information Member of the HPCC and HSF that reviewed the proposal |
| Ambassador and Head of Delegation | EC in NIGERIA | Yes | Technical support through the participation of EU-PRIME technical officers in the Committee. Member of the HPCC and HSF that reviewed the proposal |
| Senior Health Adviser | DFID | Yes | Member of the HPCC and HSF that reviewed the proposal |
| Head of AID | CIDA | Yes | Initiated the HSF Member of the HPCC and HSF that reviewed the proposal |
| Mission Director | USAID | Yes | Technical support to the proposal drafting committee Member of the HPCC and HSF that reviewed the proposal |
| Ambassador of Japan. | JICA | Yes | Member of the HPCC and HSF that reviewed the proposal |
| NGOs & CSOs Executive Secretary Managing Director Chairman President | Health Reform Foundation Of Nigeria (HERFON) Society for Family Health Rotary International Polio Plus Paediatrics Association of Nigeria | YES YES YES NO | Technical support to the proposal drafting Committee Member of the HPCC and HSF that reviewed the proposal Technical support to the proposal drafting Committee Member of HPCC and HSF Member of the HPCC and HSF that reviewed the proposal Made inputs to the proposal Sent inputs on the proposal |

To the applicant

- If the HSCC wishes to make any additional comments or recommendations on the GAVI HSS application to the GAVI Secretariat and Independent Review Committee, please do so below.

- Please explain if there has been no involvement of civil society or the private sector, and state if they are expected to have a service provision or advocacy role in GAVI HSS implementation.

## 1.4: Additional comments on the GAVI HSS application development process

There has been involvement of civil society organizations (CSOs) and the private sector in the development of the proposal. One of the major stake holders in maternal and child health, the Paediatric Association of Nigeria was invited to make inputs into the draft proposal.

On private sector participation in the drafting of the proposal, the Managing Director of Oceanic Bank Nigeria Plc who is the Chairman of Private Public Partnership for Immunization (PPPI) was also contacted for input into the draft proposal.

The draft proposal was also distributed to the State Ministries of Health and the LGAs for their inputs.

# Section 2: Country Background Information

Demography

Nigeria is one of the largest countries in Africa and occupies an area of 923,678 square kilometers. It lies within the tropics along the Gulf of Guinea on the West Coast of Africa, between the latitudes of 401' and 1309' N and longitudes 202' and 14030' E.  It shares border with the Republic of Benin to the west, the Republic of Cameroon to the east, the Republics of Niger and Chad to the north and the Atlantic Ocean to the south.

It is the most populous country in the continent with a population of 140,003,542 (Census, 2006). The population is predominantly young with about 45% under 15 years of age, 20% under 5 years while women of child bearing age (15-49 years) account for about 22% of the total population.

Socioeconomic indicators

With a per capita GNI of US$640, Nigeria is still ranked among the poorest countries in the world, with about 57% of the population living below $1 per day. (World Bank report 2006). About 64% of the country’s population live in rural areas where poverty is more predominant, thus limiting access to adequate nutrition, quality health care and other basic social services. In recognition of the high level of poverty, and as a response to meeting the MDG goals, the government developed a National Economic Empowerment and Development Strategy (NEEDS) - Nigeria’s version of Poverty Reduction Strategy Programme.

Recent assessments have shown that maternal mortality ratio is 800/100,000, under five mortality rate is 194/1000 live births, infant mortality rate is 100/1000 live births and life expectancy is 44 years (UNICEF SOWC 2007). The DPT3 coverage for 2006 is 77% (JRF 2006). This rapid increase in the administrative reporting was as a result of the Immunization Plus Days (IPDs) strategy which was adopted in April 2006 and the intensified reaching every ward approach. IPDs is a modification of the National Immunization Days (NIDs) in which routine vaccines and other health interventions are delivered to communities during polio vaccinations. The strategy delivers a range of routine antigens alongside oral polio vaccines plus other child survival interventions such as anti- helminthics, Vitamin A, distribution of insecticide treated nets etc.

Government

The Country operates a federal system of Government comprising 36 States and the Federal Capital Territory. The States are grouped into six geo-political zones and comprised of 774 Local Government Areas (LGA) serving as lowest administrative units of the three- tiers of government.  The LGAs are divided into 9555 wards which are the lowest political units.

Health System

The health system in Nigeria is based on the three tier structure of government (Federal, State and LGA). The three tiers have substantial autonomy and exercise considerable authority in the allocation and utilization of their resources.  The National Health Policy and recently, the National Health Bill ascribed roles and responsibilities to each level. Federal responsibilities include setting standards, formulation of policies and implementation guidelines, coordination, regulating practices for the health care system and delivering services at tertiary care level. States have responsibility for secondary level care while Local Governments are charged with Primary level care.  Primary Health Care is the foundation of the National Health System.

The performance of Nigeria’s health system declined appreciably in the closing decade of the last century resulting in poor health outcomes due to a number of factors including among others:

- Instability in political governance,

- Lack of commitment at state and LGA levels and

- Poor funding.

This development resulted in wide spread dilapidation of PHC infrastructure, near total breakdown of the system, declining morale and commitment of PHC workers and loss of confidence in health services by the communities. This situation, compounded by the absence of appropriate skilled health workers in the rural areas, resulted in most PHC facilities serving far less than their expected workload. In addition, there is persistence of vertical programmes, poor inter-sectoral collaboration, weak managerial capacity at the operational level for PHC services and poor health management information systems. Furthermore, lack of harmonized and coordinated health commodity procurement, storage and distribution systems presented huge challenges for the revitalization of PHC services.

The Ward Health System, which takes on the political Ward as the functional unit for PHC service delivery, was adopted as a suitable strategy for addressing the numerous challenges and accelerating progress in the attainment of Millennium Development Goals.

Based on the findings of the 2001 NPHCDA Needs Assessment, the country introduced the Ward Health System (WHS) as the functional unit for PHC service delivery. The WHS aligns the delivery of health care with the political wards, and demonstrates in concrete terms the desire of the national government to establish a people oriented and focused PHC system, which is community driven and co-managed by the health staff and community members. The homogeneity of the ward and the ability to generate grass root political commitment and support has proven far more beneficial than the former District Health System, which was based on vague boundaries created by the LGA health departments.

The focal point of WHS is the new model health centers being constructed in each of the target wards to provide Minimum Health Care Package and serve as a referral facility in the ward. Out of a total of 9555 model health centers (1/ward) proposed, 547 have either been completed or made functional or are in advanced stage of completion. In addition, 208 existing facilities are being rehabilitated and equipped through federal support.

However, GAVI funds are required to complement government’s effort at addressing improved access to health services and equity.

To the applicant

- Please provide the most recent socio-economic and demographic information available for your country. Please specify dates and data sources. (Table 2.1).

## 2.1: Current socio-demographic and economic country information

Current WB Report

| Information | Value | Information | Value |
| --- | --- | --- | --- |
| Population | 140,003,542 | GNI per capita | $US640 |
| Annual Birth Cohort | 5,791,671 | Under five mortality rate | 194 / 1000 |
| Surviving Infants* | 3,909,378 | Infant mortality rate | 100 / 1000 Live Births |
| Percentage of GNI allocated to Health | 0.7% | Percentage of Government expenditure on Health | 9.2% |

* Surviving infants = Infants surviving the first 12 months of life

To the applicant

- Please provide a brief summary of your country’s Health Sector Plan (or equivalent), including the key objectives of the plan, the key strengths and weaknesses that have been identified through health sector analyses, and the priority areas for future development (Table 2.2).

## 2.2: Overview of the National Health Sector Strategic Plan (1998-2010)

Health conditions in Nigeria have witnessed some significant improvement in the decades following independence in 1960, and particularly, since the adoption of the National Health Policy in 1988, but they still remain at a low level.  While infant mortality rate has reduced, under-5 mortality rate has remained unchanged. These important health indicators are still high when compared with countries at similar levels of development. Nigeria's public and private health care sectors expanded rapidly during the oil boom of the late 1970s, bringing about big improvements in the ratio of health facilities and personnel to population. The public spending on Health has never measured up to the 	WHO recommended benchmark though in the past three years there has been significant improvement with a current value of 9.2% for 2005.The reduction in public spending on health  over time has resulted in  serious deterioration in the quantity and quality of services.

Apart from reduction in public spending, Nigeria's health care system suffers from inefficient use of resources.  Facilities are not well maintained and there is acute shortage of materials and equipment particularly at the primary and secondary health care levels. Human resources for health are inadequate in number and inequitably distributed. This is compounded by an exodus of highly trained personnel. Confronted with stringent budgetary constraints, the Federal Government now recognizes the need for increased private sector participation.

The underlying problems of the Nigerian health system are complex, and go beyond inadequate resources and ineffective management, although these are major impediments in the delivery of health care. The issues also concern the pivotal role of health services in balancing resource constraints and population needs.  Many of these problems are inter related. They include institutional constraints occasioned by uncoordinated government health programmes, unsatisfactory health financing mechanisms; weak managerial process; lack of adequate information for decision making; lack of a functional referral system; poor involvement of the private sector; insufficient effort to bring about community participation and to respond to community needs; and insignificant multi-sectoral involvement.

In order to specifically address the Health problems of Women and Children, the Federal govt. of Nigeria adopted the Integrated Maternal, New born and Child Health (IMNCH) strategy in 2007. Response to child survival has also had its problems in that the implementation of child survival interventions has largely been vertical, focusing on immunisation, malaria control and breastfeeding promotion, Control of diarrhoeal diseases and Vitamin A supplementation with little emphasis on an integrated and multisectoral approach and devoid of the gains that could be generated through public –private sector partnership.

Integrated MNCH services involve the reorganization and reorientation of health systems to ensure the delivery of a set of essential interventions in the continuum of care for women, newborns and children. Such services include focused ante-natal care, intra-partum care, emergency obstetric and newborn care, routine post-natal care, re-positioning family planning/child spacing, infant and young child feeding. Others are prevention of malaria using ITNs, immunisation plus, prevention of mother to child transmission of HIV, management of common childhood illnesses and care of HIV exposed or infected children, prevention and management of childhood malnutrition and hygiene and sanitation A focus on the continuum of care replaces competing calls for mother or child, with a focus on high coverage of effective interventions and packages on integrating MNCH services as well as with other key programmes such as, HIV/AIDS and malaria.

The Child’s Rights Act, an overarching legal framework for child rights in the country, provides a legal framework to the IMNCH strategy. Nigeria has also captured its commitment to maternal, newborn and child health with the NEEDS, SEEDS and LEEDS documents.

# ection 3: Situation Analysis / Needs Assessment

To the applicant

GAVI HSS Support: GAVI HSS support cannot address all health system barriers that impact on immunisation and other child and maternal health services. GAVI HSS support should complement and not duplicate or compete with existing (or planned) efforts to strengthen the health system. GAVI HSS support should target “gaps” in current health system development efforts.

- Please provide information on the most recent assessments of the health sector that have identified health system barriers. (Table 3.1)

Note: Assessments can include a recent health sector review (conducted in the last 3 years), a recent report or study on sector constraints, a situation analysis (such as that conducted for the cMYP), or any combination of these. Please attach the reports of these assessments to the application (with executive summaries, if available). Please number them and list them in Annex 1.

Note: If there have not been any recent in-depth assessments of the health system (in the last 3 years), at the very least, a desk review identifying and analysing the key health systems bottlenecks will need to be undertaken before applying for GAVI HSS support. This assessment should identify the major strengths and weaknesses in the health system, and identify where capacity needs to be strengthened to achieve and / or sustain increased immunisation coverage.

## 3.1: Recent health system assessments

| Title of the assessment | Participating agencies | Areas / themes covered | Dates |
| --- | --- | --- | --- |
| A Blueprint for strengthening RI delivery system in Nigeria | FMOH, NPI, USAID, UNICEF, WHO, EU-PRIME and DFID | Policy Issues, Roles, Responsibilities & Structural Arrangements Monitoring and Evaluation Media Issues and Public Education Strengthening Ward-level Service Delivery Resource Mobilization and Partnership Coordination | July 2005 |
| Health, Nutrition and Population Country Status Report by the World Bank/FMOH | FMOH, World Bank and UNICEF | Health outcomes Household behaviour and community factors affecting health Health system and policy The role of the private sector in health Health care financing Extra resources needed to achieve the health related MDGs | Nov. 2005 |
| Rapid Assessment of the Health System of Nasarawa State of Nigeria | Health Reform Foundation of Nigeria (HERFON), Government of Nasarawa State of Nigeria, Professional Associations and CSOs in Nasarawa State | Demographic and Health Status Policy and Managerial Capacity Health Service Infrastructure Human Resources for Health Social Participation in Health Regulation and Enforcement State Strategic Health Plan, Development of Human Resources Social Health Fund, Minimum Package of Health Services | June 2006 |
| NICS 2006 | NPI, EU-PRIME, WHO, USAID, UNICEF and DFID | Infant Immunization Coverage Tetanus Toxoid Immunization coverage Immunization System functionality Factors influencing immunization uptake | March 2007 |

To the applicant

- Please provide information on the major health system barriers to improving immunisation coverage that have been identified in recent assessments listed above. (Table 3.2)

- Please provide information on those barriers that are being adequately addressed with existing resources (Table 3.3).

- Please provide information on those barriers that are not being adequately addressed and that require additional support through GAVI HSS (Table 3.4).

## 3.2: Major barriers to improving immunisation coverage identified in recent assessments

General Health System issues

- Ambiguity in the roles and responsibilities of the three tiers of government and that of the health workers.

- Inadequate political will especially at the States and LGA levels

- Inadequate funding of health care services at all levels

- Inadequate number and inequitable distribution of skilled manpower.

- Poor knowledge, attitude and managerial skills among health workers

- Great disparity in emolument of health workers by various tiers of government, leading to problems of staff attrition especially at the lower level

- Lack of update of pre-service training curricula with new innovations in the health sector and absence of systematic in-service training.

- Inadequate storage facilities and transport logistics at the LGA and ward levels

- Poor maintenance culture at the LGA and State levels

- Weak National Health Management Information Systems

- Most health facilities do not meet the minimum requirement in terms of equipment and essential health commodities.

PHC Issues

- Generally weak PHC system for effective health care services delivery

- Irregular supply of vaccines and commodities which leads to vaccine stock out and low immunization coverage.

- Community participation and ownership has been low because the Village and Ward Development Committees are not yet functional at these levels.

- Health promotion activities are not given adequate attention at all levels

- Existing micro plans are of low quality and mostly intervention specific (target populations and health facility Catchment area)

## 3.3: Barriers that are being adequately addressed with existing resources

- Ambiguity in the roles and responsibilities of the three tiers of government and that of the health workers. This is being addressed by the National Health Bill and increased advocacy to States, Local Governments and Communities.

- Inadequate political will especially at the States and LGA levels. This is also being addressed by the National Health Bill and increased advocacy to States, Local Governments and Communities.

- Health promotion activities are not given adequate attention at all levels. The existing health promotion unit has been elevated to a programme under the Public Health Department of the Federal Ministry of Health as a means of addressing this issue. Furthermore a policy and a strategic plan of action have been developed for health promotion activities.

- Irregular supply of vaccines and commodities which leads to vaccine stock out and low immunization coverage; being addressed by increased advocacy by partners to the Federal Government for increased budgeting and timely release of funds for vaccine procurement.

## 3.4: Barriers not being adequately addressed that require additional support from GAVI HSS

General Health System issues

- Inadequate funding of health care services at all levels

- Inadequate number and inequitable distribution of skilled manpower.

- Poor knowledge, attitude and managerial skills among health workers

- Inadequate storage facilities and transport logistics at the LGA and ward levels

- Poor maintenance culture at the LGA and State levels

- Lack of update of pre-service training curricula with new innovations in the health sector and absence of systematic in-service training.

- Weak National Health Management Information Systems

- Most health facilities do not meet the minimum requirement in terms of equipment and essential health commodities.

PHC Issues

- Generally weak PHC system for effective health care services delivery

- Community participation and ownership has been low because the Village and Ward Development Committees are not yet functional at these levels.

- Existing micro plans are of low quality and mostly intervention specific (target populations and health facility Catchment area)

# Section 4: Goals and Objectives of GAVI HSS Support

To the applicant

- Please describe the goals of GAVI HSS support below (Table 4.1).

- Please describe (and number) the objectives of GAVI HSS support (Table 4.2). Please ensure that the chosen objectives are specific, measurable, achievable, realistic and time-bound.

## 4.1: Goals of GAVI HSS support

The goal of the GAVI HSS support is to strengthen the Health system and reposition it to deliver effective, efficient and sustainable PHC services

The general objective is to develop the Ward Health System in 960 wards to deliver PHC services based on minimum health care package by 2010.

## 4.2: Specific objectives of GAVI HSS Support are:

4.2.1 To re-vitalise the Ward Development Committees in the selected 960 wards The Ward Health System is based on the political ward structures established throughout the country. The WDCs represent the closest administrative link between health facility services and the communities. Thus, the focus of this objective is to strengthen the ownership disposition and management of PHC activities through empowerment of the wards and community gate-keepers. It would be difficult to link services with the communities if community members do not participate in planning and monitoring of health and other social services located in their domains. In addition, the roles of the WDCs would be very critical in direct mobilization of local community resources, health promotion, increasing demand for services necessary for enhancing access by families, households and the communities. The involvement of community gatekeepers in direct management of community-based services will contribute to sustainability of the primary health care interventions. 4.2.2 To rehabilitate and equip 960 health facilities (1/ward) to deliver PHC minimum health package The PHC units serve as the catchments facilities for the wards and communities. Some of the obstacles against effective delivery of services include lack of essential drugs and basic equipment compounded by the dearth of skilled personnel. The essential drug usage would be guided by the principle of rational use. Thus, the focus of this objective is to provide minimum health care package which includes control of communicable diseases, child survival including immunization, nutrition, maternal and newborn care, non-communicable diseases, health education and community mobilization. , 4.2.3 To train and retrain PHC workers in those 960 wards on managerial capacity, and technical skills for integrated service delivery by 2010. During the Vaccine Security Mission to Nigeria in 2005, ineffective management of immunization service delivery especially at State and Local Government levels was identified as one of the weak points. Thus, the aim of this objective is to bridge management gaps to ensure that trained and skilled personnel are available at service points, and are able to conduct day-to-day managerial duties and resolve problems that may arise in the implementation of planned activities. Capacity building activities would also be conducted for service providers to help plan and implement facility based and outreach services through improvement of communication skills The GAVI HSS support will be implemented in concert with other existing health system strengthening activities such as social mobilization and programme communication to enhance the effectiveness of PHC and other public health services to provide quality preventive and curative services to improve and maintain immunization coverage. 4.2.4 To strengthen the NHMIS for programme monitoring and management in 100 LGAs by 2010. The implementation of national Health information system has been plagued with some bottlenecks making it ineffective and largely uncoordinated. Although standardized formats have been simplified and introduced at the various levels of implementation, there are still problems relating to availability of the forms, inadequate infrastructural support, non-budgetary provision for HMIS at States and Local government levels, lack of regular monitoring and supportive supervision, timeliness of reporting, feedbacks and non use of data for decision making. This objective is aimed at contributing to improving data flow pathways, provide evidence based data at national, state, local government and health facility levels for problems solving and decision making, tracking of performance and progress of PHC activities and for advocacy. 4.2.5 To strengthen the logistics system and infrastructure at the National/State/LGA/Ward levels by the end of 2010 Currently, there are different parallel channels for the distribution of programme specific health commodities. The most notable ones include the distribution of vaccines and injection devices by NPHCDA, Antiretroviral drugs distribution by National Agency for AIDS Control (NACA) and other donor agencies, distribution of ITNs by Roll Back Malaria, distribution of family planning health commodities by Reproductive Health, essential drugs distribution at state and LGA levels through the Bamako Initiative. This objective is aimed at harmonizing the existing various logistics channels so as to have a single unified delivery system, maximize the optimal use of resources for improved service delivery and ensure end-use monitoring and supervision. As an adjuvant to sustain the harmonized logistics system, training and kitting of maintenance officers on routine and preventive maintenance through institutionalizing maintenance schedules would also be put in place to prolong the lifespan of the equipment and infrastructure, reduce equipment breakdown and wastage.

# Section 5: GAVI HSS Activities and Implementation Schedule

To the applicant

- For each objective identified in Table 4.2, please give details of the major activities that will be undertaken in order to achieve the stated objective and the implementation schedule for each of these activities over the duration of the GAVI HSS support (Table 5.2 overleaf).

Note: GAVI recommend that GAVI HSS supports a few prioritised objectives and activities only. It should be possible to implement, monitor and evaluate the activities over the life of the GAVI HSS support.

Note: Please add (or delete) rows so that Table 5.2 contains the correct number of objectives for you  GAVI HSS application, and the correct number of activities for each of your core objectives. Note: Please add (or delete) years so that Table 5.2 reflects duration of your GAVI HSS application

To the applicant

- Please identify below how you intend to sustain, both technically and financially, the impact achieved with GAVI HSS support (5.1) when GAVI HSS resources are no longer available.

## 5.1: Sustainability of GAVI HSS support

Technical sustainability:

Service delivery

- National health bill clearly specifies the role of the three tiers of government, the private sector, Development Partners in service delivery with legal backing.

- The three tiers of government will maintain strong partnership with CSOs and other stakeholders in service delivery, finance, human resources and M&E

- Continued functioning of established equipment maintenance unit at states and LGAs.

- Provision of adequate funding to ensure continuous functioning of the harmonized logistics system

Human resources for health

- Continuous capacity building and re-orientation of health workers for integrated service delivery

- Strengthening institutional arrangements for human resources management at the LGA level

Monitoring, Supervision and Evaluation

- Continuous monitoring and supportive supervision for harmonized National M&E framework

- Continuous capacity building for data managers at all levels

- Policy makers to be involved in the use of data generated for evidence based decision making

Financial Sustainability:

- Increasing budgetary allocation to PHC as a proportion of total health budget is guaranteed in the National Health bill

- Increasing budgetary allocation to health as a proportion of total government budget

- Ensuring that States and LGAs provide matching grants to the National Primary Health Care Fund as provided for in the National Health Bill

- Revitalization of the Bamako Initiative at the LGA level to ensure continuous supply of essential drugs and other health commodities

- Scaling up of the community based health insurance scheme to ensure financial accessibility to health care service delivery

## 5.2: Major Activities and Implementation Schedule

| Major Activities | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 (2011) | Year 5 (2012) |
| --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Objective 1: To re-vitalise the Ward Development Committees in those 960 wards |  |  |  |  |  |
| Activity 1.1 Reactivate and re-orientate Ward Development Committees in 960 Wards over 2 years | X X X | X X X X |  |  |  |
| Activity 1.2: Develop a Ward Health Plan (WHPs), 2008- 2010, in 960 wards over 2 years | X X X | X X X X |  |  |  |
| Activity 1.3: Implement Ward Health Plans (WHPs) based on microplanning in 960 Wards over 2 years. | X X | X X X X |  |  |  |
| Objective 2: To rehabilitate and equip 960 health facilities (1/ward) to deliver PHC minimum health package |  |  |  |  |  |
| Activity 2.1 Rehabilitate 960 existing PHC facilities, one per ward over 2 years | X X X | X X X X |  |  |  |
| Activity 2.2: Equip 960 existing PHC facilities with minimum equipment package one per Ward over 2 years | X X | X X X X |  |  |  |
| Activity 2.3 Provide seed stock of essential drugs to 960 existing PHC facilities, over 2 years | X X | X X X X |  |  |  |
| Objective 3: To train PHC workers in those 960 wards on managerial capacity, and technical skills for integrated service delivery by 2010. |  |  |  |  |  |
| Activity 3.1: Training and re-training of all PHC workers in 960 wards on integrated service delivery, managerial and team building skills and resource mobilization. (Each training activity will be institution-based and for 2weeks) | X X X | X X X X |  |  |  |
| Activity 3.2: Providing monitoring and supportive supervision of trained PHC workers | X X | X X X X | X X X X |  |  |
| Objective 4: To strengthen the NHMIS for programme monitoring and management in 100 LGAs by 2010 |  |  |  |  |  |
| Activity 4.1: Provision of data management tools and equipment in the LGAs covering the target wards | X X X | X X |  |  |  |
| Activity 4.2: Facilitate data flow using ward focal persons | X X X X | X X X X | X X X X |  |  |
| Activity 4.3: Training of 2(HF service provider per ward) and 2 staff from the LGA(774) on quality assurance and data management | X X | X X |  |  |  |
| Activity 4.4: To conduct monitoring and supportive supervisory visits to strengthen NHMIS programme implementation at all levels: 4.4.1: 2 Officers per zone (2 X 6 persons) to conduct supervision of M & E activities quarterly at state level for 10 days 4.4.2: 5 State Officers per State (37 X 5 persons) to conduct supportive supervision to LGAs – quarterly for a period of 5 days 4.4.3: 2 LGA officers to conduct supportive supervision -monthly for 5 days | X X | X X X X | X X X X |  |  |
| Objective 5: To strengthen the logistics system and infrastructure at the National/State/LGA/Ward levels by the end of 2010 |  |  |  |  |  |
| Activity 5.1: Development of a harmonized logistic system for all health commodities in the country by: Establishing a core group to review existing systems and to develop a draft manual to harmonize them Convening a Stakeholders meeting /workshop to consider and approve the harmonized manual for the logistics of health commodity system (one person per state and 20 national officers including partner agencies for 2 days) | X X |  |  |  |  |
| Activity 5.2: Develop an architectural design to serve as prototype storage facility in line with international specifications to be adopted by the states and LGAs for the harmonised logistics system. (to be outsourced) | X |  |  |  |  |
| Activity 5.3: Training of LGA logistic personnel, 2/LGA (1548) on the harmonized logistic system | X X |  |  |  |  |
| Activity 5.4: Training and provision of maintenance kits, 2 per state and FCT (74). | X X |  |  |  |  |
| Activity 5.5: Provision of solar refrigerators for storage of vaccines in 960 Wards over 2 years | X X X | X X X X |  |  |  |
| Activity 5.6 Provision of maintenance support for solar refrigerators | X X X | X X X X | X X X X |  |  |

# Section 6: Monitoring, Evaluation and Operational Research

To the applicant

- All applications must include the three main GAVI HSS impact / outcome indicators:

- National DTP3 coverage (%)

- Number / % of districts achieving ≥ 80% DTP3 coverage

- Under five mortality rate (per 1000)

- Please list up to three more impact / outcome indicators that can be used to assess the impact of GAVI HSS on improving immunisation and other child and maternal health services.

Note: It is strongly suggested that the chosen indicators are linked with proposal objectives and not necessarily with activities.

- For all indicators, please give a data source, the baseline value of the indicator and date, and a target level and date. Some indicators may have more than one data source (Table 6.1).

Note: The chosen indicators should be drawn from those used for monitoring the National Health Sector Plan (or equivalent) and ideally be measured already (i.e. not an extra burden to measure). They do not have to be GAVI HSS specific. Examples of additional impact and outcome indicators are given in the tables below. It is recommended that when activities are implemented primarily at sub-national level that indicators are monitored, to the extent possible, at sub-nationally as well.

Examples of Impact Indicators

- Maternal mortality ratio

Examples of Outcome Indicators

- National measles coverage

- Proportion of districts with coverage at 80% or above

- Hib coverage

- HepB coverage, BCG coverage

- DTP1-DTP3 drop-out rate

- Proportion of births attended by skilled health personnel

- Antenatal care use

- Vitamin A supplementation rate

| Intervention | Possible indicators |
| --- | --- |
| Immunisation | National measles coverage; proportion of districts with coverage at 80% or above; BCG coverage; Polio 3 coverage; Hib coverage; HepB3 coverage |
| Maternity care | Antenatal care use; skilled birth attendance; tetanus toxoid 2 or more doses; caesarean section rate; postnatal care |
| Family planning | Contraceptive use among women |
| Treatment of sick children | oral rehydration therapy and continued feeding for children with diarrhoea; Care seeking for pneumonia; Antibiotic treatment for pneumonia |
| Nutrition | Breastfeeding rate; (start on first day, exclusive at 0-3 months, supplements at 6-9 months); vitamin A supplementation rate to children 6-59 months (within last 6 months) and postpartum to mother within 8 weeks |
| Water/sanitation | Access to safe water source; adequate sanitary facilities |
| Tuberculosis | DOTS treatment coverage (treatment success rate times case detection rate) |
| Malaria | Children with fever receiving anti-malarials; children sleeping under ITN |
| AIDS | % of HIV-positive pregnant women receiving ARVs; PMTCT among pregnant women |

To the applicant

- Please list up to 6 output indicators based on the selected activities in section 5. (Table 6.2).

- For all indicators, please give a data source, the baseline value of the indicator and date, a target level and date, as well as a numerator and denominator. Some indicators may have more than one data source (Table 6.1).

Note: Examples of output indicators that could be used, with the related numerator, denominator (if applicable) and data source are shown below. Existing sources of information should be used to collect the information on the selected indicators wherever possible. In some countries there may be a need to carry out health facility surveys, household surveys, or establish demographic surveillance. If extra funds are required for these activities, they should be included.

Examples of Output Indicators

| Indicator | Numerator | Denominator | Data Source |
| --- | --- | --- | --- |
| Systematic Supervision | Number of health centres visited at least 6 times in the last year using a quantified checklist | Total number of health centres | Health facility survey |
| Knowledge of Health Workers | Mean score of health workers in public and NGO health centres on verbal knowledge test including case scenarios |  | Health facility survey |
| Drug availability index | Average number of ten selected essential drugs that are in stock in sampled health centres |  | HMIS & Health facility survey |

## 6.1: Impact and Outcome Indicators

| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National DTP3 coverage (%) | NICS | 36.3% | NICS (2006) | 2005 | 80% | 2010 |
| 2. Number (%) of LGAs achieving ≥80% DTP3 coverage | WHO-UNICEF JRF | 310 (40%) | JRF 2006 | 2006 | 620 (80%) | 2010 |
| 3. Under five mortality rate (per 1000) | State of the world’s children report (UNICEF) | 194/1000 | State of the world’s children report (UNICEF 2007) | 2006 | 185/1000 | 2010 |
| 4.Proportion of birth attended by skilled Health personnel | NDHS | 36.3% | NDHS(2003) | 2002 | 60% | 2010 |
| 5.Antenatal care up take/proportion of women attending antenatal clinic | State of the world children(UNICEF) | 58% | State of the World children(UNICEF 2007) | 2006 | 70% | 2010 |
| 6.T.T 2+ coverage | State of the world children (UNICEF) | 51% | State of the World children(UNICEF 2007) | 2006 | 65% | 2010 |

## 6.2: Output Indicators

| Indicator | Numerator | Denominator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.Percentage of rehabilitated existing PHC facilities | No of rehabilitated existing PHC facilities | Total number of existing PHC facilities planned for rehabilitation | Monitoring and supervision report | Not Available |  | Data collection being planned 1st Quarter of 2008 | 50% | 2010 |
| 2. Percentage of existing PH facilities fully equipped | No. of existing PHC facilities fully equipped. | Total No. of PHC facilities planned for equipping | Monitoring and supervision report | 0 | Status of PHC in Nigeria: Report of NEEDS assessment survey (2001) | 2001 | 50% | 2010 |
| 3. Proportion of PHC workers trained | No of PHC workers trained | Total No of PHC workers planned for training | Training reports | Not Available |  | Data collection being planned 1st Quarter of 2008 | 70% | 2010 |
| 4. Percentage of wards with installed solar refrigerators. | Number of wards with solar refrigerators installed | Total number of wards planned to have solar refrigerators installed. | Administrative reports | Not Available |  | Data collection being planned 1st Quarter of 2008 | 50% | 2010 |
| 5 Percentage of LGAs provided with data management tools and equipment in the LGAs of the target wards. | Number of LGAs provided with data management tools and equipment in the LGAs of the target wards. | Total number of LGAs expected to be provided with data management tools and equipment in the LGAs of the target wards. | Administrative and monitoring reports | Not Available |  | Data collection being planned 1st Quarter of 2008 | 60% | 2010 |
| 6. Proportion of supervisory visit conducted by LGA to Health facilities. | Number of supervisory visit conducted by LGA to Health facilities. | Total No supervisory visits planned to be conducted. | Monitoring and supervisory reports, Annual reports | Not Available |  | Data collection being planned 1st Quarter of 2008 | 50% | 2010 |

To the applicant

- Please describe how the data will be collected, analyzed and used. Existing data collection and analysis methods should be used wherever possible. Please indicate how data will be used at local levels and ways of sharing with other stakeholders in the last column (Table 6.3).

6.3: Data collection, analysis and use

| Indicator | Data collection | Data analysis | Use of data |
| --- | --- | --- | --- |
| Impact and outcome |  |  |  |
| 1. National DTP3 coverage (%) | Data is routinely collected from the health facilities to the LGA and then to the States and National. Another method is through survey. | Data are analysed using percentage coverage tables, rates, and graphs for routine data. Survey data are analysed using WINCOSAS software. | Used for tracking performance and progress monitoring. It is shared through monthly meeting at LGA level and State and feedback. At National level through quarterly bulletin |
| 2. Number / % of LGA achieving ≥80% DTP3 coverage | This is collected from the monthly submissions of LGAs | Data are analysed using % of LGAs performing above and below 80% DPT3 benchmark coverage | Data is used for performance monitoring of LGAs. It is shared during monthly meetings and feedback reports |
| 3. Under five mortality rate (per 1000) | This data is collected through survey conducted by National Population Commission (NDHS) | Data are analysed using appropriate software. | Data is used to access outcome and impact of under 5 child survival interventions |
| 4. Proportion of birth attended by skilled Health personnel | This data is routinely collected from Health facility register and through NDHS | Proportion is derived from routine data and use of software by National Population Commission | Data is used to determine access and utilization of Health facilities. It is shared through publications |
| 5.Antenatal care use | This data is routinely collected from Health facility register and through NDHS and multiple cluster survey (MICS) | Percentage of pregnant women using ante natal care services is derived from analysis of survey data | Data is used to determine access and utilization of Health facilities. It is shared through publications |
| 6.T.T 2+ coverage | This data is routinely collected from Health facility register and through NDHS and multiple cluster survey (MICS) | Percentage of pregnant women receiving at least 2 doses of TT.This is derived from survey analysis and routine data | Data is used to determine access and utilization of Health facilities. It is shared through publications |
| Output |  |  |  |
| Indicator | Data collection | Data analysis | Use of data |
| 1.Percentage of rehabilitated existing PHC facilities | This data is collected through administrative reports and survey | The percentage is derived from analysis of administrative reports and surveys | This data is used to determine the percentage of Health facilities in good physical conditions for service delivery. It is shared through feedback, dissemination meetings and publications |
| 2. Percentage of existing PH facilities fully equipped | This data is collected through administrative reports and survey | The percentage is derived from analysis of administrative report, desk reviews and surveys | This data is used to determine quality assurance in the delivery of services. It is shared through feedback, dissemination meetings and publications |
| 3. Proportion of PHC workers trained | This data is collected through administrative reports and survey | The percentage is derived from analysis of administrative report, desk reviews and surveys | This data is used to determine the capacity of health work force to deliver quality services. It is shared through feedback, dissemination meetings and publications |
| 4. Percentage of wards with installed solar refrigerators. | This data is collected through administrative reports and surveys | The percentage is derived from analysis of administrative reports, assessment studies and surveys. | This data is used to determine the capacity of the wards to store vaccines for immunization services. It is shared through feedback, dissemination meetings and publications |
| 5 Percentage of LGAs provided with data management tools and equipment in the LGAs of the target wards. | This data is collected through administrative reports and surveys | The percentage is derived from analysis of administrative reports, assessment studies and surveys. | This data is used to determine the capacity of the LGAs for quality data management. It is shared through feedback, dissemination meetings and publications |
| 6. Proportion of supervisory visit conducted by LGA to Health facilities. | This data is collected through monitoring and supervisory reports. | The proportion is derived from analysis of monitoring and supervisory reports, | This data is used to improve staff performance and quality of health data. It is shared through feedback, dissemination meetings and publications |

To the applicant

- Please indicate if the M&E system needs to be strengthened to measure the listed indicators and if so describe which indicators specifically need strengthening. (Table 6.4).

- Please indicate if the GAVI HSS application includes elements of operational research that address some of the health systems barriers to better inform the decision making processes or health outcome. (Table 6.5).

## 6.4: Strengthening M&E system

M & E needs to be strengthened as it is listed as one of the major thrust of support and in the case of M & E the whole country is to be covered with the support.

The indicators that specifically need strengthening are listed below

1. Proportion of birth attended by skilled Health personnel

2.Antenatal care use

3. Percentage of rehabilitated existing PHC facilities.

4. Percentage of existing PH facilities that are fully equipped

5. Proportion of PHC workers trained

6. Percentage of wards with installed solar refrigerators.

7. Percentage of LGAs provided with data management tools and equipment in the LGAs of the target wards.

8. Proportion of supervisory visit conducted by LGA to Health facilities.

## 6.5: Operational Research

1. Baseline study to determine the functional status of PHC facilities in the selected 960 wards

2. A study to determine the mechanisms for sustainable financing of the minimum health package.

3. A study to examine the effectiveness of public expenditures on routine immunization at all levels of the Health sectors.

4. A study to determine factors that contribute to low coverage rate of fully immunized children in Nigeria.

# Section 7: Implementation Arrangements

To the applicant

- Please describe how the GAVI HSS support will be managed (Table 7.1).  Please also indicate the roles and responsibilities of all key partners in GAVI HSS implementation (Table 7.2).

Note: GAVI encourages aligning GAVI HSS with existing country mechanisms. Applicants are strongly discouraged from establishing a project management unit (PMU) for GAVI HSS. Support for PMUs will only be considered under exceptional circumstances, based on a strong rationale.

## 7.1: Management of GAVI HSS support

| Management mechanism | Description |
| --- | --- |
| Name of lead individual / unit responsible for managing GAVI HSS implementation / M&E etc. | An existing project implementation unit in the Dept of Planning Research and Statistics which is already managing Health System Development Fund of the World Bank |
| Role of HPCC (or equivalent) in implementation of GAVI HSS and M&E | Approve the work plan of GAVI HSS proposals from States. Review the progress of implementation of GAVI HSS Provides guidance to the Health System Forum on Policy and Technical issues on the GAVI HSS |
| Mechanism for coordinating GAVI HSS with other system activities and programs | The Health Partners Coordination Committee (HPCC) chaired by the Honourable Minister of Health and with membership drawn from all heads of UN Agencies, bilateral donor agencies, key agencies of the ministry of health and development partners coordinate inputs into the health system in general. At the State level the establishment of a similar coordinating body is in progress. GAVI/HSS Review committee will be constituted within the Nigeria Health System Forum and will include representative of the States. The committee will review and report to the HPCC. |

## 7.2: Roles and responsibilities of key partners (HPCC members and others)

| Title / Post | Organisation | HSCC member yes/no | Roles and responsibilities of this partner in the GAVI HSS implementation |
| --- | --- | --- | --- |
| Hon. Minister | Federal Ministry of Health | Yes | Chairs the Health Partners Coordination Committee. HPCC approves States work plan for implementation upon recommendation of the GAVI HSS award committee. Political advocacy to the Federal and State government to ensure programme sustainability. |
| Hon. Minister | Federal Ministry of Finance | No | Ensures availability of adequate government funds for financing health programmes |
| Hon. Minister | National Planning Commission | Yes | Ensures effective coordination of donor funds Serves as a member of the HPCC |
| Director Health Planning and Research | Federal Ministry of Health | Yes | Coordinates effective implementation of the programme. Serves as a member of HPCC. Chairs the Health System Forum which is the technical arm of the HPCC |
| Executive Director | National Primary Health Care Development Agency | Yes | Coordinates the implementation of the activities in the states and LGAs. Member of HPCC Member of the Health System Forum. Co -signatory to the existing mechanism of GAVI fund release Coordinate PHC services which include immunization. Plays advocacy role for PHC services |
| WHO Representative in Nigeria | Wold Health Organisation | Yes | Provide technical support to the country on all health matters. Member of HPCC Member of Health System Forum |
| Country Representative | UNICEF | Yes | Plays advocacy role and provides technical support to the country on all health matters. Member of HPCC Member of Health System Forum |
| Country Director | World Bank | Yes | Member of HPCC Member of Health System Forum |
| Ambassador and Head of Delegation | EC in NIGERIA | Yes | Member of HPCC Member of Health System Forum |
| Senior Health and Economic Adviser | DFID | Yes | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Head of AID | CIDA | Yes | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Mission Director | USAID | Yes | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Ambassador of Japan. | JICA | Yes | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Chairman | Rotary International Polio Plus | YES | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Executive Secretary | Health Reform Foundation Of Nigeria (HERFON) | YES | Member of HPCC Member of Health System Forum Provides technical support on Health matters |
| Hon. Commissioners | State Ministry of Health | NO | Coordinate and supervise the implementation at the state and LGA Representatives are ad hoc members of the GAVI HSS award committee |
| Consultants | GAVI (Zones) | NO | Provides technical supervision to the States and LGAs within the zones Members of GAVI HSS review and award committees |

To the applicant

- Please give the financial management arrangements for GAVI HSS support. GAVI encourages funds to be managed ‘on-budget’. Please describe how this will be achieved (Table 7.3).

- Please describe any procurement mechanisms that will be used for GAVI HSS (Table 7.4).

## 7.3: Financial management of GAVI HSS support

| Mechanism / procedure | Description |
| --- | --- |
| Mechanism for channelling GAVI HSS funds into the country | Funds will be channelled into a GAVI HSS dedicated account. This is a special account to complement government budgetary allocations to health at all levels. |
| Mechanism for channelling GAVI HSS funds from central level to the periphery | The GAVI HSS funds will be transferred from the central to the periphery through State GAVI HSS dedicated accounts after approval by the Nigeria Health Partner Coordinating Committee. For ownership, States are expected to pay a 10% counterpart funds into their State GAVI HSS dedicated account. |
| Mechanism (and responsibility) for budget use and approval | State GAVI HSS proposal with budgets are reviewed by the GAVI HSS award review committee and recommended for approval of the HPCC. On approval by the HPCC, funds are released to the various States account on confirmation of the availability of counterpart fund and prescribed signatories to the account. The State equivalent of HPCC gives final approval for utilization of funds at State and LGA levels after review of approved State and LGA work plans. |
| Mechanism for disbursement of GAVI HSS funds | Funds will be disbursed according to the approved programmes in accordance with the financial guidelines. |
| Auditing procedures | Through the use of internal and external auditors |

## 7.4: Procurement mechanisms

Health commodities to be procured, stored and distributed are

Medicines

Equipment

Supplies

The commodities are quantified based on approved work plans. Approval to tender is sought from the relevant authorities in charge. Thereafter due process certificate is obtained to award contracts. Due process is a federal government of Nigeria established pricing procedure put in place to moderate cost of goods and services in the public service.

A tendering procedure is selected, in this case open competitive bidding of pre qualified suppliers/contractors.

Selection of items to procure is done using the non proprietary international names (GENERIC) for medicines.

For equipments, compliance with international standard must be adhered to.

Thereafter quantification of all procurable items are done and matched with available funds.

Procurement process will include tendering and awards in accordance with National guidelines.

States/LGAs will procure materials and services locally.

External procurements will be through International competitive bidding.

To the applicant

- Please describe arrangements for reporting on the progress in implementing and using GAVI HSS funds, including the responsible entity for preparing the APR. (Table 7.5)

Note: The GAVI Annual Progress Report, due annually on 15 May, should demonstrate: proof of appropriate accountability for use of GAVI HSS funds, financial audit and proper procurement (in line with national regulations or via UNICEF); efficient and effective disbursement (from national to sub-national levels; in the context of a SWAp mechanism, if applicable); and evidence on progress on whether expected annual output targets and longer term outcome targets are being achieved.

## 7.5: Reporting arrangements

Implementation reports are prepared at four levels:

LGAs to State

States to Zone

Zones to National

National to GAVI Secretariat

GAVI HSS activities are reported from the lowest level of implementation to the States on a monthly basis. These monthly State reports are collated and sent to the Zones for onward transmission to the GAVI National desk on a quarterly basis. These reports and the retirements form the basis of the annual progress reports that will be sent to GAVI secretariat by May 15th every year.

To the applicant

- Some countries will require technical assistance to implement GAVI HSS support. Please identify what technical assistance will be required during the life of GAVI HSS support, as well as the anticipated source of technical assistance if known (Table 7.6).

## 7.6: Technical assistance requirements

| Activities requiring technical assistance | Anticipated duration | Anticipated timing (year, quarter) | Anticipated source (local, partner etc.) |
| --- | --- | --- | --- |
| 1. Development of a harmonized logistic system for all health commodities in the country. | 3 months | 1st quarter 2008 | International Partners |
| 2.Build capacity of Health workers in data management | 12 weeks | 3rd quarter 2008 | International Partners |
| 3.Operation research in improving immunization coverage | 9 months | 2nd, 3rd and 4th quarter 2008 | International Partners |
| 4. |  |  |  |

# Section 8: Costs and Funding for GAVI HSS

To the applicant

- Please calculate the costs of all activities for the duration of the GAVI HSS support. Please add or delete rows / columns to give the right number of objectives, activities and years. (Table 8.1)

Note: Please ensure that all support costs for management, M&E, and technical assistance are included. Please convert all costs to US$ (at the current exchange rate), and ensure that GAVI deflators are used for future costs (see guidelines on the GAVI website: www.gavialliance.org).

Note: The overall total request for GAVI HSS funds in table 8.1 should not exceed the overall total  of GAVI HSS funds allocated in table 8.2. Funds may be requested in annual trenches according to estimated annual activity costs. These may vary annually from the allocation figures in table 8.2.

## 8.1: Cost of implementing GAVI HSS activities

| Area for support |
| --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | TOTAL COSTS |
|  | 2007 | 2008… | 2009… | 2010 |  |
| Activity costs |  | US$ | US$ | US$ | US$ |
| Objective 1: To re-vitalise the Ward Development Committees in those 960 wards |  |  |  |  |  |
| Activity 1.1 Reactivate and re-orientate Ward Development Committees in 960 Wards over 2 years |  | 166,476 | 166,476 | 0 | 332,952 |
| Activity 1.2: Develop a Ward Health Plan (WHPs), 2008- 2010, in 960 wards over 2 years |  | 2,177,143 | 2,177,143 | 0 | 4,354,286 |
| Activity 1.3: Implement Ward Health Plans (WHPs) based on micro-planning in 960 Wards over 2 years. |  | 0 | 0 | 0 | 0 |
| Objective 2: To rehabilitate and equip 960 health facilities (1/ward) to deliver PHC minimum health package |  |  |  |  |  |
| Activity 2.1 Rehabilitate 960 existing PHC facilities, one per ward over 2 years |  | 5,714,286 | 5,714,285 | 0 | 11,428,571 |
| Activity 2.2: Equip 960 existing PHC facilities with minimum equipment package one per Ward over 2 years |  | 3,809,524 | 3,809,524 | 0 | 7,619,048 |
| Activity 2.3 Provide seed stock of essential drugs to 960 existing PHC facilities, over 2 years |  | 1,904,762 | 1,904,762 | 0 | 3,809,524 |
| Objective 3: To train PHC workers in those 960 wards on managerial capacity, and technical skills for integrated service delivery by 2010. |  |  |  |  |  |
| Activity 3.1: Training and re-training of all PHC workers in 960 wards on integrated service delivery, managerial and team building skills and resource mobilization. (Each training activity will be institution-based and for 2weeks) |  | 4,853,333 | 4,853,333 | 0 | 9,706,667 |
| Activity 3.2: Providing monitoring and supportive supervision of trained PHC workers |  | 213,333 | 213,333 | 213,333 | 640,000 |
| Objective 4: To strengthen the NHMIS for programme monitoring and management in 100 LGAs by 2010 |  |  |  |  |  |
| Activity 4.1: Provision of data management tools and equipment in the LGAs covering the target wards |  | 87,301 | 87,302 | 0 | 174,603 |
| Activity 4.2: Facilitate data flow using ward focal persons |  | 457,143 | 457,143 | 457,143 | 1,371,429 |
| Activity 4.3: Training of 2(HF service provider per ward) and 2 staff from the LGA(774) on quality assurance and data management |  | 121,690 | 121,690 | 0 | 243,381 |
| Activity 4.4: To conduct monitoring and supportive supervisory visits to strengthen NHMIS programme implementation at all levels: 4.4.1: 2 Officers per zone (2 X 6 persons) to conduct supervision of M & E activities quarterly at state level for 3 days 4.4.2: 5 State Officers per State (37 X 5 persons) to conduct supportive supervision to LGAs – quarterly for a period of 5 days 4.4.3: 2 LGA officers to conduct supportive supervision -monthly for 5 days |  | 59,048 264,285 95,238 | 59,048 264,286 95,238 | 59,048 264,286 95,238 | 177,143 792,857 285,714 |
| Objective 5: To strengthen the logistics system and infrastructure at the National/State/LGA/Ward levels by the end of 2010 |  |  |  |  |  |
| Activity 5.1: Development of a harmonized logistic system for all health commodities in the country by: 5.1.1: Establishing a core group to review existing systems and to develop a draft manual to harmonize them 5.1.2: Convening a Stakeholders meeting /workshop to consider and approve the harmonized manual for the logistics of health commodity system (one person per state and 20 national officers including partner agencies for 2 days) |  | 54,524 12,579 | 0 0 | 0 0 | 54,524 12,579 |
| Activity 5.2: Develop an architectural design to serve as prototype storage facility in line with international specifications to be adopted by the states and LGAs for the harmonised logistics system. (to be outsourced) |  | 7,937 | 0 | 0 | 7,937 |
| Activity 5.3: Training of LGA logistic personnel, 2/LGA (1548) on the harmonized logistic system |  | 480,794 | 0 | 0 | 480,794 |
| Activity 5.4: Training and provision of maintenance kits, 2 per state and FCT (74). |  | 64,365 | 0 | 0 | 64,365 |
| Activity 5.5: Provision of solar refrigerators for storage of vaccines in 960 Wards over 2 years |  | 1,440,00000 | 1,440,000 | 0 | 2,880,000 |
| Activity 5.6 Provision of maintenance support for solar refrigerators |  | 76,190 | 76,190 | 76,190 | 228,571 |
| TOTAL COSTS |  | 22,098,373 | 21,439,754 | 1,165,238 | 44,703,365 |

To the applicant

- Please calculate the amount of funds available per year from GAVI for the proposed GAVI HSS activities, based on the annual number of births and GNI per capita as follows (Table 8.2):

- If GNI < $365 per capita, country is eligible to receive up to $5 per capita

- If GNI > $365 per capita, country is eligible to receive up to $2.5 per capita

Note: The following example assumes the birth cohort in the year of GAVI application is 100,000, and gives the total fund allocations if the GNI < $365 per capita and if the GNI > $365 per capita.

Examples: GAVI HSS country allocation calculation

| GAVI HSS Allocation (GNI < $365 per capita) | Allocation per year (US$) |
| --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100,000 | 102,000 | 104,000 | 106,000 |  |
| Allocation per newborn | $5 | $5 | $5 | $5 |  |
| Annual allocation | $500,000 | $510,000 | $520,000 | $530,000 | $2,060,000 |

| GAVI HSS Allocation (GNI > $365 per capita) | Allocation per year (US$) |
| --- | --- |
|  | 2007 | 2008 | 2009 | 2010 | TOTAL FUNDS |
| Birth cohort | 100,000 | 102,000 | 104,000 | 106,000 |  |
| Allocation per newborn | $2.5 | $2.5 | $2.5 | $2.5 |  |
| Annual allocation | $250,000 | $255,000 | $260,000 | $265,000 | $1,030,000 |

## 8.2: Calculation of GAVI HSS country allocation

| GAVI HSS Allocation |
| --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | TOTAL FUNDS |
|  | 2007 | 2008 | 2009 | 2010 |  |
| Birth cohort | 5,791,671 | 5,977,005 | 6,168,269 | 6,365,653 |  |
| Allocation per newborn | 2.5 | 2.5 | 2.5 | 2.5 |  |
| Annual allocation |  | 14,942,512 | 15,420,672 | 15,914,132 | 46,277,316 |

Source and date of GNI and birth cohort information:

GNI:	World Bank Development Indices 2007

Birth cohort:	National Population Commission 2006

Total Other:

To the applicant:

Note: Table 8.3 is not a compulsory table.

- Please endeavour to identify the total amount of all expected health system strengthening related spending in the country during the life of the GAVI HSS application (Table 8.3).

Note: Please specify the contributions from the Government, GAVI and the main funding partners or agencies. If there are more than four main contributors, please insert more rows. Please indicate the names of the partners in the table, and group together all remaining expected contributions.  Please indicate the source of the data (Public Expenditure Review, MTEF, donor reports etc).

## 8.3: Sources of all expected funding for health systems strengthening activities

| Funding Sources | Allocation per year (US$) |
| --- | --- |
|  | Year of GAVI application | Year 1 of implementation | Year 2 of implementation | Year 3 of implementation | Year 4 of implementation | Year 5 of implementation | TOTAL FUNDS |
|  | 2007 | 2008 | 2009 | 2010 | 20… | 20… |  |
| GAVI |  |  |  |  |  |  |  |
| Government |  |  |  |  |  |  |  |
| Donor 1.(DFID) |  | US$30m | US$35m | US$40m |  |  |  |
| Donor 2. |  |  |  |  |  |  |  |
| Donor 3. |  |  |  |  |  |  |  |
| Donor 4. |  |  |  |  |  |  |  |
| Total Other |  |  |  |  |  |  |  |
| TOTAL FUNDING |  |  |  |  |  |  |  |

Source of information on funding sources:

GAVI:

Government:

Donor 1:

Donor 2:

Donor 3:

Total other:

# Section 9: Endorsement of the Application

To the applicant:

- Representatives of the Ministry of Health and Ministry of Finance, and the Chair of the Health Sector Coordinating Committee (HSCC), or equivalent, should sign the GAVI HSS application.

- All HSCC members should sign the minutes of the meeting where the GAVI HSS application was endorsed. This should be submitted with the application (numbered and listed in Annex 1).

- Please give the name and contact details of the person for GAVI to contact if there are queries.

Note: The signature of HSCC members represents their agreement with the information and plans provided in this application, as well as their support for the implementation of the plans. It does not imply any financial or legal commitment on the part of the partner agency or individual.

## 9.1: Government endorsement

The Government of NIGERIA commits itself to providing immunisation and other child and maternal health services on a sustainable basis. Performance on strengthening health systems will be reviewed annually through a transparent monitoring system. The Government requests that the GAVI Alliance funding partners contribute financial assistance to support the strengthening of health systems as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Name: PROF ADENIKE GRANGE | Name: DR SHAMSUDEEN USMAN |
| Title / Post: HON MINISTER OF HEALTH | Title / Post: HON. MINISTER OF FINANCE |
| Signature: | Signature: |
| Date: 28th September 2007 | Date: 28th September 2007 |

## 9.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent

Members of the Health Sector Coordination Committee or equivalent endorsed this application at a meeting on 8th March 2007.The signed minutes are attached as Annex 1.

| Chair of HSCC (or equivalent): |  |
| --- | --- |
| Name: PROF ADENIKE GRANGE | Post / Organisation: HON. MINISTER OF HEALTH |
| Signature: | Date: |

9.3: Person to contact in case of enquiries:

Name: DR A J OTERI	Title: GAVI FOCAL PERSON

Tel No: +2348033090404	Address: ROUTINE IMMUNIZATION UNIT

IMMUNIZATION DEPT, NPHCDA,

PLOT 681/682 PORT HARCOURT CRESCENT, AREA 11, GARKI-ABUJA

Fax No.

Email: josephoteri@yahoo.co.uk

# ANNEX 1 Documents Submitted in Support of the GAVI HSS Application

To the applicant:

- Please number and list in the table below all the documents submitted with this application.

Note: All supporting documentation should be available in English or French, as electronic copies wherever possible. Only documents specifically referred to in the application should be submitted.

| Document (with equivalent name used in-country) | Available (Yes/No) | Duration | Attachment Number |
| --- | --- | --- | --- |
| National Health Sector Strategic Plan (or equivalent) | YES | 1998-2010 | 01 |
| cMYP | YES | 2006-2010 | 02 |
| MTEF |  |  |  |
| PRSP8 |  |  |  |
| Recent Health Sector Assessment documents |  |  |  |
| HSCC minutes, signed by Chair of HSCC | YES |  |  |
| National Economic Empowerment and Development Strategy (NEEDS) | YES |  | 03 |
| Health Sector Reform Programme | YES |  | 04 |
| National Health Promotion Policy | YES |  | 05 |
| National Policy on Infant and Young child Feeding | YES |  | 06 |
| Integrated Child Survival and Development Strategic Framework and POA | YES |  | 07 |
| Operational training manual and guidelines for development of PHC | YES |  | 08 |
| Status of Primary Health care in Nigeria, Report of NEEDS assessment survey | YES |  | 09 |
| Nigeria Demographic and Health Survey 2003 | YES |  | 10 |
| National Health Management Information System Policy | YES |  | 11 |
| Blue print on Routine Immunization sustainability | YES |  | 12 |
| Implementation of the Minimum Health care package | YES |  | 13 |
| Achieving Health Related MDG goals in Nigeria | YES |  | 14 |
| Revitalization of Primary Health Care in Nigeria | YES |  | 15 |
| Revised National Health Policy | YES |  | 16 |
| Ward Health Services, operational guide | YES |  | 17 |
| PHC Profile-Technical report on PHCMIS service statistics | YES |  | 18 |
| Nigeria Health, Nutrition and Population Country status report (Vol. 1 & 2) | YES |  | 19 |
| National Policy on public-private partnership for health in Nigeria | YES |  | 20 |

# ANNEX 2 Banking Form

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNISATION |  | Banking Form |
| --- | --- | --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunisation dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |
| Name of Institution: (Account Holder) |  |
| Address: |  |
| City – Country: |  |
| Telephone No.: |  | Fax No.: |  |
| Amount in USD: | (To be filled in by GAVI Secretariat) | Currency of the bank account: |  |
| For credit to: Bank account’s title |  |
| Bank account No.: |  |
| At: Bank’s name |  |
| Is the bank account exclusively to be used by this program? | YES ( ) NO ( ) |
| By whom is the account audited? |  |
| Signature of Government’s authorizing official: |
| Name: |  | Seal: |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| SECTION 2 (To be completed by the Bank) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name: |  |  |
| Branch Name: |  |  |
| Address: |  |  |
| City – Country: |  |  |
| Swift code: |  |  |
| Sort code: |  |  |
| ABA No.: |  |  |
| Telephone No.: |  |  |
| Fax No.: |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . Is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: | Name of bank’s authorizing official: |
| 1 Name: Title: |  | Signature: |  |
|  |  | Date: |  |
| 2 Name: Title: |  | Seal: |
| 3 Name: Title: |  |  |
| 4 Name: Title: |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

TO:    GAVI – Secretariat

Att. Dr Julian Lob-Levyt

Executive Secretary

C/o UNICEF

Palais de Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative: |
| Name |  |
| Signature |  |
| Date |  |

# Footnotes

If baseline data is not available indicate whether baseline data collection is planned and when

Minutes from HSCC meetings related to HSS should be attached as supporting documentation, together with the minutes of the HSCC meeting when the application was endorsed. The minutes should be signed by the HSCC Chair. The minutes of the meeting endorsing this GAVI HSS application should be signed by all members of the HSCC.

If the application identifies activities that are to be undertaken at a sub-national level, sub-national data will need to be provided where it is available. This will be in addition to the national data requested.

Within the last 3 years.

If number of districts is provided than the total number of districts in the country must also be provided.

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

If available – and if not, the National Immunisation Plan plus Financial Sustainability Plan

if available please forward the pages relevant to Health Systems Strengthening and this GAVI HSS application