The Government of

MADAGASCAR

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and The Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

On 28 June 2000, the Government of Madagascar and the ICC submitted a proposal to GAVI and the Vaccine Fund containing specific requests for support. The proposal was accepted on 18 September 2000 and the first tranche of the funds intended for strengthening the immunization system was transferred on 8 January 2001. The second tranche, together with the supplement of USD 100 000 was transferred on 19 March 2003 and the third on 30 May 2003. A fourth tranche was transferred on 18 February 2004. The AD syringes, the safety boxes and the DTP-Hep B vaccines were duly received by the Immunization Department (ID).

This new submission concerns injection safety.

The basic data  concerning the country are as follows :

Out of a total population of 18 326 317 (2005 forecast), there are 690 536 children aged under one year.

DTP3 coverage targets:

- for 2000 and 2001, the targets were to immunize 70% of children aged under one year, i.e. 400 143 children in 2000 and 412 147 children in 2001.

- For the years 2002 and 2003, the target was to immunize 75% of the target population, namely 468 479 and 464 835 children respectively.

- With effect from 2004, the target has been to immunize 80% of the children. Thus, for 2004, there were 463 307 children to be vaccinated. The target for 2005 is 476 279 children and, for 2006,  489 615

Results for 2004:

According to the routine immunization data provided by the health statistics service,  the DTP3 coverage rate was 75%, i.e. 450 171 children under one year old, a completeness rate of 87% (cf. Monthly activity report).

To achieve the above-mentioned targets, three strategies have been adopted:

- increasing the rate of utilization of the services by improving the supply side of the immunization services and optimizing demand for them.

- promoting immunization  through social and inter-sectoral mobilization.

- implementing the Reach Every District approach at the level of the targeted districts

Roles of the ICC: Coordination and monitoring of implementation of activities.

For the year 2005, GAVI and the Vaccine Fund are requested to grant Madagascar the following :

- 660 837  AD syringes for the measles vaccine, 1 508 281  AD syringes for Tetanus and 701 526  AD syringes for BCG,

- 58 867  5-ml reconstitution syringes for the measles vaccine,  28 061 2-ml dilution syringes for the BCG and 33 432  safety boxes.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of MADAGASCAR commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	…………………………………………...

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organization | Name/Title | Date Signature |
| --- | --- | --- |

In case the GAVI Secretariat have queries on this submission, please contact :

Name: Dr RAHANTANIRINA Marie Perline

Title/Address: DIRECTOR OF FAMILY HEALTH

Tel.No: (261-20) 22 256-36

Fax No:…………………………..

E-mail:……………………………

Madagascar has been granted GAVI support since January 2001.

- Immunization-related fact sheet

| Table 1: Basic facts (year 1993, RGPH 93) |  |  |  |
| --- | --- | --- | --- |
| Population | 17 903 833 (2005 forecast)) | GNP per capita | - USD World Bank |
| Surviving Infants* | 595 349 (RGPH 93) | Infant mortality rate | 58/ 1000 |
| Percentage of GDP allocated to Health | 1.3% (2004 ) MEFB World Bank MHFP (Population) | Percentage of Government expenditure for Health Care | 7% (2004) MEFB World Bank MHFP (Population) |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2003 | 2004 | 2000 | Age group | 2001 | Age group |  | 2003 | 2004 |
| BCG |  |  | 90% | 89% | 72% | 12-23 months | 67% | 12-23 months | Tuberculosis |  |  |
| DTP | DTP1 |  | 94,6 % | 79% | 65.5% | 12-23 months |  | 12-23 months | Diphtheria | 0 | 0 |
|  | DTP3 |  | 85% | 75% | 55% | 12-23 months | 46% | 12-23 months | Pertussis | 8021 | 2974 |
| OPV3 |  |  | 84% | 79% | 58% | 12-23 months | 50% | 12-23 months | Polio | 0 | 0 |
| Measles |  |  | 87% | 98% | 55% | 12-23 months | 71% | 12-23 months | Measles | 62 233 | 35 558 |
| TT2+ (Pregnant women) |  |  | 41,45% | 48% | 48% | Pregnant women | 37% | Pregnant women | NN Tetanus | 6 | 8 |
| Hib3 |  |  | - | - | - | - | - | - | Hib | - | - |
| Yellow Fever |  |  | - | - | - | - | - | - | Yellow fever | - | - |
| HepB3 |  |  | - | 62% | 55% | 12-23 months | 46% | 12-23 months | hepB seroprevalence (if available) | - | - |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) |  |  |  |  |  |  |  |  |  |
|  |  | Infants ( > 6 months) |  |  |  |  |  |  |  |  | 3251020 (mass campaign) |

NB. These figures were communicated in April 2003 (for 2002 data)

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: The routine data for 2002 are official estimates as no survey was conducted on a national scale.

- Summary of health system development status relevant to immunization:

The National Immunization Policy is central to the country’s National Health Policy and immunization coverage constitutes a major indicator of access to health care. The Ministry of Health has drawn up a multi-year plan which summarizes the priorities of the government, particularly in the field of immunization.

In order to provide efficient community care, reforms of the health system have been undertaken :

- The provision of health care services is based on the development of the health district, the geographical coverage of which corresponds to the subprefecture (fivondronana). At present, there are 111 health districts, comprising Basic Health Centres (BHC) and District Hospital Centres (DHC). The latter provide medical and/or surgical care and constitute the first level of reference. In addition, there are 4 Regional Hospital Centres (RHC)and 2 University Hospital Centres (UHC).

- The activities relating to immunization are incorporated in the Minimum Package of Activities (MPA)  at the level of each BHC. In general, the BHCs devote between 5 and 20% of their work to EPI activities. The immunization activities are supervised by a management team at the district level, the provincial level and, where applicable, the central level.

- With regard to the budget, the reform of the health system is characterized by a decentralization of the operating budget at the level of the District Health Department (DHD). However, where necessary, the Provincial Health Directorates and the DHDs may submit their requests directly to the Immunization Department or to certain partners (UNICEF).

- With regard to the protection and the promotion of health, the main areas of attention are mother and child health, reproductive health and the promotion of life styles and behaviors that favour good health.

- The integrated management of childhood diseases is incorporated into the minimum package of activities for the child. The immunization status is checked systematically and completed within the framework of the implementation of this programme.

- The programme is managed by the Immunization Department. The ID comes under the Child Health Directorate, which is itself attached to the Ministry of Health and Family Planning's General Directorate for Family Health and the Fight against Diseases. The ID is responsible for drawing up the main lines of national EPI policy and its execution, as well as for the monitoring and assessment of the implementation of activities. The ID also provides technical and logistics support to the Health Units, in cooperation with the international agencies and the NGOs. The operations of the ID are financed out of a state budget provision which is currently managed on a one-stop-shop basis by the Administrative and Financial Department and the Investment and Logistics Department of the Ministry of Health and Family Planning. It also receives assistance from partners such as the JICA, USAID, WHO, UNICEF and GAVI.

Madagascar was granted GAVI support in 2001

4. Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: Inter Agency Co-ordinating Committee (ICC)

- Date of constitution of the current ICC: A senior ICC has been in place since 30 July 2003. The Technical ICC has been in operation since 2000 (signature of the memorandum)

- Organisational structure (e.g., sub-committee, stand-alone): Membership of the Technical ICC was extended to the other ministry departments

- Frequency of meetings: Quarterly for the Senior ICC and monthly for the Technical ICC

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chairman | Minister of Health and Family Planning (MHFP) | Dr Robinson JEAN LOUIS |
| Secretary | Immunization Department (ID) / MHFP |  |
| Members Ministerial Department s | - Ministry of National Education and Scientific Research - Ministry of the Interior and Administrative Reform - Ministry of National Defence - State Secretariat in charge of Decentralisation, Regional Development and the Communes - Ministry of the Economy, Finance and the Budget (MEFB) - Ministry of Posts and Telecommunications - Ministry of the Population, Social Protection and Leisure | Mr Henri RANJEVA Mrs RANAIVOSON RAKOTOMALALA Vololona Dr. Jaona RALAMBOSON Mr. RAKOTOJOELIMARIA Andriamihaja Zo Nirina Mr. Olivier RAJAONARISON Dr Ginette SAFARA Mr. Hery RAMANARIVO Dr Hanta BARAKA |
| Agencies | - WHO - UNICEF - USAID - JICA | Dr. Ndikuyeze André Mrs BENTEIN Barbara Mrs BENAZERGA Wendi Mr SASAKI Naoyosha |

- Major functions and responsibilities of the ICC:

- Technical ICC:

- EPI support, designing and drawing up guidelines and directives

- Participating in the assessment of the EPI

- Senior ICC:

- Decision-making concerning the main strategic options

- Advocacy activities to mobilise resources

- Lending assistance to the Ministry of Health in laying down EPI policy

- Coordinating the interventions of the various immunization partners

- Contributing to the mobilization of resources for immunization

- Monitoring progress of the programme (immunization coverage, epidemiological surveillance, annual plan of action)

The three major strategies to enhance the ICC’s role and functions in the next 12 months are as follows :

- Advocacy for the implementation of the main strategic options and for the mobilization of resources

- Strengthening the management of the programme with programme coordination and management components

- Monitoring and Assessment

- The three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal are as follows:

- Rate of utilization of AD syringes in the advanced and fixed strategies at the level of the immunization health centres

- Number of DHDs provided with an incinerator

- Incidence of APIRs at national level

Attached is the supporting document:

| - Terms of reference of the ICC | Document number 1 |
| --- | --- |
| - EPI workplan for 2005 | Document number 2 |
| - Minutes of ICC meetings in 2004 or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 3 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference:

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Vaccine management assessment | WHO, UNICEF, USAID, MH | 04-20.02.03 |
| EPI external review | WHO, UNICEF, USAID, MH | 19.05.03 – 06.06.03 |
| Data Quality Audit | GAVI | 28.07.03-11.08.03 |
| External review of AFP surveillance | WHO, UNICEF, USAID, MH | 17-20.09.03 |
| Inventory of EPI equipment | WHO, UNICEF, USAID, MH, GAVI | May-July 2003 |
| - Injection safety and waste management assessment - Survey for monitoring the quality of the national immunization campaign against measles in September / October 2004 - Study on the use of needle extractors (waste management) during the national immunization campaign against measles conducted in September-October 2004 | WHO, UNICEF, USAID, MHFP WHO, MHFP WHO, MHFP | April 2004 September-October 2004 September-October 2004 |

- The three major strengths identified in the assessments:

- Effectiveness of the financial participation within the framework of the Vaccine Independence Initiative.

- ICC meetings held on a monthly basis

- Availability of the EPI plans of action at the level of the DHDs and PHDs

- The three major problems identified in the assessments:

- Poor immunization coverage

- The wastage and drop-out rates are not calculated in the BHCs, DHDs and PHDs (lack of data and poor management, poor vaccine management)

- Shortage of AD syringe stocks due to a procurement problem

- The three major recommendations in the assessments:

- Backing up of data at all levels

- Strengthening cooperation between the EPI and the SISG

- Generalising the district approach with planning to give priority to the districts with poor DTP3-Hep B coverage.

- Attached are complete copies (with an executive summary) of:

| - The most recent assessment reports on the status of immunization services | Document number 4 |
| --- | --- |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Study of adverse post-immunization reaction (APIR) | Scheduled for 2004 but not carried out |
| Assessment of the current regulatory system concerning medicines, vaccines and medical equipment | Scheduled for Nov-Dec 2003 but not carried out |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 2 |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools, etc) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| External consultants for the construction of incinerators | April-May 2005 | WHO/UNICEF |
| External consultant for MLM training | May 2005 | WHO |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | x |  |  |
| DTP /Hep B1 | 6th week | x |  |  |
| DTP / Hep B2 | 10th week | x |  |  |
| DTP/ Hep 3 | 14th week | x |  |  |
| MEASLES | 9th month | x |  |  |
| TT | Pregnant women and women of child-bearing age |  |  |  |
| Vitamin A | 6 to 59 months | x |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

- Extending the Reach Every District approach

- Installing vaccine and EPI management software packages at the level of the administrative centres of the provinces, regions and districts (launched in June 2003, to be continued up to December 2005)

- Conducting reviews at all levels (monthly at the level of the districts, quarterly and half-yearly at the level of PHDs )

- Providing training supervision at all levels

- Developing human resources

| Table 4: Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ###### Number of |  | ###### Baseline and targets |  |  |  |  |  |  |  |  |
|  |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2004 | 2005 | 2006 |  | 2007 | 2008 | 2009 | 2010 |
| Births |  | 632 337 | 614 791 | 632 005 | 649 701 |  | 667 893 | 686 594 | 705 819 | 725 582 |
| Infants’ deaths |  | 60 704 | 35 658 | 36 656 | 37 683 |  | 38 738 | 39 822 | 40 937 | 42 084 |
| Surviving infants |  | 571 633 | 579 133 | 595 349 | 612 019 |  | 629 155 | 646 772 | 664 881 | 683 498 |
| Infants vaccinated with BCG* |  | 442636 | 532 084 |  |  |  |  |  |  |  |
| Infants vaccinated with OPV3** |  | 400143 | 477 191 |  |  |  |  |  |  |  |
| Infants vaccinated with the three doses of DTP** |  | 401143 | - | - | - |  |  | - | - | - |
| Infants vaccinated with DTP Hep B3 (use one row for any new vaccine) |  | - | 450 171 |  |  |  |  |  |  |  |
| Infants vaccinated with Measles** |  | 442 636 | 590 167 |  |  |  |  |  |  |  |
| Pregnant women vaccinated with TT+ |  | 553 295 | 326 369 |  |  |  |  |  |  |  |
| Vit A supplementation | 189 701 | 513 137 | 335 423 |  |  |  |  |  |  |  |
|  | 1 517 610 | 2 277 445 | 1823662 |  |  |  |  |  |  |  |
| * Number of infants vaccinated out of total births |  |  |  |  |  | ** Number of infants vaccinated out of surviving infants |  |  |  |  |

- Summary of major action points and timeframe for reduction of vaccine wastage.  If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

| Table 5: Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Target |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 25% | 25% | 25% | 25% | 10% | 10% | 10% | 10% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 17% | 16% | 15% | 13% | 10% | 10% | 5% | 5% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

# Injection safety

7.1  Summary of the injection safety strategy for immunization (for all proposals):

From 2001 to 2003 1) Adoption of the mixed strategy - Use of sterilisable syringes in the fixed strategy - Use of AD syringes: - for the administration of the DTP-HepB vaccine - in the advanced strategies and during mass immunization campaigns - during catch-up sessions 2) With effect from 2003, exclusive use of AD syringes at the level of all the immunization health centres for routine immunization and supplementary immunization activities 3) An injection safety and waste management assessment was conducted in April 2004. Following the assessment, the following strategic orientations have been adopted : - Rigorous application of safe injection norms, - Proper procurement of vaccines and injection supplies (bundling) - Proper management of EPI generated waste. Incinerators will be installed at the level of the administrative centres of 26 districts and six provinces with the help of the WHO. The PNPS project (fight against HIV/AIDS) is to install 40 incinerators in 40 other districts.

| - A copy of the Safe Injection Plan (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 2 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

Requirements in terms of AD syringes and reconstitution syringes for BCG

|  |  | Formula | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated with BCG | To be matched with the targets in Table 4 | 505 604 | 545 749 | 561 030 |
| B | Number of doses per child | # | 1 | 1 | 1 |
| C | Number of doses of BCG | A x B | 505 604 | 545 749 | 561 030 |
| D | Number of AD syringes (+ 10% wastage) requested | C x 1.11 | 561 221 | 605 782 | 622 744 |
| E | Buffer stock of AD syringes | D x 0.25 | 140 305 | 151 445 | 155 686 |
| F | Total AD syringes | D + E | 701 526 | 757 227 | 778 429 |
| G | Number of doses per vial | # | 20 | 20 | 20 |
| H | Number of reconstitution syringes (+ 10% wastage) requested | C x 1.11 / G | 28 061 | 30 289 | 31 137 |
| I | Total number of safety boxes (+ 10% of extra need) requested | ( F + H ) x 1.11 / 100 | 8098 | 8 741 | 8 986 |

Requirements in terms of AD syringes and reconstitution syringes for the measles vaccine

|  |  | Formula | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated with measles vaccine | To be matched with the targets in Table 4 | 476 279 | 514 096 | 553 657 |
| B | Number of doses per child | # | 1 | 1 | 1 |
| C | Number of doses of measles vaccine | A x B | 476 279 | 514 096 | 553 657 |
| D | Number of AD syringes (+ 10% wastage) requested | C x 1.11 | 528 670 | 570 646 | 614 559 |
| E | Buffer stock of AD syringes5 | D x 0.25 | 132 167 | 142 662 | 153 640 |
| F | Total AD syringes | D + E | 660 837 | 713 308 | 768 199 |
| G | Number of doses per vial | # | 10 | 10 | 10 |
| H | Number of reconstitution syringes (+ 10% wastage) requested | C x 1.11 / G | 52 867 | 57 065 | 61 456 |
| I | Total number of safety boxes (+ 10% of extra need) requested | (F + H ) x 1.11 / 100 | 7922 | 8 551 | 9 209 |

Requirements in AD syringes and reconstitution syringes for the TT vaccine

|  |  | Formula | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- |
| A | Number of women to be vaccinated with TT vaccine | To be matched with the targets in Table 4 | 543 525 | 584 731 | 601 104 |
| B | Number of doses per child | # | 2 | 2 | 2 |
| C | Number of doses of TT vaccine | A x B | 1 087 049 | 1 169 463 | 1 202 208 |
| D | Number of AD syringes (+ 10% wastage) requested | C x 1.11 | 1 206 625 | 1 298 103 | 1 334 450 |
| E | Buffer stock of AD syringes5 | D x 0.25 | 301 656 | 324 526 | 333 163 |
| F | Total AD syringes | D + E | 1 508 281 | 1 622 629 | 1 668 063 |
| G | Number of doses per vial | # | 20 | 20 | 20 |
| H | Number of reconstitution syringes (+ 10% wastage) requested | C x 1.11 / G | 60 331 | 64 905 | 66 723 |
| I | Total number of safety boxes (+ 10% of extra need) requested | ( F + H ) x 1.11 / 100 | 17 412 | 18 732 | 19 256 |

5 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. 6 It applies only for lyophilized vaccines; write zero for other vaccines.

7.3 Areas of activity to benefit from injection safety funds (for countries requesting GAVI/The Vaccine Fund to provide funds in lieu of the supply calculated above).

List of activities of the injection safety plan funded by The Vaccine Fund and by other sources: (To obtain GAVI/VAccine Fund support, complete "Area of Activity"; for AD syringes and waste disposal, complete "Source of funds")

| Source of funds | ###### Injection Safety activity | Month of start of fund utilization |
| --- | --- | --- |
| UNICEF | AD syringes and safety boxes (for BCG, Measles and TT) | 2002-2003-2004 (direct purchase by UNICEF) |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the comprehensive multi-year immunization plan that refer to the introduction of new and under-used vaccines.

As the hepatitis B vaccine is combined with the DTP, the strategies will be the same : - Organising and conducting immunization sessions in all the immunization health units, incorporating the hepatitis B vaccine with effect from December 2001 - Ensuring the continuous availability of the vaccine, using the same channels and frequency of supply - Ensuring the availability and operation of the cold chain for proper conservation of the vaccines - Including IEC in favour of the new DTP-HepB vaccine in the EPI strategic communication plan - Ensuring the monitoring and assessment of the programme

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | 1 Hepatitis B in the general population of Madagascar : Different epidemiological profiles in rural and urban areas. 1996 (Epidémiol Inf 117.133-137) | 26 January 1996 | Prevalence of hepatitis B 20.5% for the HBs antigen, 38.2% for the HBc and 6.9% for the Hbe. There is a significant difference between the rural areas (HBs 26.0%) and urban areas (5.3%) |
| Hepatitis B | 2) Infection with the hepatitis B virus : a public health problem (IPM 2000 – 66 122 :50-54) | 2000 | Prevalence of hepatitis B = 23% |
| Haemophilus influenzae | 3) Bacterial meningitis in children in Antananarivo – Multicentre study - May 2001 – Institut Pasteur of Madagascar | June 1998 to June 2000 | Causes of bacterial meningitis among children of less than 15 years in Madagascar are : - streptococcus pneumoniae = 34% - Haemophilus influenzae type B = 32% - Neisseria meningitidis = 7% - Mycobacterium tuberculosis = 5% |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- As the hepatitis B vaccine is combined with the DTP, there will be little change. However, given that the DTP-Hep B vaccine comes in 10 dose vials, as opposed to the 20 dose vial for the DTP, there will be an increase in storage capacity. - The use of the freeze-watch and 3M cards is not systematic in certain regional centres or districts. - Given the workload of the health personnel and the cost/efficiency factor, formal training is not cost effective. - The assessment (cold chain inventory) which was conducted showed that out of the 67% coverage rate of the refrigerators listed at the level of the Basic Health Centres, only 71% of them were operational. - Despite its effectiveness in reducing vaccine wastage, the application of the open vial policy remains inadequate. - The drop-out rate will be reduced by improving the monitoring of the target population and the catch-up strategy.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

The 2002 to 2006 requests for DTP/Hep B vaccines, as well as the related injection equipment, have already been sent to GAVI and accepted.

| Table 7.1: Estimated number of doses of the DTP-HepB vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to be vaccinated with DTP-HepB | To be matched with the targets of Table 4 |  |  |  |  |  |  |
| B | Number of doses per child | # |  |  |  |  |  |  |
| C | Wastage rate estimiated in % | % |  |  |  |  |  |  |
| D | Wastage factor | See list Table  |  |  |  |  |  |  |
| E | Number of doses | A x B x D |  |  |  |  |  |  |
| F | Number of vaccines in buffer stock | E x 0.25 |  |  |  |  |  |  |
| G | Total vaccine doses needed | E + F |  |  |  |  |  |  |
| H | % of vaccines requested from the Vaccine fund | % |  |  |  |  |  |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  |  |  |  |  |
| J | Number of doses per vial | # |  |  |  |  |  |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  |  |  |  |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  |  |  |  |  |
| M | Total AD syringes | K + L |  |  |  |  |  |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  |  |  |  |  |
| ##### O | Number of safety boxes (+10% extra need) | (M + N) x 1.11 / 100 |  |  |  |  |  |  |
| 1 To insert the number of infants that will be vaccinated with the first dose only (as indicated in Table 4). 2 Estimates of 100% of target number of children is adjusted if a phase-out of GAVI/VF support is intended. 3 The buffer stock for vaccines is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographical area. 4 It applies only for lyophilized vaccines; write zero for other vaccines. |  |  |  |  |  |  |  |  |

| - Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

The 2002 to 2006 requests for DTP/Hep B vaccines, as well as the related injection equipment, have already been sent to GAVI and accepted.

| Table 7.2: Estimated number of doses of the HepB vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, etc) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to be vaccinated with HepB | Match with targets of Table 4 |  |  |  |  |  |  |
| B | Number of doses per child | # |  |  |  |  |  |  |
| C | Wastage rate estimiated in % | % |  |  |  |  |  |  |
| D | Wastage factor | See Table  |  |  |  |  |  |  |
| E | Number of doses | A x B x D |  |  |  |  |  |  |
| F | Number of vaccines in buffer stock | E x 0.25 |  |  |  |  |  |  |
| G | Total vaccine doses needed | E + F |  |  |  |  |  |  |
| H | % of vaccines requested from the Vaccine fund | % |  |  |  |  |  |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  |  |  |  |  |
| J | Number of doses per vial | # |  |  |  |  |  |  |
| K | Number of AD syringes (+10% waste) | [( A x B) + F] x x 1.11 x H / 100 |  |  |  |  |  |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  |  |  |  |  |
| M | Total AD syringes | K + L |  |  |  |  |  |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  |  |  |  |  |
| ##### O | Number of safety boxes (+10% extra need) | (M + N) x 1.11 / 100 |  |  |  |  |  |  |
| 1 To insert the number of infants that will be vaccinated with the first dose only (as indicated in Table 4). 2 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended. 3 The buffer stock for vaccines is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. 4 It applies only for lyophilized vaccines; write zero for other vaccines. |  |  |  |  |  |  |  |  |

| - Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

| - Attached is the plan of action for introduction of immunization with new or under-used vaccines (if already contained within the national multi-year plan, indicate pages) | Document number 3 |
| --- | --- |

# Strategic orientations to mobilise additional resources in favour of immunization

  - Summary of the strategies which the government envisages implementing to increase the resources intended for the immunization of children and which will be converted into a Financial Sustainability Plan on the occasion of the mid-point examination. Strong points of the agreements concluded with the donor institutions (for example, the Vaccine Independence Initiative) and the use of the funds released by the debt relief.

The strategies recommended by the government in order to increase the resources intended for the immunization of children are described below: - Cooperation with the EPI partners signatories of the Memorandum for the period 2000-2003. The aim is to rationalise the utilization of resources, to coordinate activities and to monitor their implementation through the Inter-Agency Coordination Committee. - With regard to the commitment of the Madagascar government, the State contributes to the purchase of the vaccines and to the operation of the cold chain (fuel). According to the annual reports of the Immunization Department for 1997 to 2000, there was a significant increase in the government’s contribution. In 1997, the financing allocated to the Immunization Department represented 1.03% of the operating budget of the Ministry of health. In 1999, this figure rose to 5.38% and in 2000, it stood at 9.42%.

- Attached is a list of strategies to ensure sustainability and the current and projected financial mechanisms for immunization, depending on the availability of funds, including the agreements concluded with other institutions (namely, the Vaccine Independence Initiative).

Table A : Strategies for ensuring the sustainability of immunization

Participation of the partners sent to GAVI during the first submission 									(USD thousands)

| Title of the strategy / Line | Partner | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine Independence Initiative (purchase of vaccines) | Government | 43.7 | 55.911 | 76.9 | 150 | 250 | 350 | 450 | 550 |
| Vaccine Independence Initiative (purchase of fuel) | Government | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |
| EPI support | UNICEF | 400 | 895.284 | 850 | 1.100 | 1.050 | 1.050 | 1.050 | 1.050 |
| EPI support | USAID | 400 | 500 | 250 | 200 | TBD | TBD | TBD | TBD |
| EPI support | JAPAN |  | 278.6 | 136.9 | 120.456 |  |  |  |  |
| EPI support | WHO | 228 | 218 | 200 |  |  |  |  |  |
| EPI support | Rotary International | 61 | 129.698 | 68.8 |  |  |  |  |  |
| EPI support | JSI |  |  | 121.359 |  |  |  |  |  |

| - Table B.The tables of expenditure for 2000 and the resource requirements showing the sources of funds for 2000 and subsequent years are presented in Annex 1. | Document no. 4 |
| --- | --- |

- Remarks on the strategies for the reduction of recurrent costs, intended to contribute to financial sustainability (e.g. reducing the rate of vaccine wastage):

Table C					 (in USD thousands)

| EPI partners | 1997 | 1998 | 1999 | 2000 | TOTAL |
| --- | --- | --- | --- | --- | --- |
| UNICEF | 1298.973 | 2508.110 | 1900.458 | 1016.541 | 6724.082 |
| WHO | 26.0 | 304.850 | 248.099 | - | 578.949 |
| JICA | 302.400 | 228.070 | 202.436 | 136.988 | 869.894 |
| GOVERNMENT | 17.076 | 39.760 | 133.756 | 137.508 | 328.098 |
| TOTAL | 1644.449 | 3080.790 | 2484.749 | 1291.035 | 8501.023 |

The USAID funds are managed by UNICEF

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of MADAGASCAR, considering that its DTP3 coverage for 2000 was 75%, corresponding to 474 409 children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		     YES          NO

(already granted up to 2006)

- Support for New and Under-used vaccines                                     YES          NO

(already granted up to 2006)

- Support for Injection Safety                                                               YES          NO

(new request)

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in the year 2002 on the basis of the number of additional children (as compared to the baseline) targeted for immunized with DTP3 as presented in Table 4, namely 503 135. Funds will also be requested for following years as estimated in Table 4.

- The Government assumes full responsibility for managing the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

The fund is managed by the Ministry of Health, jointly with the Preventive Medicine Directorate and the Immunization Department. Each entry of funds is preceded by a request. At the peripheral level, each beneficiary has to sign a letter of commitment. The supporting documentation is sent to the Immunization Department no later than three months after the end of the activity concerned. An internal audit is carried out annually at the central, regional and peripheral level. Long-term sustainability is assured through the participation of the Madagascar government in the financing of the immunization activities (purchase of petrol, transport, staff salaries and indemnities). Technical and financial reports are to be provided.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                YES                          By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”( Annex 3) with the proposal.

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):	  YES    The amount of supplies listed in table 8

The equivalent amount of funds

| Table 8: Summary of total imunization safety supplies requested from GAVI and the Vaccine Fund (fill in the total sums of rows "F", "H" and "I" of tables 6.1, 6.2, 6.3, 6.4). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  |  | 2005 | 2006 | 2007 |
| F | Total AD syringes | for BCG |  | 701 526 | 757 227 | 778 429 |
|  |  | for DTP Hep B |  | Already acquired |  |  |
|  |  | for measles |  | 660 837 | 713 308 | 768 199 |
|  |  | for TT |  | 1 508 281 | 1 622 629 | 1 668 063 |
| H | Total reconstitution syringes |  |  | 141 259 | 152 259 | 159 316 |
| I | Total safety boxes |  |  | 33 432 | 36 024 | 37 451 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal.

# Additional comments and recommendations from the ICC

- The introduction of the vaccine against hepatitis B and the exclusive use of AD syringes in the routine EPI require further support from the EPI partners, particularly GAVI and the Vaccine Fund

- Injection safety necessitates the management of waste. Hitherto, however, the disposal of waste in general and of used equipment in particular has been carried out in a primitive manner, with wastes being burned and disposed of in pits dug in the areas surrounding the health units. Very few incinerators exist at the level of the health centres. Therefore, it is essential to provide incinerators for the administrative centres of the districts and provinces.

- It is necessary to strengthen staff training and training supervision at all levels.

- It is necessary to carry out data quality audits regularly

#### CONSOLIDATED STATEMENT OF THE SOURCE AND APPLICATION OF FUNDS FROM EPI PARTNERS – 2000 -

| Expenditure and various sources of financing for the year 2000 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Budget line | Government | Unicef | Canada | USAID | UNFIP | Rotary Int. | UK | WHO | JSI | JAPAN | Private | Total exp.. 2000 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines… | 76.923 | 100.850 | 2.772 | 24.543 | - | 10.968 | - | - | - | 39.600 | - | 255.656 |
| 1.2 | - Syringes and injection kits |  | 45.457 | - | - | 52.275 | - | - | - | - | 30.060 | - | 127.792 |
| 2. | Equipment (cold chain, spare parts, sterilisation, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators – cold boxes | - | - | - | - | - | 57.910 | - | - | - | - | - | 57.910 |
| 2.2 | - Maintenance kits | - | - | - | 18.114 | 50.202 | - | - | - | - | 19.74 | - | 70.290 |
| 2.3 | - Spare parts (cold chain) | - | 12.696 | 21.260 | - | 60.523 | - | - | - | - | 65.354 | - | 159.833 |
| 3. | Other equipment |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | - Spare parts (vehicles and motorbikes) | - | 28.930 | - | - | - | - | - | - | - | - | - | 28.930 |
| 3.2 | - Transport equipment | - | - | - | - | - | - | - | - | - | - | - | - |
| 3.3 |  IEC materials | - | - | - | - | - | - | - | - | 14.746 | - | - | 14.746 |
| 4. | Other activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | - Advanced strategies / LIDs | - | 8.964 | - | - | - | - | - | - | - | - | - | 8.964 |
| 4.2. | - Training | - | 7.139 | - | - | - | - | - | - | 28.734 | - | - | 35.873 |
| 4.3. | - Supervision / Monitoring / Assessment | - | 35.400 | - | - | - | - | 6.004 | - | 63.918 | - | 0.652 | 105.974 |
| 4.4. | - Epidemiological surveillance | - | - | - | - | - | - | - | 0.275 | - | - | - | 0.275 |
| 4.5 | - Social mobilization | - | 393.588 | 6.244 | 5.040 | 19.763 | - | - | - | 13.961 | - | - | 434.060 |
| 4.6 | - Transport of vaccines and equipment | 12.308 | 43.000 | 8..783 | - | - | - | - | - | - | - | - | 143,138 |
| 4.7 | - Anti measles campaign | - | 8.161 | - | - | - | - | - | 33.000 | - | - | - | 41.161 |
| 4.8 | - Fuel procurement | 200.000 | - | - | - | - | - | - | - | - | - | - | 200.000 |
| 4.9 | - Various taxes(VAT, stamp duty) | - | - | - | - | - | - | - | - | - | - | - | - |
| Total expenditure in 2000 |  | 289.231 | 684.185 | 39.059 | 43.161 | 182.763 | 68.878 | 6.004 | 33.275 | 121.359 | 136.988 | 0.652 | 1 605.555 |

#### CONSOLIDATED STATEMENT OF THE SOURCE AND APPLICATION OF FUNDS FROM EPI PARTNERS – 2001 -

| Ref. # | Budget line | Government | Unicef | Canada | USAID | UNFIP | GAVI | UK | WHO | JSI | JAPAN | Total budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines… | 100.000 | 76.987 | - | - | - | 328.200 | - | - | - | 23.250 | 428.437 |
| 1.2 | - Syringes and injection kits | - | - | - | - | - | 984.300 | - | - | - | 8.230 | 992.530 |
| 2. | Equipment (cold chain, spare parts, sterilisation, etc.) |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators – cold boxes | - | 135.000 | - | - | - | - | - | - | - | - | 135.000 |
| 2.2 | - Maintenance kits | - | 22.468 | - | - | - | - | - | - | - | 8.927 | 31.395 |
| 2.3 | - Spare parts (cold chain) | - | 120.000 | - | - | - | - | - | - | - | 50.020 | 170.020 |
| 3. | Other equipment |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | - Spare parts (vehicles and motorbikes) | - | 9.476 | - | - | - | - | - | - | - | - | 9.476 |
| 3.2 | - Transport equipment | - | - | - | - | 70.000 | - | - | - | - | - | 70.000 |
| 3.3 |  IEC materials | - | 35.000 | - | - | - | 10.000 | - | - | - | - | 45.000 |
| 4. | Other activities |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | - Advanced strategies / LIDs | - | 90.000 | - | - | - | 30.000 | - | - | - | - | 120.000 |
| 4.2. | - Training | - | 30.000 | - | - | - | 30.000 | - | - | - | - | 60.000 |
| 4.3. | - Supervision / Monitoring / Assessment | - | 600.000 | - | - | - | 70.000 | - | - | - | - | 670.000 |
| 4.4. | - Epidemiological surveillance | - | - | - | - | - | - | - | 4.900 | - | - | 4.900 |
| 4.5 | - Social mobilization | - | 30.000 | - | - | - | 93.500 | - | - | - | - | 123.500 |
| 4.6 | - Transport of vaccines and equipment |  | 10.000 | - | - | - | 10.000 | - | - | - | - | 40.000 |
| 4.7 | - Anti measles campaign | 20.000 | - | - | - | - | - | - | - | - | - | 250.000 |
| 4.8 | - Fuel procurement | 250.000 | - | - | - | - | - | -- | - | - | - | 642.197 |
| 4.9 Various taxes (VAT, stamp duty) 642.197 |  |  |  |  |  |  |  |  |  |  |  |  |
| Total budget for 2001 |  | 1.012.197 | 1.158.931 | - | - | 70.000 | 1.556.000 | - | 4.900 | - | 90.427 | 2.880.258 |

#### CONSOLIDATED STATEMENT OF THE SOURCE AND APPLICATION OF FUNDS FROM EPI PARTNERS – 2002 -

| Ref. # | Budget line | Government | Unicef | Canada | USAID | UNFIP | GAVI | UK | WHO | JSI | JAPAN | Total budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | - Vaccines… | 57.402 | 658.022 | - | - | - | 1.490.445 | - | - | - | 751.430 | 2.957.299 |
| 1.2 | - Syringes and injection kits | - | - | - | - | - | - | - | - | - | - | 0 |
| 2. | Equipment (cold chain, spare parts, sterilisation, etc.) |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | - Refrigerators – cold boxes | - | 69.645 | - | - | - | - | - | - | 14.000 | - | 83.645 |
| 2.2 | - Maintenance kits | - | - | - | - | - | - | - | - | - | - | 0 |
| 2.3 | - Spare parts (cold chain) | - | 229.555 | - | - | - | - | - | - | - | 1.492 | 231.047 |
| 3. | Other equipment |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | - Spare parts (vehicles and motorbikes) | 7.777 | - | - | - | - | 5.073 | - | - | - | - | 12.850 |
| 3.2 | - Transport equipment | - | - | - | - | 14.000 | - | - | 36.923 | - | - | 50.923 |
| 3.3 |  IEC materials | - | - | - | - | - | 16.913 | - | - | 20.307 | - | 37.220 |
| 4. | Other activities |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | - Advanced strategies / LIDs | - | - | - | - | - | - | - | - | - | - | - |
| 4.2. | - Training | - | 51.012 | - | - | - | 7.805 | - | 24.187 | 21.019 | - | 104.023 |
| 4.3. | - Supervision / Monitoring / Assessment | - | 71.380 | - | - | - | 2.294 | - | - | 2.992 | - | 76.666 |
| 4.4. | - Epidemiological surveillance | - | 122.175 | - | - | - | - | - | 13.000 | - | - | 135.175 |
| 4.5 | - Social mobilization | - | 82.398 | - | - | - | - | - | - | - | - | 82.398 |
| 4.6 | - Transport of vaccines and equipment |  | 9.031 | - | - | - | 11.523 | - | - | 12.211 | - | 52.765 |
| 4.7 | - Anti measles campaign | 20.000 | - | - | - | - | 51.682 | - | - | 39.727 | - | 213.474 |
| 4.8 | - Fuel procurement | 122.065 | - | - | - | - | - | -- | - | - | - | 463.769 |
| 4.9 Various taxes (VAT, stamp duty) |  | 463.769 |  |  |  |  |  |  |  |  |  |  |
| Total budget for 2002 |  | 671.013 | 1.293.216 | - | - | 14.000 | 1.585.735 | - | 74.110 | 110.256 | 752.922 | 3.856.796 |
| Total Polio NID MNT LID |  |  | 1.769.122 |  |  |  | 137.899 |  | 1.171.00 | 13.112 | - | 3.091.133 |

ANNEX  2

Summary of documentation

| Profile of the Inter-Agency Coordination Committee (ICC) |  |
| --- | --- |
| - The ICC’s workplan for the next 12 months | Document number…2 |
| - The terms of reference of the ICC | Document number 1 |
| - The minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or injection safety | Document number 3 |
| Assessment of immunization services |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 4 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation | Document number 2 |
| Multi-Year Immunization Plan |  |
| - A complete copy (with executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan (BUSINESS PLAN ). | Document number 5 |
| - Copy of the plan to achieve Injection Safety (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or relevant pages of the health plan. See annual action plan 200 : page 8 and plan of action 2000-2005 : pages 8.9.14 and 23 | Document number 6 |
| Needs not met and requiring additional resources |  |
| - Table of expenditure for 2000-2001-2002 - Table of the budget and resource requirements 2000 (Annex 1) | Document number 4 |

* Documents already sent with the initial proposal in June 2000

Where possible, submit identical hard copies and electronic files.