Revision 3

August 2001

The Government of

The Islamic Republic of Mauritania

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Islamic Republic of Mauritania is located in West Africa between the 15th. and 27 northern parallels, and has a surface area of 1 030 700 km² , a population of 2 548 157 inhabitants, and a population density of 2.5 inhabitants per square km. The annual growth rate stands at 2.6%, and life expectancy is 51.3 years of age.

The main health parameters are the:

- Infantile death rate			74/1000

- Infantile-juvenile death rate		116/1000

- Maternal death rate			747/100,000 living births

- Gross death rate				15.98/1000

- Inter-genesical interval			35 months

The expanded programme on immunisation was initiated in our country in 1977 in Keur Macène and Rosso,  two experimental areas of Trarza. Subsequently it was gradually extended, and covered the whole country in 1984.

It applied two strategies:

- A fixed strategy based on maternal and infantile health services in urban areas.

- A mobile strategy based on mobile teams in rural areas.

A third strategy, the “accelerated strategy” based on national and municipal immunisation days, was introduced in 1985, and was later included during the mograbin immunisation days between 1987 and 1994.

Mauritania subsequently devoted itself to the eradication of poliomyelitis and controlling measles by means of national immunisation days.

In 1996 the RIM opted for the vaccine independence initiative (VII) to be responsible for the purchase of vaccines and consumables.

The overall objective of the EPI is to protect children aged between 0 and 11 months against tuberculosis, diphtheria, and women of procreation age (14-44 years) against tetanus.

According to the standard health district report, the immunisation rate for DTP-3 was 61% in 2001, which corresponds to 64,907 immunised children.

The targets of the EPI for each antigen between 2002 – 2006 are as follows:

|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| BCG | 70 | 75 | 80 | 85 | 90 | 95 |
| DTP3/polio3 | 61/58 | 70 | 75 | 80 | 85 | 85 |
| MEAS | 58 | 65 | 75 | 80 | 85 | 85 |
| TT | 31 | 40 | 50 | 60 | 70 | 70 |
| Hepatitis B |  |  |  |  |  |  |
| Haemophilus Influenzae b |  |  |  |  |  |  |

The strategies adopted to achieve these targets are based on the following aims;

- Improving immunisation standards by:

- Strengthening the fixed strategy.

- Boosting the advanced strategy.

- Gradual introduction of the innovative mobile strategy.

- Implementation of a national safe immunisation strategy.

- Enhancing competence and retraining through training and supervision, increase of EPI staff numbers at the central, regional, and peripheral levels.

- Improvement of social mobilisation

- Improvement of standards regarding planning, coordination and management (increased monitoring to make EPI quality data available, including vaccine data at the regional level).

- Increased additional immunisation through mass campaigns or screening.

- Improvement of integrated epidemiological monitoring performance.

This proposal of support for GAVI consideration was drawn up by a technical committee established by the CNC/EPI, and was subsequently amended and adopted by all members of the committee.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of The Islamic Republic of Mauritania commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	Mr. DIOP ABDOUL HAMET

Title:	Minister of Health and Social Affairs

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health and Social Affairs | Mr. Diop Hamet: Minister of Health and Social Affairs |  |
|  | Dr. Dah Ould Cheikh: Secretary-General of the Ministry of Health and Social Affairs |  |
|  | Dr. Idoumou Ould Mohamed Vall: Director for the Protection of Health |  |
|  | Dr. Mariem Takhla Mint Ahmedim: Head of the Pharmacy and laboratories |  |
|  | Dr. Isagh Ould Khalef: national EPI coordinator |  |
| Ministry of National Education | Mr. Aderrahmane Ould Mohamed Sidina |  |
| Ministry of culture and Islamic guidance | Mr. Mohamed Ali Ould Septy |  |
| Ministry of the Interior, postal services, and telecommunications | Mr. Mohamed Hady Macina: technical advisor of the ministry |  |
| Ministry of Defense | Dr. Barro Souleymane |  |
| Ministry of Communication and Relations with Parliament | Mr. Mohamed Abdallahi Ould Boussery: technical advisor of the Ministry |  |
| State Secretariat for the status of women | Mr. Oumoulvadly Kamara |  |
| French Cooperation | Mrs. Gaelle Lepape |  |
| WHO | Dr. El Hadi Benzerroug: representative |  |
| UNICEF | Mrs. Ute Deseniss Gros: representative |  |
| World Bank | Mr. Souleymane Sow: representative |  |
| Rotary International | Mr. Habibou Fall: representative |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Dr. Isagh Ould Khalef 		Title/Address : National EPI Coordinator

Tel.No: (00 222) 525 17 51

Fax No. (00 222) 525 17 51		Head Office for the protection of health

E-mail : pevmsas@yahoo.fr		P.O.B 1433 Nouakchott

Alternative address :

Name : Dr. Idoumou Ould Mohamed Vall	Title/Address : Director of the health protection office

Tel.No. : (00 222) 525 12 27		P.O.B 483 Nouakchott

Fax No.(00222 525 69 43

E-mail: dps@mauritania.mr

- Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 2 548 157 | GNP per capita | 480 $US |
| Surviving Infants* | 106 768 | Infant mortality rate | 74/ 1000 |
| Percentage of GDP allocated to Health | 2.0 | Percentage of Government expenditure for Health Care | 8.0 |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage ( in percentage ) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG |  |  | 48 | 70 | 68 | 12-23 mths |  |  | Tuberculosis | 3788 | 3617 |
| DTP | DTP1 |  | 45 | 82 | 61 | 12-23 mths |  |  | Diphtheria | 0* | 0 |
|  | DTP3 |  | 31 | 61 | 33 | 12-23 mths |  |  | Pertussis | 445* | 1331 |
| OPV3 |  |  | 31 | 58 | 37 | 12-23 mths |  |  | Polio | 0* | 0 |
| Measles |  |  | 28 | 58 | 45 | 12-23 mths |  |  | Measles | 907* | 2334 |
| TT2+ (Pregnant women) |  |  | 19 | 31 | 25 | 14-45 yrs. |  |  | NN Tetanus | 1** | 11* |
| Hib3 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Hib | S.O | S.O*** |
| Yellow Fever |  |  | N/A | N/A | N/A | N/A | N/A | N/A | Yellow fever | S.O | S.O |
| HepB3 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | hepB seroprevalence (if available) | 24*** |  |
| Vit A supplementation |  | Mothers ( < 6 weeks after delivery ) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |
|  |  | Infants ( > 6 months) | 81 | 94.9 | 58 |  |  |  |  |  |  |

*Health statistics yearbook 1997, 1998** data from the epidemiological monitoring division*** study of the prevalence of Ag HBS in blood donators at the National Hospital Centre in 1996, N/A = Not Applicable

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: Recent efforts made to restart the EPI (since May 2001), with the organisation of localised multi-antigen immunisation campaigns, the mobile strategy being applied again with regular supervision in combination with improvements in collecting, analysing, and transferring of routine data from the health districts with a satisfactory completion are favourable to routine immunisation coverage – while all these aspects were not taken into account in EDSM data of 2000-2001.

- Summary of health system development status relevant to immunisation:

The main objectives of the 4th. health action plan (1981-1985) were to increase health coverage, to make preventative action a priority, and to generalise primary health care.

The main recommendations of the national master plan 1992-1996 suggested that efforts to prevent diseases and handicaps must be more vigorous and integrated. The efforts achieved have indeed resulted in a lower incidence of some main diseases: poliomyelitis, measles, and maternal /post-birth tetanus – the infantile and infantile / juvenile death rates nevertheless remain very high. Transmissible diseases and malnutrition are the main causes of morbidity and mortality in all age groups, and the use of preventative services remains low.

Immunisation coverage made significant progress between 1991 and 2000, with a continuous increase during its first stage until stagnating and even falling after 1996. The national immunisation days organised since 1995 have been very successful with coverage rates above 90%, but the polio virus still prevails as shown by a autochthonal  case of wild polio in March 2001.

Furthermore, the RIM has committed itself to the vaccine independence initiative by taking over the purchase costs of vaccines and consumables. This budget has gradually increased from 36 to 50 million.

The current master health plan (1998-2002) reconfirms this determination to continue efforts to help a majority of people. In compliance with the commitments made by the government, poliomyelitis will be eradicated by 2005, post-birth tetanus will be eliminated to achieve an incidence of less than 1 case per 1000 living births by 2005, and measles will be controlled to achieve a 90% reduction of cases, with a 95% reduction of deaths due to this disease. Immunisation against hepatitis B and haemophilus influenzae b will be gradually become a part of the EPI from 2004 onwards.

In March 1999 the RIM was declared eligible for the initiative to reduce the debt of highly indebted poor countries (HIPC), where one of the conditions regarding health is the improvement of routine immunisation coverage, particularly that of DTP3 that must be increased to 70%.

In the strategic context of the fight against poverty, four main objectives have been outlined, of which the third aims to develop human resources and the access to essential infrastructure. This objective will have the most significant effect on poverty in the long run in the way it will help productivity and improve the living conditions of the poor. Particularly access to education and health services considerably reduces the vulnerability of the poor.

The framework of medium-term budget planning for the implementation of health strategies part of the anti-poverty strategy has specified three key objectives to reduce poverty:

- Improvement of health indicators of the Mauritanian population with strong emphasis on improving indicators regarding the most deprived sections of the population, and reduction of infantile, infantile/juvenile, and maternal mortality (e.g. reducing infantile mortality in urban areas from 75/1000 in 2001 to 60/1000 by 2004).

- Limiting the effect of costs (spending) on the income of the poor.

- Enhancing the participation of the poor.

The overall objective is to increase health spending per inhabitant from 8 US Dollars in 1999 to 14 US Dollars in 2002 in order to reach 16 US Dollars per inhabitant in the coming years.

# 	Relevant section(s) of strategies to develop the health system

	National master plan for health 1998-2002 (pages 36-59) 	number of documents 1 & 2

	Medium-term budget framework 2002-2004 (pages 3-8, 20 and 29)

# Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC: Inter-Agency Coordinating Committee for the EPI

- Date of constitution of the current ICC :  05 February 2002

- Organisational structure (e.g., sub-committee, stand-alone) : Logistical sub-committee, social mobilisation sub-committee, epidemiological monitoring sub-committee, and National Immunisation days sub-committee.

- Frequency of meetings : 1 per month during the 1st. quarter of 2002, subsequently 1 quarterly meeting during the second quarter.

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Minister of Health and Social Affairs | Mr. Diop Abdoul Hamet |
| Secretary | National EPI Coordinator | Dr. Ishagh Ould Khalef |
| Members | Secretary – General of the MSAS | Dr. Dah Ould Cheikh |
|  | Director of health protection | Dr. Idoumou Ould Mohamed Vall |
|  | Head of the pharmacy and laboratories | Dr. Mariem Takhla Mint Ahmedou |
|  | Representative of the National Education Ministry | Mr. Abderrahmane Ould Mohamed Sidina |
|  | Representative of the Ministry of Culture and Islamic guidance | Mr. Mohamed Ali Ould Septy |
|  | Technical advisor from the Ministry of the Interior, post offices and telecommunications | Mr. Mohamed Hady Macina |
|  | Representative of the Ministry of Defense, Head of the pediatric section (military hospital) | Dr. Barro Souleymane |
|  | Technical advisor of the Ministry of Communication and relations with parliament | Mr. Mohamed Abdallahi Ould Boussery |
|  | Representative of the State Secretariat for the condition of women | Mrs. Oumouvadly Kamara |
|  | Representative of French Cooperation | Mrs. Gaelle LEPAPE |
|  | Permanent representative of WHO | Dr. El Hadi Benzerroug |
|  | Permenanent representative of UNICEF | Mrs. Ute Deseniss Gros |
|  | Representative of the World Bank | Mr. Souleymane Sow |
|  | Representative of Rotary International | Mr. Habibou Fall |

- Major functions and responsibilities of the ICC:

- Elaborating a national immunisation policy against infectious diseases with epidemiological potential that can be eradicated.

- Specifying the diseases targeted by the programme.

- Follow-up of the implementation of the immunisation programme.

- Outlining goals, strategies and appropriate measures for the programme.

- Ensuring that the programme runs smoothly.

- Adopting action plans and implementing biannual plans by sector for immunisation and activity reports.

- Informing all national and international partners who are likely to support the expanded programme on immunisation.

- Supporting and encouraging information exchange and information feedback on a national level, operational with regard to external partners.

- Coordinating activities and commitments of partners.

- Ensuring that the partnership established by the National Committee reveals itself as a positive support for both the routine EPI and the national immunisation days.

- Four major strategies to enhance ICC’s role and functions in the next 12 months :

- Enhancement of logistics and the cold chain.

- Implementation of the strategic communication plan for development & social mobilisation.

- Increased integrated epidemiological monitoring.

- Qualitative improvements of national immunisation days, synchronised door to door.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- Drop-out rate between DTP1 and DTP3.

- Drop-out rate of vaccines.

- Integrated epidemiological monitoring  (AFP).

- Number of health facilities using auto-destruct syringes and safety boxes.

Attached are the supporting documents :

| - Terms of reference of the ICC | Document number 4 |
| --- | --- |
| - ICCs workplan of next 12 months | Document number 3 |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number 5 |

# Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Document based analysis of the routine EPI and disease monitoring | MSAS/WHO/ UNICEF | JAN 2002 |
| External review of the EPI in Mauritania, September 2001 to April 2002 | WHO/UNICEF/ICP EPI | APR 2002 Version |
| Demographic and health survey in Mauritania. | MSAS/FNUAP/ USAID / Central Statistical Bureau, National Statistics Bureau | 2000-2001 |
| Strategic communication plan for development / social mobilisation | MSAS/WHO/ UNICEF | 2001 |

- The three major strengths identified in the assessments :

- Membership of the vaccine independence initiative

- Good storage capacity at the central level.

- Creation of an integrated epidemiological monitoring system

- Creation of a coordination committee for national programmes of communication / pleading /

- Social mobilisation.

- The three major problems identified in the assessments :

- Low immunisation coverage

- Lack of means of communication (radio, fax, e-mail, vehicles…)

- Inadequate social mobilisation

- The three major recommendations in the assessments :

- Improvement of routine immunisation quality standards and integrated monitoring of diseases.

- Greater community participation and improvement of social mobilisation.

- More widespread additional immunisation.

- Attached are  complete copies (with an executive summary) of :

| - the most recent assessment reports on the status of immunization services | Document number 6,7,8 |
| --- | --- |
| - a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 9 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Financing of the EPI |  |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 10 |
| --- | --- |

(available)

| - Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| Consultants | 2002 - 2004 | WHO/UNICEF/IDA |
| Training programmes | 2002 - 2003 | WHO/UNICEF/IDA |
| Management tools | 2002 - 2003 | WHO/UNICEF/IDA |

| Table 3 : Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : |  | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG & POLIO | At birth | x |  |  |
| DTP1/POLIO 1 | 6 weeks | x |  |  |
| DTP2/POLIO 2 | 10 weeks | x |  |  |
| DTP3/POLIO 3 | 14 weeks | x |  |  |
| Measles | 9 months | x |  |  |
| TT 1 | After age 14 / during pregnancy | x |  |  |
| TT 2 | 4 weeks after TT 1 | x |  |  |
| TT 3 | 1 year after TT 2 | x |  |  |
| TT 4 | 1 year after TT 3 | x |  |  |
| TT 5 | 1 year after TT 4 | x |  |  |
| Vitamin A | 1st.dose after 6 months of age 2nd. dose 6 months later | x |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

Improvement of immunisation quality by:

- Enhancing the fixed strategy

- Re-boosting the advanced strategy

- Re-launching the mobile strategy

- Gradual introduction of the innovative mobile strategy

- Implementation of the national injection safety strategy

- Better training and retraining

- Improvement of social mobilisation

- Improvement of management and planning standards

- Increased additional immunisation through organised mass campaigns or screening.

- Improvement of integrated epidemiological monitoring performance.

| Table 4 : Baseline and annual targets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of |  | Baseline | Targets |  |  |  |  |  |  |  |
|  |  | 2000 | 2001 | 2002 |  | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births |  | 121 037 | 124 184 | 127 413 |  | 130 718 | 134 117 | 137 604 | 141 182 |  |
| Infants’ deaths |  | 74/1000 | 74/1000 | 74/1000 |  | 72/1000 | 72/1000 | 70/1000 | 70/1000 |  |
| Surviving infants |  | 106 768 | 114 945 | 117 984 |  | 121 306 | 124 461 | 127 772 | 131 298 |  |
| Infants vaccinated with BCG* |  | 58 098 | 86 929 | 95 560 |  | 104 571 | 114 000 | 123 844 | 134 407 |  |
| Infants vaccinated with OPV3** |  | 33 098 | 70 117 | 82 589 |  | 93 291 | 99 569 | 108 606 | 111 604 |  |
| Infants vaccinated with DTP3** |  | 33 098 | 70 117 | 82 589 |  | 93 291 | 99 569 | 108 606 | 111 604 |  |
| Infants vaccinated with**: (use one row for any new vaccine) |  | N/A | N/A | N/A |  | N/A | 24 892 | 38 332 | 111604 |  |
| Infants vaccinated with Measles** |  | 29 895 | 66 669 | 76 690 |  | 90 976 | 99 569 | 102 218 | 111 604 |  |
| Pregnant women vaccinated with TT+ |  | 22 997 | 38 498 | 50 966 |  | 65 359 | 80 471 | 96 329 | 98 828 |  |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A |  |
|  | Infants (> 6 months) | 328 179 | 384 901 | 415 693 |  | 426 501 | 437 590 | 448 967 | 460 640 |  |
| * Target of children out of total births |  |  |  |  | ** Target of children out of surviving infants |  |  |  |  |  |

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

- 1998: Survey carried out to ascertain wastage rates in 6 Wilaya which revealed the importance of monitoring wastage rates.

- 1998: The supply of vials containing 10 doses was standardised.

- 1999: Elaboration of national directives for opened vials, and training of health staff on policies pertaining to opened vials

- 2000: Implementation of computerised management of antigens.

- 2001: Implementation of EPI data and cold-chain follow-up management.

- 2002: Updating of directives regarding the use of opened vials in the context of the dissemination of directives to restart the EPI (ministerial memorandum).

- 2002: Introduction of systematic feedback to Wilaya’s regarding vaccine monitoring.

- 2002 : Training of regional EPI centres on managing the programme (including vaccine management).

- 2002:  Review of the vaccine supply plan at the central level (2 supply runs per year instead of 1).

| Table 5 : Estimate of annual DTP wastage and drop out rates |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual | Targets |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 46.6% | 33.7% | 25 | 25 | 20 | 20 | 15 |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 31 | 24 | 20 | 15 | 10 | 7 | 5 |  |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates. N/A

- Planning and constraints for the Polio Eradication Initiative:

Mauritania is a very large country with a very spread out population, with a hardly developed communication network, and health coverage that remains insufficient.

Data on performance of the routine immunisation programme and monitoring of targeted diseases is often incomplete and arrives late. Data on immunisation coverage shows low rates for all antigens including OPV, with high wastage rates that are pronounced in view of the low use of health facilities.

Synergies remain to be developed between the division and supervision of management teams of the routine immunisation programme.

Mauritania organises eradication campaigns against polio and for the control of measles since 1995. Coverage rates exceeding 90% have not yet made it possible to stop the circulation of the wild polio virus (isolation of an autochtonal wild polio case in 2001), hence the importance to have synchronised door-to-door NID’s with the goal of reaching the final areas where the wild polio virus still causes very occasional cases of AFP.

The quality of the NID’s will be improved in the short run, with a better run active monitoring system and the organisation of screening campaigns if required. Special emphasis shall be placed on restarting the routine EPI programme.

# Injection safety

7.1	Summary of the injection safety strategy for immunization (for all countries):

In order to contribute to improving the state of health of the population, the government of the RIM has committed itself to ensuring the secure and rational use of injections to avoid any risk to the person receiving injections, to those administering these, and to the community. The RIM has therefore elaborated a multi – annual plan in the context of the EPI and the vaccine independence initiative for the implementation of the national injection safety strategy based on the following considerations:

2000: Generalisation of the use of AD syringes as injection material of the EPI.

2000: Survey of injection safety that singled out pitfalls.

2001:

Elaboration of a national policy project regarding injection safety.

Elaboration of a multi-year plan for the implementation of an injection safety policy based on the following:

Training / retraining / supervision of health staff (public & private sectors) regarding stock management, injection safety, rationalisation of prescriptions, and waste management.

Long-term budgeting approach for the purchase of vaccines and consumables.

Regular supply of injection material, of samples, and consumables only usable once.

Communication with the community regarding injection safety through Information and education.

Construction / repairing incinerators.

| - Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 11 |
| --- | --- |

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1: Estimated supplies for safety of vaccination with BCG ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 95 560 | 104 571 | 114000 | 134 407 | 134 407 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of BCG doses | A x B | 95 560 | 104 571 | 114000 | 123 844 | 134 407 |
| D | AD syringes (+10% wastage) | C x 1.11 | 106 071 | 116 074 | 123 654 | 137 467 | 149 192 |
| E | AD syringes buffer stock | D x 0.25 | 26 517 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 132 588 | 116 074 | 123 074 | 137 467 | 149 192 |
| G | Number of doses per vial | # | 20 | 20 | 20 | 20 | 20 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 7359 | 6443 | 6863 | 7630 | 8281 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 1554 | 1360 | 1449 | 1567 | 1748 |

Table 6.2 : Estimated supplies for safety of vaccination with DTP ( Use  one table for each vaccine BCG, DTP, TT and measles, and  number them from 6.1 to 6.4)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 82587 | 93291 | 99569 | 108606 | 111604 |
| B | Number of doses per child (for TT woman) | # | 3 | 3 | 3 | 3 | 3 |
| C | Number of DTP doses | A x B | 247761 | 279873 | 298707 | 325818 | 334 812 |
| D | AD syringes (+10% wastage) | C x 1.11 | 275014 | 310659 | 331567 | 361658 | 371641 |
| E | AD syringes buffer stock | D x 0.25 | 68753 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 343768 | 310659 | 331567 | 361658 | 371641 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G |  |  |  |  |  |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 3816 | 3448 | 3680 | 4014 | 3717 |

Table 6.3 : Estimated supplies for safety of vaccination with MEAS ( Use  one table for each vaccine BCG, DTP, TT and measles, and  number them from 6.1 to 6.4)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 76690 | 90976 | 99569 | 102218 | 111604 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 | 1 |
| C | Number of MEAS doses | A x B | 76690 | 90767 | 99569 | 102218 | 111604 |
| D | AD syringes (+10% wastage) | C x 1.11 | 85126 | 100984 | 110522 | 113452 | 123880 |
| E | AD syringes buffer stock | D x 0.25 | 21281 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 106407 | 100984 | 110522 | 113452 | 123880 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G | 8512 | 1010 | 1105 | 1134 | 1238 |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 1276 | 1234 | 1240 | 1272 | 1389 |

Table 6.4 : Estimated supplies for safety of vaccination with TT ( Use  one table for each vaccine BCG, DTP, TT and measles, and  number them from 6.1 to 6.4)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination (for TT target of women) | Match with targets in table 4 | 50965 | 65363 | 80475 | 96328 | 98828 |
| B | Number of doses per child (for TT woman) | # | 5 | 5 | 5 | 5 | 5 |
| C | Number of TT doses | A x B | 254825 | 326815 | 40375 | 481640 | 494140 |
| D | AD syringes (+10% wastage) | C x 1.11 | 282856 | 362765 | 446636 | 534620 | 584594 |
| E | AD syringes buffer stock | D x 0.25 | 0 | 0 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 282856 | 362765 | 446 | 534620 | 548954 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 |
| H | Number of re-constitution syringes (+10% wastage) | C x 1.11 / G |  |  |  |  |  |
| I | Number of safety boxes (+10% of extra need) | ( F + H ) x 1.11 / 100 | 3140 | 4027 | 4958 | 5934 | 6090 |

  - Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | ###### Area of support | Start of fund utilization |
| --- | --- | --- |
|  | AD syringes and waste disposal boxes | 2002 |
| GAVI/Vaccine Fund |  |  |

(Use as many rows as necessary

# New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

The vaccine against hepatitis B will be gradually introduced in the routine EPI as of 2004, and will concern the two most populated wilaya (regions) of Nuakchott and Noudhibou which account for 27% of the total population of the country. The vaccine will be extended to the rest of the country as of 2006.

An initial study of the haemophilus influenzae b vaccine is planned for 2003 to gather missing data on this subject, with its introduction in the immunisation programme due to take place in 2004.

It is with this in mind that a regular and progressive supply of vaccines and consumables has been taken into account in the multi-year plan that will be preceded by a strengthening of technical and logistical capacity. A process of monitoring and assessment will take place simultaneously with the introduction of the new vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B | Study of the prevalence of HBS in blood donors at the National Hospital Centre | 1996 | 24% |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines: N/A

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- The introduction of new vaccines will require:

- Increased technical capacity ( training) and logistical means.

- Increased storage capacity for vaccines and consumables in the Moughataas and some Wilayas.

- Training and supervision of health agents on the correct storage of vaccines in the cold chain and during transport.

- More rigorous monitoring of temperature mornings and evenings.

- Introduce a list (?) of refrigeration during supervision.

- Actual implementation of the policy regarding opened vials.

- Providing feedback at all levels regarding vaccine monitoring.

- Adjusting intervals of supply deliveries to Wilayas and Moughataas according to storage capacity.

- Improving management of services to reduce dropout rates and loss of vaccines.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulas)

| Table 7.1: Estimated number of doses of hepatitis B vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to receive new vaccine | match with targets in table 4 |  |  | 6228 | 9581* | 111604** |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in percent | % |  |  | 25 | 20 | 15 |  |
| D | Equivalent wastage factor | See list in table  |  |  | 1.33 | 1.25 | 1.18 |  |
| E | Number of doses | A x B x D |  |  | 24842 | 35929 | 395078 |  |
| F | Number of vaccines buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total of vaccine doses needed | E + F |  |  | 31053 | 35929 | 395078 |  |
| H | Percentage of vaccines requested from the Vaccine Fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  | 31053 | 35929 | 395078 |  |
| J | Number of doses per vial | # |  |  | 10 | 10 | 10 |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  | 25572 | 31905 | 371642 |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  | 6393 | 7976 | 92911 |  |
| M | Total of AD syringes | K + L |  |  | 31965 | 39881 | 464553 |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  |  |  |  |  |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 |  |  | 426 | 531 | 5157 |  |

*in 2004 & 2005: Immunisation only in two regions (Nouakchott and Dahklet Nouadhibou)

** in 2006: expansion of immunisation to the entire country.

| Table  : Wastage rates and factors |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulas as per table 7.1)

| - Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# Table 7.2 : estimated number of doses of haemophilus influenzae b vaccine, vials of 10 doses

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 |  |  | 6226* | 9581 | 111 604 |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in percent | % |  |  | 25 | 20 | 15 |  |
| D | Equivalent wastage factor | See list in table  |  |  | 1.33 | 1.25 | 1.18 |  |
| E | Number of doses | A x B x D |  |  | 24 842 | 35 929 | 395078 |  |
| F | Number of vaccines buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total of vaccine doses needed | E + F |  |  | 31053 | 35929 | 395078 |  |
| H | Percentage of vaccines requested from the Vaccine Fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  | 31053 | 35929 | 395078 |  |
| J | Number of doses per vial | # |  |  | 10 | 10 | 10 |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  | 25572 | 31905 | 371642 |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  | 6393 | 7976 | 92911 |  |
| M | Total of AD syringes | K + L |  |  | 31965 | 39881 | 464553 |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  | 3447 | 3988 | 4386 |  |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 |  |  | 393 | 487 | 5206 |  |

*In 2004 & 2005; immunisation will only occur in 2 regions (Nouakchott and Dahklet Noudhibou)

** In 2006; immunisation will be carried out in the whole country.

Table 7.3: Estimated number of doses  of  hepatitis B  vaccine, 1 dose per vial

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 |  |  | 6226* | 9581* | 111604 |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in percent | % |  |  | 5 | 5 | 5 |  |
| D | Equivalent wastage factor | See list in table  |  |  | 1.33 | 1.25 | 1.18 |  |
| E | Number of doses | A x B x D |  |  | 24842 | 35929 | 395078 |  |
| F | Number of vaccines buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total of vaccine doses needed | E + F |  |  | 31053 | 35929 | 395078 |  |
| H | Percentage of vaccines requested from the Vaccine Fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  | 31053 | 35929 | 395078 |  |
| J | Number of doses per vial | # |  |  | 1 | 1 | 1 |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  | 25572 | 31905 | 371642 |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  | 6393 | 7976 | 92911 |  |
| M | Total of AD syringes | K + L |  |  | 31965 | 39881 | 464553 |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  |  |  |  |  |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 |  |  | 426 | 531 | 5157 |  |

*In 2004 & 2005; immunisation will only occur in 2 regions (Nouakchott and Dahklet Noudhibou)

** In 2006; immunisation will be carried out in the whole country.

Table 7.4: Estimated number of doses  of  hepatitis B  vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …)

|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine | match with targets in table 4 |  |  | 6226* | 9581 | 111604 |  |
| B | Number of doses per child | # |  |  | 3 | 3 | 3 |  |
| C | Estimated wastage rate in percent | % |  |  | 5 | 5 | 5 |  |
| D | Equivalent wastage factor | See list in table  |  |  | 1.33 | 1.25 | 1.18 |  |
| E | Number of doses | A x B x D |  |  | 24842 | 35929 | 395078 |  |
| F | Number of vaccines buffer stock | E x 0.25 |  |  | 6211 | 0 | 0 |  |
| G | Total of vaccine doses needed | E + F |  |  | 31053 | 35929 | 395078 |  |
| H | Percentage of vaccines requested from the Vaccine Fund | % |  |  | 100 | 100 | 100 |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  | 31053 | 35929 | 395078 |  |
| J | Number of doses per vial | # |  |  | 1 | 1 | 1 |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  | 25572 | 31905 | 371642 |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  | 6393 | 7976 | 92911 |  |
| M | Total of AD syringes | K + L |  |  | 31965 | 39881 | 464553 |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  | 7096 | 8853 | 55654 |  |
| ##### O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 |  |  | 434 | 541 | 10881 |  |

*In 2004 & 2005; immunisation will only occur in 2 regions (Nouakchott and Dahklet Noudhibou)

** In 2006; immunisation will be carried out in the whole country.

# Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan by the time of the mid-term review. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

The Government is planning to increase the mobilisation of resources intended for the immunisation of children:

- Relying more heavily on the National Coordination Committee of the EPI.

- Gradually increasing state contributions by making the most of the HIPC initiative.

- Increasing community involvement in financing of peripheral activities.

- Using safety funds at a decentralised level to finance the functioning of the cold chain (purchase of gas, etc…).

| - Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

- Vaccines whose price does not vary according to packaging size (new vaccines  and others such as DTP and the polio vaccine with low cost variations between 10-20%). The cost reduction for such vaccines is invariable  linked to the reduction of wastage due to the use of opened vials and small quantities – a key factor.

- Vaccines whose cost varies significantly according to packaging size (e.g. TT: 49% cost increase between 10-20 doses). A cost reduction for this vaccine can only be achieved by reducing the wastage rate. A reduction of recurrent costs could therefore be achieved with 20 dose packages instead of 10, even if wastage rates are high.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Islamic Republic of Mauritania

considering that its DTP3 coverage for 2000 was 31%%  corresponding to 33098 number of children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 29434 (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 9 : New and under-used vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Hepatitis B | 10 | 2004 | 155 256 | 119 205 |
| Haemophilus Influenzae b (multi-doses) | 10 | 2004 | 124 205 | 119 768 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are entitled to receive US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 8

The equivalent amount of funds

| Table 8: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 2002 | 2003 | 2004 | 2005 | 2006 |
| F | Total AD syringes | for BCG | 132 588 | 116 074 | 123 654 | 137 467 | 149 192 |
|  |  | for other vaccines | 733 031 | 804 408 | 888 725 | 1 009 730 | 1 044 115 |
| H | Total of reconstitution syringes |  | 15 881 | 7 453 | 7 968 | 8 764 | 9 514 |
| I | Total of safety boxes |  | 9 786 | 10 069 | 11 327 | 12 787 | 12 944 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

# Additional comments and recommendations from the ICC

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2000 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expend-iture in 2000 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure in 2000 |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 2000 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |  |
| --- | --- |
| - Attached are the relevant section(s) of strategies for health system development | Document number 1,2 |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |  |
| - ICC’s workplan of next 12 months | Document number 3 |
| - Terms of reference of the ICC | Document number 4 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number 5 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report(s) on the status of immunization services | Document number 6,7,8 |
| - Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number 9 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 10 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number 10 Document number 11 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 2000 and resource needs (Annex 1) | Document number 12 |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
| #### City – Country : |  |  |  |  |  |  |  |  |  |  |
| Telephone No. : |  |  |  | Fax No. : |  |  |  |  |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  |  |
| For credit to : Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No. : |  |  |  |  |  |  |  |  |  |  |
| At : Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited ? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : |  |  |  |  |  |  |  |  | Seal : |  |
| #### Title : |  |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  |  |  |  |  |
| Branch Name : |  |  |  |  |  |
| Address : |  |  |  |  |  |
| City – Country : |  |  |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code : |  |  |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No : |  |  |  |  |  |
| Fax No : |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : |  |  |
| 1 Name : Title : |  |  | Signature : |  |  |
|  |  |  | Date: |  |  |
| 2 Name : Title : |  |  | Seal: |  |  |
| 3 Name : Title : |  |  |  |  |  |
| 4 Name : Title : |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

General population and habitat census of 2000

demographic and health survey of 2000-2001

The document “ documentary analysis of the EPI and monitoring” was elaborated by WHO consultants.

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and

Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and

Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and

Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and

Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible