# DRAFT

# Introduction of Hepatitis B Vaccine in Afghanistan

# Kabul

# March, 2005

# Executive Action Document

Introduction of Hep B vaccine in Afghanistan

Burden of disease:

There are very few studies on viral hepatitis in Afghanistan. However, available studies suggest that hepatitis B virus (HBV) infection is an important public health problem of interme and a major cause of morbidity and mortality.

- Based on blood donor screening data and community surveys, it is estimated that 7% (1.7 million persons) of the general population have chronic HBV infection

- Hepatitis B is a leading cause of cirrhosis of the liver and primary hepatocellular carcinoma.

  - It is estimated that approximately 11,000 persons in each birth cohort will die each of HBV-induced liver disease without the introduction of hep B vaccine into the EPI program.

- HBV infection is a leading cause of acute viral hepatitis in Afghanistan

- The most important and effective strategy for the prevention of HBV-related chronic liver disease in Pakistan is introduction of hep B vaccine into the EPI program

Strategy for introduction of hep B vaccine into EPI

The EPI program has developed a comprehensive strategy for the introduction of hep B vaccine into the national immunization program.

- Application for GAVI support for vaccine introduction using combination vaccine DTP-HepB.

  - Phased financial contribution by the Government of Afghanistan and its partners for vaccine purchase

- Nationwide integration of DTP-HepB combo into EPI in 2006

- Applied research related to hep B vaccine introduction

  - Studies to evaluate prevalence of hepatitis B surface antigen (HBsAg) among pregnant women in different parts of the country

  - Serosurvey among children to assess the prevalence of chronic HBV infection prior to vaccine introduction.

- In the event that combination vaccine is not available, the MOH will implement a phased introduction of monovalent hep B vaccine in 2006.

Plan of action

- Finalize GAVI application

- Develop advocacy and social mobilization material

- Under take advocacy   and social mobilization activities to support hep B vaccine introduction in Afghanistan.

- Develop training materials and plan for vaccine introduction according to availability of combination versus monovalent vaccine

  - Training should include

    - Schedule of  Hep B vaccine in EPI (if monovalent)

    - Multiple injections during a single visit  ( if monovalent)

    - Proper storage and handling of hep B vaccine

    - IM administration of hep B vaccine

    - Strategy to ensure EPI vaccines are not diverted to private sector or non target age groups.

    - Reporting

- Monitor hep B vaccine coverage along with other EPI indicators.

- Develop a research plan to evaluate

  - Prevalence of HBsAg among pregnant women in different parts of Afghanistan

  - Prevalence of HBsAg among children in a few sentinel sites to monitor long term impact of vaccine introduction

Quantity of vaccines required.

Preference 1 .  DPT-HEP B (comb)

This presentation of vaccine, if provided by GAVI will be introduced nationwide from  January 1, 2006 as it will like DPT from  operational point of view.

For 2006,   a total of 4,462,708 million doses of  DPT-Hep B (combo) vaccine in 10 dose vials  including 25 % buffer stock i.e 100% requirement of DPT-HepB 1 target   will be requested  from GAVI.

The detailed requirement of vaccine  doses , with source of funding for next five years  is given in the table below:

Table : Year wise requirement of DPT-HepB (combo) vaccine and source of funding

|  | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
| Total Doses of DPT-Hep B (combo ) required | 4,462,708 | 3,737,092 | 3,909,969 | 3,860,015 | 3,952,659 |
| Doses requested from GAVI | 4,462,708 | 3,737,092 | 3,127,975 | 2,702,010 | 2,371,595 |
| Percentage of the total requirement requested from GAVI | 100 | 100 | 80 | 70 | 60 |
| Doses to be procured by GOA and its partners | 0 | 0 | 781,994 | 1,158,005 | 1,581,064 |

The rationale for choosing DPT-Hep B (combo) vaccine for EPI Afghanistan  is  because of the following  advantages:

- Fewer injections

- Fewer AEFI

- No increase in  coold room storage

- Minimal training requirement

- Nation wide introduction possible

- Coverage tracks  with DPT3.

Preference 2 -HEP B  vaccine (monovalent)

In case Afghanistan is approved for Hep B monovalent vaccine, it will be introduced in a phased manner. In phase 1, it will be introduced from January 1, 2006 in the Central region comprising of approximately 26% of the target population of the country. The phase 2 will begin from January 1, 2007 when   it will be introduced in all the remaining portions of the country.

The detailed requirement of Hepatitis B (monovalent)  vaccine  doses , with source of funding for next five years  is given in the table below:

Table : Year wise requirement of HepB (monovalent) vaccine and source of funding

|  | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
| Total Doses of Hep B (monovalent) required | 1,168,006 | 4,612,964 | 3,909,969 | 3,860,015 | 3,952,659 |
| Doses requested from GAVI | 1,168,006 | 4,612,964 | 3,127,975 | 2,702,010 | 2,371,595 |
| Percentage of the total requirement requested from GAVI | 100 | 100 | 80 | 70 | 60 |
| Doses to be procured by GOA and its partners | 0 | 0 | 781,994 | 1,158,004 | 1,581,063 |

Timeline and detailed action plan and indicators for Hep B vaccine introduction in Afghanistan

| Activity: Advocacy/Development of plan of action/training | 2005 | 2006 | Responsible | Indicator | Means of verification | Target |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  | 2005 | 2006 |
| Finalize national plan, review by ICC and submission to GAVI | x |  |  |  |  |  |  | NEM | Plan submitted | Covering letter by MoH regarding submission of the proposal. | Done |  |
| Identify national EPI focal point(s) for measles and hep B | x |  |  |  |  |  |  | NEM / DG PM & PHC | Focal point identified | Official notification | X |  |
| Establish task force on hepatitis B vaccine introduction | x |  |  |  |  |  |  | ICC | T.F established | Official notification | X |  |
| Revise recording, reporting documents to reflect hep B vaccine introduction | x |  |  |  |  |  |  | Task Force on Hep B vaccine introduction | Documents revised | Revised (updated) documents | 100% |  |
| Ensure availability of resources (GAVI new vaccines window) | x |  |  |  |  |  |  | NEM | Availability of resources | Letter of approval by GAVI | 100% |  |
| Prepare appropriate training material for Master trainers, EPI Supervisors and vaccinators | X |  |  |  |  |  |  | Task Force on Hep B vaccine introduction | Training material developed | Training material available | 100% |  |
| Training of Master Trainers |  | X |  |  |  |  |  | Task Force on Hep B vaccine introduction | Conduction of Training workshops | Workshop report/s | 20 |  |
| Training of EPI supervisors & vaccinators |  | x | x |  |  |  |  | Task Force on Hep B vaccine introduction | % of staff trained | Report of training courses | 80% | 20% |
| Activity: Advocacy/Development of plan of action/training | 2005 | 2006 | Responsible | Indicator | Means of verification | Target |
|  | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  | 2005 | 2006 |
| Training of Regional Cold room manager |  | X |  |  |  |  |  | National Cold Chain Manager | -Number Trained | Training report | 80 |  |
| Review of preparations for introduction of Hep B vaccine |  | X | X | X |  |  |  | National ICC ( Q3 & Q4 meeting) | Review meetings | Minutes of meetings | 2 | 1 |
| Advocacy meetings at National level |  | x | x |  |  |  |  | National ICC | Number of meetings | Minutes of meetings | 2 |  |
| Advocacy meetings at Regional & Provincial level |  | X | X |  |  |  |  | Regional & Provincial ICC | Number of meetings | Minutes of meetings | 34 | 68 |
| Develop, print and distribute social mobilization materials. Media campaign and briefing material |  | X | X |  |  |  |  | Task Force on Hep B vaccine introduction | Required material prepared Media campaign undertaken | Relevant material Campaign material | 2 2 | 4 |
| Activity: Operational research for program evaluation Activity /T |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify focal point for hep B program evaluation |  |  |  | X |  |  |  |  | F.P identified | Official notification |  | 1 |
| Identify & secure resources to support baseline evaluation of HBV burden of disease |  |  | X |  |  |  |  | National EPI Focal point for measles and hepatitis B | Resource identified | Letter of commitment or equivalent |  | 100% |
| Development of protocol to evaluate prevalence of HBsAg among pregnant women |  |  |  | x |  |  |  | Focal Point for Hep B program evaluation | Protocol developed | Copy of the protocol |  | X |
| Activity: Advocacy/Development of plan of action/training | 2005 | 2006 | Responsible | Indicator | Means of verification | Target |
|  | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  |  |  | 2005 | 2006 |
| Procure kits for HBsAg testing |  |  |  |  | x |  |  | National EPI Focal point for measles and hepatitis B | # of kit procured | Stock register or equivalent |  | 200 |
| Train teams on survey methods |  |  |  |  |  | X |  | Focal Point for Hep B program evaluation | Training workshops | Workshop report |  | 10 |
| Finalize national plan, review by ICC and submission to GAVI | x |  |  |  |  |  |  | NEM | Plan submitted | Covering letter by MoH regarding submission of the proposal. |  | X |
| Identify national EPI focal point(s) for measles and hep B | x |  |  |  |  |  |  | NEM / DG PM & PHC | Focal point identified | Official notification |  | 1 |

National Task Force for introduction of Hepatitis B vaccine in EPI Afghanistan

Members

- NEM- EPI  ( Chairman)

- Deputy NEM- EPI  (Secretary)

- WHO Technical Advisor EPI

- UNICEF Project Officer EPI

- National GAVI Immunization Advisor

- Sr.EPI Trainer

- National Cold Chain Manager

Terms of Reference

- Will act as a technical body to brief National ICC on the relevant issues pertaining to introduction of Hepatitis B vaccine in the EPI

- Will prepare training material for all levels of EPI Staff

- Will  train the master trainers.

- Will modify the reporting instruments

- Will under take field visits , as individual member or sub group to monitor the preparations for introduction of Hepatitis B vaccine in the field, including the training imparted by the master trainers  and subsequent monitoring of the service delivery.

- Will assist the National, Regional and Provincial ICCs , if required by them, as individual members or sub group during the advocacy meetings.

- Will coordinate research activities pertaining to hepatitis undertaken by EPI

- May Co-opt any other member or members having specialized technical capabilities or as representative of a partner agency/NGO  to assist the task force in undertaking its responsibilities as mentioned above.

- The composition of the task force and its Terms of Reference may be modified by National ICC as and when required.

Prevention of HBV-related chronic liver disease in Afghanistan

- BACKGROUND AND RATIONALE

  - Epidemiology of Hepatitis B virus (HBV) infection I

HBV infection is a major public health problem worldwide. Approximately 30% of the world’s population, or about 2 billion persons, have serologic evidence of current or past HBV infection. Of these, an estimated 360 million have chronic HBV infection and more than 500,000 chronically infected persons die each year from liver cancer and cirrhosis. HBV is second only to tobacco as a known human carcinogen.

A safe and effective vaccine against HBV infection has been available since the early 1980s with an increasing number of countries introducing hepatitis B (HepB) vaccine into their routine childhood immunization schedule. HepB vaccine provides protection when given either before or very shortly after exposure. At least 85–90% of HBV infections are vaccine-preventable. WHO has recommended since the early 1990’s that hepatitis B vaccine be integrated into routine infant immunization programmes in all countries with sufficient disease burden.

In countries with high and intermediate HBV-endemicity, most HBV-related disease burden results from the sequels of chronic HBV infection acquired at birth or in early childhood. Thus, the primary objective of Hep B immunization in these countries is to prevent perinatal and early childhood HBV transmission and reduce the prevalence of chronic HBV infection .  The contribution of perinatal HBV transmission to overall disease burden varies by the prevalence of HBsAg among pregnant women and the prevalence of HBeAg among women who are HBSAg-positive.  In communities with high prevalence of HBsAg and high prevalence of HBeAg, perinatal transmission can account a substantial proportion (up to 40%) of all chronic HBV infections among children. These infections can be prevented by the timely administration of Hep B vaccine at birth (within 24 hours) and completion of the vaccination series by 6 months of life.

Chronic liver disease is an important public health problem in Afghanistan and prevention of HBV transmission is an important public health priority. The Ministry of Public Health (MOPH) plans to introduce Hep B vaccine into the Expanded Program on Immunization in 2006 through an application for new vaccine introduction to Global Alliance for Vaccines and Immunization. Based on a burden of disease assessment, routine infant immunization is the most effective strategy to prevent HBV infection and death due to HBV-induced chronic liver disease in Afghanistan.

- BURDEN OF DISEASE

  - Prevalence of chronic HBV infection

There are very few data on the prevalence of chronic HBV infection in Afghanistan. Data from blood bank screening from sites throughout the country revealed a prevalence of HBsAg of 7.6% in 2002 and 6.7% in 2003 (Table 1).  In 2003, a cross sectional serosurvey was conducted among Afghan refugees residing in camps in Balochistan, Pakistan.  These camps included long term and recent arrivals with a total population of 320,000. Overall, HBsAg testing was conducted on 903 persons from 304 families using a rapid a one-step HBsAg antigen detection device. Overall, 8.3% of the population were HBsAg positive. The prevalence of HBsAg among refugees entering the US was reported to be 4.1% in 1991.

Table 1. Prevalence of chronic HBV infection in Afghanistan

| Source | Year | No. tested | No. HBsAg + | Percent |
| --- | --- | --- | --- | --- |
| ICRC blood banks | 2002 | 13815 | 1056 | 7.6 |
| ICRC blood banks | 2003 | 14100 | 940 | 6.7 |
| Community survey of refugees in Balochistan | 2003 | 903 | 75 | 8.3 |
| Afghan refugees in the United States | ‘91 | NA | NA | 4.1 |

The age-specific prevalence of HBsAg was evaluated in the community-based study in Balochistan and revealed 5.9% of children had evidence of chronic HBV infection and an increasing prevalence among older age groups (Table 2).  In this study 7.1% of mothers were HBsAg-positive.  Children born to HBsAg positive mothers were more likely to HBsAg-positive (25%) when compared to children born to HBsAg-negative mothers (4.4%).

Table 2. Sero-prevalence of HBsAg by age group among Afghan Refugees in Pakistan

| Age (Years) | Total Observations | HBsAg Positive Cases (n) | Sero-prevalence | 95%C.I |
| --- | --- | --- | --- | --- |
| 0-5 | 119 | 7 | 5.9% | 2.4 - 11.9 |
| 6-10 | 130 | 6 | 4.6% | 1.7 - 9.7 |
| 11-15 | 40 | 2 | 5.0% | 0.9 - 15.5 |
| 16-20 | 38 | 3 | 7.9% | 1.6 - 21.3 |
| 21-30 | 191 | 17 | 8.9% | 5.2 - 13.8 |
| 31-40 | 199 | 21 | 10.5% | 6.6 - 15.7 |
| 41-50 | 119 | 13 | 11% | 5.9 - 17.9 |
| > 50 | 67 | 6 | 8.9% | 3.3 - 18.5 |

  - Chronic Liver disease in Afghanistan and Pakistan

There is one published study on the etiology of chronic liver disease in Afghanistan. In a study of 14 patients admitted to Jamhuriat hospital in Kabul revealed 7 had evidence of chronic HBV infection.  This finding is consistant with other studies in the region indicating HBV infection is a leading cause of chronic liver disease (Table 3).

Table 3. Serologic studies of patients with chronic liver disease in Afghanistan and Pakistan

| Study | Disease | No. evaluated | Percent positive |
| --- | --- | --- | --- |
|  |  |  | HBV | HCV | HBV and HCV |
| Pakistan |  |  |  |  |  |
| Zuberi | Liver cancer | 599 | 59 | 10 | 6 |
| Mujeeb | Liver cancer | 54 | 43 | 9 | 24 |
| Quereshi | Liver cancer | 366 | 60 | NA | NA |
| Malik | Cirrhosis | 24 | 21 | 13 | NA |
| Afghanistan |
| Lesser | Cirrhosis | 14 | 50 | NA | NA |

  - Estimates of HBV disease burden in Afghanistan

To estimate hepatitis B disease burden we used a tool developed by the Centers for Disease Control and Prevention in the United States. This tool estimates the number of persons in a birth cohort who develop chronic HBV infection through perintal, early childhood or adult exposures. Based on numerous studies on the natural history of HBV infection acquired during those timeframes, the CDC tool estimates the number of deaths would be expected with and without hep B vaccine introduction. Key parameters that are used in the tool include:

    - Prevalence of chronic HBV infection (HBsAg) among women of childbearing age

    - Prevalence of HbeAg among HBsAg-positive women

    - Prevalence of early childhood infection  (anti-HBc by the age of 5 years)

    - Lifetime risk of HBV infection

    - Vaccination coverage

    - Vaccination coverage at birth

Several models were developed using this tool (Appendix 1-4). A basic model with the following assumptions was used to estimate the impact of hep B vaccination on disease burden (Appendix 1) for cohorts born in 2005.

HBsAg among women of childbearing age	  7%

HBeAg among HBsAg-positive women=      	15%

Anti-HBc by the age of 5 years                     	30%

Lifetime risk of HBV infection			60%

Vaccination coverage 			80%

Vaccination coverage at birth			 0%
This model indicates there would be 600,000 HBV infections among this cohort resulting in 117,181 HBV infections (Table 4).  While approximately 3% of the acute infections are acquired in the perintal period, these infections would result in 12% of the chronic HBV infections. Similarly, it is estimated 47% of the acute infections would occur in early childhood resulting in 73% of the chronic HBV infections.

| Table 4. Number of Acute Infections by Age at Acquisition of Infection (Future burden) |
| --- |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 15,400 | 15,400 | 0 | 0% |
| Early Childhood Infection | 284,600 | 68,304 | 216,296 | 76% |
| Late Infection | 300,000 | 72,000 | 228,000 | 76% |
| Total Infections | 600,000 | 155,704 | 444,296 | 74% |
| Number of Chronic Infections by Age at Acquisition of Infection (Future burden) |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 13,860 | 13,860 | 0 | 0% |
| Early Childhood Infection | 85,344 | 20,483 | 64,862 | 76% |
| Late Infection | 17,977 | 4,315 | 13,663 | 76% |
| Total Infections | 117,181 | 38,657 | 78,524 | 67% |
| Number of Deaths by Age at Acquisition of Infection (Future burden) |
| Perinatal Infection | 1,264 | 1,264 | 0 | 0% |
| Early Childhood Infection | 7,903 | 1,897 | 6,006 | 76% |
| Late Infection | 2,013 | 483 | 1,530 | 76% |
| Total deaths | 11,179 | 3,644 | 7,536 | 67% |

Overall, these data indicate significant disease burden associated with HBV infection and that introduction of vaccine into EPI would have significant impact on disease burden.

- Strategy for introduction of hep B vaccine into EPI

  - Introduction of DTP-Hep B combination vaccine in 2006

The MOPH discussed at length the introduction of hep B vaccine in an ICC meeting on March 9, 2005.   During this meeting there was extensive discussions about the advantages and disadvantages of whether to introduce combination versus monovalent vaccine. Consensus was reached on the following key issues:

- Introduction of hep B vaccine in 2006

- Use of combination vaccine

- Schedule of hep B will be the same as DTP

- In the event that combination vaccine is not available, the MOHP will introduce monovalent hep B vaccine.

The MOHP will conduct studies to further define the risk of perinatal HBV transmission and assess the feasibility of giving a birth dose of vaccine.   The EPI program is applying for GAVI support for vaccine introduction using combination vaccine DTP-HepB and anticipates there will be a phased financial contribution by the Government of Afghanistan and its partners for vaccine purchase. If combination vaccine is available, there are plans for nationwide introduction in 2006.  If combination vaccine is not available, the MOHP plans a phased introduction of monovalent vaccine.

- Plan for monitoring the impact of hep B vaccine

  - Perinatal transmission
Currently, there is little information on the prevalence of HBsAg among pregnant women in Afghanistan.   A cross sectional survey on a representative sample of pregnant women in different governorates will be conducted to evaluate the prevalence of HBsAg. Serum samples that are HBsAg-positive will be tested for hepatitis B e anitigen. Based on these results, the MOPH will estimate the risk of perinatal HBV transmission. If it is felt that the risk is a high, a strategy for the introduction of a birth dose of vaccine will be developed.

  - Early childhood transmission 
To monitor the impact of vaccine on early childhood HBV transmission, baseline cross sectional serosurveys will be conducted on a representative sample of children in 2 to 3 representative areas (urban and rural). Follow-up serosurveys will be conducted among new cohorts of children born after vaccine introduction  ction of monovalent hep B vaccine in 2006

- Plan of action

  - Finalize GAVI application

  - Develop advocacy to support hep B vaccine introduction in Afghanistan.

  - Develop training materials and plan for vaccine introduction according to availability of combination versus monovalent vaccine

  - Training should include

    - Schedule of for hep B vaccine in EPI (if monovalent)

    - Multiple injections during a single visit

    - Proper storage and handling of hep B vaccine

    - IM administration of hep B vaccine

    - Strategy to ensure EPI vaccines are not diverted to private sector

    - Monitor hep B vaccine coverage along with other EPI indicators.

    - Develop a research plan to evaluate

      - Prevalence of HBsAg among pregnant women in different parts of Afghanistan

      - Prevalence of HBsAg among children in a few sentinel sites to monitor long term impact of vaccine introduction

Appendix 1. Model 1 with 7% HBsAg prevalence.

|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| --- | --- | --- | --- | --- |
| Total HBV infections | 600,000 | 155,704 | 444,296 | 74% |
| Acute symptomatic hepatitis B cases | 118,614 | 28,584 | 90,030 | 76% |
| Chronic HBV infections | 117,181 | 38,657 | 78,524 | 67% |
| HBV-related deaths: |  |  |  |  |
| Acute hepatitis B | 498 | 120 | 378 | 76% |
| Cirrhosis | 6,350 | 2,094 | 4,255 | 67% |
| Hepatocellular carcinoma | 4,332 | 1,430 | 2,902 | 67% |
| Total Deaths | 11,179 | 3,644 | 7,536 | 67% |
| B. Number of Infections by Age at Acquisition of Infection (Future burden) |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 15,400 | 15,400 | 0 | 0% |
| Early Childhood Infection | 284,600 | 68,304 | 216,296 | 76% |
| Late Infection | 300,000 | 72,000 | 228,000 | 76% |
| Total Infections | 600,000 | 155,704 | 444,296 | 74% |
| C. Number of Chronic Infections by Age at Acquisition of Infection (Future burden) |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 13,860 | 13,860 | 0 | 0% |
| Early Childhood Infection | 85,344 | 20,483 | 64,862 | 76% |
| Late Infection | 17,977 | 4,315 | 13,663 | 76% |
| Total Infections | 117,181 | 38,657 | 78,524 | 67% |
| D. Number of Deaths by Age at Acquisition of Infection (Future burden) |  |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 1,264 | 1,264 | 0 | 0% |
| Early Childhood Infection | 7,903 | 1,897 | 6,006 | 76% |
| Late Infection | 2,013 | 483 | 1,530 | 76% |
| Total Deaths | 11,179 | 3,644 | 7,536 | 67% |
|  | Deaths |  |  |  |
| Acute hepatitis B | 163 |  |  |  |
| Cirrhosis | 1,207 |  |  |  |
| Hepatocellular carcinoma | 916 |  |  |  |
| Total Deaths | 2,286 |  |  |  |
| Appendix. Input values |  |  |  |  |
| Prevalence HBsAg among women of child bearing age: |  | 7 |  |
| Prevalence HBeAg among HBsAg-positive women of child bearing age: | 15 |  |
| Prevalence of any marker of HBV infection among 5 year olds: | 30 |  |
| Prevalence of any marker of HBV infection among 30+ year olds: | 60 |  |
| Estimated Hepatitis B3 coverage: |  |  | 80 |  |
| Estimated coverage with birth dose hepatitis B vaccine: |  | 0 |  |

Appendix 2. Model 2 with 5% HBsAg prevalence

| The following is a summary of the results for a surviving birth cohort of 1000000 individuals over the course of their lifetime. |
| --- |
| A. Disease Events Prevented (Future burden) |  |  |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Total HBV infections | 600,000 | 152,360 | 447,640 | 75% |
| Acute symptomatic hepatitis B cases | 119,010 | 28,646 | 90,364 | 76% |
| Chronic HBV infections | 114,541 | 35,014 | 79,527 | 69% |
| HBV-related deaths: |  |  |  |  |
| Acute hepatitis B | 499 | 120 | 380 | 76% |
| Cirrhosis | 6,207 | 1,897 | 4,310 | 69% |
| Hepatocellular carcinoma | 4,234 | 1,295 | 2,939 | 69% |
| Total Deaths | 10,941 | 3,312 | 7,629 | 70% |
| B. Number of Infections by Age at Acquisition of Infection (Future burden) |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 11,000 | 11,000 | 0 | 0% |
| Early Childhood Infection | 289,000 | 69,360 | 219,640 | 76% |
| Late Infection | 300,000 | 72,000 | 228,000 | 76% |
| Total Infections | 600,000 | 152,360 | 447,640 | 75% |
| C. Number of Chronic Infections by Age at Acquisition of Infection (Future burden) |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 9,900 | 9,900 | 0 | 0% |
| Early Childhood Infection | 86,664 | 20,799 | 65,864 | 76% |
| Late Infection | 17,977 | 4,315 | 13,663 | 76% |
| Total Infections | 114,541 | 35,014 | 79,527 | 69% |
| D. Number of Deaths by Age at Acquisition of Infection (Future burden) |  |
|  | Number Without Program | Number With Program | Number Prevented | Percent Reduction |
| Perinatal Infection | 903 | 903 | 0 | 0% |
| Early Childhood Infection | 8,025 | 1,926 | 6,099 | 76% |
| Late Infection | 2,013 | 483 | 1,530 | 76% |
| Total Deaths | 10,941 | 3,312 | 7,629 | 70% |
|  | Deaths |  |  |  |
| Acute hepatitis B | 164 |  |  |  |
| Cirrhosis | 1,180 |  |  |  |
| Hepatocellular carcinoma | 895 |  |  |  |
| Total Deaths | 2,239 |  |  |  |
| Appendix. Input values |  |  |  |  |
| Prevalance HBsAg among women of child bearing age: |  | 5 |  |
| Prevalence HBeAg among HBsAg-positive women of child bearing age: | 15 |  |
| Prevalence of any marker of HBV infection among 5 year olds: | 30 |  |
| Prevalence of any marker of HBV infection among 30+ year olds: | 60 |  |
| Estimated Hepatitis B3 coverage: |  |  | 80 |  |
| Estimated coverage with birth dose hepatitis B vaccine: |  | 0 |  |