Revision 3

August 2001

The Government of the Republic of Niger

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and the Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Republic of Niger is located at the centre of the Sahel desert in West Africa, and does not have access to the sea. It is surrounded by Algeria and Libya to the north, by Benin and Nigeria to the south, Burkina Faso and Mali to the west, and Chad to the east.

In 2001, the population number was estimated at 11, 127,476 inhabitants on the basis of the last general census of the population in 1988, of which 4.7% are children aged between 0-11 months, 5.2% are pregnant women, and 22% are women at a reproductive age. The GNP stood at US$ 200 in 1998, and growth is negative. The state is committed to the independent immunisation initiative. The review of the EPI carried out in February and March 2001 revealed a coverage rate of 23% for DTCP3, a drop-out rate of 37%, and a 39% coverage rate for DTCP1 with children aged between 0-11 months. The elaboration of the EPI strategic plan required the involvement of all development partners acting at various levels of the health system. The workshop held in Dosso between 11-15 September was attended by representatives of the European Union, Helen Keller International, GTZ, with support from the technical staff part of the WHO representative team and two WHO consultants. The main strategic objectives are the improvement of access to immunisation services (new initiatives in advanced and mobile strategies), increased demand (intensified social mobilisation by using previous experience with NID’s, and encouraging community involvement), and improvement of services provided aimed at reducing the drop-out rate.

The objectives are as follows:

Reducing the burden linked to diseases of the EPI.

Increasing the immunisation by anti-genes coverage rate to 80% in 2006.

The Republic of Niger would like to receive help for immunisation services and safety procedures during injections.

Annual objectives for 2002 - 2006:

| Anti-genes | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- |
| BCG | 60% | 65% | 70% | 75% | 80% | 80% |
| DTCP3 | 40% | 50% | 60% | 70% | 80% | 80% |

| POLIO3 | 40% | 50% | 60% | 70% | 80% | 80% |
| --- | --- | --- | --- | --- | --- | --- |
| MEASLES | 40% | 50% | 60% | 70% | 80% | 80% |
| VAT2 + | 50% | 60% | 70% | 70% | 80% | 80% |

Needs of SAB, safety boxes, and costs for injection safety :

|  | ITEMS | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| F | Auto – blocking syringes : total | For BCG | 749 597 | 619 467 | 639 909 | 661 026 |
|  |  | Other vaccines | 5 406 667 | 4 468 070 | 4 615 516 | 4 767 828 |
| H | Reconstitution syringes - total | 149 919 | 154 867 | 159 977 | 165 257 |
| I | Safety receptacles - total | 69 999 | 58 191 | 60 111 | 62 095 |

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of THE REPUBLIC OF NIGER commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Minister of Public Health and Disease Prevention

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Minister of Public Health | Mr. Ibrahim KOMA |  |
| WHO / Niger | Dr. Bernard LALA |  |
| UNICEF / NIGER | Mme. Mary ROODKOWSKY |  |
| ROTARY INTERNATIONAL | Mr. Gaston KABA |  |
| PNUD / NIGER | Mr. Steven URSINO |  |
| FNUAP / NIGER | Mr. Mohamed BARAKET |  |
| WORLD BANK | Mr. Geoffrey BERGEN |  |
| PAM /NIGER | Mr. Joseph KABORE |  |
| EUROPEAN UNION | Mme. Irène HOREIS |  |
| HELEN KELLER INTERNATIONAL | Dr. Xavier CRESPIN |  |
| CARE INTERNATIONAL | Mr. Douglas STENBERG |  |
| JAPANESE COOPERATION | Mr. Yoshinobu SUGIYAMA |  |
| BELGIAN COOPERATION | Mr. Théophile BAERT |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Dr. BARKIRE Arouna	Title/Address : National Director of the EPI

Tel.No. : 75 20 73

Fax No. :75 20 62

E-mail : pev@intnet.ne

Alternative address : Minister of Public Health and the struggle against epidemics

Name : Dr. Hassane Adamou		Title/Address : Secretary - General

Tel.No. : 72 27 82

Fax No.: 73 35 70

E-mail :……………………………                         ……………………………….

3 Immunization-related fact sheet

| Table 1 : Basic facts (For the year 2000 or most recent; specify dates of data provided) |
| --- |
| Population | 11 127 476 | GNP per capita | $US 200 in 1996 |
| Surviving Infants* | 522 991 | Infant mortality rate | 123/ 1000 in 1998 |
| Percentage of GDP allocated to Health | 2.3% | Percentage of Government expenditure for Health Care | 6% in 1999 |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases |
| --- |
| Trends of immunization coverage ( in percentage ) | Vaccine preventable disease burden |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 1999 | 2000 | 1999 | Age group | 2000 | Age group |  | 1999 | 2000 |
| BCG | 37 | 35.5 | N/A | N/A | 47% | 12 mths | Tuberculosis | N/A | N/A |
| DTP | DTP1 |  | 36 | N/A | N/A | 39% | 12 mths | Diphtheria | 0 | 17 |
|  | DTP3 | 22 | 23 | N/A | N/A | 22% | 12 mths | Pertussis | 2446 | 5585 |
| OPV3 | 22 | 23 | N/A | N/A | 22% | 12 mths | Polio | 10 | 94 |
| Measles | 71 | 35 | N/A | N/A | 21% | 12 mths | Measles | 36.156 | 21.319 |
| TT2+ (Pregnant women) | 41 | 31 | N/A | N/A | 36.6% | (P.Wo) | NN Tetanus | 30 | 55 |
| Hib3 | N/A | N/A | N/A | N/A | N/A | N/A | Hib | SO | N/A |
| Yellow Fever | N/A |  | N/A | N/A | 13% | 12 mths | Yellow fever | 0 | 0 |
| HepB3 | N/A | N/A | N/A | N/A | SO |  | hepB seroprevalence (if available) | SO | SO |
| Vit A supplementation | Mothers ( < 6 weeks after delivery ) |  | N/A | N/A | N/A | SO |  |  |  |  |
|  | Infants ( > 6 months) |  | N/A | N/A | N/A | SO |  |  |  |  |

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: 22% is the official coverage rate of DTP3 in Niger, and is the most accurate estimation based on the national immunization survey carried out in 2001 during the EPI review.

- Summary of health system development status relevant to immunization:

After independence, the health policy of Niger was primarily centred on individual curative health care that was free of charge, and characterised by the low participation of communities and a concentration of health care infrastructures in urban areas.

Between 1965 and 1974, various socio-economic development plans recommended the integration of preventive and curative health care and to start decentralisation.

The Republic of Niger made a fundamental choice by opting for an overall integrated health care system that coordinates preventive, educational, and promotional actions for all communities.

The Republic of Niger has therefore subscribed to several regional and international declarations such as ALMA ATA in 1978, the primary health care policy of which has been implemented.

After several years of implementation of this policy, the actions taken have not shown the results anticipated.

In view of this failure, the Republic of Niger has made a fundamental change in order to speed up the implementation of the primary health care strategy to reach the universal objective of health for all in 2000.

In 1987, the Republic of Niger committed itself to implementing the Bamako initiative so as give a new boost to the health care system and to reorganise the way it works with the participation of the population concerned in terms of management and financing.

The national sovereign conference held in 1991 had recommended the implementation of the African health care development scenario in 3 phases  and the mechanism for community participation, namely the recovery of expenses with regard to payments made by beneficiaries for health care, as soon as possible.

The recovery of expenses is currently taking place at all health care units of the country.

- The health care system  is being completely restructured since 1994, with reforms concerning:

- The availability of basic good quality medicines and vaccines.

- The speeding-up of the decentralisation process with the creation of 42 health care districts.

- The assessment of the health care development programme (1994-2000).

- The elaboration a sectoral decennial plan for 2000-2009 is near to completion.

| Attached are the relevant section(s) of strategies for health system development | Document number no.1 |
| --- | --- |

# 4 Profile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

- Name of the ICC… Inter Agency Co-ordinating Committee (ICC/EPI)

- Date of constitution of the current ICC : Bylaw no. 00253/MSP/CAB of 23 November 1999 amended by bylaw no. 174/MSP/CAB of 23 August 2001.

- Organisational structure (e.g., sub-committee, stand-alone) : 3 sub-committees (Social mobilisation sub-Committee, Monitoring sub-Committee, and Logistical sub-Committee).

- Frequency of meetings : normally once per month, and once per week during preparation and implementation of the NID’s.

- Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | General Secretary of the Ministry of Public Health and Disease Prevention. | Dr. Hassane Adamou |
| Secretary | Director of the EPI | Dr. Barkiré Arouna |
| Members | See list attached …………. | See list attached |

Main functions and responsibilities:

- Elaboration and implementation of immunisation strategies.

- Providing support for the assessment and approval of plans of the EPI at all levels.

- Helping the National Administrators of the EPI to ensure a transparent and efficient management of the programme.

- Supporting and encouraging the exchange of information and retro-information at all levels of the National Health System along with partners.

- Ensuring the coordination of action taken by the partners with regard to immunisation

- Coordinating the planning of all immunisation activities.

- The sub-Committee of Social Mobilisation is responsible for:

Elaborating the strategies of social mobilisation.

Participating in the creation of an array of social mobilisation activities.

Contributing to the elaboration of social mobilisation backing.

Elaboration of a media file and messages to be disseminated in the context of the EPI.

Contributing to the elaboration of national communication plans for the EPI and monitoring.

Provide assistance to the planning, supervision, and implementation of communication initiatives.

Participating in the assessment of the impact of social mobilisation activities.

Developing interaction between other national communication structures.

- The sub-Committee for Logistics is responsible for:

Helping the regions and districts in managing logistical means.

Making suggestions to enhance mobilisation, distribution and allocation of logistical means to the ICC in the context of the EPI.

Participating in the elaboration of strategies aiming to improve the upkeep of logistics.

Ensuring a rational management of resources made available to the EPI and NID’s.

Investigating the logistical means available from other ministerial and private departments that can be used during the NID’s.

- The sub-Committee for monitoring is responsible for:

Analysing and suggesting strategies to re-start the EPI.

Providing information and retro-information to the ICC/EPI related to the DSNIS.

Suggesting and carrying out the surveys on the impact of action taken and on the objectives of the EPI.

Preparing all technical documentation for decision-making by the ICC/EPI, and documentation to be made available to the districts, especially during NID’s.

Helping with planning, follow-up, and assessment of action taken with regard to immunisation and control of disease in the field.

Preparing NID management support.

Gathering  and analysing the results, and ensuring feedback about NID’s and their effect.

Helping with the drafting of technical and financial reports on the EPI and the NID’s/NND’s.

NB NND = National Micro-Nutrient Days

- The diagram below shows the functional relationship of the ICC with other institutions of the Health Sector:

- Three main strategies aimed at enhancing the role and functions of the ICC in the 12 months ahead:

- Drafting of an agreement memorandum regarding the EPI following the development of a 2001 action plan. The memorandum is a tool that will make the Inter-Agency Committee operational, and its objective will be to stimulate the cooperation between the Ministry of Health and its partners to boost the EPI. It will enable the rationalisation of the use of resources for more effective assistance, and for increased efficiency of managerial capacities of government officials involved in the EPI. The approval time shall be one year, with an assessment of progress made in February of every year that will be mentioned by the Minister and the partners (Head of the mission.

- Creation of a core-group of the EPI within the ICC that will ensure a quarterly review (February, April, July, and October) of the implementation of the memorandum.

- Creation of a sub-committee in charge of data management, its consolidation, and identifying operational research themes.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

Drop-out rate

Rate of DTP1

Coverage rate of routine (smallpox?) immunisation (0-11 months).

Attached are the supporting documents :

| Terms of reference of the ICC | Document number no.2 |
| --- | --- |
| ICCs workplan of next 12 months | Adoption of the multi-year plan. Submission to GAVI. Coordination of polio NID. Quarterly review of EPI. Statuary coordination meetings. |
| Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number no.3 |

# 5 Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunisation services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Population and health surveys | CARE/MACRO Intl./Ministry of planning, MPH | 1998 |
| MICS survey | UNICEF | 1999 |
| Review of the EPI | WHO/UNICEF/ MPH |  |

- The three major strengths identified in the assessments :

- There is high level political involvement in the form of financing of vaccines and expendables by the government.

- Good implementation of  the polio eradication initiative with satisfactory results during the NID’s, with no new cases of the wild polio virus reported in the past year.

- Expansion of the cold chain with all the health facility equipment financed by Japanese cooperation.

- The three major problems identified in the assessments :

- Insufficient development of human resources.

- Insufficient support for logistics and transport.

- Insufficient social mobilisation.

- The three major recommendations in the assessments :

- Ensuring the development of human resources (training & supervision).

- Ensuring material and financial logistical support (supplies & increased supply of equipment to immunisation centres.

- Ensuring neighbourhood IEC.

- Attached are  complete copies (with an executive summary) of :

| the most recent assessment reports on the status of immunization services | Document number 4 |
| --- | --- |
| a list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number 5 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| Component or area | Month/Year |
| --- | --- |
| Study of loss rates | February 2002 |
| Initial study of the MAPI | July 2002 |

# 6 Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| Attached is a complete copy (with an executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 6 |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |
| --- |
| Type of technical support | Period for the support | Desired from which agency |
| Initiative for the eradication of TMNN | 2001 | WHO/UNICEF |

| Table 3 : Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |
| --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in : | Comments |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | x |  |  |
| Oral polio vaccine | At birth | x |  |  |
| DTP1/OPV1 | 6 weeks | x |  |  |
| DTP2/OPV2 | 12 weeks | x |  |  |
| DTP3/OPV3 | 14 weeks | x |  |  |
| Anti-Measles vaccine | 9 months | x |  |  |
| Vitamin A | After the age of 6 months | x |  | ½ a capsule < 1 year |
| VAT1 | Women of procreation age at first contact | x |  |  |
| VAT2 | 1 month after the first | x |  |  |
| Yellow fever vaccination | 9 months | x | x (21 border districts) | Southern border districts |

- Summary of major action points and timeframe for improving immunization coverage:

| Table 4 : Baseline and annual targets |
| --- |
| Number of | Baseline | Targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births | 549.372 | 567.501 | 586.229 | 605.574 | 625.558 | 646.202 | 667.526 | 689.555 |
| Infants’ deaths | 43.088 | 44.510 | 45.479 | 47.496 | 49.063 | 50.682 | 52.355 | 54.083 |
| Surviving infants | 506.284 | 522.991 | 540.250 | 588.078 | 576.495 | 595.519 | 615.171 | 635.472 |
| Infants vaccinated with BCG* | 237.953 | 55% | 60% | 65% | 70% | 75% | 80% | 80% |
| Infants vaccinated with OPV3** | 111.382 | 30% | 40% | 50% | 60% | 70% | 80% | 80% |
| Infants vaccinated with DTP3** | 111.382 | 30% | 40% | 50% | 60% | 70% | 80% | 80% |
| Infants vaccinated with**: (use one row for any new vaccine) |  |  |  |  |  |  |  |  |
| Infants vaccinated with Measles** | 106.320 | 30% | 40% | 50% | 60% | 70% | 80% | 80% |
| Pregnant women vaccinated with TT+ | 199.422 | 40% | 50% | 60% | 70% | 70% | 80% | 80% |
| Vit A supplementation | Mothers (< 6 weeks from delivery) | N/A |  |  |  |  |  |  |  |
|  | Infants (> 6 months) | N/A |  |  |  |  |  |  |  |
| * Target of children out of total births | ** Target of children out of surviving infants |

- Summary of major action points and timeframe for reduction of vaccine wastage. If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate. :

| Table 5 : Estimate of annual DTP wastage and drop out rates |
| --- |
|  | Actual | Targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Wastage rate | 25% | 25% | 20% | 18% | 15% | 12% | 10% | 10% |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 35% | 32% | 30% | 25% | 20% | 18% | 15% | 10% |

- Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.

- Planning and constraints for the Polio Eradication Initiative:

Synchronised National Immunisation Days have been introduced in Niger, with successful NID’s every year since 1997. Monitoring has improved, with all 110 cases investigated in 1999 as opposed to only 12 out 56 cases investigated in 1997. The challenge is to integrate the monitoring of measles and to prepare certification. No new cases of the polio virus have been reported since January. Niger has to carry out NID’s for another 3 years,

# 7 Injection safety

  - Summary of the injection safety strategy for immunization (for all countries):

| Attached is a copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number …….. |
| --- | --- |

Significant progress has been made with regard to injection safety that the plan aims to enhance, especially;

- The SAB is adopted with regard to immunisation, and the plan sets out the development of a national policy for safe injections.

- A technical summary that outlines the main points of the WHO/UNICEF policy has been disseminated to all doctors.

- Training of all those involved must take place before the end of the second year (see page 26 and action III and activity no.3)

- The Government has included the construction of an incinerating furnace as obligatory equipment (infrastructure) to be part of any peripheral formation plan prior to the granting of building permission.

- This shows the political commitment to proper methods in providing health care. The injection safety plan has been included in the logistical plan of the current document.

7.2	Injection safety equipment (For countries submitting a request for injection safety support).

The following tables calculate the amount of supplies requested for injection safety:

Table 6.1: Estimated supplies for safety of vaccination with …… ( Use one table for each vaccine BCG, DTP, TT and measles, and number them from 6.1 to 6.4)

| 6.1. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| BCG | 2002 | 2003 | 2004 | 2005 | 2006 |
| Number of children | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Number of doses per child | 1 | 1 | 1 | 1 | 2 172 733 |
| Number of doses of BCG | 540 250 | 558 078 | 576 495 | 595 519 | 2 787 904 |
| Auto-destruct syringes | 599 678 | 619 467 | 639 909 | 661 026 | 680 615 |
| Buffer stock of auto-destruct syringes | 149 919 | 0 | 0 | 0 | 2 879 525 |
| Total auto-destruct syringes | 749 597 | 619 467 | 639 909 | 661 026 | 3 560 140 |
| Number of doses of BCG vials | 20 | 20 | 20 | 20 | 20 |
| Number of reconstitution syringes | 29 984 | 30 973 | 31 995 | 33 051 | 154 729 |
| Number of safety boxes | 8 653 | 7 220 | 7 458 | 7 704 | 41 235 |
| 6.2. |  |  |  |  |  |
| DPT | 2002 | 2003 | 2004 | 2005 | 2 006 |
| Number of children | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Number of doses per child | 3 | 3 | 3 | 3 | 2 172 733 |
| Number of doses of DPT | 1 620 750 | 1 674 235 | 1 729 485 | 1 786 557 | 2 787 904 |
| Auto-destruct syringes | 1 799 033 | 1 858 401 | 1 919 728 | 1 983 079 | 680 615 |
| Buffer stock of auto-destruct syringes | 449 758 | 0 | 0 | 0 | 2 879 525 |
| Total auto-destruct syringes | 2 248 791 | 1 858 401 | 1 919 728 | 1 983 079 | 3 560 140 |
| Number of doses per DPT vial | 10 | 10 | 10 | 10 | 10 |
| Number of safety boxes | 24 962 | 20 628 | 21 309 | 22 012 | 154 729 |

| Measles | 2002 | 2003 | 2004 | 2005 | 2 006 |
| --- | --- | --- | --- | --- | --- |
| Number of children | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Number of doses per child | 1 | 1 | 1 | 1 | 1 |
| Number of doses | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Auto-destruct syringes | 599 678 | 619 467 | 639 909 | 661 026 | 682 840 |
| Buffer stock of auto-destruct syringes | 149 919 | 0 | 0 | 0 | 0 |
| Total auto-destruct syringes | 749 597 | 619 467 | 639 909 | 661 026 | 682 840 |
| Number of doses per vial | 10 | 10 | 10 | 10 | 10 |
| Number of reconstitution syringes | 59 968 | 61 947 | 63 991 | 66 103 | 68 284 |
| Number of safety boxes | 8 986 | 7 564 | 7 813 | 8 071 | 8 337 |
| 6.4. |  |  |  |  |  |
| TT | 2002 | 2003 | 2004 | 2005 | 2006 |
| Number of women | 597 723 | 617 448 | 637 824 | 658 872 | 680 615 |
| Number of doses per woman | 2 | 2 | 2 | 2 | 2 |
| Number of TT doses | 1 195 447 | 1 234 897 | 1 275 648 | 1 317 744 | 1 361 230 |
| Auto-destruct syringes | 1 326 946 | 1 370 735 | 1 415 969 | 1 462 696 | 1 510 965 |
| Buffer stock of auto-destruct syringes | 331 737 | 0 | 0 | 0 | 0 |
| Total auto-destruct syringes | 1 658 683 | 1 370 735 | 1 415 969 | 1 462 696 | 1 510 965 |
| Number of doses per TT vial | 10 | 10 | 10 | 10 | 10 |
| Number of safety boxes | 18 411 | 15 215 | 15 717 | 16 236 | 16 772 |
| 6.5. |  |  |  |  |  |
| Yellow fever | 2002 | 2003 | 2004 | 2005 | 2005 |
| Number of children | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Number of doses per child | 1 | 1 | 1 | 1 | 1 |
| Number of doses | 540 250 | 558 078 | 576 495 | 595 519 | 615 171 |
| Auto-destruct syringes | 599 678 | 619 467 | 639 909 | 661 026 | 682 840 |
| Buffer stock of auto-destruct syringes | 149 919 | 0 | 0 | 0 | 0 |
| Total auto-destruct syringes | 749 597 | 619 467 | 639 909 | 661 026 | 682 840 |
| Number of dose per vial | 10 | 10 | 10 | 10 | 10 |
| Number of reconstitution syringes | 59 968 | 61 947 | 63 991 | 66 103 | 68 284 |
| Number of safety boxes | 8 986 | 7 564 | 7 813 | 8 071 | 8 337 |
| OVERALL REQUIREMENTS | 2002 | 2003 | 2004 | 2005 | 2005 |
| BCG syringes | 749 597 | 619 467 | 639 909 | 661 026 | 3 560 140 |
| DPT, VAR, TT, FJ syringes | 5 406 667 | 4 468 070 | 4 615 516 | 4 767 828 | 6 436 785 |
| reconstitution syringes | 149 919 | 154 867 | 159 977 | 165 257 | 291 297 |
| safety boxes | 69 999 | 58 191 | 60 111 | 62 095 | 229 410 |

7.3	Areas for injection safety funds (For countries requesting funds equivalent to the supplies calculated above).

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | Area of support | Start of fund utilization |
| --- | --- | --- |
| Government | AD syringes and waste disposal boxes | 1999 |
| GAVI/Vaccine Fund | Training, study of loss rate, social mobilisation, drafting of a manual and information posters | 2002 |

(Use as many rows as necessary

# 8 New and under-used vaccines

- Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulas)

| Table 7.1: Estimated number of doses of ………... vaccine (Specify one table for each presentation of any vaccine and number it 7.2, 7.3, …) |
| --- |
|  |  | Formula | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| A | Number of children to receive new vaccine | match with targets in table 4 |  |  |  |  |  |  |
| B | Number of doses per child | # |  |  |  |  |  |  |
| C | Estimated wastage rate in percent | % |  |  |  |  |  |  |
| D | Equivalent wastage factor | See list in table ( |  |  |  |  |  |  |
| E | Number of doses | A x B x D |  |  |  |  |  |  |
| F | Number of vaccines buffer stock | E x 0.25 |  |  |  |  |  |  |
| G | Total of vaccine doses needed | E + F |  |  |  |  |  |  |
| H | Percentage of vaccines requested from the Vaccine Fund | % |  |  |  |  |  |  |
| I | Number of doses requested from the Vaccine Fund | G x H / 100 |  |  |  |  |  |  |
| J | Number of doses per vial | # |  |  |  |  |  |  |
| K | Number of AD syringes (+10% wastage) | [( A x B) + F] x x 1.11 x H / 100 |  |  |  |  |  |  |
| L | Number of AD syringes buffer stock | K x 0.25 |  |  |  |  |  |  |
| M | Total of AD syringes | K + L |  |  |  |  |  |  |
| N | Number of reconstitution syringes (+10% wastage) | I x 1.11 / J |  |  |  |  |  |  |
| O | Number of safety boxes (+10% of extra need) | (M + N) x 1.11 / 100 |  |  |  |  |  |  |

| Table ( : Wastage rates and factors |
| --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulas as per table 7.1)

| Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages) | Document number…… |
| --- | --- |

# 9 Strategic directions to mobilise additional resources for immunization

- Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan by the time of the mid-term review. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief :

The Republic of Niger is committed to the initiative of  independent immunisation, and the government spends close to $US 1.000.000 per year on vaccines and expendables. The Japanese cooperation has just finished the complete renovation of the cold chain. A review of the cold chain was recently carried out, and a workshop to elaborate the national maintenance and transport policy is being planned. All this will help to improve the immunisation services while reducing wastage. The Government has decided to allocate 13% more than its current budget to the EPI every year.

| Tables of expenditure for 2000 and resource needs detailing the sources of funds for 2000 and subsequent years are attached in Annex 1. | Document number .…. |
| --- | --- |

- Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

# 10 Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Republic of Niger

considering that its DTP3 coverage for 2000 was 22%  corresponding to 111.382 children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 104.718 children. Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

Use of the funds: A special GAVI account will be opened and managed by the Director of Financial Affairs of the Ministry of Public Health and Disease Prevention, with a double signature from the General Secretary of the MPH/LCE and the National Director of the EPI. The procedures adopted by the Inter-Agency Committee shall be implemented: justification of the funds 1 month after cash disbursement, technical & financial statement during the quarterly review meeting. The request shall be examined and approved during a regular meeting of the Inter-Agency Committee, the authorisation for spending shall be granted by the President of the Inter-Agency Committee.

Financial viability: In addition to continuing payments for services provided and for all normal vaccines of the EPI,  The Government is equally committed to allocating a budget for disease prevention (vaccines and expendables) that corresponds to 35% financial commitment of the budget. The Government decides on the basis of the recommendation from the Support Project Group for the Structural Adjustment Programme (PAPAS) to ensure a 13% annual budget increase.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

10.2 SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 9 : New and under-used vaccines requested from GAVI and the Vaccine Fund |
| --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are entitled to receive US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

10.3 SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 8

X	The equivalent amount of funds

| Table 8: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES requested from GAVI and the Vaccine Fund (fill in the total sums of rows “F”, “H” and “I” of tables 6.1,6.2, 6.3, 6.4. |
| --- |
|  | ITEM | 2002 | 2003 | 2004 | 2005 |
| F | Total AD syringes | for BCG | 749.597 | 619.467 | 639.909 | 661.026 |
|  |  | for other vaccines | 5.406.667 | 4.468.070 | 4.767.828 | 6.436.785 |
| H | Total of reconstitution syringes | 149.919 | 154.867 | 159.977 | 165.257 |
| I | Total of safety boxes | 69.999 | 58.191 | 60.111 | 62.095 |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Details” form (Annex 3) with the proposal.

# 11  Additional comments and recommendations from the ICC

a) Recommendations to the Government:

- To sustain political commitment at a high level with view to developing immunisation services on a long-term basis.

b) To the those in charge of the Expanded programme on Immunisation:

- Regularly provide technical and financial reports on activities carried out with the support of GAVI.

- To comply with the transparent management mechanisms outlined in this application, especially with regard to financial matters.

C) To the ICC:

- To ensure consistent technical and financial follow-up of the implementation of the strategic plan of the EPI.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 2000 from different sources |
| --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expend-iture in 2000 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| Total expenditure in 2000 |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |

Table 2

| Budget for 2000 (Fill in a similar table for subsequent years) |
| --- |
| Ref. # | Category / Line item | Contributions committed by partners | Total projected needs | Unmet needs |
|  |  | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 1.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilisation…) |  |  |  |  |  |  |  |  |  |
| 2.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 2.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | Line item … |  |  |  |  |  |  |  |  |  |
| 3.2 | Line item …3 |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |

ANNEX  2

Summary of documentation

| Background information on Health System Development status |
| --- |
| Attached are the relevant section(s) of strategies for health system development | Document number……. |
| Profile of the Inter Agency Co-ordinating Committee (ICC) |
| ICC’s workplan of next 12 months | Document number……. |
| Terms of reference of the ICC | Document number…… |
| Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | Document number…… |
| Immunization Services Assessment |
| Most recent, national assessment report(s) on the status of immunization services | Document number…… |
| Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | Document number…… |
| Multi-Year Immunization Plan |
| Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…… |
| Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number…… Document number…… |
| Unmet needs requiring additional resources |
| Tables of expenditure for 2000 and resource needs (Annex 1) | Document number…… |

ANNEX  3

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  | Banking Details |
| --- | --- | --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below : |
| Name of Institution : (Account Holder) |  |
| Address : |  |
| City – Country : |  |
| Telephone No. : |  | Fax No. : |  |
| Amount in USD : | ( To be filled in by GAVI Secretariat ) | Currency of the bank account : |  |
| For credit to : Bank account’s title |  |
| Bank account No. : |  |
| At : Bank’s name |  |
| Is the bank account exclusively to be used by this programme? | YES ( ) NO ( ) |
| By whom is the account audited ? |  |
| Signature of Government’s authorizing official : |
| Name : |  | Seal : |
| Title : |  |  |
| Signature : |  |  |
| Date : |  |  |

| SECTION 2 ( To be completed by the Bank ) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name : |  |  |
| Branch Name : |  |  |
| Address : |  |  |
| City – Country : |  |  |
| Swift code : |  |  |
| Sort code : |  |  |
| ABA No. : |  |  |
| Telephone No : |  |  |
| Fax No : |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : | Name of bank’s authorizing official : |
| 1 Name : Title : |  | Signature : |  |
|  |  | Date: |  |
| 2 Name : Title : |  | Seal: |
| 3 Name : Title : |  |  |
| 4 Name : Title : |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    	GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative : |
| Name |  |
| Signature |  |
| Date |  |

ANNEXE 1

#### Besoins financiers et besoins à satisfaire en matière de vaccination (milliers d'USD)

Tableau 1

| DEPENSE EN 2000 ET DIFFRENTES SOURCES DE FINNACEMENT |
| --- |
|  |  | Contributions des partenaires | Total DEPENSES EN 2000 | Besoins non satisfaits |
| Réf. # | Catégorie / Ligne | Organe exécuteur | Gouvernement | Secteur privé ONGs | OMS | UNICEF | JAPON | CEE |  |  |
| 2. | Renforcement Institutionnel |  |  |  |  |  |  |  |  |  |
| 2.01.02 | Proposer la revision de l’arrêté N°0012/MSP du 12/08/96 portant attribution du PEV | MSP /DNPEV | - |  |  |  |  |  | - | - |
| 3 | Mobilisation sociale |  |  |  |  |  |  |  |  |  |
| 3.02.02 | Réviser, diffuser les spots sur la vaccination | Comité Mobilisation sociale |  |  |  | - |  |  | 10.000.0000 | - |
| 3.02.05 | Imprimer les pagivoltes Affiches sur la vaccination | DNPEV, Comité |  |  |  | - |  |  | 60.000.000 | - |
| 4 | Supervision Suivi, Evaluation |  |  |  |  |  |  |  |  |  |
| 4.02.02 | Appuyer le suivi de la chaîne de froid | DNPEV |  |  | - | - |  |  | 6.000.000 | - |
| 4.02.04 | Organiser la revue du PEV | DNPEV, DDS, District |  |  | - | - |  | - | 67.000.000 | - |
| 6 | INSFRASTRUCTURE ET EQUIPEMENT |  |  |  |  |  |  |  |  |  |
| 6.05.01 | Commander le matériel de chaîne de froids | DNPEV |  | - | - | - |  |  | 110.000.000 | - |
| 6.05.02 | Entretenir les chambre froides et les groupe électrogènes | DNPEV |  |  |  | - |  |  | 2.000.000 | - |
| 7 | MEDICAMENT ESSENTIEL, seringue et GAZ |  |  |  |  |  |  |  |  |  |
| 7.02.02 | Commander les vaccins et materiel d’injection de routine | DNPEV | - |  |  |  |  | - | 101.000.000 |  |
| 7.02.04 | Commander la vitamine a | DNPEV-HKI-IUNICEF | - |  | - | - |  |  | 162.000.000 | - |
| 8. | Lutte contre la maladie |  |  |  |  |  |  |  |  |  |
| 8.01.04 | Organisation JNV | DNPEV |  |  |  |  |  |  | 1.016.000.000 | - |
| 9 | Atelier , Formation et recyclage |  |  |  |  |  |  |  |  |  |
| 9.01.01 et 9.01.02 | Organiosation des atelier de microplanification | DNPEV | - |  | - | - |  |  | 22.600.000 | - |
| 10 & 11 | SEMINAIRE, REUNION ET VOYAGE DETUDE |  |  |  |  |  |  |  |  |  |
| 11.02.02 | Colloques internationaux | MSP DNPEV |  | - | - | - |  | - | 5.000.000 | - |
| Engagement total |  |  |  |  |  |  |  | 1.561.600.000 |  |
| 1En cas de cofinancement, ou de système de financement agrégé, veuillez indiquer de façon aussi précise que possible le total du financement et/ou le montant des contributions des partenaires. 2 Veuillez utiliser la version électronique du document et insérer le nombre nécessaire de colonnes pour les contributions des partenaires. 3 Veuillez utiliser la version électronique du document pour insérer autant de lignes que nécessaire. |

Tableau 2

| Budget pour 2000 (Remplir un tableau similaire pour les années suivantes) |
| --- |
|  |  | Contributions des partenaires | Total besoins projetés | Besoins non satisfaits |
| Réf. # | Catégorie / Ligne | Organe exécuteur | Gouvernement | Secteur privé ONGs | OMS | UNICEF | JAPON | CEE |  |  |
| 2. | Renforcement Institutionnel |  |  |  |  |  |  |  |  |  |
| 2.01.02 | Proposer la revision de l’arrêté N°0012/MSP du 12/08/96 portant attribution du PEV | MSP /DNPEV | - |  |  |  |  |  | - | - |
| 3 | Mobilisation sociale |  |  |  |  |  |  |  |  |  |
| 3.02.02 | Réviser, diffuser les spots sur la vaccination | Comité Mobilisation sociale |  |  |  | - |  |  | 10.000.0000 | - |
| 3.02.03 | Réviser les modules de formations IEC/PEV | DNPEV, DHP/EPS, Comité |  |  |  | - |  |  | 2.000.000 | 2.000.000 |
| 3.02.04 | Réviser les pré test des supports confectionnés | DNPEV, DHP/EPS, Comité |  |  |  | - |  |  | 3.000.000 | 3.000.000 |
| 3.02.05 | Imprimer les pagivoltes Affiches sur la vaccination | DNPEV, Comité |  |  |  | - |  |  | 60.000.000 | - |
| 3.02.06 | Reproduire les nx modules | Dnpev comité |  |  | - | - |  |  | 5.000.000 | 5.000.000 |
| 4 | Supervision Suivi, Evaluation |  |  |  |  |  |  |  |  |  |
| 4.01.01 | Organiser des missions de travail dans les DDS en collaboration avec les autres directions centrales | MSP, DN/PEV DC, |  |  |  | - |  |  | 6.000.000 | 6.000.000 |
| 4.02.01 | Monitorer les activités du PEV | DNPEV |  |  |  | - |  |  | 5.000.000 | 5.000.000 |
| 4.02.02 | Appuyer le suivi de la chaîne de froid | DNPEV |  |  | - | - |  |  | 6.000.000 | - |
| 4.02.03 | Organiser l’évaluation PSEBC | DNPEV, DDS, Aguié, Mirriah |  |  |  | - |  |  | 3.600.000 | 3.600.000 |
| 4.02.04 | Organiser la revue du PEV | DNPEV, DDS, District |  |  | - | - |  | - | 67.000.000 | - |
| 4 | INSFRASTRUCTURE ET EQUIPEMENT |  |  |  |  |  |  |  |  |  |
| 6.0302 | Exécuter et achever la construction de trois hangars | DNPEV | - |  |  |  |  |  | 15.000.000 | 15.000.000 |
| 6.03.02 | . Suivre l’exécution de trois Hangars PEV | DNPEV DDS | - |  |  |  |  |  | 500.000 | 500.000 |
| 6.04.02 | Achat d’un poste téléviseur, d’un magnétoscope plus fongibles | DNPEV |  |  | - | - |  |  | 1.500.000 | 1.500.000 |
| 6.05.01 | Commander le matériel de chaîne de froids | DNPEV |  | - | - | - |  |  | 110.000.000 | - |
| 6.05.02 | Entretenir les chambre froides et les groupe électrogènes | DNPEV |  |  |  | - |  |  | 2.000.000 | - |
| 6.05.03 | Réparer le groupe électrogène de la DRSP de Niamey | DNPEV | - |  |  | - | - |  | 9.000.000 | 9.000.000 |
| 6.05.05 | Doter le PEV en Carburant | MSP | - |  |  |  |  |  | 2.000.000 | 2.000.000 |
| 6.05.06 | Réparer le camion frigorifique de la DNPEV | MSP/DNPEV/SERPA | - |  | - | - |  |  | 4.600.000 | 4.600.000 |
| 6.05.07 | Fournir du gaz au formation sanitaire | DNPEV | - | - | - | - |  |  | 50.000.000 | 50.000.000 |
| 6.05.08 | Imprimer les support du PEV | MSP/DNPEV/ | - |  | - | - |  |  | 25.000.000 | 25.000.000 |
| 7 | MEDICAMENT ESSENTIEL, seringue et GAZ |  |  |  |  |  |  |  |  |  |
| 7.02.02 | Commander les vaccins et materiel d’injection de routine | DNPEV | - |  |  |  |  | - | 750.000.000 | 101.000.000 |
| 7.02.03 | APPROVISSIONNEMENT DES Régions en vaccins et matériel | DNPEV | - |  | - | - |  |  | 2.500.000 | 2.500.000 |
| 7.02.04 | Commander la vitamine a | DNPEV-HKI-IUNICEF | - |  | - | - |  |  | 162.000.000 | - |
| 8. | Lutte contre la maladie |  |  |  |  |  |  |  |  |  |
| 8.01.01 | Révision des supports | DNPEV | - |  | - | - |  |  | 5.000.000 | 5.000.000 |
| 8.01.02 | Elaborer et diffuser unguide surveillance | DNPEV | - |  | - | - |  |  | 2.000.000 | 2.000.000 |
| 8.01.03 | Approche H.Risque TNN | DNPEV |  |  | - | - |  |  | 25.000.000 | 25.000.000 |
| 8.01.04 | Organisation JNV | DNPEV |  |  |  |  |  |  | 1.016.000.000 | - |
| 8.01.05 | Mettre en ouvre les Stragégie Mobile décentralisée et Avancée | DNPEV | - |  | - | - |  |  | 75.000.000 | 75.000.000 |
| 8.01.06 | Apui district Pilote | DNPEV | - |  | - | - |  |  | 40.000.000 | 40.000.000 |
| 8.01.07 | contrôle, Rougeole dans 16 district s | DNPEV |  |  |  |  |  |  | 50.000.000 | 50.000.000 |
| 9 | Atelier , Formation et recyclage |  |  |  |  |  |  |  |  |  |
| 9.01.01 et 9.01.02 | Organiosation des atelier de microplanification | DNPEV | - |  | - | - |  |  | 22.600.000 | - |
| 9.01.03 | Organisation atelir Mob.soc | DNPEV | - |  | - | - |  |  | 7.000.000 | 7.000.000 |
| 9.0202 | Formation en reparation et entretien de chaine de froids | DNPEV | - |  | - |  |  |  | 11.000.000 | 11.000.000 |
| 9.02.04 | Formation des gestion des consomables | DNPEV | - | - | - | - | - | - | 40.000.000 | 40.000.000 |
| 9.02.05 | Epidémiologie et sante publique | DNPEV |  | - |  | - |  |  | 4.000.000 | 4.000.000 |
| 10 & 11 | SEMINAIRE, REUNION ET VOYAGE DETUDE |  |  |  |  |  |  |  |  |  |
| 10.02.01 | Voyage d’etude | DNPEV |  |  | - | - |  |  | 6.000.000 | 6.000.000 |
| 11.01.02 | Seminaire Nationale | DNPEV |  | - | - | - |  | - | 10.700.000 | 10.700.000 |
| 11.02.02 | Colloques internationaux | MSP DNPEV |  | - | - | - |  | - | 5.000.000 | - |
| Engagement total |  |  |  |  |  |  |  |  |  |
| 1En cas de cofinancement, ou de système de financement agrégé, veuillez indiquer de façon aussi précise que possible le total du financement et/ou le montant des contributions des partenaires. 2 Veuillez utiliser la version électronique du document et insérer le nombre nécessaire de colonnes pour les contributions des partenaires. 3 Veuillez utiliser la version électronique du document pour insérer autant de lignes que nécessaire. |

# Footnotes

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3 an explanation of the difference should be provided.

The country should aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Vaccine Fund, excluding the wastage of vaccines.

Only for lyophilized. Write zero for other vaccines.

A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Please submit hard copy documents with an identical electronic copy whenever possible

# Text boxes

###### ICC / EPI

Public Health Ministry

Partners taking part in the deveopment of the health sector