The Government of

BHUTAN

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Signatures of the Government

The Royal Government of Bhutan (RGOB) commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:	…………………………………………...

Title:  Secretary, Ministry of Health and Education, Royal Government of Bhutan

Date:   22 June 2000

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |
| Ministry of Health and Education RGOB | Dr. Sangay Thinley Secretary |  |
| Health Department RGOB | Dr. Gado Tshering Director of Health |  |
| Health Department RGOB | Dr. Rinchen Chophel Joint Director of Health Care and International Health Division |  |
| Health Department RGOB | Dr. Pem Namgyal Deputy Secretary of Policy and Planning Division |  |
| Ministry of Health and Education RGOB | Mr. Thinley Wangdi Deputy Secretary Accounts and Finance |  |
| Health Department RGOB | Dr. K.C. Buragohain Technical Advisor |  |
| Health Department RGOB | Dr. T.B. Rana Technical Advisor |  |
| Health Department RGOB | Dr. Tenzin Penjor Joint Director, PHD |  |
| Health Department RGOB | Mr. Thinley Dorji EPI Program Officer |  |
| WHO | Dr. Orapin Singhadej Resident Representative |  |
| WHO | Dr. Kunzang Jigme Technical Advisor |  |
| WHO | Mr. Norbu Wangchuk National Program Officer |  |
| UNICEF | Ms. Alegria Mendoza Resident Representative |  |
| UNICEF | Ms. Bindhya Pradhan HAN Program Officer |  |
| UNICEF | ###### Ms. Tashi Zomba HAN Program Assistant |  |
| JICA | Mr. Yasuyuki Mori Resident Representative |  |
| JICA | Mr. Kuenlay Dorji National Program Officer |  |
| DANIDA | Mr. Bjarne Jensen Chief Technical Advisor |  |
| Ministry of Home Affairs RGOB | Mr. Karchung Tshering |  |
| Royal Bhutan Army RGOB | Dr. Karma Tshering Chief Medical Officer |  |

Signed this day of :  __________________________________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name :   Dr. Sangay Thinley		Title/Address:

Secretary

Ministry of Health and Education

Dr. Gado Tshering		 Director of Health, RGOB

### Dr. Rinchen Chophel		 Joint Director of Health Care and

### International Health Divison, RGOB

Tel.No:   	975-2-323454

Fax No:  	975-2-323527

E-mail:	           sangay@druknet.net.bt

- Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 636,499 | GNP per capita | 547 $US |
| Infants 0-11 months | 19,095 | Infant mortality rate | 70.7 / 1000 |
| Percentage of GDP allocated to Health |  | Percentage of Government expenditure for Health Care |  |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation on: |  |
| - Overall government health policies and strategies | Document number: 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Please refer to Document #1 for this information |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number: 2 |
| - Government policies and practices on private sector participation, as it relates to immunization | NOT APPLICABLE FOR BHUTAN |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported |  | Survey |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 15009 | 14367 |  |  | Diphtheria | 0 | 1 |  |  |
| DTP3 | 13668 | 13986 |  |  | Pertussis | 0 | 96 |  |  |
| OPV3 | 13540 | 14156 |  |  | Polio | 0 | 0 | 0 | 0 |
| Measles | 11295 |  |  |  | Measles | 66 | 84 |  |  |
| TT2+ Pregnant Women | 9036 | 6189 |  |  | NN Tetanus | 0 | 0 | 0 | 0 |
| Hib | NA | NA |  |  | Hib | NA | NA |  |  |
| Yellow Fever | NA | NA |  |  | Yellow fever | NA | NA |  |  |
| HepB |  | 13467 |  |  | HepB seroprevalence (if available) |  |  |  |  |

# Profile of the Inter Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency coordinating mechanism which is referred to in this document as ICC)

- Name of the ICC:     National Technical Committee for NIDS and SNIDS

- Date of constitution of the current ICC:  1995 (May)

- Organizational structure (e.g., sub-committee, stand alone) :   Focus for immunization program only but composed of a variety of Health Deparment staff, donors and other related sector representatives.

- Frequency of meetings:    Initially quite often but more recently only twice a  year.

- Composition:    As listed on the following page …

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Secretary, Ministry of Health And Education, Royal Government of Bhutan | ### Dr. Sangay Thinley |
| Secretary | Director of Health Health Department, Royal Government of Bhutan | ### Dr. Gado Tshering |
| Members | - Health Department (RGOB) - Health Department (RGOB) - Ministry of H and E (RGOB) - Health Department (RGOB) - Health Department (RGOB) - Health Department (RGOB) - Health Department (RGOB) - WHO - WHO - UNICEF - UNICEF - UNICEF - JICA - JICA - DANIDA - Ministry of Home Affairs, RGOB - Royal Bhutan Police, RGOB …………. | Dr. Rinchen Chophel Dr. Pem Namgyal Mr. Thinley Wangchuk Dr. K.C. Buragohain Dr. T.B. Rana Dr. Tenzin Penjor Mr. Thinley Dorji Dr. Orapin Singhadej Dr. Kunzang Jigme Ms. Alegria Mendoza Ms. Bindhya Pradhan Ms. Tashi Zomba Mr. Yasuyuki Mori Mr. Kuenlay Dorji Mr. Bjarne Jensen Mr. Karchung Tshering Dr. Karma Tshering |

- Major functions and responsibilities :

- Organization and planning for execution of NIDS and SNIDS. - To oversee assessments of the EPI program and review monitoring and evaluation components. 3. To address other issues related to EPI programs in Bhutan as required.

- The following diagram shows the ICC functional relationships with other institutions in health sector :

(No diagram) The committee is composed of senior health policy makers and planners, representatives from the donor community, and other technical support personnel working directly with the Health Department. Field health staff and representatives from the Ministry of Home Affairs and the Royal Bhutan Army are also involved specifically for logistical coordination and for additional support to social mobilization efforts and involvement of other related sectors.

Find attached the following documents :

| - Terms of reference of the ICC | Please see information included in Document #3. |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Document number : 3 |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| ### 1. Acute Flaccid Paralysis Surveillence | RGOB, WHO and UNICEF | ### From 1997 Onwards |
| ### 2. Vaccine Vial Monitoring | ### RGOB and WHO | 1998 |
| ### 3. Coverage Impact Reports | RGOB, WHO and UNICEF | 1995 – 2000 |

- The following are the three major problems identified in the assessments :

Not Applicable

- The following are the three major recommendations in the assessments :

From the above assessments, the following recommendations have been proposed: - Continued and additional inservice training is required for health workers. - Increased monitoring is necessary for « at risk » populations. 3. Additional improvement is indicated for reporting guidelines and systems.

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document numbers: #4 – AFP # 5 – VVM #6 – Coverage Report |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | ### Please see documents listed above. |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| ### Mop-Up Campaign for TT and Measles (for Districts reporting below 80%) | 2000 | ###### US$ 50,000 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Please refer to document #1 for information |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 13,986 |
| Used doses of DTP |  |

- Estimated annual targets

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 19686 | 20297 | 20926 | 21575 | 22244 | 22934 |
| Doses of DTP planned to be used | 89406 | 91336 | 94167 | 97088 | 100098 | 10320 3 |

# New and under-used vaccines

###### ***NOT APPLICABLE FOR BHUTAN***

Find below a summary of those aspects of the plan, mentioned in section five,  that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

***NOT APPLICABLE FOR BHUTAN***

- Planning for hepB vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 20,297 | 20,926 | 21,575 | 22,244 | 22,934 |
| Total vaccine doses required | 91,336 | 94,167 | 97,088 | 100,098 | 103,203 |
| Preferred vial size(s) | 5 dose | 5 dose | 5 dose | 5 dose | 5 dose |
| Estimated wastage rate | 1.5 doses | 1.5 doses | 1.5 doses | 1.5 doses | 1.5 doses |
| % of vaccines requested from the Fund | NONE | NONE | GAVI 100% | GAVI 100% | GAVI 100% |
| AD syringes | GAVI 100% | GAVI 100% | GAVI 100% | GAVI 100% | GAVI 100% |

1 AD syringe required per dose

- Planning for Hib vaccinations:  NOT APPLICABLE FOR BHUTAN

NOTE :  If any study in the region indicates Hib benefit for decreasing morbidity and mortality from ARI, Bhutan may be interested in futher exploring.

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

- Planning for yellow fever vaccinations:  NOT APPLICABLE FOR BHUTAN

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number…… |
| --- | --- |

(NOT APPLICABLE FOR BHUTAN)

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | ### SEE TABLE BELOW |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The relevant documents are attached.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Document number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Vaccines |  | US $ |  |  |  |  |  |  |  |  |
| 1a. DANIDA |  | 50000 | 50000 | 50000 | 50000 | 50000 |  |  |  |  |
| 1b. JICA/UNICEF |  | 76574 | 76574 | 76574 | 76574 | 76574 |  |  |  |  |
| 2. Syringes and Needles |  | US $ |  |  |  |  |  |  |  |  |
| 2a. DANIDA |  | 3181 | 3181 | 3181 | 3181 | 3181 |  |  |  |  |
| 2b. JICA/UNICEF |  |  |  |  |  |  |  |  |  |  |
| 3. Other Items (including equipment, cold chain, support, etc.) |  | US $ |  |  |  |  |  |  |  |  |
| 3a. DANIDA |  | 47477 | 47477 | 47477 | 47477 | 47477 |  |  |  |  |
| 3b. JICA/UNICEF |  | 34697 | 34697 | 34697 | 34697 | 34697 |  |  |  |  |
| Specify contributions in USD made by each partner sharing the strategy (Government, name of donor…) |  |  |  |  |  |  |  |  |  |  |

PLEASE REFER TO DOCUMENTS #7, #8 and #9

FOR DETAILS REGARDING SOURCES AND BREAKDOWN OF AVAILABLE FUNDING UNTIL 2002.

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document number…… |
| --- | --- |

***NOTE:  NOT APPLICABLE FOR BHUTAN***

***NOTE: NOT APPLICABLE FOR BHUTAN***

# Preferred channel of funds

# (Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government | X | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

Major concerns of the ICC is on long-term sustainability of immunization services. Since this also a concern for GAVI and GAVI is supporting innovations in improving immunization services, the Bhutan Health Trust Fund is an innovative means of addressing issues of sustainability of Primay Health Care in general and in particular immunization programs. The RGOB of Bhutan would be especially interesed in GAVI’s ability to contribute to the Bhutan Health Trust Fund.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

**NOTE:  SEE PAGE 13 FOR BREAK DOWN AND DOCUMENTS #7 and #8.**

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor 4 | Donor n.. 2 | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item n3… |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| Total expenditure in 1999 |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

NOTE :  PLEASE SEE PAGE NUMBER 13 AND DOCUMENTS #7 and #8

Table 2

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | Donor 11 | Donor 2 | Donor 3 | Donor n.. 2 |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  | 129755 |  |
| 1.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 1.2 | - Line item n3… |  |  |  |  |  |  |  |  |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  | 82174 |  |
| 2.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 2.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Line item 1 |  |  |  |  |  |  |  |  |  |
| 3.2 | - Line item n… |  |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  | 211929 |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | AS ABOVE – DOCUMENT #1. |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | ### Document number 2 |
| - Government policies on private sector participation, as it relates to Immunization. | NA |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC | See Document #3 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number 3 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document numbers : 4 AFP 5 VVM 6 ICR |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | NA |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Refer to Document #1 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | NA |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document numbers 7 and 8 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | As above |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | NA |

Please submit hard copy documents with an additional electronic copy wherever possible