Application Form for Country Proposals

Providing approximately two years of support for an

HPV Demonstration Programme

Submitted by

The Government of Sierra Leone

Date of submission: 30th October 2012

Deadline for submission:  31 October 2012

Please submit the Proposal using the form provided.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE

GRANT TERMS AND CONDITIONS

Countries will be expected to sign and agree to the following GAVI Alliance terms and conditions in the application forms, which may also be included in a grant agreement to be agreed upon between GAVI and the country:

FUNDING USED SOLELY FOR APPROVED PROGRAMMES

The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance for this application will be used and applied for the sole purpose of fulfilling the programme(s) described in this application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for this application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.

AMENDMENT TO THIS PROPOSAL

The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in this application. The GAVI Alliance will document any change approved by the GAVI Alliance, and this application will be amended.

RETURN OF FUNDS

The Country agrees to reimburse to the GAVI Alliance, all funding amounts that are not used for the programme(s) described in this application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.

SUSPENSION/ TERMINATION

The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in this application, or any GAVI Alliance-approved amendment to this application.  The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in this application if a misuse of GAVI Alliance funds is confirmed.

ANTICORRUPTION

The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with this application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.

AUDITS AND RECORDS

The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.

The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds.  If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this application is accurate and correct and forms a legally binding obligation on the Country, under the Country’s law, to perform the programmes described in this application.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARENCY AND ACCOUNTABILITY POLICY

The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and will comply with its requirements.

ARBITRATION

Any dispute between the Country and the GAVI Alliance arising out of or relating to this application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English.

For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance.  For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.

The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in this application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death.  Country is solely responsible for all aspects of managing and implementing the programmes described in this application.

Use of commercial bank accounts

The eligible country government is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support, including HSS, ISS, CSO and vaccine introduction grants.  The undersigned representative of the government confirms that the government will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.

Application Specification

Q1.	Please specify for which type of GAVI support you would like to apply to.

| Preferred vaccine (bilavent (GSK) or quadrivalent (Merck)) See below for more information | Month and year of first vaccination | Preferred second presentation1 |
| --- | --- | --- |
| Bilavent (GSK) | June 2013 | Quadrivalent (Merck) |

For more information on vaccines:  http://www.who.int/immunization_standards/vaccine_quality/PQ_vaccine_list_en/en/index.html

1 This “Preferred second presentation” will be used in case there is no supply available for the preferred presentation of the selected vaccine (“Vaccine” column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

Executive Summary

Q2.	Please summarize the country’s HPV Demonstration Programme plan.

Genital Human Papillomavirus (HPV) is the most common sexually transmitted virus.  Being highly transmissible, the greater majority of sexually active men and women are infected with HPV at some time in their lives. Over 20 million people are currently infected, and about 6 million more get infected each year. HPV is usually spread through sexual contact, predominantly but not exclusively through penetrative intercourse.

In general, most HPV infections are transient and benign. However, persistent genital infection with certain viral genotypes can lead to the development of anogenital precancers and cancers. Diseases caused by HPVs include cancers of the cervix, vagina, vulva, penis and anus; a subset of head and neck cancers; anogenital warts; and recurrent respiratory papillomatosis.

Cervical cancer is the 2nd leading cause of cancer deaths among women around the world.  Cervical cancer is also the most common cancer affecting women in developing countries. It has been estimated to have been responsible for almost 260 000 deaths in 2005, of which about 80% occurred in developing countries.

Cervical cancer incidence rates portray a pattern of disparity across regions. In 2005, there were about 500,000 cases of cervical cancer and 260,000 related deaths worldwide. Cervical cancer incidence rates vary from 1–50 per 100,000 females; rates are highest in Latin America and the Caribbean, sub-Saharan Africa, Melanesia, and south-central and South-East Asia. Most cases of cervical cancer are diagnosed in women aged above 40 years.

Sierra Leone has gone through a decade long civil strife with massive population displacement and the breakdown of administrative and physical structures for the effective delivery of social services. Most of the factors that promote Sexually transmitted infections are prevalent in the country.

Though cervical cancer is known to exert a sizeable burden of disease on the population, there are definite challenges in responding to the situation appropriately. Fortunately, a cancer register has recently been opened by the Directorate of Non-Communicable Diseases to document the incidence and prevalence of various cancers in Sierra Leone. Currently, the facilities for screening and treatment are remote. Therefore, opportunities for screening and treatment should be explored and put in place as a matter of urgency. The existence of a ppunlic health laboratory at the Lakka Hospital is a good foundation on which to build.

There is no cure for HPV infection, but some of the problems it causes can be treated. HPV vaccine is important because it can prevent most cases of cervical cancer in females, if it is given before a person is exposed to the virus.

The proposed HPV demonstration in two districts of Sierra Leone heralds opportunities for circumventing and ameliorating the awkward consequences of HPV infection among adolescent girls before they assume adult life. During the pilot phase, we intend to explore effective strategies of service delivery and document issues circumscribing the delivery of HPV vaccines to young girls using an integrated strategy.  Worthwhile lessons learnt during this phase can be confidently utilized to expand to other districts in the future.

Immunisation Programme Data

Q3.	Please provide national coverage estimates for Penta 3 for the two most recent years from the WHO/UNICEF Joint Reporting Form in the table below. If other national surveys of DPT3 coverage have been conducted, these can also be provided in the table below.

| Trends of national Penta3 coverage (percentage) |
| --- |
| Vaccine | Reported | Survey |
|  | Year-2010 | Year-2011 | Year-2010-EPI coverage survey | Year-MICS – 4, 2010 |
| Penta 3 | 95% (JRF 2011) | 91% (JRF 2011) | 86% | 71.8% |

Q4.	If survey data is included in the table above, please indicate the years the surveys were conducted, the full title, and if available the age groups the data refer to.

The EPI coverage survey was done in 2010 and covered immunization of children <1 and women of child bearing age and pregnant women for TT immunization. Similarly the Multiple Indicator Cluster Survey 4 (MICS4) was done in 2010 and looked at the same set of population for immunization.

Note: The IRC may review previous applications to GAVI for a general understand of country’s capacities and challenges.

HPV Demonstration Programme Plan

District(s) profile

Q5.	Please describe which district or districts have been selected for the HPV Demonstration Programme, completing all components listed in the table below.

| Component | District 1-Bo | District 2-Western Area Urban |
| --- | --- | --- |
| Topography (% urban, % rural) | 40% of the population lives and urban areas while 60% lives in rural areas (source: Census data 2004, Statistics Sierra Leone) | 40% of the population lives in urban areas while 60% lives in rural areas (source: Census data 2004, Statistics Sierra Leone) |
| Number and type of administrative subunits, e.g., (Chiefdoms/Zones) | 15 chiefdoms (source: Census data 2004, Statistics Sierra Leone) | 30 zones (source: Census data 2004, Statistics Sierra Leone) |
| Total population | 624,389 (source: Census data 2004, Statistics Sierra Leone) | 991,618 (source: Census data 2004, Statistics Sierra Leone) |
| Total female population (%) | 320,175 (51.3%) (source: Census data 2004, Statistics Sierra Leone) | 485,095 (49%) (source: Census data 2004, Statistics Sierra Leone) |
| Total female population aged 9-13 years (% of total female population) | 40,848 (source: Census data 2004, Statistics Sierra Leone) | 70,272 (source: Census data 2004, Statistics Sierra Leone) |
| Number and type of public health facilities | 110 Peripheral Health Units (PHUs), 1 secondary hospital | 107 PHUs, 8 secondary/tertiary hospitals |
| Number and type of health workers in all district public health facilities | Midwifery Sister - 1 CHO - 32 CHA - 9 SECHN - 29 MCH Aide - 194 EDCU Assistant - 37 Nursing Aide - 13 TOTAL = 315 (Source: December 2010 Attendance Returns, HRH) | Midwifery Sister - 2 CHO - 16 CHA - 2 SRN - 3 SECHN - 75 MCH Aide - 221 EDCU Assistant - 4 Nursing Aide - 39 TOTAL = 362 (Source: December 2010 Attendance Returns, HRH) |
| Number and type of private health facilities | Mission | Private | NGO | Mission | Private | NGO |
|  | 7 | 11 | 3 | 13 | 20 | 3 |
| Number and type of health workers or staff in private health facilities in the district | Midwifery Sister - 6 SRN - 7 CHO - 10 SECHN - 21 MCH Aide - 5 Nursing Aide - 18 TOTAL = 67 (Source: DHMT) | Midwifery Sister - 12 SRN - 18 CHO - 6 SECHN - 35 MCH Aide - 26 Nursing Aide - 46 TOTAL = 143 (Source: DHMT) |
| Number and type of public and private primary and secondary schools | Public | Private | Public | Private |
|  | Pri. | Sec. | Pri. | Sec. | Pri. | Sec. | Pri. | Sec. |
|  | 115 | 10 | 454 | 99 | 75 | 32 | 409 | 211 |
| Number of teachers in public and private primary and secondary schools | 974 | 150 | 1,378 | 1,024 | 687 | 345 | 3,214 | 2,345 |
| Estimates of the number and percent of girls attending school for each of the following ages: 9 year old girls 10 year old girls 11 year old girls 12 year old girls 13 year old girls | 9 year old girls--------8,060(20%) 10 year old girls------8,010 11 year old girls------8,690 12 year old girls------8,312 13 year old girls------7,768 (total=40,840) (Source: 2004 Census data, Statistics Sierra Leone) | 9 year old girls--------10,774 (15%) 10 year old girls------16,936 11 year old girls------15,605 12 year old girls------15,478 13 year old girls------14,479 (total=73,272) (Source: 2004 Census data, Statistics Sierra Leone) |
| Estimates of the number and percent of girls out of school for each of the following ages: 9 year old girls 10 year old girls 11 year old girls 12 year old girls 13 year old girls | 9 year old girls--------2,263 10 year old girls------686 11 year old girls------449 12 year old girls------206 13 year old girls------99 (total=3,701) (Source: 2004 Census data, Statistics Sierra Leone) | 9 year old girls--------471 10 year old girls------89 11 year old girls------419 12 year old girls------876 13 year old girls------545 (total=2400) (Source: 2004 Census data, Statistics Sierra Leone) |

Sources of data: 2004 Census, District Health Management Teams, HRH Attendance reports 2012

Q6.	Please give a brief description of why this district (or districts) was (were) selected to participate in the HPV Demonstration Programme.

The chosen districts are heavily populated and are primarily cosmopolitan in nature. Nevertheless, there is a growing range of peri-urban and rural settlements in both of them. They have a scope of very good socio economic facilities such as schools, job opportunities and other social amenities, which attract people from other districts within the country.  In addition, politically and administratively, these districts herald the first and second largest capital cities, including the capital city of the country, which is located in Freetown. These characteristics combined with ongoing infrastructural developments in these districts, render them reasonable options for HPV demonstration. The scenario of a spectrum of population with diverse socio-economic and settlement patterns proffers an excellent avenue for programme implementation, monitoring, supervision and evaluation as well as measuring the impact of HPV vaccine over time across the social strata. Demographically, these districts do not only have the highest numbers of adolescent girls but they also register the highest statistics of school going girls in the country. Moreover, the HPV demonstration can be feasibly integrated with other adolescent health programmes that are predominantly implemented in schools within these districts.

Q7.	Please describe the operations of the EPI programme in the district(s) selected for the HPV Demonstration Programme.

| Component | District 1-Bo | District 2-Western Area Urban |
| --- | --- | --- |
| Number and type of administrative subunits (e.g. health facilities) used for routine vaccine delivery | 110 | 60 |
| Number and type of outreach sessions in a typical month used for routine vaccine delivery | There are 4 outreach sessions per month per Health facility | There are 4 outreach sessions per month per Health facility |
| Penta 3 coverage | 82% Year 2011 (JRF 2011) | 68% Year 2011 (JRF 2011) |
| Polio3 coverage | 81% Year 2011 (JRF 2011) | 67% Year 2011 (JRF 2011) |
| Measles first dose coverage | 78% Year 2011 (JRF 2011) | 66% Year 2011 (JRF 2011) |
| TT2+ (pregnant women) | 124% Year 2011 (JRF 2011) | 62% Year 2011 (JRF 2011) |

Q8.	Please summarize the performance of the district EPI programme as reported in any recent evaluation, for example identifying resources available, management, successes, and challenges.

A post Introduction Evaluation (PIE) for PCV was conducted in October 2011. A summary of the findings are as follows:

- There are committed and dedicated healthcare workers to provide immunization services.

- There is high political commitment

- Immunization services are integrated with other child health interventions

- The staff are knowledgeable on immunization services

- There is adequate coldchain space for storage of vaccines

- There is in integrated disease surveillance system

- Injection safety practice is done

- There is a good relationship between health workers and the community.

Some of the challenges were:

- There is limited collaboration between healthcare workers and communities for effective immunization services

- There are frequent breakdowns of the cold chain equipments

- There is heavy workload on healthcare workers

- There are limited training materials on immunization in health facilities for training of Health workers or for use with communities or community health workers

Q9a.	Please describe any current or past linkages the district EPI programme has had with the primary and/or secondary schools in the district, e.g., going to schools for health education, delivery of vaccinations, outreaches, etc.

EPI services are integrated with other healthcare services in all the districts. The districts work in close collaboration not only with health partners but also with other line ministries and agencies. The Ministry of Health and Sanitation works in close collaboration with the Ministry of Education at national and district levels for TT immunization in schools. The TT in school immunization services is provided in the form of outreach sessions and during each outreach session, health education messages are as well given on a spectrum of topics including immunization, family planning, nutrition and personal and environmental hygiene.

Q9b.	Please indicate if gender aspects relating to introduction of HPV vaccine are addressed in the demonstration programme?

Gender aspects are part of the overall national immunization plan and policy. Gender equity is enshrined in the EPI Policy in Sierra Leone. As a demonstration of addressing gender issues, the EPI policy in Sierra Leone makes provision for immunization of women of child bearing age and pregnant women with TT vaccination. Similarly, the revised EPI policy makes provision for the HPV vaccination to school going girls in Sierra Leone. The sensitisation in the demonstration program will explain why vaccination is for girls only (and not for boys). However, the boys will need to support the girls as much as needed for good health, social and economic outcomes.

Q9c.	Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?

There has been no evidence or studies demonstrating socio-economic and/or gender barriers to immunization in Sierra Leone. The target populations have always been very receptive of immunization services in the country. Immunisation services are part of the Free Health Care in Sierra Leone

Objective 1: HPV vaccine delivery strategy

Q10.	Please describe the HPV vaccine delivery strategy selected (school-based, facility-based, outreach, mixed, other, etc.) and the rationale for its selection.

The goal of the HPV demonstration program is to show the benefits expected from the reduction/prevention of  the incidence of cervical cancer among girls in the country irrespective of educational or socio-economic status. It is also expected that the lessons learnt from this demonstration will be used when HPV vaccine delivery will be extended country-wide. Immunization services are provided through two main strategies: Static and Outreach either to ‘ordinary’ communities or to ‘captured’ communities eg schools. The vaccine delivery strategy will be a hybrid of static and outreach strategy. The outreach (in schools) will provide the services to school going girls and the static and outreach to other communities will capture those that are not going to school.

Note: If the application proposes to use school as a venue for HPV vaccine delivery the minimal proportion of girls of the target vaccination cohort or target grade that is enrolled in school must be 75% nationwide (not only in the selected district).

The vaccine will be delivered to the target population in various locations and not only in schools.

Q11.	If schools are being used as a venue for HPV vaccine delivery, please state the percentage of girls in the target age group which are attending school in the district(s).

The percentage of girls attending school in the target age group (9 yrs) is as follows: Bo is 78% and Western Urban is 96%

Q12. Please identify a single year of age (or single grade in school) target vaccination cohort within the target population of 9-13 year old girls. Describe the total number of girls included and the proportion of the adolescent (10-19 year old) and female (all ages) population they represent. Identify the data source for this information and state whether these data have been validated by other means.

According to the 2012 projected census 2004 population data, the total number of girls aged 9 years is 21,576 (in Bo and Western Urban). This number constitutes 10% of girls aged 10-19 years. Similarly the proportion of this age group among the total female population is 1.3%.

Q13.	If the target population is a single grade in school, describe the percentage of girls in the target grade which are between the ages of 9 and 13 years and the data source.

Although the target population is a single cohort, however, their selection is not based on grade in school because not all of them are in school. Therefore the vaccine delivery strategy will be to target this cohort both in school and out of school.

Note: If the strategy selects eligible girls based on their grade in school, then at least 80% of the girls in the target age group should be between 9 and 13 years of age (the WHO recommended age group for HPV vaccine).

Q14.	Please describe how eligible out-of-school girls will be identified and the mechanism for providing them an opportunity to receive HPV vaccine.

The out-of-school girls will be provided with HPV vaccination through the static and outreach immunization sessions.

Q15.	Please describe the mechanism for reaching all the target girls with three doses who were missed on the main vaccination days, specifying plans for reaching hard-to-reach or marginalized girls.

The EPI policy on immunization clearly states that immunization services must be provided on a daily basis whenever a target shows up for immunization. Girls missed on main vaccination days will be encouraged to go to the static vaccination centre or an outreach point to be vaccinated. All the districts have immunization plans based on the RED approach. The RED approach contains strategies to reaching hard-to-reach or marginalised communities with all immunization services. The HPV vaccination will be delivered as part of a comprehensive overall immunization package.

Q16.	Please summarize ability to manage all the technical elements which are common to any new vaccine introduction, e.g. cold chain equipment and logistics, waste management, vehicles and transportation, adverse events following immunization (AEFIs), surveillance, and monitoring, noting past experience with new vaccine introductions (such as rotavirus, pneumococcal vaccine, or others).

In preparation for the HPV demonstration, the country, not only for this purpose, has conducted series of cold chain assessments both at district and national level to address the challenges of cold chain management. In a bid to expand the cold chain facility at national level, a new national walk-in cold room is being installed to accommodate additional vaccine in future. Similarly, battery less solar refrigerators have being provided to all districts to augment the cold chain capacity at their level. At health facility level, similar equipments have been introduced in some facilities and will gradually rolled over to strategic health facilities. In addition, districts are encouraged to institutionalize preventive cold chain maintenance plans and activities. Incinerators are being constructed in districts and the use of safety boxes and appropriate disposal methods will be continued. HPV surveillance will be part of the Integrated Disease Surveillance and Response (IDSR). Monitoring tools have already been reviewed to capture HPV as an integral part of the Health Management Information System HMIS.

Q17.	Please describe the cold chain status for the selected district and the data source(s) for this information. Information such as the number of cold storage facilities, function and working order of the facilities, storage capacity (and any excess capacity), distribution mechanism for routine delivery of vaccines, status of vaccine carriers and icepacks (e.g., supply shortages or excesses), and plan for HPV vaccine storage and distribution during the HPV Demonstration Programme.

| Component | District 1-Bo | District 2-Western Area Urban |
| --- | --- | --- |
| Number and type of cold storage facilities | 58 solar refrigerators, 4 ice-lined refrigerators, 4 deep freezers (District cold chain assessment report 2012) | 47 solar refrigerators, 5 ice-lined refrigerators, 3 deep freezers (District cold chain assessment report 2012) |
| Functioning and working order of the facilities | 52 functioning solar refrigerators, 4 functioning ice-lined refrigerators, no functioning deep freezers (District cold chain assessment report 2012) | 47 solar refrigerators, 5 ice-lined refrigerators, 3 deep freezers (District cold chain assessment report 2012) |
| Storage capacity (any excess) | The storage capacity at district and PHU level is adequate for the HPV demonstration. Cold chain expansion will continue as a routine activity in the EPI plan. (District cold chain assessment report 2012) | The storage capacity at district and PHU level is adequate for the HPV demonstration. Cold chain expansion will continue as a routine activity in the EPI plan. (District cold chain assessment report 2012) |
| Distribution mechanism | A combination of mechanisms are used for vaccine distribution. The DHMT during their routine distribution of free health care supplies also takes vaccine along to PHUs. Also, some PHU staff pick up vaccine supplies at district level. The district also uses the NGOs to assist with the distribution of vaccines and supplies. (District cold chain assessment report 2012) | A combination of mechanisms are used for vaccine distribution. The DHMT during their routine distribution of free health care supplies also takes vaccine along to PHUs. Also, some PHU staff pick up vaccine supplies at district level. The district also uses the NGOs to assist with the distribution of vaccines and supplies. (District cold chain assessment report 2012) |
| Number and status of vaccine carriers | 167geostyle vaccine carriers are available and are in good condition. (District cold chain assessment report 2012) | 44 geostyle functioning, 12 faulty vaccine carries. (District cold chain assessment report 2012) |
| Number and status of icepacks (any shortages or excess) | 767ice packs are available in good condition. (District cold chain assessment report 2012) | 789 ice packs are available and are in good condition. (District cold chain assessment report 2012) |

Q18.	Additional district cold chain information if necessary:

[Type text]

Objective 1: HPV vaccine delivery training and community sensitisation & mobilisation plans

Q19.	Please describe initial plans for training of health workers and others who will be involved in the HPV Demonstration Programme.

Training materials for the new vaccine will be adapted from existing global/regional materials or new materials will be developed if existing ones are either not appropriate or are insufficient. A training of trainers will be conducted at national level during the second quarter of 2013. The trainers will then train all health workers by the end second quarter in 2013 for the demonstration proper.

Q20.	Please describe initial communication plans for sensitizing and mobilizing communities for the HPV Demonstration Programme.

A detailed advocacy/social mobilization plan will be developed, which will be limited to the outline of activities below that are envisaged to support the introduction.

- Conducting high-level advocacy meetings with political and religious leaders

- Development of messages for the various channels of communication

- Briefing of media personnel to ensure that content of message are correct

- Media Campaign

- Conducting community meetings on the demonstration of the vaccine

- Meetings will be held with school authorities to sensitize them on the new vaccine demonstration.

- Launching ceremony in the presence of high level officials.

Q21.	Briefly describe any initial thinking about potential barriers or risks to community acceptance and the process or communication plan that might be used to address this. Consider briefly describing any positive leverage points that might be beneficial for programme implementation to promote acceptability.

Potential barriers to immunization will be first of all prevented by ensuring that HPV vaccination as with other immunization services is delivered to target beneficiaries safely. The social mobilization and programme communication will take into consideration the socio-cultural characteristics of the various communities. Evidence based messages regarding the safety of HPV vaccines will be used to address any issue of refusal or barriers to immunization. The stake holders will be engaged to address any issue of barriers to HPV vaccination. Spots of barriers will be identified and relevant stakeholders contacted or utilized to address such issues.

Objective 1: HPV vaccine delivery evaluation plan

Q22.	Indicate the agency/person who will lead the evaluation required for the “Learn by Doing” objective.

WHO and UNICEF who are the traditional agencies for immunization services evaluations will conduct the evaluation to address the “learn by doing” objective.

Objective 2: Assessment of adolescent health interventions

Q23.	Please summarize the anticipated activities for the assessment of adolescent health interventions, such as planning milestones, stakeholder meetings, methodology for the assessment, process for identifying a lead for this activity, and the process to involve the TAG in this work.

- Planning meetings will be held with relevant stakeholders to discuss the assessment of adolescent health interventions. The participation of the National school Health programme will be tapped into for the planning activities.

- A team of assessors will be identified, indicators for the assessment will be developed, Tools will be developed to collect information on the assessment exercise, the assessors will be trained on how to conduct the assessment. The teams will be deployed in randomly selected schools, health facilities and communities to carry out the assessment exercise. The findings will be compiled and a final report prepared and shared with relevant stakeholders for their inputs.

- The school health Programme being the body charged with the responsibility of providing adolescent health services in the country will be the lead for this exercise.

- The Technical Advisory Group (TAG) will oversee and support the process as relevant.

Objective 3: Development or revision of cancer control or cervical cancer prevention and control strategy

Q24.	Please summarize the planned activities for the development or revisions of a national cervical cancer prevention and control strategy, such as planning milestones, stakeholder meetings, methodology for developing the strategy, process for identifying a lead for this activity, and the process to involve the TAG in this work.

The process of development of a national cervical cancer prevention and control strategy will be done under the following headings:

- Planning mile stone

- Identification of relevant stake holders for advocacy, resource mobilization, technical inputs etc

- Identification of relevant resources

- Coordination mechanism

- Implementation of strategy

- Monitoring and evaluation of strategy

- Stakeholder meetings

- Development of concept paper on cervical cancer prevention and control strategy

- Convening of relevant stakeholder meetings

- Discussion of cervical cancer prevention or control strategy

- Meetings with specific groups

- Methodology for developing the strategy

- Stakeholder working groups will be developed

- TORs for the different working groups will be developed

- Action points for each group will be developed

- Inputs will be made by all groups

- Harmonisation of various inputs will be done

- Final strategy will be developed and shared with partners

- Process for identifying a lead for this activity

- Various meeting by the Technical Coordinating Committee (TCC) and Health Sector Strategic Group (HSSG) will be held to identify a lead for this activity

- process to involve the TAG in this work.

- Various collaboration meetings will be held to fully involve the TAG in the development and implementation of this strategy.

Technical advisory group

Q25.	Please identify the membership and terms of reference for the multi-disciplinary technical advisory group established that will develop and guide implementation of the HPV Demonstration Programme and list the representatives (at least positions, and ideally names of individuals) and their agencies.

- Countries are encouraged to use their ICC or a subset of the ICC as the multi-disciplinary TAG.

- The TAG must at least have representatives from the national EPI programme, cancer control, education, and the ICC (if separate from the ICC), and adolescent and/or school health (if they are represented within the Ministry of Health).

Enter the family name in capital letters.

| Agency/Organisation | Name/Title | Area of Representation1 |
| --- | --- | --- |
| Ministry of Health and Sanitation | Hon. T. M. BOBOR-SAWYERR Ag. Minister of Health and Sanitation | Top Management Team |
| Ministry of Health and Sanitation | Alhaji Dr. Kisito S. DAOH Chief Medical Officer | Top Management Team |
| Ministry of Health and Sanitation | Dr. Alhassan SEISAY Deputy Chief Medical Officer/Director of Primary Health Care | Top Management Team |
| Ministry of Health and Sanitation | Mr. Joseph T. KANU. Permanent Secretary | Top Management Team |
| Ministry of Health and Sanitation | Mr. Amara S. KOROMA Director of Financial Resources | Health Finance |
| Ministry of Health and Sanitation | Dr Samuel A. S. KARGBO Director of Reproductive and Child Health | Reproductive and Child Health |
| Ministry of Health and Sanitation | Dr. Donald BASH-TAQI Director of Non communicable Diseases | Non communicable disease |
| Ministry of Health and Sanitation | Dr. Edward MAGBITY Deputy Director of Policy and Planning | Policy and planning |
| Ministry of Health and Sanitation | Dr. Sarian KAMARA Manager of Reproductive Health/Family Planning | Reproductive Health |
| Ministry of Health and Sanitation | Rev. Dr. Thomas T. SAMBA Programme manager, Child Health/EPI | Immunization |
| Ministry of Health and Sanitation | Dr. Samuel KITEL Programme manager National School Health Programme | School Health |
| Ministry of Finance | Hon. Dr. Samura KAMARA Minister of Finance | Finance sector |
| Ministry of Education | Hon. Dr. Minkailu BAH Minister of Education | Education Sector |
| WHO | Dr. Wondimagegnehu ALIMU. WHO country Representative | Health Development partner |
| UNICEF | Mr Roeland MONASCH UNICEF Country Representative | Health Development partner |
| SABIN | Dr. Clifford W. KAMARA- Senior Programme Officer. | Health Development partner |
| Health for All Coalition | Mr. Charles MAMBU Executive Director | Civil Society |

1Area of representation includes cancer control, noncommunicable disease, immunisation, adolescent health, school health, reproductive health, maternal or women’s health, cervical cancer prevention, nursing association, physicians, health communications, midwives, civil society group, education, etc.

Q26.	If known, please indicate who will act as the chair of the technical advisory group.

Enter the family name in capital letters.

|  | Name/Title | Agency/Organisation | Area of Representation |
| --- | --- | --- | --- |
| Chair of Technical Advisory Group | Hon. T. M. BOBOR-SAWYERR Ag. Minister of Health and Sanitation | Ministry of Health and Sanitation | Hon. Minister of Health and Sanitation |

Project manager/coordinator

Q27.	List the contact details, position, and agency of the person who has been designated to provide overall coordination for the day-to-day activities of the two-year HPV Demonstration Programme, taking note that a technical officer/lead/manager from EPI might be most suitable as a part of their current role and responsibilities.

Enter family name in capital letters.

| Name | Rev. Dr. Thomas T SAMBA | Title | Programme Manager, Child Health/EPI Programme |
| --- | --- | --- | --- |
| Tel no | +232 76 662 162 |  |  |
| Fax no |  | Agency | Ministry of Health and Sanitation |
| Email | ttsamba@yahoo.com | Address | Medical Stores Compound, New England, Freetown, Sierra Leone |

Timeline

The HPV Demonstration Programme will include immunization of the cohort of girls in two consecutive years (Figure I). Countries are required to begin vaccinating in the demonstration district within two years of the application.

Figure I. HPV Demonstration Programme timeline

|  | First round of vaccination | Evaluation of first round | Second round of vaccination |
| --- | --- | --- | --- |
|  | Assessment feasibility integrated delivery Start cancer control strategy | If feasible, test joint delivery of services Finalisation of cancer control strategy |
| Planning | Year 1: demo project implementation | Year 2 |

Q28.	Please modify as necessary and complete the timeline below for the main activities for HPV vaccination, assessment of adolescent health interventions, and development/revision of a national cervical cancer prevention and control strategy planned for the HPV Demonstration Programme. Applicants may want to complete this in MS Excel.

Please see attached Excel file for the timeline of activities.

Budget

Q29.	Please provide a draft budget for year 1 and year 2, identifying activities to be funded with GAVI’s programmatic grant as well as costs to be covered by the country and/or other partner’s resources.

Note: If there are multiple funding sources for a specific cost category, each source must be identified and their contribution distinguished in the budget.

| Cost category | Funding source | Estimated costs per annum in US$ |
| --- | --- | --- |
|  |  | Year 1 | Year 2 |
| TAG meetings | GAVI | 5,000 | 2,500 |
| Programme management and coordination | GOSL, GAVI | 10,000 | 6,000 |
| Cold chain equipment | GOSL, UNICEF | 5,000 | 5,500 |
| Other capital equipment (describe) Rehabilitation of coldrooms and stores (national and districts) | GOSL, GAVI, UNICEF, WHO | 15,000 | 10,000 |
| Personnel, including salary supplements and/or per diems | GOSL, GAVI | 4,000 | 5,500 |
| Transport | GOSL, UNICEF | 6,000 | 5,000 |
| Training | GAVI | 30,000 | 20,000 |
| Community sensitization and mobilization | GAVI, UNICEF | 10,000 | 11,000 |
| Waste disposal | GAVI, UNICEF | 4,000 | 4,500 |
| AEFI monitoring | GAVI, WHO | 3,000 | 3,500 |
| Monitoring and supportive supervision | GOSL, GAVI | 6,000 | 5,000 |
| Evaluation of vaccine delivery | GAVI | 40,000 | 20,000 |
| Assessment of feasibility of integrating ADH with HPV vaccines | GAVI | 5,000 | 3,000 |
| Drafting national cervical cancer prevention and control strategy | GAVI | 10,000 | 5,000 |
| Technical assistance from local experts | GAVI | 25,000 | 15,000 |
| Subtotal for which GAVI funds are being requested |  | 145,000 | 50,000 |
| Subtotal from other funding sources |  | 33,000 | 71,500 |
| TOTAL |  | 178,000 | 121,500 |

Procurement of HPV vaccine

HPV vaccines must be procured through UNICEF. Auto-disable syringes and disposal boxes will be provided.

Q30.	Using the estimated total for the target population in the district and adding a 25% buffer stock contingency, please describe the estimated supplies needed for HPV vaccine delivery in each year in the table below.

| Required supply item | # Year 1 (2013) | Year 1 (2013) cost US$ |
| --- | --- | --- |
| Number of vaccine doses | 87,350 | 436,752 |
| Number of AD syringes | 87,350 |  |
| Number of safety boxes | 1,165 pcs. ( 47 cartons) |  |
| TOTAL |  |  |

| Required supply item | # Year 2 (2014) | Year 2 (2014) cost US$ |
| --- | --- | --- |
| Number of vaccine doses | 89,097 | 445,487 |
| Number of AD syringes | 89,097 |  |
| Number of safety boxes | 1,188 pcs. (48 cartons) |  |
| TOTAL |  |  |

Q31.	Please indicate how funds for operational costs requested in your budget in section 6 should be transferred by the GAVI Alliance (if applicable).

The fund should be transferred into the CH/EPI account. The account details are provided in the table below.

Financial Management Arrangements Data Sheet

| Information to be provided by the recipient organization/country |
| --- |
| 1. Name and contact information of the recipient organization(s) | Ministry of Health and Sanitation 4th Floor Youyi Building, Freetown, Sierra Leone |
| 2. Experiences of the recipient organization with GAVI, World Bank, WHO, UNICEF, GFATM or other donors-financed operations (e.g. receipt of previous grants) | Yes If YES, please state the name of the grant, years and grant amount: GAVI grants have been received by the Ministry of Health and Sanitation for INS, ISS, HSS and New Vaccine introduction grant. Please see table (a) immediately below this table for the type, time and amount of grant received. and provide the following: For completed Grants: What are the main conclusions with regard to use of funds? Funds have been used based on approved planned activities. However, we note with concern that the processing of funds from GAVI is very bureaucratic and funds are sometimes either not forth coming or unduly delayed. For on-going Grants: Most recent financial management (FM) and procurement performance rating? Financial management (FM) and procurement implementation issues? |
| 3. Amount of the proposed GAVI HPV Demo grant (US Dollars) | $145,000 in year 1 and $ 50,000 in year 2 |
| 4. Information about financial management (FM) arrangements for the GAVI HPV Demo Programme: |  |
| Will the GAVI Demo Programme resources be managed through the government standard expenditure procedures channel? | Yes, the Grant will be managed through the government standard expenditure procedures channel within the Ministry of Health and Sanitation in line with the GAVI transparency and accountability policy. |
| Does the recipient organization have an FM or Operating Manual that describes the internal control system and FM operational procedures? | Yes, the Accountant General’s Department has an Operational Manual (AGD) including the Ministry of Economic Development FRMS. The MOHS has drafted an accounting manual which is being finalized. All GAVI funds are coordinated by the Child Health EPI/Programme under the supervision of Top Management Team of the Ministry of Health and Sanitation The system of approval of proposals and implementation of annual plans includes all partners who constitute the Health Sector Steering Group (HSSG) formerly ICC. |
| What is the budgeting process? | Plans of action (POAs) are developed annually based on programme priorities in line with the Health Sector Strategic Plan (HSSP). The planning cycle for MOH&S starts in October each year and ends in early December. During this time, planning takes place at district and national levels. All cost centers including programmes have the responsibility of developing their annual plans with descriptive activities based strategies and priorities. These plans are now costed for various activities and submitted to the Directorate of Policy Planning and Information for compilation. Budgets are prepared by the Program Manager and is approved during HSSG meetings |
| What accounting system is used or will be used for the GAVI HPV Demo Programme including whether it is a computerized accounting system or a manual accounting system? | At central level a computerized system is used and at program and district levels, excel is used. However, there are plans to computerize the entire financial management system within the MOHS. |
| What is the staffing arrangement of the organization in accounting, auditing, and reporting? Does the implementing entity have a qualified accountant on its staff assigned to the GAVI HPV Demo Programme? | The use of GAVI funds is supervised by the Directorate of Financial Resources in the Ministry of Health and Sanitation. The Directorate has qualified accounting and auditing staff. |
| What is the bank arrangement? Provide details of the bank account at the Central Bank or at a commercial bank proposed to receive GAVI HPV funds and the list of authorized signatories. Include titles. | Sierra Leone Commercial Bank, Siaka Steven Street. Signatories: 1. Joseph Tech KANU - Permanent Secretary MOHS 2. Dr Kisito S .DAOH – Chief Medical Officer MOHS |
| In the implementation of the HPV Demonstration Programme, do you plan to transfer funds from central to decentralized levels (provinces, districts etc.)? If yes, how will this funds transfer be executed and controlled? | Funding for district is based on approved planned activities. Such funds for the implementation of activities at district level will be transferred directly into the respective district accounts or directly paid through cheques. Requisition for these funds will be made through the CH/EPI Programme manager to the Chief Medical Officer and Permanent Secretary Ministry of Health and Sanitation. The Director of Financial Resources will be mandated by the Permanent Secretary to transfer and control such funds. The requested funds will be transferred and controlled by the Directorate of Financial Resources in the Ministry of Health and Sanitation. All activities supporting immunization will be coordinated by the Programme Manager CH/EPI Programme. |
| Does the implementing entity keep adequate records of financial transactions, including funds received and paid, and of the balances of funds held? | Yes this information is kept at two levels. The CH/EPI programme maintains financial records of all transactions. Balance sheet, statements of accounts and financial statements are always prepared as and when required. The Directorate of Financial Resources solicits and stores this information on a regular basis. |
| How often does the implementing entity produce interim financial reports? | Customarily financial reports are prepared on a quarterly basis |
| Are the annual financial statements audited by an external audit firm or Government audit institution (e.g. Auditor General Department…)? | There are three annual independent audits. By the internal audit department of the Ministry of Health and Sanitation By Auditor General’s Department External audit firm (for all GAVI funds). External Audit Firm – BUN TEJAN DOHERTY AND CO |
| 5. Information about procurement management arrangements for the GAVI HPV Demo Programme: |  |
| What procurement system is used or will be used for the GAVI HPV Demo Programme? | All vaccines and supplies will be procured by UNICEF. There is a procurement unit in the Ministry of Health and Sanitation that does all major procurements for different programmes or departments. However, minor procurements are done by the Child Health/EP Programme or districts as approved by the TMT based on standard guidelines. |
| Does the recipient organization have a procurement plan or a procurement plan will be prepared for this HPV Demo Programme? | A procurement plan is being prepared based on planned activities in accordance with the standard procurement guidelines. |
| Is there a functioning complaint mechanism? | Yes there is a complaint mechanism for all procurements in the Ministry of Health and Sanitation. |
| What is the staffing arrangement of the organization in procurement? Does the implementing entity have an experienced procurement specialist on its staff? | The procurement unit in the Ministry of Health and Sanitation is manned by trained and qualified personnel on procurement issues. |
| Are there procedures in place for physical inspection and quality control of goods, works, or services delivered? | Yes there are such procedures in place. |

**** Table: a- GAVI support to Sierra Leone

|  | Program Year | Grand Total |
| --- | --- | --- |
| Category of support | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | in USD |
| HSS |  |  |  |  |  |  |  | 1,154,000 | 530,750 |  |  |  | 1,684,750 |
| INS |  | 116,041 | 111,503 | 45,116 |  |  |  |  |  |  |  |  | 272,660 |
| ISS | 90,000 | 90,000 | 180,000 | 910,780 |  | 335,160 | 358,500 |  |  |  |  |  | 1,964,440 |
| Vaccine Introduction Grant |  | 100,000 |  |  |  |  |  |  | 100,000 |  |  |  | 200,000 |

Signatures

Government

The Government of Sierra Leone acknowledges that this Programme is intended to assist the government to determine if and how it could implement HPV vaccine nationwide. If the Demonstration Programme finds HPV vaccination is feasible (i.e. greater than 50% coverage of targeted girls) and acceptable, GAVI will encourage and entertain a national application during the second year of the Programme. Application forms and guidelines for national applications are available at www.gavialliance.org. The data from the Demonstration Programme and timing of a national application are intended to allow uninterrupted provision of vaccine in the demonstration district and nation-wide scale-up.

The Government of Sierra Leone would like to expand the existing partnership with the GAVI Alliance for the improvement the health of adolescent girls in the country, and hereby requests for GAVI support for an HPV Demonstration Programme.

The Government of Sierra Leone commits itself to improving immunisation services on a sustainable basis. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of targeted adolescent girls with HPV vaccine as outlined in this application.

The Government of Sierra Leone acknowledges that some activities anticipated in the demonstration programme could be considered research requiring approval by local ethics committees (e.g., collecting data from a random sample of parents of eligible girls for the HPV vaccine coverage survey). We acknowledge we are responsible for consulting and obtaining approval from appropriate local ethics committees (e.g., human subject protection committee or Institutional Review Boards) in our country, as required. By signing this application, the Government of Sierra Leone and the TAG members acknowledge that such approval may be necessary and that it will obtain such approval as appropriate.

The table in Section 6 of this application shows the amount of support requested from the GAVI Alliance as well as the Government of Sierra Leone’s financial commitment for the HPV Demonstration Programme.

Please note that this application will not be reviewed by GAVI’s Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Education or their delegated authority.

Q33.	Please provide appropriate signatures below.

Enter family name in capital letters.

| Minister of Health (or delegated authority) | Minister of Education (if social mobilization, vaccination or other activities will occur through schools) (or delegated authority) |
| --- | --- |
| Name | Hon. T.M. BOBOR-SAWYER | Name | Dr. Minkailu BAH |
| Date |  | Date |  |
| Signature |  | Signature |  |

Q34.	This application has been compiled by:

Enter the family name in capital letters.

| Full Name | Position | Telephone | Email |
| --- | --- | --- | --- |
| Rev. Dr. Thomas T. SAMBA | Programme Manager, Child Health/EPI Programme | 0023276662162 | ttsamba@yahoo.com |
| Dr. Nuhu MAKSHA | Immunization Specialist UNICEF | 0023276901211 | nmaksha@unicef.org |
| Dr. Pamela MITULA | EPI/Team Leader, WHO | 0023276751171 | mitulap@sl.afro.who.int |
| Mr. Amara S. KOROMA | Director of Financial Resources, Ministry of Health and Sanitation | 0023276612853 | sanimeh@yahoo.com |
| Dr. Clifford W. KAMARA | Senior Programme Coordinator SABIN Institute |  | Cliff.Kamara@Sabin.org |

National Coordinating Body – Inter-Agency Coordinating Committee (ICC) for Immunisation

Q35.	We the members of the ICC, HSCC, or equivalent committee met on [Type text] to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER : [Type text].

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature |
| --- | --- | --- |

Q36.	In case the GAVI Secretariat has queries on this submission, please contact:

Enter family name in capital letters.

| Name | Rev. Dr. Thomas T. Samba | Title | Programme Manager, Child Health/EPI Programme |
| --- | --- | --- | --- |
| Tel no | 0023276662162 |  |  |
| Fax no |  | Address | Medical Stores Compound, New England, Freetown |
| Email | ttsamba@yahoo.com |  |  |

Optional supplementary information

Q37. (Optional)	If available, countries may provide additional detail in the table below on training content, role, and framework.

| Who will be trained | Role in vaccine delivery (e.g., sensitization, mobilization, immunization, supervision, monitoring, etc.) | Training content (e.g., basics on cervical cancer, HPV, HPV vaccine, IEC messages, safe injections, AEFI monitoring, etc.) | Who will provide the training? |
| --- | --- | --- | --- |
| Health workers | Immunization, monitoring | basics on cervical cancer, HPV, HPV vaccine, IEC messages, safe injections, AEFI monitoring, | WHO,UNICEF, Ministry of Health and Sanitation |
| Supervisors | sensitization, mobilization, immunization, supervision, monitoring | basics on cervical cancer, HPV, HPV vaccine, IEC messages, safe injections, AEFI monitoring | WHO,UNICEF, Ministry of Health and Sanitation |
| Teachers | sensitization, mobilization, | IEC messages | UNICEF, Ministry of Health and Sanitation |
| School officials | sensitization, mobilization, | IEC messages | UNICEF, Ministry of Health and Sanitation |
| District leaders | sensitization, mobilization, | IEC messages | UNICEF, Ministry of Health and Sanitation |
| Other: |  |  |  |
| Other: |  |  |  |
| Other: |  |  |  |

Q38. (Optional)	If available, countries may provide additional detail in the table below on the types of information and/or materials that may be used/disseminated, to which audience, by which mechanism, and the frequency of each.

| Types of information or materials (e.g., leaflet, poster, banner, handbook, radio announcement, etc.) | Audience receiving material (girls, parents, teachers, health workers, district officials, community groups, etc.) | Method of delivery (e.g., parent meetings, radio, info session at school, house visit, etc.) | Who delivers (e.g., teachers, health workers, district official, etc.) | Frequency & Timing (e.g., daily, weekly, twice before programme starts, etc.; day of vaccination, two weeks before programme begins, etc.; ) |
| --- | --- | --- | --- | --- |
| leaflet, poster, banner, handbook, radio announcement | girls, parents, teachers, health workers, district officials, community groups, | parent meetings, radio, info session at school, house visit, etc | teachers, health workers, district official, | daily, weekly, twice before programme starts, etc.; day of vaccination, two weeks before programme begins, etc |

Q39. (Optional)	Technical partners (e.g. local WHO staff) are required to participate in planning and conducting the evaluation of HPV vaccine delivery. Please specify if such (an) expert(s) already exist on the country team (name, title, organization). Alternatively, or in addition, an international participant can be requested through technical partners if additional expertise is thought necessary.

From experience, new vaccine introduction has always been a dynamic process with a lot of inherent challenges. In the event that we identify the need for additional expertise during the course of this process, the country will request such technical assistance through the  WHO country office and/ or UNICEF.

Q40. (Optional)	In the table below, countries can provide a brief summary of the current adolescent health services or interventions and health education activities and implementing agencies in the district selected to implement the HPV Demonstration Programme.

Please add additional tables if necessary.

|  | intervention | intervention | intervention | intervention |
| --- | --- | --- | --- | --- |
| Description of intervention | Sensitization | Provide ASRH services | Immunization (TT in schools) | Deworming |
| Agency and provider delivering the intervention | MoHS UNFPA WHO UNICEF HKI PPASL Restless Development ADSL SALYAN | MoHS PPASL | MoHS | MoHS HKI |
| Target population by age, grade, and sex | School Age & young people ( 6 – 24years) Classes 1- SSS3 Male & Female | Adolescent and young people both in and out of School Age 10- 24years Male and Female | In school adolescent Age 12 -24years Female | School age and young people (6 – 24years) Male & Female |
| Number and types of facilities implementing | 184 PHUs 3 Youth centres | 184 PHUs 3 Youth centres | 184 PHUs | 184 PHUs |
| Geographic location(s) of the intervention (where in the country) | Western Urban Bo district in the South | Western Urban Bo district in the South | Western Urban Bo district in the South | Western Urban Bo district in the South |
| Timing of the intervention (when) | Quarterly | Daily | On Schedule | Biannually (STH) Annually (SCH) |
| Frequency of the intervention (how often) | Quarterly | Daily | On Schedule | Biannually (STH) Annually (SCH) |
| Coverage of the target population (recent year) |  |  |  |  |
| Coordinating agency | National School and Adolescent Health Programme | National School and Adolescent Health Programme | National School and Adolescent Health Programme | National School and Adolescent Health Programme |
| Collaborating partners | UNFPA WHO UNICEF HKI PPASL Restless Development ADSL SALYAN | UNFPA WHO UNICEF HKI PPASL Restless Development ADSL SALYAN | UNICEF | HKI |
| Implementation costs of the intervention, if known |  |  |  |  |
| Funding source, if known | UNFPA WHO UNICEF HKI | UNFPA WHO | UNICEF | HKI |
| Data source(s) for the information on each intervention |  |  |  |  |

Q41. (Optional)	Provide a brief summary of the current cervical cancer prevention and treatment services and implementing agencies in the district selected to implement the HPV Demonstration Programme. If available, countries can include information on target populations, delivery structure, and funding sources.

[Type text]

Q42. (Optional)	Describe the plan for securing Ministry of Health approval of the draft national cervical cancer prevention and control strategy and any activities for dissemination to national, sub-national, and/or local partners and stakeholders.

Prior to the development of this application,  an inception HSSG meeting was held to request for approval for the application for the demonstration. Following completion of the application, an endorsement meeting will be convened for the final application to be submitted to GAVI. When HSSG approves the final document, the Ministry of Health and Sanitation will give approval for the HPV Demonstration in the country. The Ministry of Health and Sanitation will establish a National cervical prevention and control strategy.

Q43. (Optional)	If known, please indicate the representatives of the TAG that will be involved in the assessment of the feasibility of integrating selected adolescent health interventions with delivery of HPV vaccine.

Enter the family name in capital letters.

|  | Name/Title | Agency/Organisation | Area of Representation |
| --- | --- | --- | --- |
| TAG member involved in assessment of ADH interventions |  |  |  |
| TAG member involved in assessment of ADH interventions |  |  |  |
| TAG member involved in assessment of ADH interventions |  |  |  |
| TAG member involved in assessment of ADH interventions |  |  |  |
| TAG member involved in assessment of ADH interventions |  |  |  |

Q44. (Optional)	If known, please indicate the representatives of the TAG that will be involved in the development or revision of a draft national cervical cancer prevention and control strategy.

Enter the family name in capital letters.

|  | Name/Title | Agency/Organisation | Area of Representation |
| --- | --- | --- | --- |
| TAG member involved in cervical cancer strategy |  |  |  |
| TAG member involved in cervical cancer strategy |  |  |  |
| TAG member involved in cervical cancer strategy |  |  |  |
| TAG member involved in cervical cancer strategy |  |  |  |

Q45. (Optional)	If present, please describe the distribution of de-worming medication (anti-helminths) in the district(s).

| Component | District 1-Bo | District 2 –Western Area Urban |
| --- | --- | --- |
| Organization of the de-worming programme | Deworming is done as a routine service and during supplemental immunization activities or African Vaccination Weeks | Deworming is done as a routine service and during supplemental immunization activities or African Vaccination Weeks |
| Lead agency | WHO and UNICEF | WHO and UNICEF |
| Implementing agency and partners | Ministry of Health and Sanitation | Ministry of Health and Sanitation |
| Funding source(s) | Government of Sierra Leone, WHO, UNICEF and other agencies or partners | Government of Sierra Leone, WHO, UNICEF and other agencies or partners |
| Frequency and timing of implementation, e.g. twice yearly in March and October | During supplemental activities, de-worming is done in May and November each year. | During supplemental activities, de-worming is done in May and November each year. |
| Number in target population by age group and sex | 84,460 The target population for the interventions are not disaggregated by age. (Source: Projected 2004 census data. Statistics Sierra Leone) | 133,883. The target population for the interventions are not disaggregated by age. (Source: Projected 2004 census data. Statistics Sierra Leone) |
| De-worming coverage by age group and sex | May 2011: 82,934 (98.2%) November 2011: 84,496 (100%) ( source: Administrative coverage) | May 2011: 160,982 (120.2%) November 2011: 260,908 (194.9%) ( source: Administrative coverage) |

Q46. (Optional)	If present and relevant, please describe any organized semi-annual health days (e.g., Child Health Days) that are currently implemented in the district(s).

| Component | District 1 -Bo | District 2- Western Area Urban |
| --- | --- | --- |
| Organization of the semi-annual health days | Maternal and Child Health Week or African Vaccination Day in May and November each Year | Maternal and Child Health Week or African Vaccination Day in May and November each Year |
| Lead agency | WHO and UNICEF | WHO and UNICEF |
| Implementing agency and partners | Ministry of Health and Sanitation | Ministry of Health and Sanitation |
| Funding source(s) | Government of Sierra Leone, WHO, UNICEF and other agencies or partners | Government of Sierra Leone, WHO, UNICEF and other agencies or partners |
| Frequency and timing of implementation, e.g. twice yearly in March and October | During supplemental activities, de-worming is done in May and November each year. | During supplemental activities, de-worming is done in May and November each year. |
| Services delivered | Vaccination, Vitamin A supplementation, de-worming, defaulter tracing, MUAC, etc. | Vaccination, Vitamin A supplementation, de-worming, defaulter tracing, MUAC, etc. |
| Number in target population by age group and sex | The target population for OPV vaccination in 2011 was 108,014. The target population for the interventions are not disaggregated by age. (Source: Projected 2004 census data. Statistics Sierra Leone) | The target population for OPV vaccination in 2011 was 171,369. The target population for the interventions are not disaggregated by age. (Source: Projected 2004 census data. Statistics Sierra Leone) |
| Coverage of the different services delivered by age group and sex | May 2011: 109,914 (101.8%) ( source: Administrative coverage) | May 2011:180,716 105.5(%) ( source: Administrative coverage) |

Q47. (Optional)	If present, please describe any organized health education programmes implemented at schools and/or in the community that are currently implemented in the district(s).

| Component | District 1 -Bo | District 2- Western Area Urban |
| --- | --- | --- |
| Organization of the health education programme |  |  |
| Lead agency |  |  |
| Implementing agency and partners |  |  |
| Funding source(s) |  |  |
| Frequency of services, e.g. once a month, weekly, etc. |  |  |
| Services delivered |  |  |
| Location(s) of service delivery |  |  |
| Number in target population by age group and sex | [Type text], data source [Type text] | [Type text], data source [Type text] |
| Coverage of the different services delivered by age group and sex | [Type text], data source [Type text] | [Type text], data source [Type text] |