|  |  | [V1.4]. |  |
| --- | --- | --- | --- |
| Gavi New Vaccine Support Application Form.. Submitted by.. The Government of.. Bolivia.. Date of submission: 1 May 2016.. Submission Deadline:.. i..; 1 May 2016.. ii... 1st May 2015.. 9 September 2015.. iii... Select start and end year of your comprehensive Multi-Year Plan (cMYP).. Start year.; 2016.. End year.; 2020.. Form revised in 2015.. (To be used with Guidelines of November 2015).. Note: Please ensure that the application has been received by Gavi on or before the day of the deadline... |

GAVI GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country (“Country”) confirms that all funding provided by the Gavi Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in this application. Any significant change from the approved programme(s) must be reviewed and approved in advance by Gavi. All funding decisions for this application are made at the discretion of the Gavi Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify Gavi in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. Gavi will document any change approved and this application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to Gavi all funding amounts that are not used for the programme(s) described in this application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by Gavi, within sixty (60) days after the Country receives Gavi's request for a reimbursement and be paid to the account or accounts as directed by Gavi.. SUSPENSION/ TERMINATION. Gavi may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in this application, or any Gavi-approved amendment to this application. Gavi retains the right to terminate its support to the Country for the programmes described in this application if a misuse of Gavi funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by Gavi shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with Gavi, as requested. Gavi reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how Gavi funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of Gavi funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against Gavi in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI TRANSPARENCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the Gavi Transparency and Accountability Policy (TAP) and will comply with its requirements.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage Gavi cash-based support. The Country confirms that it will take all responsibility for replenishing Gavi cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and Gavi arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either Gavi or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by Gavi. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: Gavi and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. Gavi will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application....

1. Type of support requested. Please specify for which type of Gavi support you would like to apply... Type of Support; Vaccine; Start year; End year; Preferred second presentation[1]. Routine New Vaccines; HPV quadrivalent, 1 dose/vial, LIQUID; 2017; 2017; HPV bivalent, 2 doses/vial, LIQUID.. [1] Gavi may not be in a position to accommodate all countries first product preferences, and in such cases, Gavi will contact the country to explore alternative options. A country will not be obliged to accept its second or third preference, however Gavi will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country... [2] Gavi would appreciate feedback from countries on feasibility and interest of selecting and being shipped multiple Pentavalent vaccine presentations (1 dose and 10 dose vials) so as to optimise wastage, coverage and cost. Please refer to section 6.2....

2. Table of contents.. 1. Type of support requested. 2. Table of contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body – Inter-Agency Coordinating Committee for Immunisation. 4.1.3. Signature Table for the Coordinating Committee for Immunisation. 4.2. National Immunisation Technical Advisory Group (NITAG). 4.2.1. The NITAG. 5. Immunisation Programme Data. 5.1 Background information. 5.1.1 Lessons learned. 5.1.2 Health planning and budgeting. 5.1.3 Gender and equity. 5.1.4 Data quality. 5.1.6 HPV specific facts. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.2.1 HPV specific targets. 5.3. Targets for preventive campaign(s). 5.4. Targets for One time mini-catchup campaign(s). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.1.1 HPV burden specific information. 6.1.2 Delivery strategy for HPV vaccine. 6.2 Requested vaccine (HPV quadrivalent, 1 dose/vial, LIQUID). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by Gavi (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campaigns. 8. Procurement and Management. 8.1 Procurement and Management of New and Under-Used Vaccines Routine. 8.2 Procurement and Management for NVS Preventive Campaign(s). 8.3 Product licensure. 8.4. Vaccine Management (EVSM/EVM/VMA). 8.5 Waste management. 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. List of documents attached to this proposal. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 HPV quadrivalent, 1 dose/vial, LIQUID. Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B: Rounded up portion of supply that is procured by Gavi and estimate of relative costs in US$. Table Annex 1.1 C: Summary table for HPV quadrivalent, 1 dose/vial, LIQUID. Table Annex 1.1 D: Estimated quantity of HPV quadrivalent, 1 dose/vial, LIQUID, injection safety materials and corresponding country budget. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 2.1 HPV bivalent, 2 dose/vial, LIQUID. Table Annex 2.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 2.1 B: Rounded up portion of supply that is procured by Gavi and estimate of relative costs in US$. Table Annex 2.1 C: Summary table for HPV bivalent, 2 dose/vial, LIQUID. Table Annex 2.1 D: Estimated quantity of HPV bivalent, 2 dose/vial, LIQUID, injection safety materials and corresponding country budget. Annex 3 - NVS Preventive campaign(s). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C Accelerated transition phase - Minimum country co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors. Table Annex 4E Vaccine maximum packed volumes. 12. Banking form...

3. Executive Summary.. Please provide a summary of your country's proposal, including the following information:. ; For each specific request, NVS routine support or NVS campaign :. ; The duration of support. ; The total amount of funds requested. ; Details of the vaccine(s), if applicable, including the reason for the choice of presentation. ; Month and year projected for vaccine introduction (including campaigns and routine immunisation). ; Relevant baseline data, including:. ; DTP3 and measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ; Target population of yellow fever and meningitis A risk evaluations. ; Birth cohort, targets and immunisation coverage by vaccines. ; Country preparedness. ; Summary of planned activities to prepare for vaccine launch, including EVM assessments, progress on EVM improvement plans, communication plans, etc.. ; Summary of EVM assessment and progress on EVM improvement plan.. ; The nature of stakeholders' participation in developing this proposal. ; Inter-Agency Coordinating Committee (ICC). ; Partners, including CSO involvement.. The Plurinational State of Bolivia has a population of 10,985,059 inhabitants (Census, 2012), and a population density of 9.13 inhabitants per square kilometre. The population is a young one, with 62.86% aged between 15 and 64. The country's Expanded Programme on Immunisation has been operating since 1979 to the present with a basic schedule consisting of vaccines such as BCG, OPV and DPT. In response to priority health problems, new vaccines were added subsequently, such as pentavalent, MMR, DT, YF and influenza, and with Gavi support, pneumococcal and rotavirus. Due to the high incidence of cervical cancer – one of the highest in the world, as the leading cause of death in women of childbearing age on the national scale – and given the availability of effective vaccines, the Bolivian Ministry of Health has decided to include HPV in the national immunisation schedule for 9-year-old girls. Quadrivalent HPV in single-dose presentation has been chosen because i) it covers a greater number of genotypes, ii) single doses facilitate immunisation operations, and iii) it has a lower wastage factor (5%) Following are the details of the target population, its needs, and HPV vaccine cost for 2017: Total population of 9-year-old girls 119,280 No. of doses needed for 100% coverage with two-dose schedules 238,560 No. of doses plus wastage factor of 5% in single doses 250,488 Unit cost vaccine dose US$ 2.25 Total cost vaccine dose US$ 563,598 Gavi financing for one cohort US$ 2.25 / dose year of introduction: US$ 281,799. Government of Bolivia co-financing US$ 2.25 / dose year of introduction: US$ 281,799 Moreover, to recover the cohorts of girls not immunised over the past four years, we seek to expand immunisation to girls aged 10 to 12 to accelerate impact on the disease, for which reason the Plurinational State of Bolivia's Ministry of Health requests access to the Gavi preferential price of US$ 4.50/dose. To ensure 100% coverage with second HPV doses in the target population, immunisation with this vaccine will follow EPI routine immunisation strategies, which include: immunisation in the facility on demand, immunisation for communities without health services or remote communities by mobile brigades and immunisation by referral to the health services. For DT immunisation to schoolchildren, the health staff of each facility coordinate with the schools in their working area and program the timelines for immunisation. HPV immunisation will be added to this effort through immunisation campaigns for schoolchildren twice a year. By way of synthesis, immunisation for schoolchildren (77% of the target group) is projected for March (first dose) and for September (second dose), and in addition will be administered on demand in health services and to scattered communities through brigades to reach those girls who are not enrolled in the educational system. Moreover, the girls will be referred to schools or health facilities. The strategy of communication and social mobilisation will contribute to the enrolment of 100% of the girls, since its central strategy entails the community-based participation of the social structure: indigenous authorities, agrarian unions and school councils involving teachers, students and heads of families. According to the national evaluation and the WHO/UNICEF joint appraisal form 2015, Bolivia in 2015 achieved the highest coverage rates for the five-year period: BCG: 99%, OPV: 88.3%, Pentavalent: 88.6%, PCV 13: 86.1%, Rotavirus: 88.7%. The most important achievement was simultaneity in vaccine administration to children under 1 year of age. In one-year-olds, coverage with MMR and YF was 94.9 and 88.1, respectively. The abandonment rate for OPV and pentavalent was 9% and 20% of the municipalities exceeded 95% with pentavalent. 34% of the total population live in these municipalities (83,604 children). Problems with the population denominators persist, so the EPI conducts regular rapid coverage monitoring that reveals coverage rates superior to 90%. Effective Vaccine Management (EVM) evaluation by an external PAHO/WHO technical team is scheduled for November. The Programme will prepare its Continuous Improvement Plan based on its findings and recommendations. This proposal was prepared on the basis of National Immunisations Committee (NIC) criteria issued during its 2014, 2015 and 2016 sessions, with the participation of other institutions such as the cancer foundation and the society of cancerology, among others; in addition, to establish technical coordination to guarantee an integrated approach to cervical cancer prevention, the ad hoc committee for HPV introduction into the EPI was formed, which includes representatives from the school health and the adolescent health programmes, the national cancer register, representatives from the Ministries of Education and the Economy and Finance, and the chairpersons of the congress and senate health commissions, FAM, ACOBOL, and the maternity and safe childbirth board. The ICC likewise analysed feasibility and its potential support. The ICC was strengthened by the participation of the Chairman of GRUS Salud, which groups together all bilateral and multilateral health cooperation, and PROCOSI, which coordinates the leading health NGOs in Bolivia...

4. Signatures.. 4.1. Signatures of the Government and National Coordinating Bodies.. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation.. The Government of Bolivia would like to expand the existing partnership with Gavi for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for Gavi support for:.. HPV quadrivalent, 1 dose/vial, LIQUID for routine introduction... The Government of Bolivia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that Gavi and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application... Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENTS NUMBER: 2 and 3 in section 10. Attachments.. Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Dr Ariana Campero Nava signed on 28 April 2016; Name; Mr Luis Arce Catacora. Date; Date. Signature; Signature.. Proof of involvement of the Ministry of Education will also be required for HPV Routine Support. The Ministry of Education will either have to be involved in the ICC process (preferred option) and/or the Minister of Education (or delegated authority) must provide its signature. The signature is attached as DOCUMENT NUMBER: {0} in section 10. Attachments. Minister of Education (or delegated authority). Name; Mr Roberto Aguilar Gómez signed on 28 April 2016. Date. Signature.... This report has been compiled by (these persons may be contacted in case the Gavi Secretariat has queries on this document):.. Full Name; Position; Telephone; Email. Raul Montesano; PAHO/WHO Bolivia EPI Consultant; (591) 75267617; montesanora@bol.ops-oms.org. Rosario Quiroga; EPI; (591) 71559716; rosarioquirogamorales@gmail.com. Susana Solano; National EPI Manager; (591) 2-2442473, (591) 65345738; susolromero@gmail.com. Werner Valdes; EPI; (591) 70654006; wernervaldes@yahoo.es.. 4.1.2. National Coordinating Body – Inter-Agency Coordinating Committee for Immunisation.. Agencies and partners (including development partners and NGOs) supporting immunisation services are coordinated and organised through an inter-agency coordinating mechanism (ICC, Health Sector Coordinating Committee (HSCC), or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the Gavi NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below... Profile of the ICC, HSCC or equivalent committee.. Name of the committee; EPI Inter-agency Coordination Committee, EPI ICC. Year of constitution of the current committee; 1987.. Organisational structure (e.g., sub-committee, stand-alone); ICC Chairperson, Minister of Health, technical secretariat head office EPI, PAHO/WHO technical assistance and. Frequency of meetings; Quarterly.. The Terms of Reference or Standard Operating Principles of the ICC, including information on its members, quorum, procedure for resolving disputes and meeting calendars are attached as DOCUMENT NUMBER: 4... Major functions and responsibilities of the ICC/HSCC:.. Approves and co-finances EPI five-year and annual plans Supports new initiatives and searches for strategic foreign and domestic EPI allies.. Please describe how partners have provided support in preparation of the proposal:.. They have taken part in proposal review and approval meetings and also are members of the ad hoc committee for HPV introduction Advocacy and influence on sub-national authorities: departmental and municipal governments, support fields of individual international cooperation agencies Backing the Ministry of Health in the implementation of this new cancer prevention policy.. 4.1.3. Signature Table for the Coordinating Committee for Immunisation.. We the members of the ICC, HSCC, or equivalent committee[1] met on 26/04/2016 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting approving this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 7 (please use the list of signatures in the section below)... Please refer to Annex C of the ‘Gavi HSS and NVS General Guidelines’ for more information on ICCs... Function; Title / Organisation; Name; Please sign below to indicate the attendance at the meeting where the proposal was endorsed; Please sign below to indicate the endorsement of the minutes where the proposal was discussed. Chair; Ministry of Health; Dr Ariana Campero Nava. Secretary; EPI Head Office; Dr Susana Solano. Members; PAHO/WHO; Fernando Leanes. UNICEF; Sun AH KIM SUH. UNFPA; Ana Angarita Noguera. IDB; Luis Buscarons. GRUS Salud; Luis Buscarons. CIES; Jose luis Alfaro. PROCOSI; José Ignacio Carreño.. On submitting the proposal, we confirm that quorum was reached. Yes.. The minutes of the last three ICC meetings are attached as DOCUMENT NUMBER: 6... 4.2. National Immunisation Technical Advisory Group (NITAG).. Has a NITAG been established in the country? Not selected.. In the absence of a NITAG, countries should clarify the role and functioning of the advisory group and describe plans to establish a NITAG. This document is attached as Document no 8....

5. Immunisation Programme Data.. 5.1 Background information.. Please complete the table below, using data from available sources. Please identify the source of the data and the date. Where possible use the most recent data and attach the source document... ▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 9. Please attach the cMYP costing tool as DOCUMENT NUMBER 10.. ▪; Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 0.. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.. ▪; Please refer to the attached risk assessments in the case of yellow fever and meningitis A mass preventive campaigns... Please use the most recent data available and specify the source and date... Figure; Year; Source. Total population; 10,985,059; 2016; INE [National Statistics Institute]. Birth cohort; 251,838; 2016; INE. Infant Mortality Rate; 50; 2012; ENDSA 2008 [DHS] Ministry of Health / INE. Surviving infants[1]; 243,613; 2016; INE/SNIS [National Health Information System]. GNI per capita (US$); 3,116; 2012; INE. Total health expenditure; 1,857,503,689; 2013; Study of national accounts. Total government health expenditure; 791,932,463; 2013; Study of national accounts.. [3] Surviving infants = Infants surviving the first 12 months of life... 5.1.1 Lessons learned.. New vaccine support for routine immunisation.. If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points or actions taken to address them. Please refer to previous Post Introduction Evaluations (PIE), if applicable. If they are included in the Introduction Plan, please cite the section only. If this information is already included in NVIP/POA, please reference the document and in which section/page this information can be found.. Lessons Learned; Action Points. In 2000, Bolivia relaunched the programme as a second-generation EPI with the introduction of the pentavalent and MMR vaccines to replace DPT, simple measles and YF in one-year-old children. This change was a result of the analysis and recommendations of the NIC in the course of its first sessions and as the beginning of a policy open to new vaccine introduction.; • Formation of the NIC, strengthening of the ICC • Promulgation of the Financial Law in 1999 for vaccine and syringe purchase with national funds. Acknowledged subsequently in the Vaccine Act of 2005, enabling funding for the EPI up to the present • IEC strategy based on a CAP study • Cold chain inventory update. Introduction of rotavirus, influenza and subsequently the pneumococcal vaccine.; • IEC strategies for different audiences • Keeping the cold chain inventory up to date • Innovative mobilisation strategies • Health staff training • The NIC undertook incidence study through its subsidiaries. Introduction of IPV to substitute first OPV dose; • Health staff training was intensified, since ENCOVA (the Immunisation Coverage Survey) found that health personnel were reluctant to administer simultaneous injectable vaccines. • Audio-visual media were prioritised, such as a video for staff in which experts explained the harmlessness of injectable vaccines and some immunisation techniques to diminish pain.. Pilot test of HPV immunisation to fifth-graders; • Intervention model with 3 different operating strategies: Immunisation at school, immunisation in health facilities set up for immunisation on demand and transport of mobile units • Coordination with departmental and local education authorities • Technical guidelines on information, cold chain • Implementation of informed consent sheet • Coverage rates of over 90% were achieved • IEC strategy for teachers, students and heads of families.. 5.1.2 Health planning and budgeting.. Please provide information on the planning and budgeting cycle in your country. The planning and budgeting cycle observes a fiscal year from January to December.. Please indicate the name and date of the relevant planning document for health. Economic and Social Development Plan (ESDP) 2016-2020 and Health Sector Plan (HSP) 2010-2020. It is to be noted that this Health Sector Plan is under revision to adapt it to ESDP 2016-2020, which includes guidelines from the Patriotic Agenda for 2025 and formulates pillar 3 on the universal character of health services.. Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.). As a state planning rule, sector and programme plans should harmonise with a line of action for the same term as the ESDP and the HSP. The EPI aligns with the reduction of infant and maternal mortality in the Health Sector Plan. EPI five-year plans have been prepared since 1987, when the ICC was formed. The five-year plan also reflects technical and strategic elements from the TAG recommendations for immunisation, the NIC and other international guidelines. The EPI Five-Year Plan 2016-2020 has the aim of reducing the risks of death and illness from vaccine-preventable diseases through the universal administration of vaccines and timely, efficient, high-quality epidemiological surveillance conducted by health personnel trained for such purposes with a view to the medium term. . Its most relevant specific objectives are: • To ensure the availability of all the vaccines on the basic schedule to guarantee timely and complete routine immunisation with all the vaccines throughout the Bolivian territory. • To ensure the proper conservation, storage and transport of vaccines from the manufacturing laboratory to the health facilities, up to the final beneficiaries, which is to say community members. • To ensure the effectiveness of VPD epidemiological surveillance to detect cases in a timely manner and as an indispensable decision-making tool. . To introduce vaccines into the national schedule in keeping with the epidemiological situation, the needs of the population and the availability of new vaccines as a standing policy. • To ensure safe immunisation through the use of quality vaccines, the performance monitoring of human resources throughout the entire immunisation process, and timely response to adverse events following immunisation (AEFI) up to final waste disposal. • To ensure a system of supervision, monitoring and evaluation of immunisation and epidemiological surveillance processes on all levels. • To develop and apply community work and negotiation tools for EPI management, above all on the local level. Included as priorities in the Five-Year Plan are the introduction of the VPH vaccine and health system and EPI strengthening activities.. Please indicate the national planning budgeting cycle for health. The national planning budgeting cycle is conducted in the framework of the plural Bolivian economic model oriented towards improving the quality of life and well-being of all Bolivians and the guidelines for budget formulation and planning, of mandatory application for public sector entities. On the national scale, these include: the organs of the Plurinational State and bodies exercising functions of control and defence, of society, the state, autonomous departmental, regional, municipal and original indigenous countryside governments. These institutions are obliged to prepare strategic or five-year plans and annual operating plans (AOPs) with budgets linked to their medium and short-term development objectives and aims, as appropriate, to send to the Ministry of the Economy and Finance for analysis and consolidation as General State Budget, which is afterwards approved by the Plurinational Legislative Assembly. An AOP basically contains the following points: a) situation analysis, b) definition of management objectives for every financial year, c) definition of management indicators, d) determination of work and investment operations, and e) determination of the resources required for the execution of the operations projected in the AOP. The planning process on the three levels of state starts in August – national, departmental and municipal – and culminates in October, on the local level, with broad community participation, which are later sanctioned on the legislative level.. Please indicate the national planning cycle for immunisation. The planning budgeting cycle for the EPI is part of the planning budgeting cycle of the health sector and includes items for the purchase of services and goods, vaccines, syringes, safety boxes, travel expenses, allowances, tickets, materials and supplies, and personal and non-personal services... 5.1.3 Gender and equity.. Please describe any barriers to access, utilisation and delivery of immunisation services at district level (or equivalent) that are related to geographic, socio-economic and/or gender equity. Please describe actions taken to mitigate these barriers and highlight where these issues are addressed in the vaccine introduction plan(s).. The Ministry of Health, in its policy and planning documents, makes the strategic objective of universal access to integrated health services explicit. In the case of the EPI, the focus on equity takes the form of i) 100% as the planned target population per vaccine type; i.e., 100% of males and females; ii) the application of several complementary strategies in order to reach 100% of the population, such as immunisation in health services, during campaigns and by mobile brigades sent to remote and scattered communities without health services. This focus guarantees immunisation without discrimination by gender, race or geographic location. It should be underscored that, in order to reach all Bolivians, the country is implementing the MiSalud programme with approximately 6,000 doctors going from house to house and promoting the timely immunisation of boys and girls, in addition to other health interventions. To date, there are approximately 6,000 primary healthcare doctors distributed in areas with priority classifications: indigenous populations, rural areas and peripheral urban areas.. Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s).. The EPI has trace indicators making it possible to assess fulfilment of this focus on equity. The ENCOVA survey done in 2013 shows that there are no statistically significant differences in immunisation coverage rates by gender or by race. As regards area of residence, in fact, rural areas have higher coverage rates than urban areas, and it is in these places where areas of poverty still concentrate. This finding enabled the EPI to develop specific action plans for those cities with lower coverage. On another hand, analysis by poverty quintiles according to ENDSA 2008 revealed that the programme reaches the entire target population in terms of equal opportunities, there being no inverse relationship between coverage level, degree of mother's education or quintile of wealth. The messages in the various communication and mobilisation strategies address the family, strengthening the responsibility shared between mothers and fathers and social organisations of men as well as women.. Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems.. Immunisation data entry by gender was introduced into the information system (SNIS) on the national level starting in 2015. Enrolment and monitoring booklets for girls and boys have been in implementation for over a decade. The electronic nominal immunisation record is projected for implementation over the short term. This will maintain data analysis breakdowns.. Is the country currently in a situation of fragility (e.g. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought or others)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities.. In Bolivia, there are periods of the year when draught occurs in the highlands and in El Chaco, and flooding in the lowlands. To respond to this type of emergencies in a timely manner, there are inter-institutional emergency committees headed by the Ministry of Defence with the active participation of the Ministry of Health to implement action plans that include vaccine administration in the short-schedule mode; i.e., the interval between doses is reduced to one month. This also takes advantage of family concentrations in shelters to complete immunisation schedules. Undoubtedly, due to special geographical factors, there are specific situations that make it impossible to reach the entire population – for example, in the case of communities only accessible by water. Schedules are completed once the emergency is over. On another hand, civil insecurity in some cities and departmental capitals hampers the activity of mobile brigades or the implementation of timetables convenient to the characteristics of the population. The application of specific strategies to handle these bottlenecks is underway.. If available, please provide additional information and documents on subnational coverage data, e.g. comparing urban/rural districts or districts with highest/lowest coverage, etc.. In 2015, Bolivia achieved significant immunisation coverage rates in infants under one year of age: 99% with BCG, 88.6% with pentavalent, 88.3% with polio and 88.7% with rotavirus, 86.1% with pneumococcal; in one-year-old children, 94.9% with MMR and 88.1% with YF. In pentavalent coverage, the departments of Tarija, Beni, Cochabamba, Chuquisaca, Oruro and La Paz show coverage above the national average, while Santa Cruz, Pando and Potosí have coverage levels below 87%. Only Tarija and Chuquisaca have a drop-out rate lower than 5%; the others duplicate the maximum rate allowed. It is along this line that an opportunity for improvement exists in 7 of the 9 departments. As regards complete basic schedules, ENCOVA 2013 shows that, on the national level, the rural area is higher (94%) than the urban area (87%) – the rural areas of the departments of Oruro, La Paz and Chuquisaca show the highest coverage rates in Bolivia (95%, 96% and 97%, respectively). On the other extreme, the lowest coverage rates are in the cities of El Alto, La Paz and Trinidad (82.8%, 83.9% and 84.4%, respectively)... 5.1.4 Data quality.. Please attach a data quality assessment (DQA), report if one has been completed within the previous 48 months (DOCUMENT NUMBER: 27). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER: 11, DOCUMENT NUMBER: 28).. If DQA not available, please briefly describe plans to establish mechanisms for data quality assessment.. The last international data quality assessment was conducted by PAHO/WHO in 2010, finding data quality optimal. Data precision in correlation with the booklets and SNIS records is 100%, the precision between booklets and the web platform was 100%, and the data had a quality index of 94%. Weaknesses in data quality control were also identified on the management and local levels and in information feedback. The next DQA is scheduled for November. The pilot test for a method of EPI data quality assessment was conducted in August 2012. The sample included 4 municipalities, La Paz, Santa Cruz, Warnes and San José de Chiquitos. Although the purpose was to validate the tools, the results are useful in EPI data quality management. The most outstanding results were: the data quality of the primary records against the monthly report ranged from 97% to 103%. The proportion between doses recorded as against the district data ranged from 85% to 96%, and from the district to the national report it was 100%. Report availability ranged from 96% to 100%. Consistency between third pentavalent doses and OPV on the national scale is 100%; for the district level, 75%; and for the network it is 100%. Although the results are good, problems are clearly observed on the network level, prioritising the need for human resource training in network data management. See Annex 27.. Please indicate what routine mechanisms to independently assess the quality of administrative data are in place, and if so what these mechanisms are and how they enable the country to track changes in data quality over time.. The EPI has a supervision and monitoring system in place by level, with a methodology and tools that are pertinent to human resources supervision, rapid coverage monitoring in the population and data quality control. Nevertheless, staff rotation, frequent changes on the local management levels and insufficient financial resources provoke interruptions in the supervision plans. The templates used for data quality monitoring make it possible to measure data concordance. With respect to record booklets and infant health cards as against the consolidated monthly report from the facility itself, the network, the SEDES and the national level, results are greater than 90%. Nevertheless there are some difficulties to be found in their manual processing. Once these have been identified in supervision, they will be subject to improvement plans per health facility, including in-situ training with data from the facility itself. The ENCOVA has shown that real coverage rates are above the administrative coverage rates by almost 10 percentage points in terms of all vaccines.. Please detail what household surveys have been conducted in recent years to independently assess immunisation coverage and equity, and describe any survey plans for the coming five year period.. The last demography and health survey, ENDSA, was conducted in 2008. It analysed immunisation coverage rates by age and vaccine type, zone of residence, mother's level of schooling and wealth quintile. ENCOVA is a probabilistic, population-based survey, with representation at departmental level and for the municipality of El Alto; the survey was designed by a team of immunisation experts and the fieldwork was carried out by an independent team with extensive experience in population-based field studies. ENCOVA 2013 collated written information from children’s immunisation booklets (86%) and health facilities records (5%), to ensure that the information obtained was of high quality. According to ENCOVA, only 6 out of 3,600 children surveyed had not received any immunisation, and real coverage was between 10% and 15% higher than was given in the administrative data for every biological. Periodic conduct of such immunisation coverage surveys has been projected, the next for 2017....

5.1.5 HPV specific facts.. Please demonstrate country’s ability to deliver a complete multi-dose series of vaccines to at least 50% of a one-year cohort selected from the population of 9-13 year old girls the target vaccination cohort in at least one typical district using a similar strategy to the one proposed for HPV vaccine delivery. For each district, fill-in:.. District Information. Name of the district; El Alto municipality. Size of population of the district; 848,452. Describe how the district is divided into rural and urban areas:; El Alto is a relatively young municipality. Every year, it receives internal migrants, largely Aymara, from the rural area of La Paz, Oruro and Potosí, who arrive with community customs and varying perceptions of the health services. 74% of the children are enrolled in the school system and 97% of these in primary school. There are 258 educational centres. The municipality consists of 14 municipal districts. One of the districts has only 784 inhabitants and represents the rural area. El Alto has 3 health networks, 76 health centres and 7 secondary care hospitals. 96.6% of the girls on schedule were reached in this particular municipality... Please specify what was the multi-dose vaccine used (HPV/TT/others)? What was the vaccination schedule?. During the demonstration phase, conducted in 2009-2011, the quadrivalent HPV vaccine was used per the three-dose schedule, with an interval of 0-2-6 months.. Describe the vaccination strategy used (school based, health centre based, mixed)? How was it carried out, who carried it out, who was the lead department/agency? What age/sex was the multi-dose vaccine delivered to? If it was school based, how many schools were targeted? Was it age based or grade based?. The process was conducted in 33 schools on fifth-grade girls from the primary level (the students were basically aged 9 to 13, although 2% were 14 years old). The schools were selected in CIES intervention areas. The demonstration process was under the management of a non-government organisation, CIES, which coordinated with the Ministry of Health, obtaining the authorisation and support of the authorities, with ministry resolutions by way of legal framework. Implementation was conducted in three phases: the first in El Alto, rural Chuquisaca and Oruro; the second expanded to urban areas such as Potosí, Sucre and Trinidad; and lastly Tarija was included in a third phase. This means that the test took place in 8 of the 9 departments, making it possible to avail of perceptions from the entire country, apart from the main lessons learned during implementation. The management model defined four stages i) Planning and coordination ii) Awareness-raising, training and information iii) Immunisation, and iv) monitoring. In Stage 1, coordination was established with the Ministry of Health, the Departmental Health Services (SEDES) and the service networks. The age 9-to-13 target group was defined, along with the 3-dose application, immunisation strategy, the preparation of documents with technical guidelines, working plan and calendar, cold chain, itinerary of vaccine distribution and immunisation calendar. In Stage 2, the strategy of direct or interpersonal communication was developed to raise awareness among families, teachers and students, headmasters and health staff regarding the problem of cervical cancer, technical aspects of immunisation, techniques, AEFIs among the CIES health staff, and public networks, with the aid of flip charts, basic guides on integrated cancer care and frequently-asked questions from the population. In Stage 3, immunisation was conducted in schools under the doctors and nurses of the public health networks and CIES health staff. Immunisation took the form of a campaign (everyone on the same day). Doses were administered per protocol, the informed consent form signed by the parents was introduced and logged on pre-established templates, and the immunisation card was turned over. In addition, the health networks were supplied with vaccines for immunisation on the demand of those not attending classes. CIES provided vacuum flasks for vaccine conservation where necessary. In Stage 4, monitoring was done by schools on the basis of the template records.. What was the number of targeted population? What was the number in target population who started the multi-dose series? What was the number in the target population who received all doses?. 3,900 girls were programmed during the first phase and coverage with third doses was 95.9% 30,400 girls were programmed during the second phase and coverage with third doses was 98% And 50,900 were programmed during the third phase and only first doses of HPV were administered. Other reports from CIES itself mention that 3,789 girls received 3 doses in 2009; 27,597 girls in 2010 and 44,610 girls in 2011. The important fact about these data is the high capacity for monitoring and schedule follow-up for schoolchildren, since they exceed 95% in coverage with three doses (schedule followed by CIES for those years).. Please provide the source of data for estimation of the target population:. During the demonstration phase, these were the school records by grade, which firstly served to determine the number of girls and afterwards served for monitoring up to the completion of three-dose schedules. During this phase of implementing routine HPV immunisation, we will use school records for the girls enrolled on the local level and the community census for those not going to school.. If applicable, please detail what additional people beside the target population also received the vaccine:. Girls aged 14 in the 5th grade who ask for immunisation... Table 5.1.5: (Please refer to WHO/UNICEF JRF).. Girl age; HPV 1st dose; HPV 2st dose; HPV 3st dose. 9 years old; 3,540; 3,540; 3,540. 10 years old; 3,844; 3,844; 3,844. 11 years old; 6,776; 6,776; 6,776. 12 years old; 8,026; 8,026; 8,026. 13 years old; 7,904; 7,206; 7,206. 14 years old; 608; 608; 608. + 15 years old. Unknown.. Was there an evaluation of the ‘project’? If so, who performed it? Please provide a short summary of the evaluation methodology and/or provide the evaluation report if available (Document No: 16). Please ensure this summary (and/or the attached report) includes a costing analysis of the proposed delivery strategy or strategies. Refer to section 10. Attachments 3.. Evaluation took place by level: in each municipal terminus on the local level, on the departmental health services level and on the national level. The methodology focused on the results using the "3rd dose %" indicator based on the programmed population – fifth-graders – and on systematising the main lessons learned. Along the lines of coordination and planning, on the local level, it is of vital importance to schedule the 3 doses based on the consensus of all the players. The informed consent sheet generated mistrust – why so for this vaccine and not for the rest. In the middle of the process, this was interrupted. For this reason, implementing it now is ruled out, but on another hand, informative events for parents, teachers and students are to be implemented from the start. As regards awareness-raising, training and information, the material produced and used in support of the process was well-received by the primary and secondary audiences. Coordination with the social structure should be active from the outset to prevent situations of crisis. All of these lead to the conclusion that the planning process takes a long time, so that six months of planning and coordination should be provided for. With regard to immunisation and monitoring, it was found important to immunise the girls after breakfast in school. However, it cannot be confirmed that the two fainting spells reported as negligible AEFIs were due to the vaccine......

5.2. Baseline and Annual Targets (NVS Routine Support).. Please refer to cMYP pages to assist in filling-in this section... Number Base Year; Baseline and Targets. 2015; 2017. Total births; 251,838; 256,950. Total infants' deaths; 8,225; 9,805. Total surviving infants; 243,613; 247,145. Total pregnant women; 267,178; 272,592. Target population vaccinated with OPV3[1]; 215,110; 234,703. OPV3 coverage[2]; 88 %; 95 %. Target population vaccinated with DTP1[1]; 237,357; 234,703. Target population vaccinated with DTP3[1]; 215,876; 234,703. DTP3 coverage[2]; 89 %; 95 %. Wastage [3] rate in base-year and planned thereafter (%) for DTP; 10; 5. Wastage [3] factor in base year and planned thereafter for DTP; 1.11; 1.05. Number of girls in the target cohort; 0; 119280. Target population vaccinated with 1st dose of HPV; 0; 119,280. Target population vaccinated with last dose of HPV; 0; 119,280. HPV quadrivalent coverage 1st dose; 0 %; 100 %. HPV quadrivalent coverage last dose; 0 %; 100 %. First presentation HPV quadrivalent, 1 dose/vial, LIQUID. Wastage [3] rate in base-year and planned thereafter (%); 0; 5. Wastage [3] factor in base-year and planned thereafter (%); 1.00; 1.05. Maximum wastage rate for HPV quadrivalent, 1 dose/vial, LIQUID; 5 %; 5 %. Second presentation:. Wastage [3] rate in base-year and planned thereafter (%); 0; 10. Wastage [3] factor in base-year and planned thereafter (%); 1.00; 1.11. Maximum wastage rate for; 10 %; 10 %. Target population vaccinated with 1st dose of Measles; 229,537; 233,075. Measles coverage[2]; 94 %; 94 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 9 %; 0 %.. [1] Indicate total number of children vaccinated with either DTP alone or combined.. [2] Number of infants vaccinated out of total surviving infants.. [3] The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100 Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.... 5.2.1 HPV specific targets. Single year cohort of girls to be vaccinated with HPV should be within the WHO-recommended target population of 9-13 year old girls.. Please specify the source of data that was used to estimate the number of girls in target and reported in the above table under “Target population vaccinated with HPV“. 119,280 girls are to be immunised in 2017. We expect to reach 100% with two doses during the schoolyear. Data source is the INE. The 9-year-old cohort consists of 119,280 girls....

5.3. Targets for preventive campaign(s).. Support for the preventive campaign will not be given this year....

5.4. Targets for One time mini-catchup campaign(s). No One time mini-catchup campaign this year...

6. New and Under-Used Vaccines (NVS Routine).. 6.1. Assessment of burden of relevant diseases (if available). If already included in detail the Introduction Plan or Plan of Action, please cite the sections only... Disease; Title of the assessment; Date; Results. Cervical cancer; Progress in Cervical Cancer Prevention, Cervical Cancer Action Report, Source: Gobolcan:; 2012; The standardised incidence of cervical cancer by age in 2012 was 47.7 for every 100,000 women and the mortality rate was 21.0.... 6.1.1 HPV burden specific information. Has the country undertaken an assessment of the burden of cervical cancer? If so, describe the burden, and when and how the assessment was done. If not, countries may report on Globocan data (available on the WHO HPV information Centre website at http://www.who.int/hpvcentre/en).. According to the latest data from GLOBOCAN 2012, in Bolivia there were 2,029 new cases of women diagnosed with cervical cancer and 845 died of this cause. The incidence of cervical cancer standardised by age in 2012 was 47.7 for every 100,000 women and the mortality rate was 21.0 for every 100,000 women – the highest in the region of the Americas, with a considerable increase since 2008, when Bolivia had the sixth-highest rate of incidence and mortality in the Americas, at 36.4 and 16.6 respectively for every 100,000 women (GLOBOCAN 2008). Cervical cancer is the most frequent cancer among the female population of Bolivia. It is a significant public health problem in the country; according to the latest estimates − approximately four to five women die every day in Bolivia for this reason, causing the breakdown of families and communities, and every day, eight new cases of cervical cancer are diagnosed in Bolivian women. The incidence of this disease has become increasingly more frequent in young adult women. The departments of Potosí and Oruro are the most affected, with incidence rates of 93.5 and 60.9 for every 100,000 women (data from 2004) In Bolivia, there is no published work about virus prevalence with normal cytological testing in the general population, but there are references in isolated studies that report subtype 16 as the most prevalent, combined with subtype 18. Other authors point to subtype 16 combined with subtypes 31, 51 and 68.. Describe the existing cervical cancer prevention and control activities.. Activities for the timely detection of cervical cancer began in the institutional sphere in 1984 (through NGOs, in 1970) and the component of early screening began as a programme in 1989. Since then, there have been standardising and educational documents on procedure. In 2008, the Ministry of Health defined Strategic Plan 2009-2015 with a view to reducing the disease and mortality rate due to cervical cancer through strategic interventions of health promotion, disease prevention, diagnosis, treatment and monitoring for cervical cancer in the health services network. The strategic activities being implemented are: - Information, education, training and awareness-raising: health staff recruitment supported by printed matter. - Development of human resources: inclusion of the subject matter in university curricula, colposcopy training. - Equipment and strengthening of health facilities: with infrastructure, equipment and supplies for Pap tests and VIA, patient body fluids and cytology data, biopsies, etc. - Information and communications to users, to the system through the SNIS, and from the health services in the active search for patients. - Supervision and monitoring: individual and group surveillance activities. - Research: projects on characterising genotypes. - Social participation and control to increase coverage in preventive primary services. However, although progress has been made, the results are not satisfactory. To date, the evaluation of this plan and the formulation of the new Strategic Plan for 2016-2020 are still in course. The introduction of the vaccine will strengthen the integrated approach to cervical cancer prevention.. Has the country developed a roadmap or strategy for establishing or strengthening a national comprehensive approach to cervical cancer prevention and control? No. If Yes, please attach and refer to section 10. Attachments (Document No 15). If No, are there plans for the country to develop such a roadmap or strategy in the future? Please describe- when, who will be leading the development of the plan, and which agencies will be involved.. Bolivia has a National Programme for the Prevention, Control and Monitoring of Cervical Cancer. It relies on Strategic Plan 2009-2015, the updating of which is still in progress. This is under the Health Network and Quality Unit. On another front, in 2014, the Ministry of Health began the national cancer register, with its base in the epidemiology unit. In addition, the school and adolescent health programmes implement activities in education for health addressed to these population groups. The National Health Information System records cases of possible cancer, and the National Institute of Health Laboratories (INLASA) keeps the pap test records. Based on this diagnosis and the confirmation of cervical cancer as a priority public health problem, the policy decision was made to organise an integrated national programme on the prevention and control of cervical cancer, including the introduction of HPV into the national immunisation schedule. As a first step, the first inter-programme coordination meeting was held among all those involved, identifying common lines of action for cancer prevention and control. The lines of action for the cervical cancer programme are oriented towards: information, education, training and awareness-raising, human resource development, equipment – strengthening health facilities – information and communication, monitoring and supervision, research and social control and participation. In the school health programme, lines of action are envisioned in terms of influence on public policy and national, departmental and municipal budgets, management and implementation of quality standards, management of information and know-how, health sector human resource development, strengthening of the citizenry in defending and demanding the right of infants and schoolchildren to health, and the implementation of a system for planning, monitoring and evaluation (the SIPME). In the adolescent health programme, the priority lines of action are: generation and analysis of strategic and timely information in the health situation of adolescents and youth, strengthening of health service systems in terms of care that can respond to the needs of adolescents and youth, advocacy and cross-sectoral work for the implementation of health policies for adolescents and youth, the promotion of activities on contraception in adolescents and the promotion and strengthening of activities addressing the community that can benefit the health and integrated development of adolescents and youth. As has been said, the Ministry of Health views the introduction of this vaccine as an opportunity to accelerate structuring of the cervical cancer programme along integrated lines, with tracking indicators for primary and secondary preventive care, unique contents and messages, and a specialised information and surveillance system, taking advantage of the strengths of all the programmes and strengthening the results.. 6.1.2 Delivery strategy for HPV vaccine. Please specify the chosen age cohort for HPV vaccination: 9 years old. Please describe the HPV vaccination strategy and plan (when vaccinations will be scheduled, who will do vaccinations, how will the vaccine logistics be assured, coordination between the schools and health personnel, the plan to ensure all three doses are delivered, and plans for reaching girls who may be absent on the day of scheduled vaccinations, etc.). The HPV Introduction Plan is for nationwide coverage; i.e., in the nine departments and 339 municipalities. For the year of introduction, girls aged 9 to 12 will be immunised, with the aim of reaching 100%; for the following years, the 9-year-old cohorts will be immunised. To implement the HPV introduction plan, account is being taken of the principal lessons learned from the extensive country experience in vaccine administration to girls of school-going age, as well as from specific demonstrations of HPV immunisation. Hence, the strategies of systematic routine immunisation applied by the EPI will be applied i) on demand in health services, as part of the programmes addressing adolescent health and health at school ii) in immunisation in educational centres iii) in the referral of girls not enrolled for such period to schools or health services iv) in other operative activities with immunisation brigades in remote areas and vulnerable populations. These strategies, implemented simultaneously throughout the health service network, and intensively over one month at the start of the schoolyear (March) for the application of the first dose and six month afterwards (September) for the second dose, lead to expectations of achieving 100% coverage for the target population. The first dose to schoolgirls will be administered in March 2017 and the second dose in September of the same year, towards the target of immunising 100 % of the girls. HPV will be included in the national immunisation schedule starting 1 March 2017 nationwide. It will be done by the public network immunisation services in coordination with the educational centres. The most significant challenges in HPV introduction into the country are: - Achieving acceptance by the parents and some population sectors regarding a vaccine associated with sexuality for adolescent girls; forecasting and reducing the impact of anti-vaccine groups and religious leaders; and involving the population in the social audit and control of the programme, along with the support of regional and local governments. - Disseminating information on integrated primary care prevention of cervical cancer; i.e., Pap tests, VIA and education for health. - Disseminating information about vaccine effectiveness, safety and quality in communities and among scientific associations through the media and activities of communication and social mobilisation. - Achieving Ministry of Education coordination and support to conduct the immunisation of 100% of the school-going girls within a short period of time, ensuring completion of the two-dose schedule during one and the same schoolyear. - Reaching the girls who are not enrolled or who abandon school through the health facilities, referral campaigns during the same period of time, and field immunisation activities. - Guaranteeing the sustainability of activities through procedures that can be assimilated and adopted by the health services, the communities and the municipal and departmental governments. The strategy of immunisation in school ensures high coverage, with school enrolment at over 95% and an acceptable continuity, thanks to the distribution of the Juancito Pinto voucher to all public school students, and a homogeneous offer in educational centres throughout the country. On its side, the Juana Azurduy voucher will promote the immunisation campaign and cervical cancer detection, prevention and control activities. The immunisation lists by grade, age and educational centre, reflecting the names of the girls, addresses, date of first dose administration and schedule of the second dose, will be used for the immunisation taking place in educational centres, and as well to ensure immunisation with two doses. The vaccines and syringes will be ensured for this. Those girls not attending educational centres will be called to come to the schools or the health services during the same period through social organisations; a list will be drawn up with the same data for monitoring and the application of the second dose. Mobile brigades will be programmed for the girls living in scattered and remote communities, drawing up the pertinent information and scheduling their second dose. The departmental health services (SEDES) and the municipal health networks will take charge of vaccine supply logistics:. Irrespective of the strategy, provide a description of existing health services and/or health education currently being provided to young adolescents (both girls and/or boys) within the 9-13 year old age group; and indicate and potential synergy by integrating with HPV vaccination:. a. For health services (this can include: what health services are provided, to which age/sex group, whether it’s mandatory or voluntary, regularly or ad-hoc, in school or out of school, who provides these (government, NGOs), how often, what is the uptake in the community, how is it perceived by the community.). 2015 marks the start of a new management period in the Government of the Plurinational State of Bolivia – the same that begins with the Integrated National Development Plan to LIVE WELL 2015-2020, in which health policies and activities are incorporated into pillar 3, along with education and sports, the horizon of which is the formation of an integrated human being. The other pillars offer opportunities for a cross-cutting application of the health policy, with cross-sector interventions to provide for integrated health in childhood, school-going age, adolescence, adulthood and senior adulthood. The Ministry of Health is tasked with the constitutional mandate of generating objective conditions for the full exercise of the Bolivian population's Right to Health. To achieve this, it identifies the institutionalisation of the Single Health System as a strategic mechanism, including the traditional medicine of the original indigenous nations and peoples of the countryside. The Single Health System, along with Intercultural Community and Family Health (SAFCI) policy, is based on: - Network strengthening by levels of complexity. - Operativity of functional networks. - Structuring of health promotion and disease prevention activities. - Participation of public and private operators in complementary relations. - Regulation, established by the Ministry of Health, wherein progress in the Single Health Register is vital and strategic. - Civic participation. - Structuring along with other rights, basic to a cross-sectoral approach. The health plan takes account of the population in its different vital cycles: the newborn, infancy, school-going age, adolescence, adulthood and senior adulthood. The services offered to children and adolescents are health promotion and disease prevention, including dT immunisation, promotion of healthy nutrition and eating habits, care. For 2015, the public system service network avails of 339 municipal health networks and 3816 health facilities, of which 3526 are primary care facilities, 223 are secondary care facilities and 65 are tertiary care.. b. For health education (this can include: the topic, whether it is national, sub-national, in school or out of school, who provides the education, how often, is it in the school curriculum, are there NGOs providing these? How is it perceived by the community? Has there been an evaluation and if so, how was it evaluated and what were the findings?). The Health Sector Plan, the health promotion plan, the health plans for infancy, school-going age, adolescence, nutrition and the EPI, among others, develop the component of education for family health, oriented towards the prevalent problems of every age group, providing information on how to prevent and control these problems. Lately, new impulse has been given to sex education, with emphasis on the prevention of unwanted pregnancies and violence, in coordination with the Ministry of Health. Activities on the preservation of the environment and Mother Earth have also been encouraged. This line of action will be handled nationwide and complemented by the SEDES and the networks. Observable in our experience of the demonstration phase with CIES was the importance of working with differentiated audiences in education for health, and information for parents, teachers and schoolchildren. The focus has to be integrated, taking advantage of the opportunity to favour the primary prevention of cervical cancer. Once listeners are informed, the acceptance of everyone involved is achieved. It may be noted that, in private consultation, the spontaneous demand for this vaccine exists. The Ministry of Health is experienced in the routine systematic application of dT with no difficulty in public and private educational centres. At the same time, it should be noted that administration of this vaccine has been taking place for over a decade.. Please describe the communications and social mobilisation plan for the HPV vaccination strategy (what activities will be done to educate and raise awareness of the vaccination plan to the target population, their parents/guardians, the wider community, community leaders, groups of influence, etc.; who will provide this education and what materials will be used; how often will these activities occur vis-a-vis the proposed vaccination schedule.). HPV introduction into the national schedule poses several challenges to be considered in the design and implementation of communication strategies for the different players involved, particularly in school councils that include students, teachers and heads of families. It represents a challenge for the EPI and the MoH, since this is a vaccine applied in pre-adolescence, in developing countries largely to girls, and is related to diseases associated with sexual activity, which, in some sectors of society, is still perceived as a myth. The communication plan will include activities with leaders of social organisations who have authority over the communities. Hence, they are the best means to transmit effective and clear information regarding the advantages of immunisation. The topics and content to disseminate will consider social structure, with a care for cultural adaptation with respect to existing ethnic diversity. Communication media and opinion leaders will be informed through departmental workshops to secure their support during promotion and the execution of activities, as well as in adequately handling the information provided by groups who are against vaccines. This vaccine has systematically been subjected to attack, smear and disinformation campaigns in all countries introducing it, basically from anti-vaccine groups and religious organisations manipulating contents and information media that are hard to control and that generally exert great influence and impact on the population. Since this entails immunisation in adolescents, special care will be taken in handling taboo subjects. The MoH will call for groups of communicators who are experts in health to develop the Communication and Social Mobilisation Plan and a Crisis Plan that can give proper information about the diseases prevented, the characteristics of the vaccine, and the effects expected over the medium and long term. Some of the key ideas should revolve around the following subjects: - Cervical cancer is the foremost cause of death in women of childbearing age in Bolivia, causing around 450 deaths yearly, with devastating effects on families and the society. - Two vaccines that have proven safe and effective have been used for over 10 years in countries around the world, and in Bolivia these have also been applied in private medical practice. - The vaccine is made of synthetic particles imitating the structure of HPV. Hence, it has no biological capacity and cannot cause the infection. It does not contain any type of hormone and has no effect whatsoever on human sexuality. - The vaccine contains the elements to prevent infection by the virus types that most frequently cause cancer in men as well as women. - Rigorous studies on side effects have been conducted in vaccine introduction, showing that these are minimal, generally local, and that they disappear by themselves in only a few days leaving no damage or after-effects in immunised persons; moreover, the surveillance of adverse effects conducted in all the countries using the vaccine has shown that it is one of the safest, most effective that exist. Audio-visual and printed communication materials will also be produced, culturally pertinent to the three majority regions of the country, such as: - Banners with the immunisation schedule updated with HPV. - Almanacs in the educational centres to set immunisation with the second dose, containing messages about cancer. - Practical guides on immunisation techniques. - Decentralised official launches and one national launch. - Radio and TV spots and micro-documentaries of cultural relevance. - Booklets for students, teachers and families....

Please select strategy that the country will choose to deliver the HPV vaccine: Mixed strategy including schools and health centres... School-based strategy. Bolivia: strategy to deliver HPV vaccine does not include a "School-based strategy".. INSTRUCTIONS. Description should include:. Primary/secondary/tertiary, grades in each category, majority age in each grade. Number of schools in the country (public/government schools, private school, or other categorization if possible and relevant for the country). What is the school year (which month to which month). When are the school holidays? (Approximated months, days if possible). When are the major examinations? (Approximated month).. In Bolivia, the educational system contemplates the starting cycle, primary with 6 grades, and secondary also with 6 grades. In the rural areas, multi-grade educational centres are common. Analysis of the distribution of girls by age and grade for 2014 enabled us to observe that 85% of those between 9 and 12 are in the third, fourth and fifth grades of primary. 5% are in the first year of secondary and 10% in the first and second year of primary. This is why scheduling cannot be based on grades. It will have to be by age, also considering the existence of multi-grade educational centres. The key activities are: - Coordination on the national, departmental and local levels – nationally to back the legal regulatory framework and inter-institutional agreement, the departmental level in support of joint SEDUCA-SEDES programmatic planning and the issuance of instructions, and the local level to prepare calendars and inventories of girls by age and grade, to disseminate information and cervical cancer prevention with the vaccine and for other integrated health activities. - Preparation of technical guidelines: calculation of vaccines per school, definition of responsibilities (teachers/health staff/community leaders); lists of girls enrolled by grade and age, census of girls with first doses. - Special communication strategies to address teachers, students and families. There are approximately 16,000 educational centres throughout the country. The schoolyear begins in February and ends in November. The most important examinations take place quarterly (April, June, September and November).. Please specify whether girls will be vaccinated by selection of a specific age. Table 6.1.2 a.. Number of; Base year; Target year. 2015; 2017. Target population of girls in chosen age; 119,280. Girls of chosen age enrolled in schools; 93,038.....

If girls are to be vaccinated by a specific grade, please specify grade. and provide the below data relative to the target grade:. Table 6.1.2.b.. Age of girls in grade; Number of girls in grade / age; % of girls in targeted population. 8 years old; 0; 0. 9 years old; 0; 0. 10 years old; 0; 0. 11 years old; 0; 0. 12 years old; 0; 0. 13 years old; 0; 0. 14 years old; 0; 0. TOTAL girls 9-13 years old; 0. TOTAL girls 14 years old and above; 0. Total; 0.. Note:. (1) To add new Age of girls in grade, clock in the New item icon in the Action line. Use the Delete item icon to delete a specific Age of girls in Grade.. Please provide a source for the enrolment data (e.g., national statistics office, MOE, recent census, school registers, etc.). The school records of each educational centre and data from the Educational Information System.. How will the school-based strategy capture those girls not in school? (Will out-of-school girls be invited to join school-attending girls on the days of vaccination? Will separate outreach sessions be scheduled for them? Will existing outreach posts be used? Will out-of-school girls be asked to come to the local health centre? Will vaccination nurses do home visits?). Capture will be based on combined strategies and tactics between the health services and the community social structure. Immunisation services in Bolivia are offered the year round through regular immunisation in health centres or through mobile brigades sent to remote communities, routinely at least 4 times a year. Local micro-planning will make it possible to avail of the census of target girls according to whether or not they attend educational centres and their scheduling by type of strategy.. If any, please describe special considerations to be made for marginalised or migrating populations?. 77% of the girls are enrolled in schools. For the 22% of them that do not attend school, following strategies are defined: 1) Referral of those girls scheduled at the same time to the educational centres or the health services. 2) Mobile brigades that will go to the scattered remote communities. 3) Upon demand at the health services. Every health facility will undertake micro-planning based on an inventory of educational centres in its working area. In addition to the census of girls from the target group, the girls not attending school will be put on census for scheduling based on the strategy agreed on with community authorities and women's organisations. Bolivia has a broad experience in the immunisation of large numbers that includes migrants and the underserved population.... Health centre-based strategy. Please describe the health system and services for the target population at the health centres: (This can include: Number and type of health centres in the country by level (national, sub-national, district), (by public/government, private, or other categorization relevant for the country and if available). What services for 9-13 year old girls are routinely available in these health centres? What are the general operating day/times for service delivery in the health centres? How vaccinations are delivered in the existing health centres? By whom, to what population, etc.). The health system is composed of the following subsectors: public, short-term insurance, NGOs and private. The public system has Immunisation in all subsectors is from Monday to Friday, six hours daily – this timetable applies in 24-hour facilities. In rural areas, there is a greater affluence of population at weekends and at times that the health staff and the population agree are working days. DT has been offered at these centres for 26 years, with great demand. Immunisation is given basically by the nursing aide and, in some cases, by nurses. The health staff take advantage of every contact with the target population to refer them to immunisation posts from out-patient clinics, paediatrics or dentistry. Another technique used is to make announcements through community organisations or agents, sports clubs, mothers' associations, etc. Each health facility has population sectors identified as accessible, less accessible or reluctant towards the health services. Based on these categories, they define the communities in the rural area, or the districts in urban areas that should be attended by mobile brigades, in which the entire health team of doctors, nurses, aides and dentists participate. The method includes the census of girls in the target group with all the exact data, who are programmed for subsequent doses that may be delivered on demand or by a new visit from the mobile brigade. On this occasion, the doctors and nurses from the MiSalud programme will promote the vaccine as an effective method to prevent cervical cancer.. How will the health centre-based strategy capture all the girls who are eligible?. This strategy addresses approximately 23% of the girls not going to school or abandoning it before the end of the schoolyear. It will form part of routine immunisation, which is the same all year round: on demand, generated by the social communication campaign, or through mobile brigades programmed by each centre based on actual circumstances and needs. Programming is done at least 4 times a year.. If applicable, please describe special considerations to be made for marginalised or migrating populations?. On the operative level, following technical EPI guidelines, the health service network programmes for reaching 100% of the population in its care. This includes scattered remote communities of difficult access, which in some cases are peripheral urban areas, for target population immunisation with all vaccines. HPV will be included in this routine immunisation in addition to immunisation in existing educational centres......

6.2. Requested vaccine (HPV quadrivalent, 1 dose/vial, LIQUID). As reported in the cMYP, the country plans to introduce HPV quadrivalent, using HPV quadrivalent, 1 dose/vial, LIQUID.. When is the country planning to introduce this vaccine? January 2017. Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. Gavi will work closely with countries and their partners to address these issues.. Please summarise the cold chain capacity (at central and other levels) and readiness to accommodate new vaccines, taking into consideration training, cold chain equipment and other logistical requirements. If cold chain expansion is required, state how it will be financed, and when it will be in place. The Independent Review Committee requires assurance that the cold chain is ready or will be ready for the routine introduction of the new vaccine, and evidence/plans need to be provided. All proposals that include Gavi- financing for cold chain equipment intended for vaccine storage shall need to procure equipment pre-qualified by WHO under their Performance Quality and Safety (PQS) program. The purchase of non-PQS equipment will only be considered on an exceptional basis, with justification and advance agreement from Gavi.. PAHO supported the cold chain installed capacity evaluation for IPV introduction, identifying some needs on the departmental level and equipment items at the end of their useful lives for replacement. This is all included in the Gavi transition plan and in the plans of municipal governments... 6.2.1. Co-financing information.. The policy of co-financing is not applicable to this exceptional opportunity..... 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1. 2017. SP - Number of children to be vaccinated with the 1st dose; Table 5.2; #; 119,280. Number of children to be vaccinated with the last dose; Table 5.2; #; 119,280. Last dose immunisation coverage; Table 5.2; %; 100 %. Country co-financing for total needs; %; 50%......

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$). 2017. Number of vaccine doses; #; 156,600. Number of AD syringes; #; 167,157. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total amount of country co-financing; $; 789,029... 6.2.4. Portion of supply to be procured by Gavi (and cost estimate, US$). 2017. Number of vaccine doses; #; 156,600. Number of AD syringes; #; 167,156. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total Gavi grant amount; $; 789,029.......

6.2.5. New and Under-Used Vaccine Introduction Grant. Calculation of Vaccine Introduction Grant for the HPV quadrivalent, 1 dose/vial, LIQUID.. Year of New Vaccine Introduction; Girls in the cohort (Table 5.2); Share per girl in the cohort; Total in US$. 2017; 119,280; 2.40; 286,272.. The Grant will be based on a maximum award of $2.40 per girl in the birth cohort with a minimum starting grant award of $100,000... Please describe how the Gavi Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan)... A detailed budget template for HPV introduction is available, indicating the flow of the Gavi grant to promote key activities, such as: advocacy and resource mobilisation to achieve fund allocation from domestic sources, corresponding to departmental and municipal governments. To do this, meetings will be held with governors, mayors and, above all, their coordinating entities such as FAM and ACOBOL for municipalities, the Presidential Ministries and the autonomous governments. This point was already announced during the consultations for proposal preparation. Strategic alliance with the Ministry of Education will also be formed. Official contact has already been established to jointly prepare a critical path identifying all the legal and technical tools and techniques for coordination on the national level and on the level of decentralised entities. The EPI proposal for joint work was very well received. Planning and programming workshops based on the lessons learned in the demonstration phase, requiring sufficient margins in terms of time and participation to achieve successful immunisation campaigns in educational centres and in routine EPI activities. Geo-referencing and micro-planning will be critical keys in this stage. Training for teams of facilitators in every department to start a chain of processes towards the coordination of networks and municipal health networks in aspects of planning HPV, vaccines and immunisation procedures, information systems, AEFIs and crisis management. Cold chain: complementary equipment for field teams such as vacuum flasks. Promotion, communication and social mobilisation to design a strategy and plan that includes working with grassroots social organisations and the production of culturally pertinent multi-media material. Information and surveillance systems to strengthen primary records, adaptation of formats, computing systems. Monitoring and supervision, CAP surveys and other tools to identify immunisation barriers and determine actual HPV immunisation coverage. Evaluation to support participative evaluation processes with strategic allies in education and FAM, ACOBOL, etc. The budget template figures as attachment 22 and as well attachment 10... Please complete the ‘Detailed budget for VIG / Operational costs’ template provided by Gavi and attach as a mandatory document in the Attachment section... Detailed budget attached as Document No. 22... Where Gavi support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs... Other supplementary national resources will be mobilised such as: AOP 2017 of the EPI with national resources will include the budget to supplement gaps in several lines. This is prepared in August. AOPs of departmental governments and municipal governments for 2017, aspects already announced with the Ministry of the Economy and FAM... 6.2.6.Technical Assistance.. Please describe any particular area(s) the Ministry would require technical assistance to support the introduction of HPV quadrivalent.......

7. NVS Preventive Campaigns. Support for the preventive campaign will not be given this year...

8. Procurement and Management.. 8.1 Procurement and Management of New and Under-Used Vaccines Routine.. Note: The meningococcal vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)... a) Please show how the support will operate and be managed including procurement of vaccines (Gavi expects that most countries will procure vaccine and injection supplies through UNICEF or PAHO’s Revolving Fund).. According to the Vaccine Act of Bolivia, vaccines, syringes and other supplies must be purchased through the PAHO Revolving Fund.. If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the Gavi Alliance) is requested, please document:. ; A description of the mechanism and the vaccines or commodities to be procured by the country. ; Assurance that vaccines will be procured from the WHO list of pre-qualified vaccines, indicating the specific vaccine from the list of pre-qualification. For the procurement of locally-produced vaccines directly from a manufacturer which may not have been prequalified by WHO, assurance should also be provided that the vaccines purchased comply with WHO’s definition of quality vaccines, for which there are no unresolved quality problems reported to WHO, and for which compliance is assured by a fully functional National Regulatory Authority (NRA), as assessed by WHO in the countries where they are manufactured and where they are purchased.. No other mechanism is required.. c) If receiving direct financial support from Gavi (such as operational support for campaigns or VIG activities), please indicate how the funds should be transferred by Gavi.. Through the PAHO.. d) Please indicate how the co-financing amounts will be paid (and who is responsible for this).. Gavi funds for co-financing will be paid directly into the PAHO Revolving Fund.. e) Please describe the financial management procedures that will be applied for the management of the NVS direct financial support, including procurement.. Grant funds will be managed through PAHO/WHO without administrative charges. The funds will be implemented according to the plan approved upon request by the EPI and per the detailed budget in Document 22.. f) Please outline how coverage of the introduced vaccine will be monitored, reported and evaluated (refer to cMYP and Introduction Plan).. Through monthly monitoring of immunisation, including the two periods of school immunisation and routine immunisation to the girls vaccinated through other strategies. Result indicators are: - % coverage of girls with second doses. - Drop-out rate. - % of educational centres with coverage > 95% Process indicators - % of SEDES with implemented plans - % of municipalities with implemented plans - % of educational centres with information - No of educational centres with census of girls aged 9 to 12 - Number of out-of-school girls with second doses Progress reports are prepared in accordance with Gavi and EPI Bolivia standards. g) If applying for measles second dose, does the country wish to have the support in cash or in-kind? N/A.. 8.2 Procurement and Management for NVS Preventive Campaign(s).. Support for the preventive campaign will not be given this year.. 8.3 Product licensure.. For each of the vaccine(s) requested, please state whether manufacturer registration and/or national vaccine licensure will be needed in addition to WHO prequalification and, if so, describe the procedure and its duration. In addition, state whether the country accepts the Expedited Procedure for national registration of WHO-prequalified vaccines.. Note that the necessary time for licensure should be factored into the introduction timeline and reflected in the Vaccine Introduction Plan or Plan of Action... For each of the vaccine(s) requested, please provide the actual licensure status of the preferred presentation and of any alternative presentations, if required... Please describe local customs regulations, requirements for pre-delivery inspection, special documentation requirements that may potentially cause delays in receiving the vaccine. If such delays are anticipated, explain what steps are planned to handle these... Please provide information on NRA in the country, including status (e.g. whether it is WHO-certified). Please include points of contact with phone numbers and e-mail addresses. UNICEF will support the process by communicating licensing requirements to the vaccine manufacturers where relevant..... 8.4. Vaccine Management (EVSM/EVM/VMA).. It is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 5 years... When was the last EVM conducted? October 2015.. Please attach the most recent EVM Assessment Report (DOCUMENT NUMBER: 20, 19, 21); the corresponding EVM improvement plan (DOCUMENT NUMBER: 1); and progress on the EVM improvement plan (DOCUMENT NUMBER: 21). The improvement plan should include a timeline, a budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation... If any of the mandatory documents previously mentioned (EVM Assessment Report, Progress on the EVM Improvement Plan) is not available, explain this situation and refer to other documents, eg, Post Introduction Evaluation (PIE) and EPI external reviews... When is the next EVM assessment projected? November 2016.. The national EPI has requested conduct of EVM, initially programmed for 2015, which was reprogrammed for 2016. A workshop in preparation for EVM was conducted in October 2015, with the participation of EPI managers, SEDES cold chain and logistics technicians and the national team. Evaluation has been rescheduled for November 2016 and progress is expected in the Improvement Plan in time for HPV introduction..... 8.5 Waste management.. Countries must have a detailed waste management and monitoring plan as appropriate for their immunisation activities. This should include details on sufficient availability of waste management supplies (including safety boxes), the safe handling, storage, transportation and disposal of immunisation waste, as part of a healthcare waste management strategy. Please describe the country’s waste management plan for immunisation activities (including campaigns).. Waste management is included in EPI standards. Nevertheless, advantage will be taken of the introduction of this new vaccine to update and strengthen existing technical guidelines. All immunisation posts have all the supplies necessary at their disposal (recipients, bags, identification) to implement differentiated separation of the waste generated in vaccine administration – including HPV vaccination – which activity must be coherent with the institutional programme implemented in the health facility. Relevant supplies Safety boxes for uncapped sharps, to be destroyed afterwards as per standard. Used and expired vaccine vials will be collected in recipients for final disposal. Safe manipulation along secure lines for workers to prevent pricking; not recapping, filling up to 75% of capacity, sealing and bringing waste to final disposal....

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. Dr Gladys Quiroga, cancer foundation congratulates the Ministry of Health and the team who did the work; it is complete, with technical and financial analyses. Despite having started the discussion in 2014, it seems to her that 2017 is still a little far, asks for acceleration of the process. She considers Gavi support an opportunity to recover four cohorts of girls who have not been immunised. Senator Erwin Rivero, chairman of the senate commission for social, health and education policies congratulates “the Ministry of Health for the decision to introduce this vaccine. He said: "it is a social debt we owe the women of Bolivia and the time has come to pay it back." Dr Colque, congress commission for health: "This was not introduced before due to price barriers and non-availability [of resources] in the PAHO revolving fund." He requests integrated handling and sustainability of the work for ten years to achieve medium and long-term impact. Dr José Luis Alfaro, CIES is glad to see "that the efforts of all these years is finally materialising." Dr Adalid Zamora, NIC chairman, proposes formation of the ad hoc committee for HPV introduction, which proposal was unanimously accepted, and the document of its creation was signed. Ms Roxana Zaconeta, the specialist in charge of gender, generations and social justice in the Ministry of Education: "To introduce this vaccine is to respond with deeds to a priority problem of Bolivian women, with full respect for their rights, audacity and courage", and congratulates the Ministry of Health for the initiative. Dr Fernando Leanes, PAHO representative congratulates the Ministry of Health for a very solid and firm proposal on the need to introduce this vaccine into the national EPI schedule....

10. List of documents attached to this proposal.. 10.1. List of documents attached to this proposal.. Table 1 : Mandatory attachments checklist.. Document Number; Document; Section; File. Approvals. 1; MoH Signature (or delegated authority) of Proposal; 4.1.1.; Annex 1.pdf File desc: Letter from the Minister to Gavi dated 29 April Date/Time: 30/04/2016 03:00:35 Size: 50 KB. 2; MoF Signature (or delegated authority) of Proposal; 4.1.1.; Annex 2.pdf File desc: Signature of the Ministers of Health and Education dated 28 April 2016 Date/Time: 01/05/2016 10:50:30 Size: 211 KB. 3; MoE signature (or delegated authority) of HPV Proposal; 4.1.1.; Annex 2.docx File desc: Date/Time: 01/05/2016 09:51:46 Size: 778 KB. 4; Terms of Reference for the ICC; 4.1.2.; Annex 4 ICC ToR File desc: ICC ToR / regulations Date/Time: 29/04/2016 02:43:03 Size: 30 KB. 5; Minutes of ICC/HSCC meeting endorsing proposal; 4.1.3.; anexo 6 actas del CCI.docx File desc: Minutes of ICC approving the proposal and corresponding signatures Date/Time: 29/04/2016 02:57:44 Size: 14 KB. 6; Signatures of ICC or HSCC or equivalent in Proposal; 4.1.3.; Annex 5.pdf File desc: Signed on 26 April 2016 Date/Time: 30/04/2016 02:59:12 Size: 272 KB. 7; Minutes of last three ICC/HSCC meetings; 4.1.3.; Annex 6 Meeting and Signatures 260416 ICC-1.pdf File desc: Date/Time: 01/05/2016 06:19:48 Size: 1 MB. 8; Role and functioning of the advisory group, description of plans to establish a NITAG; 4.2.1.; Annex 8 IC functions and signatures.doc File desc: NIC functions. The table of signatures is in other documents, in addition to all the NIC minutes where the subject was discussed Date/Time: 29/04/2016 02:48:28 Size: 33 KB. Vaccine planning, financing and management. 9; Comprehensive Multi Year Plan - cMYP; 5.1; Annex 9 Five-year_Plan_2015_-_2020 COMPONENTS.doc File desc: Narrative of five-year plan 2016-2020 Date/Time: 30/04/2016 11:05:13 Size: 4 MB. 10; cMYP Costing tool for financial analysis; 5.1; Copy of 1 EPI Five-year Plan 2016-2020.xls File desc: Date/Time: 01/05/2016 09:47:45 Size: 1 MB. 11; Supervision and evaluation plan and surveillance plan within the supervision plans existing in the countries; 5.1.5.; Annex 11.xlsx File desc: Date/Time: 01/05/2016 09:53:58 Size: 37 KB. 12; Vaccine introduction plan; 5.1; HPV Introduction Plan WHO format FINAL 2B 270416 2201.doc File desc: Date/Time: 30/04/2016 06:34:41 Size: 1 MB. 15; HPV roadmap or strategy; 6.1.1.; Annex 15.docx File desc: Date/Time: 01/05/2016 10:09:25 Size: 13 KB. 16; HPV summary of the evaluation methodology; 5.1.6.; Annex 16 HPV Evaluation Methodology.docx File desc: Date/Time: 30/04/2016 03:57:28 Size: 15 KB. 19; EVM Report; 8.3; Annex 19.docx File desc: Date/Time: 01/05/2016 10:10:21 Size: 12 KB. 20; Improvement plan based on EVM; 8.3; Annex 19.docx File desc: Date/Time: 01/05/2016 10:10:53 Size: 12 KB. 21; EVM improvement plan progress report; 8.3; Annex 19.docx File desc: Date/Time: 01/05/2016 10:11:20 Size: 12 KB. 27; Data quality assessment (DQA) report; 5.1.5.; Annex 27 Quality Assessment GaviWHO.pdf File desc: This is the last external evaluation conducted in Bolivia, although its objective was more to validate methodology and tools. Date/Time: 29/04/2016 02:45:59 Size: 179 KB.. Table 2 : Optional attachments checklist.. Document Number; Document; Section; File. 13; Introduction Plan for the introduction of RCV / JE / Men A into the national programme; 7.x.4; File not uploaded. 17; Evidence of commitment to fund purchase of RCV for use in the routine system in place of the first dose of MCV; 7.x.3; File not uploaded. 18; Campaign target population documentation; 7.x.1, 6.x.1; File not uploaded. 22; Detailed budget template for VIG / Operational Costs; 6.x,7.x.2, 6.x.2; Copy of HPV Budget 2016-2020-1.xls File desc: Date/Time: 01/05/2016 09:19:30 Size: 584 KB. 23; Risk assessment and report on consensus meeting for MenA conjugate vaccines. If DTT was used instead, include this information.; 7.1; File not uploaded. 25; A description of partner participation in preparing the application; 4.1.3.; Annex 25 Partner Participation in Structuring the Proposal.docx File desc: Date/Time: 01/05/2016 06:37:25 Size: 14 KB. 26; Minutes of NITAG meeting with specific recommendations on the NVS introduction or campaign; 4.2; Annex 26E Summons NIC and Ad hoc Committee 250416.pdf File desc: Date/Time: 29/04/2016 03:06:08 Size: 1 MB. 28; DQA improvement plan; 5.1.5.; File not uploaded. 29; Plan of Action for campaigns; 7.1, 7.x.4; File not uploaded. 30; Other Document; Checklist, HPV Calendar and Budget.xlsx File desc: Date/Time: 30/04/2016 11:31:25 Size: 37 KB. Copy of HPV Budget 2016-2020-1.xls File desc: HPV introduction budget Date/Time: 30/04/2016 11:47:56 Size: 584 KB. Summary HPV Baseline and Epidemiological Surveillance.docx File desc: Date/Time: 30/04/2016 11:52:14 Size: 19 KB. Gavi country capacity evaluation.pdf File desc: Date/Time: 01/05/2016 09:15:32 Size: 1 MB...

11. Annexes... Annex 1 - NVS Routine Support. Annex 1.1 - NVS Routine Support (HPV quadrivalent, 1 dose/vial, LIQUID). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2017. Number of vaccine doses; #; 156,600. Number of AD syringes; #; 167,200. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total amount of country co-financing; $; 789,500... Table Annex 1.1 B: Table Annex 1.1 B: Rounded up portion of supply that is procured by Gavi and estimate of relative costs in US$.. 2017. Number of vaccine doses; #; 156,600. Number of AD syringes; #; 167,200. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total Gavi grant amount; $; 789,500......

Table Annex 1.1 C: Summary table for vaccine HPV quadrivalent, 1 dose/vial, LIQUID. ID. Data from; 2017. Number of surviving infants; Table 5.2; #; 247,145. Number of children to be vaccinated with first dose; Table 5.2; #; 119,280. Number of children to be vaccinated with second dose; Table 5.2; #; 119,280. Immunisation coverage with the second dose; Table 5.2; %; 100%. Number of doses per child; Parameter; #; 2. Estimated vaccine wastage factor; Table 5.2; #; 1.05. No. of doses per vial; Parameter; #; 1. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; No. Safety boxes required; Parameter; #; No. gs; Gavi support; Parameter; %; 50%. ca; AD syringe price per unit; Table Annex 4A; $; 0.041. cr; Reconstitution syringe price per unit; Table Annex 4A; $; 0. cs; Safety box price per unit; Table Annex 4A; $; 0.005. fv; Freight cost as % of vaccines value; Table Annex 4B; %; 11.00%......

Table Annex 1.1 D: Table Annex 1.1 D: Estimated quantity of HPV quadrivalent, 1 dose/vial, LIQUID, injection safety materials and corresponding country budget (page 1).. Formula; 2017. Total; Government; Gavi. A; Gavi support; Gavi support; 50.00 %. B; Number of children to be vaccinated with first dose; Table 5.2; 119,280; 59,640; 59,640. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 238,560; 119,280; 119,280. E; Estimated vaccine wastage factor; Table 5.2; 1.05. F; Number of doses needed including wastage; D x E; 250,488; 125,244; 125,244. G; Vaccines buffer stock; Buffer on doses needed = (D - D of previous year) x 25% Buffer on wastages = ((F - D) - (F of previous year - D of previous year)) x 25%, = 0 if negative result G = [buffer on doses needed] + [buffer on wastages]; 62,622; 31,311; 31,311. I; Total vaccine doses needed; Round up ((F + G) / Vaccine package size) * Vaccine package size; 313,200; 156,600; 156,600. J; No. of doses per vial; Vaccine parameter; 1. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 334,313; 167,157; 167,156. L; Reconstitution syringes (+ 10% wastage) needed; (I / J) x 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) / 100 x 1.11; 0; 0; 0. N; Cost of vaccines needed; I x vaccine price per dose (g); 1,409,400; 704,700; 704,700. O; Cost of AD syringes needed; K x AD syringe price per unit (ca); 13,624; 6,812; 6,812. P; Cost of reconstitution syringes needed; L * reconstitution price per unit; 0; 0; 0. Q; Cost of safety boxes needed; M x safety box price per unit (cs); 0; 0; 0. R; Freight cost for vaccines needed; N x freight cost as of % of vaccines value (fv); 155,034; 77,517; 77,517. S; Freight cost for devices needed; (O+P+Q) x freight cost as % of devices value (fd); 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 1,578,058; 789,029; 789,029.. Note: Gavi vaccine support is limited to 50% of the quantity of doses needed for the campaign and a vaccine introduction grant for routine introduction.........

Annex 2 - NVS Routine – Preferred Second Presentation.. Annex 2.1 - NVS Routine Support (HPV bivalent, 2 dose/vial, LIQUID). Table Annex 2.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2017. Number of vaccine doses; #; 165,600. Number of AD syringes; #; 169,200. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total amount of country co-financing; $; 852,500... Table Annex 2.1 B: Table Annex 1.1 B: Rounded up portion of supply that is procured by Gavi and estimate of relative costs in US$.. 2017. Number of vaccine doses; #; 165,600. Number of AD syringes; #; 169,200. Number of re-constitution syringes; #; 0. Number of safety boxes; #; 0. Total Gavi grant amount; $; 852,500......

Table Annex 2.1 C: Summary table for vaccine HPV bivalent, 2 dose/vial, LIQUID. ID. Data from; 2017. Number of surviving infants; Table 5.2; #; 247,145. Number of children to be vaccinated with first dose; Table 5.2; #; 119,280. Number of children to be vaccinated with second dose; Table 5.2; #; 119,280. Immunisation coverage with the second dose; Table 5.2; %; 0. Number of doses per child; Parameter; #; 2. Estimated vaccine wastage factor; Table 5.2; #; 1.11. No. of doses per vial; Parameter; #; 2. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; No. Safety boxes required; Parameter; #; No. gs; Gavi support; Parameter; %; 50%. ca; AD syringe price per unit; Table Annex 4A; $; 0.041. cr; Reconstitution syringe price per unit; Table Annex 4A; $; 0. cs; Safety box price per unit; Table Annex 4A; $; 0.005. fv; Freight cost as % of vaccines value; Table Annex 4B; %; 11.00%......

Table Annex 2.1 D: Estimated quantity of HPV bivalent, 2 dose/vial, LIQUID, injection safety materials and corresponding country budget (page 1).. Formula; 2017. Total; Government; Gavi. A; Gavi support; Gavi support; 50.00 %. B; Number of children to be vaccinated with first dose; Table 5.2; 119,280; 59,640; 59,640. C; Number of doses per child; Vaccine parameter (schedule); 2. D; Number of doses needed; B x C; 238,560; 119,280; 119,280. E; Estimated vaccine wastage factor; Table 5.2; 1.11. F; Number of doses needed including wastage; D x E; 264,802; 132,401; 132,401. G; Vaccines buffer stock; Buffer on doses needed = (D - D of previous year) x 25% Buffer on wastages = ((F - D) - (F of previous year - D of previous year)) x 25%, = 0 if negative result G = [buffer on doses needed] + [buffer on wastages]; 66,201; 33,101; 33,100. I; Total vaccine doses needed; Round up ((F + G) / Vaccine package size) * Vaccine package size; 331,100; 165,550; 165,550. J; No. of doses per vial; Vaccine parameter; 2. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 338,285; 169,143; 169,142. L; Reconstitution syringes (+ 10% wastage) needed; (I / J) x 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) / 100 x 1.11; 0; 0; 0. N; Cost of vaccines needed; I x vaccine price per dose (g); 1,523,060; 761,530; 761,530. O; Cost of AD syringes needed; K x AD syringe price per unit (ca); 13,786; 6,893; 6,893. P; Cost of reconstitution syringes needed; L * reconstitution price per unit; 0; 0; 0. Q; Cost of safety boxes needed; M x safety box price per unit (cs); 0; 0; 0. R; Freight cost for vaccines needed; N x freight cost as of % of vaccines value (fv); 167,537; 83,769; 83,768. S; Freight cost for devices needed; (O+P+Q) x freight cost as % of devices value (fd); 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 1,704,383; 852,192; 852,191.. Note: Gavi vaccine support is limited to 50% of the quantity of doses needed for the campaign and a vaccine introduction grant for routine introduction.........

Annex 3 - NVS Preventive campaign(s)..... Support for the preventive campaign will not be given this year.. Annex 4.. Table Annex 4A: Commodities Cost.. Estimated prices of supply are not disclosed... Table Annex 4B: Freight cost as percentage of value.. Vaccine Antigens; VaccineTypes; 2017. HPV quadrivalent, 1 dose/vial, LIQUID; HPV*; 11.00 %...

Table Annex 4D: Wastage rates and factors.. The following table shows the wastage rates for routine and campaign vaccines, set for 2017... Vaccine; Doses per vial; Maximum Vaccine wastage rate*; Benchmark Vaccine wastage rate**. Meningococcal A, 10 dose(s) per vial, LYOPHILISED; 10; 50 %; 10 %. Pneumococcal (PCV13), 1 doses/vial, Liquid; 1; 5 %; 0 %. Pneumococcal (PCV10), 2 doses/vial, Liquid; 2; 10 %; 0 %. JE, 5 dose(s) per vial, LYOPHILISED; 5; 10 %; 10 %. Yellow Fever, 10 doses/vial, LYOPHILISED; 10; 40 %; 0 %. Yellow Fever, 5 doses/vial, LYOPHILISED; 5; 10 %; 0 %. HPV bivalent, 2 doses/vial, LIQUID; 2; 10 %; 0 %. HPV quadrivalent, 1 dose/vial, LIQUID; 1; 5 %; 0 %. MR 10 dose(s) per vial, LYOPHILISED; 10; 15 %; 0 %. Rotavirus 2-dose schedule; 1; 5 %; 0 %. Rotavirus 3-dose schedule; 1; 5 %; 0 %. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 10; 40 %; 0 %.. Comments:.. * Source - WHO indicative wastage rates.. ** Source - Country APRs and studies, approved by WHO, UNICEF, and the Gavi Secretariat... Note: HPV demonstration project wastage rates are the same as for the national introduction of the vaccine... Table Annex 4E Vaccine maximum packed volumes.. Kindly note that this table is for reference purposes only and includes Gavi- and non Gavi-supported vaccines... Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule </cf>; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Japanese Encephalitis; JE_lyo; lyophilized; SC; 1; 5; 2.5; 2.9. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; IM; 1; 10; 2.6; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Monovalent OPV-1; mOPV1; liquid; oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; oral; 20; 1.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio; OPV; liquid; oral; 4; 10; 2. Polio; OPV; liquid; oral; 4; 20; 1. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Rota vaccine; Rota_liq; liquid; oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; oral; 3; 1; 45.9. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1...

12. Banking form.. In accordance with the decision on financial support made by Gavi, the Government of Bolivia hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):; Ministerio de Salud [Ministry of Health]. Address:; Plaza del Estudiante. City Country:; La Paz, Bolivia. Telephone no.:; 2495053; Fax no.:; 2492900. Currency of the bank account:; Bolivianos. For credit to:. Bank account's title:; Min Salud, Programa Ampliado de Inmunización a niel nacional. Bank account no.:; 100000015534642. Bank's name:; Banco Union S.A... Is the bank account exclusively to be used by this program? False.. By who is the account audited? Internal auditors of the Ministry and the Auditor's Office.. Signature of Government’s authorizing official.. Seal. Name:; Ariana Campero Nava. Title:; MINISTER OF HEALTH. Signature:. Date:; 29/04/2016:.. FINANCIAL INSTITUTION. Bank's name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. Fax no.:.; CORRESPONDENT BANK. (In the United States).. I certify that the account No is held at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:.. Name of bank’s authorizing official. Signature:. Date:. Seal:...