|  |  | [V3.10] |  |
| --- | --- | --- | --- |
| GAVI Alliance Application Form for Country Proposals For Support to: Routine New Vaccines Support Submitted by The Government of Uganda Date of submission: 14 September 2013 Deadline for submission: 15 September 2013 Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) Start Year 2012 End Year 2016 Form revised in 2013 (To be used with Guidelines of June 2013) Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public. |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland . The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. Application Specification Please specify for which type of GAVI support you would like to apply to. Type of Support Vaccine Start Year End Year Preferred second presentation[1] Routine New Vaccines Support HPV quadrivalent, 1 dose(s) per vial, LIQUID 2015 2016 [1] GAVI may not be in a position to accommodate all countries first product preferences, and in such cases, GAVI will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country. [2] GAVI would appreciate feedback from countries on feasibility and interest of selecting and being shipped multiple Pentavalent vaccine presentations (1 dose and 10 dose vials) so as to optimise wastage, coverage and cost. Please refer to section 6.2.

2. Table of Contents 1. Application Specification 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation 4.1.3. Signature Table for the Coordinating Committee for Immunisation 4.2. National Immunization Technical Advisory Group 4.2.1. The NITAG 5. Immunisation Programme Data 5.1 Background information 5.1.1 Lessons learned 5.1.2 Health planning and budgeting 5.1.3 Preparatory activities 5.1.4 Gender and equity 5.1.5 Data quality 5.1.6 HPV specific facts 5.2. Baseline and Annual Targets (NVS Routine Support) 5.2.1 HPV specific targets 5.3. Baseline and Annual Targets for Preventive Campaign(s) 6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) 6.1.1 HPV burden specific information 6.1.2 Delivery strategy for HPV vaccine 6.2 Requested vaccine (HPV quadrivalent, 1 dose(s) per vial, LIQUID) 6.2.1 Co-financing information 6.2.2 Specifications of vaccinations with new vaccine 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$) 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$) 6.2.5 New and Under-Used Vaccine Introduction Grant 7. NVS Preventive Campains 8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine 8.2 Procurement and Management for NVS Preventive Campaign(s) 8.3 Vaccine Management (EVSM/EVM/VMA) 8.4 Waste management 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) 10. List of documents attached to this proposal 11. Annexes Annex 1 - NVS Routine Support Annex 1.1 HPV quadrivalent, 1 dose(s) per vial, LIQUID Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ Table Annex 1.1 C Summary table for vaccine HPV quadrivalent, 1 dose(s) per vial, LIQUID Table Annex 1.1 D Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1) Annex 2 - NVS Routine – Preferred Second Presentation Annex 3 - NVS Preventive campaign(s) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking Form

3. Executive Summary Please provide a summary of your country's proposal, including the following the information: l For each specific request, NVS routine support or NVS campaign : ¡ The duration of support ¡ The total amount of funds ¡ Details of the vaccine(s), if applicable, including the reason for the choice of presentation ¡ Projected month and year of introduction of the vaccine l Relevant baseline data, including: ¡ DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) ¡ Birth cohort, targets and immunisation coverage by vaccines l Country preparedness ¡ Summary of EVM assessment and progress on EVM improvement plan l The nature of stakeholders' participation in developing this proposal ¡ Inter-Agency Coordinating Committee ¡ Partners Ugandais applying for GAVI support for HPV scale up to the rest of the country in 2015. . The HPVvaccine applied for is HPV quadrivalent, one dose per vial liquid that shall beadministered to girls of age cohort 10 years who are in Primary 4, for the inschool girls; and 10 year old girls who are out of school through routineimmunization community outreaches such as Child Days Plus (April and October)and stand alone for 2nd dose. The GAVIsupport for HPV scale up shall run from 2015 up to 2016. The portion of supply to be procured by GAVIAlliance for the HPV is $16,374,774 and $ 43,898,111, and to be procured byGovernment of Uganda is $7,026,880 and $6,917,753 for 2015 and 2016 respectively. The GAVIintroduction grant for HPV in 2015 is $1,980,739. The UgandaBureau of Statistics uses proportions of 2.2% of the total population of 37,513,984to determine the number of 10-year old girls equivalent to 825,308 in 2015. The baseline data for DPT3 andMeasles coverage for the children under one year is DPT3 78 %, Measles coverage 82% and BCG coverage of 82%(WHO/UNICEF Estimates 2012 Revision – Draft). The country conducted EVMA inJuly 2011 and implementation of the Improvement Plan is in progress. According to the EVMA and Cold ChainAssessment the available storage capacity of 38,750 Litres at the NationalVaccine Store, the country is ready to introduce PCV in routine immunization in2013. The required additional cold chain storagecapacity for introduction of HPV in 2015 and Rotavirus in 2016 vaccines is26,048 Litres and 5,981 Litres at the national and district levelrespectively. Thetotal cost of $ 583,552 will be required for procurement of the cold chainequipment to strengthen storage capacity at National and district levels inpreparation for the introduction of HPVand Rotavirus vaccines in 2015 and 2016 respectively. The country has conducted EVM trainings forall District Cold Chain Technicians and EPI Focal Persons as part of the EVMimprovement plan and an update of the cold chain inventory has been conducted.The findings of the inventory have been used to forecast the cold chainrequirements for the proposed new vaccines introduction. The Ministry of Health has wellestablished Long Term Institutional Arrangements (LTIA) in place. The technical information and approval flowis from EPI technical committee to Maternal and Child Health Technical WorkingGroup, Senior Management Committee and ultimately to Health Policy AdvisoryCommittee which is the equivalent of the Interagency National CoordinationCommittee. The Health Policy AdvisoryCommittee is the highest approving body for all the GAVI proposals andresponsible for endorsing all GAVI proposal applications. The proposal having gone through all thelevels of LTIA was circulated to HPAC members and discussed in their meeting of04.09.2013. The HPAC members madecomments and inputs that have been incorporated in the proposal prior to submissionto GAVI.

4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation The Government of Uganda would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests GAVI support for: HPV quadrivalent, 1 dose(s) per vial, LIQUID routine introduction The Government of Uganda commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only). Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January. The payment for the first year of co-financed support will be around January 2015 for HPV quadrivalent, 1 dose(s) per vial, LIQUID. Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 1 and 2 in Section 10. Attachments. Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name Hon. Dr. Ruhakana RUGUNDA Name Hon. Maria KIWANUKA Date Date Signature Signature Proof of involvement of the Ministry of Education will also be required for HPV Routine Support. The Ministry of Education will either have to be involved in the ICC process (preferred option) and/or the Minister of Education (or delegated authority) must provide its signature. The signature is attached as DOCUMENT NUMBER : {0} in Section 10. Attachments. Minister of Education (or delegated authority) Name Hon. Jessica EPEL ALUPO Date Signature This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document): Full name Position Telephone Email Dr Annet KISAKYE WHO / EPI team Leader 256 772 504668 kisakyean@who.int Dr Edward KOMAKECH PATH Uganda / Deputy Country Director +256 772 735505 ekumakech@path.org Dr Emmanuel MUGISHA PATH Uganda / Country Director +256 772 657777 emugisha@path.org Dr Eva KABWONGERA UNICEF / Health Specialist +256 772 595658 ekabwongera@unicef.org Dr Fred Sebisubi MOH / Principal Pharmacisit +256 750 740967 sebisubi@yahoo.co.uk Dr Gerald SSEKITO Country Director, MCHIP +256 772 464674 gssekitto@yahoo.com Dr Mayanja Robert MOH/EPI Program manager +256772593482 mayarobe@yahoo.com Dr Solomon FISSEHA WHO / Cluster leader IVD&DPR +256 772 721977 fissehas@ug.afro.who.int Dr. Henry LUZZE Senior Medical Officer- EPI +256772368329 luzzehenry@hotmail.com Mr. Andrew Bakainanga WHO NPO/ AII +256 772 373 231 bakainangaa@ug.afro.who.int Ms Pamela H. ZANINKA Asst. Eng. Off- Cold Chain +256772409130 hzaninka@yahoo.com Ms. Sheeba AFGHAN UNICEF/Communication Specialist +256 417 171403 safghan@unicef.org Sr. Betty IRWASI Senior Nursing Officer- EPI +256772515197 bettyirwa@yahoo.com 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. Profile of the ICC, HSCC, or equivalent committee Name of the committee Health Policy Advisory Committee (HPAC) Year of constitution of the current committee 2000 Organisational structure (e.g., sub-committee, stand-alone) HPAC is a Stand alone committee, but receives reports monthly from 9 technical working groups, MCH T Frequency of meetings Monthly The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4. Major functions and responsibilities of the ICC/HSCC: HPAC is the Coordinating body that advises both government and partners on the implementation of the National Health Policy and the Health Sector Strategic Plan (HSSP). Provides overall policy advice and strategic coordination of the sector. Oversees the management of annual health sector budget process. Please describe how partners have provided support in preparation of the proposal: This proposal has extensively been developed and shared widely within the Ministry of Health institutional framework, discussed in detail at all levels and forums from the EPI technical meeting where immunization developmental partners attended and these included WHO, UNICEF, National Medical Stores, Sabin vaccine Institute, American Red Cross, Clinton Health Access Initiative (CHAI), USAID/MCHIP, PATH and CDC/AFNET. This was followed by a presentation to maternal and child health technical working group who approved for onward submission to the Senior Top Management and endorsed by HPAC an equivalent of ICC in Uganda where it was endorsed. At all opportunities the red only password was shared with the participants for their review prior to the meeting date and a power point presentation was made by the program during the meetings where an input was provided by all partners to enrich the proposal. 4.1.3. Signature Table for the Coordinating Committee for Immunisation We the members of the ICC, HSCC, or equivalent committee [1] met on the 04/09/2013 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 6 (please use the list for signatures in the section below). Please refer to Annex D of the Guidelines for more information on ICCs. Function Title / Organisation Name Please sign below to indicate the attendance at the meeting where the proposal was endorsed Please sign below to indicate the endorsement of the minutes where the proposal was discussed Chair MOH Dr Asuman Lukwango Secretary MOH Dr Barigye Members AMREF Abenet Berhanu Private Sector Dr Harold Bisase District Local Government Dr Driwale Alfred USAID/Uganda Karen Klimowski UPMB DR Tony Tuwesigye Belgian Embassy Wouter Cools Medical Bureau (FBO) Dr. Sam Orach World Bank Dr Peter Okwero MOF Juliet Kyokuhaire By submitting the proposal we confirm that the quorum has been met. Yes The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 7. 4.2. National Immunization Technical Advisory Group Has a NITAG been established in the country ? No

5. Immunisation Programme Data 5.1 Background information Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document. ▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 10. Please attach the cMYP costing tool as DOCUMENT NUMBER 11. ▪ Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12 ▪ Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate. Please use the most recent data available and specify the source and date. Figure Year Source Total population 34,131,400 2012 UBOS Statistical abstract June 2012 Infant mortality rate (per 1000) 54 2011 Uganda Demographic Health Survey 2011 (UDHS 2011) Surviving infants[1] 1,467,650 2012 UBOS GNI per capita (US$) 510 2011 World Bank 2011; http://data.worldbank.org/country/uganda Total Health Expenditure (THE) as a percentage of GDP 9 % 2011 World Bank General government expenditure on health (GGHE) as % of General government expenditure 12 % 2011 MOH Annual performance Report 2011 [1] Surviving infants = Infants surviving the first 12 months of life 5.1.1 Lessons learned Routine New Vaccines Support If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points or actions taken to address them. Please refer to previous Post Introduction Evaluations (PIE), if applicable. Lessons Learned Action Points Uganda has experience from the introduction of the Pentavalent in June 2002 and the HPV Demostration project 2008. Several lessons were learnt and these included: For pentavalent vaccine introduction - Low dose vial (1 or 2 doses per vial) reduces wastage but increases storage space and distribution costs. - New vaccine introduction requires adequate planning for cold chain capacity and /or review of the shipment planning. - Thorough assessment of cold chain capacity by level is very critical - Training is critical to prepare health workers for new vaccine introduction - New vaccine introduction required additional dry storage space for injection materials at national level due to inadequate storage space - Planning for waste management (Disposal of used vials and sharps) - Intensive social mobilization is required to prepare the Public for the uptake of new vaccines - The process requires to review and update monitoring tools - Adequate supply of the new vaccine is very important to meet the demand created at the introduction phase hence the need to use estimates by using the first dose and not third dose The cold chain system was expanded at peripheral level to address the gap - MoH earmarked funds for distribution of vaccines - The programme developed a training manual and conducted cascade training for Pentavalent vaccine - The programme reviewed and updated the monitoring tools. These updated materials were then disseminated to all health facilities and are beeing used. - The programme planned to expand the central vaccine store to cater for the increased volume of new vaccines. This has been included in the GAVI HSS support as part of the repgramming process. - Early social mobilization by use of political and cultural and religious leaders increased the uptake of the underutilized vaccine - Utilization of first dose of the proposed antigen if it is a multidose vaccine reduced a situation of having stock outs at a time which was not anticipated. Lessons learnt from the HPV vaccine demonstration project that was condcuted in 2 districts using cervarix provided an opportunity for improved implementations and these have been used during the process of scaling up to 12 additional districts where additional lessons will be learnt: These were learnt through a formative research 1. Formative research, which was done before the vaccinations, was very critical in identifying the key issues for HPV vaccine delivery such as delivery strategy elements, communication and advocacy strategy, training needs, identification of stakeholders, assessment of the health and education systems among others and these needed to be addressed before introduction. 2. Government endorsement for a new vaccine like HPV was very important for its acceptance and successful implementation at all levels. 3. Comprehensive and effective educational materials and community sensitisation create an enabling environment for acceptability. 4. Implementing the HPV vaccination project provided the opportunity to assess and strengthen health care systems such as the cold chain, knowledge and skills of health workers in vaccine management, data management and immunisation in general, and the CDP programme in particular. 5. Targeted training of persons involved in programme implementation is essential for programme success such as health workers, teachers, community leaders 6. Joint planning meetings promoted close collaboration between the departments of health and education and encouraged a cooperative environment during vaccination sessions. 7. Schools can be used as a venue for HPV vaccinations 8. Selecting girls for HPV vaccination based on their grade/class in school may be easier to implement than use of outreach or other routine immunization services 9. HPV vaccines can be integrated into the existing management and administration strategies used for routine immunisations 10.Adding HPV vaccine to an existing, funded health programme, such as Child Days Plus, can reduce recurrent programme costs 1. AN Assessment of communities’ needs regarding information on cervical cancer and HPV vaccines, vaccine delivery strategies that would be received well by parents and girls, and health systems’ capacities, including cold chain, transportation arrangements, and health worker availability, should be a part of preparation planning prior to HPV vaccine introduction. This has been addressed during the scale up to 12 additional districts and more lessons will be learnt that will be used during the nationwide introduction. 2. Early mobilization through involvement by political leaders such as HE the President of Uganda has raised awareness about the importance of acceptance of new vaccine introduction. 3. The Key messages to communities will build on positive previous experience with vaccines and emphasise the preventive nature of HPV vaccine in relation to cervical cancer. This has been done for the scale up phase to 12 additional districts. Community leaders will play an essential role in transmitting these messages. 4. Current capacities of health systems have been reviewed to leverage well-functioning aspects of the system and uncover any weaknesses that need to be strengthened. This has been done through the EVMA and Cold Chain Assessment. 5. All persons involved in programme implementation in particular health workers and teachers were trained on the basics of cervical cancer and HPV vaccination and programme components for the 12 districts, including data collection to fully understand the entire process of HPV vaccination. 6. Micro-planning exercises for programme implementation have been held jointly between schools and sub-county and district health authorities plus personnel involved in CDP programme to ensure smooth implementation of the programme. 7. Schools are considered as the primary location to find and vaccinate eligible girls. Back-up measures, such as mop-up sessions at HC II or HC III, are also available to cover for school absenteeism or non-attending girls. 8. In the context where it is difficult to establish the age of eligible girls, vaccinating girls by class (grade) has been considered, grade 4 with an estimate that there are more 10 year old in that grade. 9. The current vaccine supply, storage, management, and distribution system will be utilized to integrate HPV vaccine into the system at the district level in the 12 districts to also reduce the cost of vaccination programme. 5.1.2 Health planning and budgeting Please provide information on the planning and budgeting cycle in your country The Health Sector Strategic and Investment Plan (HSSIP) and the second National Health Policy cover the period 2010/11 - 2014/15 and 2010/11 – 2019/20 respectively. These define the medium and long term health agenda and operationalise the Republic of Uganda’s aspiration as outlined in the National Development Plan (NDP) of 2010/11 - 2014/15 and Public Investment Plan (PIP) 2010/11 – 2012/13. Annually, plans of action are developed by programs and aggregated into annual work plan for Ministry of Health. This also involves districts developing comprehensive work plans that feed into the national plan. The budgeting process is closely aligned with the work plan development and the planning cycle of the financial year that runs from July to June. Please indicate the name and date of the relevant planning document for health The following documents are relevant for Ministry of health during the planning process: 1) National Development plan (NDP) 2010/11-2014/15 2) The second National Health Policy (NHP) July 2010 3) Health Sector Strategic Investment plan (HSSIP) 2010/11-2014/15 4) Uganda Bureau of Statistics (UBOS) abstract June 2012 (which is released annually in June) 5) Uganda Demographic Health Survey (UDHS) 2011 6) WHO/UNICEF Joint Reporting Format (JRF) 2012 Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.) The cMYP has been updated in August 2013 to align it with the UBOS June 2012 abstract release, updated cMYP WHO guidelines May 2013 and the national documents as mentioned above namely the NDP, NHP, HSSIP, JRF and UDHS . Please indicate the national planning budgeting cycle for health Financial year from 1st July to 30th June Please indicate the national planning cycle for immunisation Financial year from 1st July to 30th June

5.1.3 Preparatory activities Please provide an outline of all preparatory activities for vaccine(s) introduction Uganda is planning to roll out HPV vaccination to the remaining 98 districts and will use the findings from the demonstration project including the 12 additional districts supported by MERCK to ensure a smooth introduction into the routine immunization program. The following activities will be implemented in preparation of the roll out of HPV to all districts: Key policy decisions have to be taken at the national mainly the burden of disease targeted for vaccine and all the cost and operational implications involved. Once GAVI has approved then the proposal will be presented to the National Coordination Committee to monitor the status of preparedness for the vaccine introduction The NCC has sub committees namely, Resource Mobilisation committee, Social Mobilisation committee, Micro Planning and Training, Cold Chain and Logistics committee and Surveillance, Monitoring and Evaluation and AEFI Committee. These committees are assigned different activities that are presented to the NCC. The preparatory activities for new vaccine introduction will be aligned with the core EPI components and support functions as highlighted below: There will be implemented prior to proposed date of vaccine introduction in April 2015: 1. Planning and coordination Strengthen and expand the existing national coordination committees including Ministry of Education and support them to conduct regular planning and coordination meetings Establish a National Immunization Technical Advisory Group committee Conduct monthly stake holders coordination meetings to review the status of implementation of an activity plan for new vaccine introduction Finalize, print and disseminate EPI policy documents e.g. the second EPI policy, EPI standards Implementation of the cold chain improvement plan 2. Logistics and cold chain: Conduct a Cold Chain Assessment for informed decisions on cold chain capacity and adequacy Forecast , procure cold chain equipment and logistics Develop a distribution plan for cold chain equipment and other EPI logistics Develop training manuals Conduct training at central and district level for cold chain technicians Conduct a vaccine freezing study Conduct an Effective Vaccine Management Assessment 3. Advocacy and communication: Roll out and advocacy and communication strategic plan Plan launching, social mobilization and advocacy plans Develop, Print and disseminate the IEC materials Organizing net work meetings with stakeholders and relevant government bodies to promote information sharing, joint micro planning sharing human and other resources in actual implementation of activities Advocacy with GOU to increase screening and treatment sites as indicated in the cervical cancer strategic plan to every health facility 4. Surveillance: Update the AEFI surveillance guidelines Update the Causality assessment protocol Support the functionality of the national AEFI task force Training of health workers on new vaccine surveillance Establish baseline data on intussusceptions Conduct a national cancer registry review Conduct an assessment of regional referral hospital to further expand the national rotavirus surveillance network 5. Training Develop training materials for new vaccine introduction conduct cascade training from national level to health facility level through regional and district levels 6. Monitoring and evaluation update monitoring tools to incorporate reporting requirements for HPV Build capacity at district level to ensure that regular Data quality assessments are conducted 7. Waste management Assess capacity at the operational level ability of proper and timely waste management - support districts to strengthen capacity for waste management 5.1.4 Gender and equity Please describe any barriers in access to immunisation services that are related to geographic, socio-economic and/or gender equity and actions taken to mitigate these barriers. Highlight where these issues are addressed in the vaccine introduction plan(s). Immunization in Uganda is implemented within the health system and there are barriers that affect access to services and hence cause equity problems. 1. Geographical barriers: these include hard to reach areas due to physical barriers e.g. eastern and south western region which are mountainous and hilly terrain coupled with poor road network. This has caused inequalities in distribution of human resources, in most cases qualified health workers will not be willing to work in these areas. The GOU has put in place strategies to address this gap which include: Attain and retain the right Human Resouces for Health numbers and skills mix in the health sector through advocacy for annual increases in recruitment to increase the proportion of skilled positions in order to improve quality health services delivery in those areas. The Uganda Parliamentarian Immunization Forum is spearheading this activity; Use evidence to advocate for appropriate remuneration of health workers; Provide decent and safe accommodation for health workers at health facilities especially in hard to reach areas through GAVI HSS; some local governments have put in place a mechanism provide incentive schemes for attraction and retention of health workers in hard-to-reach areas while addressing the gender and human rights aspects 2. Socio economic barriers: According to the 2007 household survey, there remains a significant inequality in access to health care. These inequalities occur due to differences in socio-economic status and geographical location. Twenty eight percent (28%) of the households in Uganda are experiencing catastrophic payments. The incidence of catastrophic health expenditure ranges from 24.8% in the richest quintile to 28.3% in the poorest quintile and between 23.4% in the eastern region and 38.1% in the western region. One of the key objectives of the National Development Plan is to increase household incomes and promotion of equity through working to reduce catastrophic health expenditures by households 3. Gender barriers: these include level of education and marriage status in decision making which is critical for immunization. The UDHS shows that about 53 percent of the women mainly decide by themselves how their earnings are to be spent, 32% report that they make the decision jointly with their husband/partner; while 13 percent report that the decision is mainly made by their husband/partner. There are variations in the proportion of women who make independent decisions about their earnings ranging from 24% in Eastern region to 79% in Kampala. This shows that women in urban areas are more likely to make independent decisions compared to those in rural areas. The strategies put in place to address these barriers include free education for all with an additional entry point in higher institution for girls, Coordination with Civil Society Organizations (CSOs), (including women centered organizations) especially those working in the area of health consumer rights such as Uganda National Health Consumers’ Organization to build awareness among individuals and communities about their rights and responsibilities. Related to NV introduction the following approaches will be utilized in line with what has been mentioned above: 1. Utilization of Civil Society Organizations (CSOs) in the identified areas 2. Utilization of Ministry of Education (MOE) to ensure that messages are sent to homes where children are denied free education 3. Extra financial support for hard to reach areas by provision of hardship allowances through government funding Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s). Immunization in Uganda is implemented within the health system and there are barriers that affect access to services and hence cause equity problems. 1. Geographical barriers: these include hard to reach areas due to physical barriers e.g. eastern and south western region which are mountainous and hilly terrain coupled with poor road network. This has caused inequalities in distribution of human resources, in most cases qualified health workers will not be willing to work in these areas. The GOU has put in place strategies to address this gap which include: Attain and retain the right HRH numbers and skills mix in the health sector through advocacy for annual increases in recruitment to increase the proportion of skilled positions in order to improve quality health services delivery in those areas. The Uganda Parliamentarian Immunization Forum is spearheading this activity; Use evidence to advocate for appropriate remuneration of health workers; Provide decent and safe accommodation for health workers at health facilities especially in hard to reach areas through GAVI HSS; some local governments have put in place a mechanism provide incentive schemes for attraction and retention of health workers in hard-to-reach areas while addressing the gender and human rights aspects 2. Socio economic barriers: According to the 2007 household survey, there remains a significant inequality in access to health care. These inequalities occur due to differences in socio-economic status and geographical location. Twenty eight percent (28%) of the households in Uganda are experiencing catastrophic payments. The incidence of catastrophic health expenditure ranges from 24.8% in the richest quintile to 28.3% in the poorest quintile and between 23.4% in the eastern region and 38.1% in the western region. One of the key objectives of the National Development Plan is to increase household incomes and promotion of equity through working to reduce catastrophic health expenditures by households 3. Gender barriers: these include level of education and marriage status in decision making which is critical for immunization. The UDHS shows that about 53 percent of the women mainly decide by themselves how their earnings are to be spent, 32% report that they make the decision jointly with their husband/partner; while 13 percent report that the decision is mainly made by their husband/partner. There are variations in the proportion of women who make independent decisions about their earnings ranging from 24% in Eastern region to 79% in Kampala. This shows that women in urban areas are more likely to make independent decisions compared to those in rural areas. The strategies put in place to address these barriers include free education for all with an additional entry point in higher institution for girls, Coordination with CSOs, (including women centered organizations) especially those working in the area of health consumer rights such as Uganda National Health Consumers’ Organization to build awareness among individuals and communities about their rights and responsibilities. Related to NV introduction the following approaches will be utilized as earlier mentioned above with a focus on increasing community demand for new vaccine and addressing all concerns /rumours related to HPV namely: 1) Updated country Multi Year Plan (cMYP), 2012-2016 which addresses the short term and medium term program priorities and this program document is to be used as a resource mobilization tool with allocation of more resources to hard to reach areas<?xml:namespace prefix = o /> (2) Two Year UNEPI revitalization plan derived from the cMYP addresses priority interventions to revamp the immunization performance in the country. It focuses on major priorities and activities to solve cited problems in various program assessments and is to be used as a resource mobilization tool (3) EPI annual work plan developed with focus on priority interventions for immunization and monitored at all levels of implementation and all levels of MOH (4) National Communication Strategy for Routine Immunization was developed and is being rolled out to all districts . This is targeting to reduce the disparities in social and economic barriers and improve access and utilization for immunization (5) The MOH has a Recruitment and Enhancement plan to cater for human resource in the health institutions target a coverage of greater than 65% staffing. Since 2013 it is being implemented and recruitment is on going to cover the disparity in Human Resource (6) A national RED approach rollout by MOH and Health development Partners to ensure Routine Immunization Strengthening (7) HPV vaccination will target female pupils of primary schools in Primary 4 class (who in most cases are usually 10 year olds) while for the out of school the target age will be girls aged 10 year olds for girls (in the community). HPV vaccination will not cover males of the similar age group due to the associated costs of vaccination and lack of evidence based disease burden of HPV infection in males. Also the communication strategy takes into account the gender roles and responsibilities and gender structure within the community. Therefore, gender specific strategies using appropriate channels to reach both females and males have been designed as part of the communication strategy (8) Utilization of CSOs in the identified areas Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems. Effective January 2012, Ministry of Health through Health Management Information System (HMIS) tools (tally sheets, monthly reports and electronic database) disaggregated data by gender including immunization data. Previously there has been no sex disaggregation for routine immunization data. Is the country currently in a situation of fragility (eg. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities. In 2013, Uganda faced an influx of refugees and some districts were affected by floods especially in the western part of the country. The total number of refugees arriving in Uganda from DRC is 67,000. The refugees are being received temporarily in a transit camp in Bundibugyo in Bubukwanga settlement. Some of the refugees are still managing on their own outside the camp or others are being housed by relatives and friends. The conflict situation in Congo is not yet settled and could became volatile in the near future. This could result in a new influx of refugees to South West Uganda. It is difficult to predict how the conflict will unfold but if it continues Uganda is likely to receive more girls that will create more demand for HPV vaccination in addition to other routine antigens for children below 1 year of age. This in return will affect the denominator used for vaccine estimates and hence shoratges. However during the distribution of the vaccine to the affected districts this will be taken into account by increasing their denominator by 10%. Probably this increase will be covered by the buffer stock indicated in the forecasting tool and hence the country may not face any serious vaccine shortages. 5.1.5 Data quality Please attach a data quality assessment report, if one has been completed within the previous 36 months (DOCUMENT NUMBER : 13). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER : 14, DOCUMENT NUMBER : 15).

5.1.6 HPV specific facts Please demonstrate country’s ability to deliver a complete multi-dose series of vaccines to at least 50% of the target vaccination cohort in an average size district using a similar strategy to the one proposed for HPV vaccine delivery. For each district, fill-in: District Information Name of the district Nakasongola Size of population of the district 156,500 Describe how the district is divided into rural and urban areas: The district covers an area of 4,909 sq.KM and has a 3 Counties, 9 Subcounties and 1 Town council. The population is mainily rural 99% and urban 1%. District Information Name of the district Ibanda Size of population of the district 255,100 Describe how the district is divided into rural and urban areas: The district covers an area of 967 sq.KM and has 1 County with 7 Sub-counties and 3 town councils. The population is mainily rural 99% and urban 1%. District Information Name of the district Bududa Size of population of the district 180,600 Describe how the district is divided into rural and urban areas: The district covers an area of and has 1 county with 16 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Busia Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 1 county with 10 sub counties and one town coucil. The population is mainly rural 83% and urban 17% District Information Name of the district Isingiro Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 3 counties with 18 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Kamwenge Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 2 counties with 14 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Katakwi Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 2 counties with 9 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Kayunga Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 3 counties with 9 sub counties and one town coucil. The population is mainly rural 93.3% and urban 6.7% District Information Name of the district Mityana Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 2 counties with 15 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Nebbi Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 1 county with 16 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Oyam Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 2 counties with 12 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Rukungiriri Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 3 counties with 11 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Ntungamo Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 4 counties with 18 sub counties and one town coucil. The population is mainly rural99% and urban 1% District Information Name of the district Lira Size of population of the district Describe how the district is divided into rural and urban areas: The district covers an area of and has 3 counties with 13 sub counties and one town coucil. The population is mainly rural99% and urban 1% Please specify what was the multi-dose vaccine used (HPV/TT/others)? What was the vaccination schedule? The HPV demonstration project districts of Nakasongola and Ibanda (2 districts) used the single dose HPV Bivalent (Cervarix) vaccine that followed the schedule of 0, 1 month and 6 months from 1st dose. <?xml:namespace prefix = o /> Under phase I, in addition to the 2 demonstration project districts, 12 new districts were selected basing on the performance of routine immunization using the RED approach (poor performers and good performers) and prevalence of HIV among adolescents as a proxy for STD/HPV). The actual vaccination for the first dose started in September 2012 and second dose in November 2012. However giving the third dose had challenges with vaccine shortages due to delayed shipment by national level to sub national level following challenges in logistics management. For the districts of Bududa, Busia, Kayunga, Katakwi, Isingiro, Kamwenge, Mityana, Nebbi, Oyam, Lira, Rukungiriri and Ntungamo (12 districts) Gardasil vaccine was used that followed the schedule of 0, 2 months and 6 months from the first dose. Describe the vaccination strategy used (school based, health centre based, mixed)? How was it carried out, who carried it out, who was the lead department/agency? What age/sex was the multi-dose vaccine delivered to? If it was school based, how many schools were targeted? Was it age based or grade based? The Strategy used in the HPV demonstration project in the two districts (Ibanda and Nakasongola) : HPV demonstration vaccination projects: This was conducted in 2008 and 2009 in two Districts Ibanda and Nakasongola . The target population was in-school girls and out of school girls. Two different vaccine delivery strategies were identified from the results of formative research, which suggested that schools could be a viable venue to reach the target age group Ibanda district: The district used school-based grade/class selection strategy and selection of girls was by grade/class (primary 5) and 10 years old girls who were out of school. Nakasongola district: The district used integration strategy where HPV vaccine was delivered during Child Day’s Plus of April and October for the 1st and 3rd dose. The 2nd dose of HPV was delivered through routine immunization services as a stand alone outside Child Day's plus months. In both of the districts, for out of school girls they were vaccinated through either through community outreaches or at health facilities. Bridging phase (Hybrid strategy): The bridging phase was a period of implementation so as to guide the government to make decisions about HPV vaccine introduction in the country. In this period additional lessons were learnt through using a mix of methods in delivering the HPV vaccinations to the target population in the two districts, thereby referred to as “hybrid vaccine delivery strategy”. In 2010 Uganda received an additional donation of vaccines to implement the hybrid strategy. This approach was conducted during Child Days Plus in April and October plus a standalone month and Selection of girls by grade or class. All girls in primary 4 were vaccinated. The hybrid strategy involved selecting girls for vaccination based on grade/class (because this was much more feasible) and vaccinating them during child days plus in an integrated manner (because this was cost effective). These were the major recommendations from the PATH demonstration project report. Methods: For in school girls, they were vaccinated from schools during Integrated Child Health Days Plus (CDP) months (April and October) for 1st and 3rd dose vaccination. The CDP months are a period of accelerated child survival package delivery in the districts. The 2nd dose was delivered as standalone school visit program. For out of school girls, they were vaccinated through community outreach and at health facilities. The vaccination was conducted by trained health workers in the districts. Implementation: The implementers were: MOH/UNEPI/PATH/District Local Government The lead department was: Ministry of Health-Uganda National Expanded Program on Immunization (UNEPI) and PATH. Age/Sex: Primary 4 pupils in schools and 10 years old Female if out of school No. of Schools targeted (2010 data): 225 primary schools (Nakasongola) 256 primary schools (Ibanda) Vaccinating by age or grade: Vaccination was by age during outreach and by grade from primary schools. The scale up approach in 14 districts following a donation of Gardasil vaccine from MERCK, the hybrid strategy was used. It involved selection of girls by class (girls in primary 4 irrespective of age) and while carrying out vaccinations for girls out of school (10 year old after screening by health workers) during child days plus activities or any outreach/static routine immunization activities conducted for the under one year old. It was referred to as a hybrid strategy because it resulted from a combination of two demonstration vaccine delivery strategies from the two districts mentioned above. All vaccination doses were completed within one calendar year to minimize lost to follow up. What was the number of targeted population? What was the number in target population who started the multi-dose series? What was the number in the target population who received all doses The following table summarizes the coverage by district for the 14 districts that have implemented HPV vaccination in 2012, the most recent data<?xml:namespace prefix = o /> No District Targeted population Number of girls who received 3 doses 1 Nakasongola 1,923 1,637 (85.1%) 2 Ibanda 2,835 2,448 (86.3%) 3 Bududa 2869 1455 (51%) 4 Busia 4779 3646 (76%) 5 Isingiro 6744 2057 (31%) 6 Kamwenge 5357 1503 (28%) 7 Katakwi 2804 1308 (47%) 8 Kayunga 5806 4397 (76%) 9 Mityana 5063 3683 (73%) 10 Nebbi 5572 1303 (23%) 11 Oyam 6047 4521 (75%) 12 Rukungiriri 5225 3783 (72%) 13 Lira 14 Ntungamo Please provide the source of data for estimation of the target population: For demonstration project<?xml:namespace prefix = o /> Gathering information from census and school registers to estimate the total population of girls eligible for vaccinations was done in each district for each year of implementation. Ibanda estimated the number of girls enrolled or attending primary grade five in addition to those who might not be attending school but were ten years of age. In Nakasongola for the first year of implementation, the national census was used to estimate the possible number of ten-year-old girls who would be eligible for vaccination, according to the strategy. Based on the process and results from estimating the eligible population in the first year, Nakasongola embarked on a headcount of girls who might be ten years of age and thus eligible for vaccinations prior to implementing the second year. For scale up project: Using the demonstration project, girls in Primary 4 were estimated to be on average 10 years old and represent 1.6% of the total population. Therefore the estimates in the 12 districts used this proportion to estimate girls aged 10 years. If applicable, please detail what additional people beside the target population also received the vaccine: NONE received the vaccine. Table 5.1.6: (Please refer to WHO/UNICEF JRF) Girl age HPV 1st dose HPV 2st dose HPV 3st dose 9 years old 5,352 3,890 1,742 10 year old 17,483 11,487 5,225 11 year old 14,253 11,802 5,717 12 year old 21,497 16,594 7,007 13 year old 12,895 11,045 6,126 14 year old 6,303 5,961 3,130 15+ year old 2,106 2,296 1,132 Unknown 0 0 0 Was there an evaluation of the ‘project’? If so, who performed it? Please provide a short summary of the evaluation methodology and/or provide the evaluation report if available (Document number No: 16). Refer to section 10. Attachments An evaluation of the HPV demonstration project was conducted in 2010 as follows: a) The coverage survey was done by PATH. b) The Acceptability and Feasibility assessment was conducted by Makerere University Child Health Development Centre (CHDC) c) Formative research results from the HPV vaccines: Evidence for Impact project Methodology of evaluation: i) The PATH coverage survey used the WHO cluster probability proportionate to size survey method. A quantitative questionnaire was used also to evaluate the acceptability of the vaccine and this was administered as part of the coverage survey. ii)The Makerere University Acceptability and Feasibility evaluation used Qualitative Focus Group discussions and Individual Interviews. The Evaluation of the HPV introduction in Uganda found that people in diverse Contexts are supportive of action to address cervical cancer, in spite of concerns and obstacles that will need to be addressed. The strategies tested in Uganda’s demonstration project included: Uganda’s HPV vaccine delivery strategy: The strategy explores two possible strategies for introduction and delivery of the HPV vaccine: Offer vaccine as part of Child Days Plus (a semiannual event in Uganda designed to reach all children with a package of health services). Vaccinate girls at school through a “stand-alone” strategy, with special efforts to reach out-of school girls. Select targeting strategy for girls (by age or by grade in school) and generate accurate target population estimates to ensure adequate quantities of the vaccines and other supplies. Ensure systematic and early communication within the Ministry of Health and among it and the districts, the education sector, and key financial planning bodies. Address gaps in cold chain and logistics capacity, in part by involving the national immunization unit at every stage of assessment and planning. Monitor HPV vaccination coverage as part of Uganda’s current system for immunization tracking, and respond promptly and appropriately to adverse events following vaccination. Uganda’s HPV vaccine communications strategy: key elements Disseminate accurate information to address currently low levels of knowledge about cervical cancer, HPV, and the HPV vaccine, using local terms and languages. Develop messages that build on positive perceptions of vaccination and recent successes in reducing the burden of common childhood diseases. Raise awareness about vaccination safety measures, including training health workers to administer the vaccine and manage side effects at schools and other sites. Promote understanding that the HPV vaccine has been proven safe and effective in extensive, international clinical trials and is already being provided in many countries. Publicize endorsement of HPV vaccination by the Uganda Ministry of Health, health workers, education officials, and other national, district, and community leaders. Reach out to “decision-makers” at all levels, as everyone from children to national political leaders may play a role in deciding whether a child is vaccinated. Uganda’s HPV vaccine advocacy strategy: key elements Develop policy guidelines that set national standards for HPV vaccination, and integrate these into an existing policy. Partner with the Ministry of Health to generate momentum and leadership from other key ministries and stakeholders at the national level. Engage and mobilize district officials and others responsible for implementation. Make information available to policymakers—including through the media—on the seriousness of cervical cancer, the vaccine’s properties, usefulness, cost, and potential economic benefits. Explain how HPV vaccination is consistent with Uganda’s health priorities. This research was conducted by the Child Health and Development Centre (CHDC), Faculty of Medicine, Makerere University, in collaboration with the Association of Obstetricians and Gynecologists of Uganda (AOGU), with technical and financial support from PATH.

5.2. Baseline and Annual Targets (NVS Routine Support) Please refer to cMYP pages to assist in filling-in this section. Number Base Year Baseline and Targets Baseline and Targets 2012 2015 2016 Total births 1,655,373 1,819,428 1,877,650 Total infants’ deaths 187,723 98,249 101,393 Total surviving infants 1,467,650 1,721,179 1,776,257 Total pregnant women 1,706,570 1,819,428 1,877,650 Target population vaccinated with BCG 1,349,713 1,728,456 1,783,767 BCG coverage 82 % 95 % 95 % Target population vaccinated with OPV3 OPV3 coverage 82 % 90 % 90 % Number of infants vaccinated (to be vaccinated) with DTP1 1,303,272 1,686,755 1,740,731 Number of infants vaccinated (to be vaccinated) with DTP3 1,149,656 1,549,061 1,598,631 DTP3 coverage 78 % 90 % 90 % Wastage[1] rate in base-year and planned thereafter (%) for DTP 10 10 10 Wastage[1] factor in base-year and planned thereafter for DTP 1.11 1.11 1.11 Number of girls in the target cohort 68263 618980 851718 Target population vaccinated with 1st dose of HPV quadrivalent 62,221 557,083 783,581 Target population vaccinated with 3rd dose of HPV quadrivalent 50,879 495,185 698,409 HPV quadrivalent coverage 1st dose 75 % 80 % 82 % HPV quadrivalent coverage 3st dose 91 % 90 % 92 % First Presentation: HPV quadrivalent, 1 dose(s) per vial, LIQUID Wastage[1] rate in base-year and planned thereafter (%) {0} 5 5 5 Wastage[1] factor in base-year and planned thereafter (%) 1.05 1.05 1.05 Maximum wastage rate value for HPV quadrivalent, 1 dose(s) per vial, LIQUID 5 % 5 % 5 % Number of infants vaccinated (to be vaccinated) with 1st dose of TT+ 834,239 1,273,599 1,502,120 TT+ coverage 49 % 70 % 80 % Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100 12 % 8 % 8 % [1] Number of infants vaccinated out of total births [2] Number of infants vaccinated out of total surviving infants [3] Indicate total number of children vaccinated with either DTP alone or combined [4] Number of pregnant women vaccinated with TT+ out of total pregnant women [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period. 5.2.1 HPV specific targets Single year cohort of girls to be vaccinated with HPV should be within the WHO-recommended target population of 9-13 years old girls Please specify the source of data that was used to estimate the number of girls in target and reported in the above table under “Target population vaccinated with HPV“ The girls to be vaccinated are: 1) School pupils in primary 4 and the estimated age of these girls is 10 years based on the HPV demostration project as described above in section 5.1.6. 2) For the out of school girls the target age will be 10 years screened by the health workers. The source of this data is the Uganda Bureau of Statistics using population projection of the national population census which was last conducted in 2002. The next national population and housing census is scheduled for 2014.

5.3. Baseline and Annual Targets for Preventive Campaign(s) No NVS Prevention Campaign Support this year

6. New and Under-Used Vaccines (NVS Routine) 6.1. Assessment of burden of relevant diseases (if available) Disease Title of the assessment Date Results Human Papilloma Virus WHO/ICO HPV information centre, summary report update September 15, 2010 This report estimates that every year 3577 women are diagnosed with cervical cancer and 2464 die from the disease with projected number of new cancer casesa and deaths by 2025 being 6407 and 4281 respectively. Cervical cancer ranks as the 1st most frequent cancer among women in Uganda, and the 2nd most frequent cancer among women between 15 and 44 years of age. The report also estimated the prevalence (%) of HPV 16 and/or HPV 18 among women with cervical cancer is 74.1 while the crude incidence rate per 100,000 women is 22.6. Human Papilloma virus Clinical report 2006 Katahoire et al further observed that 35% (484/1400) of patients seen in the gynecology out patients in Mulago national referral hospital had suspected cervical cancer. Deaths due to cervical cancer of the total gynecological deaths were at 70%. Results: Three hundred and eighty (380) of 1,275 (29.8%) women were followed up for a median time of 18.5 months (inter-quartile range 9.7-26.6). Sixty-nine (69) women had incident HPV infections during 226 person-years of follow-up reflecting an incidence rate of 30.5 per 100 person-years. Incident HPV infections were marginally associated with HIV positivity (RR = 2.8, 95% CI: 0.9 - 8.3). Clearance for HPV type-specific infections was frequent ranging between 42.3% and 100.0% for high- and 50% and 100% for low-risk types. Only 31.2% of women cleared all their infections. Clearance was associated with HIV negativity (Adjusted clearance = 0.2, 95% CI: 0.1 - 0.7) but not with age at study entry, lifetime number of sexual partners and multiplicity of infections. The prevalence of low-grade squamous intraepithelial lesions (LSILs) was 53/365 (14.5%). None of the women had a high-grade cervical lesion (HSIL) or cancer. Twenty-two (22) of 150 (14.7%) HPV negative women at baseline developed incident LSIL during follow-up. The risk for LSIL appeared to be elevated among women with HPV 18-related types compared to women not infected with those types (RR = 3.5, 95% CI: 1.0 - 11.8). Conclusions: Incident HPV infections and type-specific HPV clearance were frequent among our study population of young women. These results underscore the need to vaccinate pre-adolescent girls before initiation of sexual activity. 6.1.1 HPV burden specific information Has the country undertaken an assessment of the burden of cervical cancer? If so, describe the burden, and when and how the assessment was done. If not, countries may report on Globocan data (available on the WHO HPV information Centre website at http://www.who.int/hpvcentre/en). Cervical cancer is the most common reproductive health cancer among women in Uganda accounting for up to 40% of all cancers recorded in the Kampala cancer registry as well as for 80% of all female malignancies. By the time of diagnosis up to 90% of cervical cancers are inoperable. Clinical reports from 2006 indicated that cases of cervical cancer occupied up to 30% of gynaecological beds at Mulago Hospital. However, this trend is increasing: a study funded by PATH and carried out by the Child Health and Development Centre (Makerere University) in April 2007 showed the bed occupancy for cervical cancer to be at 63.5%. In 2006, about 40% of all female patients receiving radiotherapy had cervical cancer (Wabinga, et al 2000). However, cancer cases recorded in the hospitals are just a tip of an iceberg. Cancer patients are stigmatized in society. They often do not go to health facilities, but stay home and die painfully. The Globocan data described current burden of invasive cervical cancer in Uganda as follows Crude incidence rate per 100,000 women at 22.6 Age-standardized incidence rate at 47.5 Cumulative risk (%). Ages 0-74 years at 5.2 Annual number of new cancer cases 3577. According to the cancer registry for the period of 1998 -2002 in Kyandondo County, there were 649 cases of cancer of the cervix with a crude rate per 100,000 women at 16.4 and the age standardized rate of 45.8. Describe the existing cervical cancer prevention and control activities. Uganda has a strategic plan for cervical cancer prevention and control 2010-2014 that clearly stipulates the key activities to implement by the districts to address the core objective of prevention and control. In continum of the present strategic plan the MOH is in process of updating and developing the next 5 year strategic plan. The core interventions for prevention and control of cervical cancer indicated in the strategic plan include efforts to prevent HPV infection through HPV vaccination of girls 10–14 years old, for primary prevention, and use of feasible cervical screening and pre-cancer treatment modalities, namely visual inspection with acetic acid and cryotherapy, visual inspection with lugol's iodine and conventional PAP smears for secondary prevention of cervical cancer amongst women ages 25–49 years. However, these services are available in very few health centres in Uganda, contributing to low screening rates and unequal distribution of services in the country. Research is ongoing to determine a system that will work best, and be cost effective, accessible, and affordable. However, there is insufficient funding for establishing and maintaining screening and treatment facilities for cervical cancerous lesions at levels of health care. Has the country developed a roadmap or strategy for establishing or strengthening a national comprehensive approach to cervical cancer prevention and control? Yes If Yes, please attach and refer to section 10. Attachments. (Document N°17) If No, are there plans for the country to develop such a roadmap or strategy in the future? Please describe- when, who will be leading the development of the plan, and which agencies will be involved. Not Applicable 6.1.2 Delivery strategy for HPV vaccine Please specify the chosen age cohort for HPV vaccination: 10 years old Please describe the HPV vaccination strategy and plan (when vaccinations will be scheduled, who will do vaccinations, how will the vaccine logistics be assured, coordination between the schools and health personnel, the plan to ensure all three doses are delivered, and plans for reaching girls who may be absent on the day of scheduled vaccinations, etc.) The HPV vaccination of eligible girls will be conducted during the Child Days plus (CDP) in the months of April and October and a standalone vaccination for the second dose which is not coinciding with the CDP days. The target age group will be girls who are at least 10 years old through Primary 4 or through community outreach of non-scholl attendees 10 years. Schools will be used as the primary venue for HPV vaccination in the country. Delivering HPV vaccinations in primary schools was found a successful strategy during the demonstration project, since more than 85% of girls are attending school this will enable reaching high coverage. The eligible girls who are not attending school will be targeted through pre-planned monthly community outreaches or at health facilities where routine immunization is provided on a daily basis. Screening of all girls aged 10 years will be done by the health workers. At the district level, planning for HPV vaccination is multi-sectoral including Health and Education department including other stakeholders. Each health facility will map out schools in its catchment area and make a schedule with the respective schools. Teachers and health workers will participate in the process of planning and actual administration of HPV vaccine. Teachers will be responsible for registering all eligible girls in schools and mobilization, follow up of missed girls and also report any girls who would have missed attending a class sessions after vaccination as possible Adverse Event Following Immunisation (AEFI) monitoring. The health workers will be responsible for the delivery of vaccines and actual vaccination of the girls. The girls not attending school will be vaccinated by the health workers during planned community outreaches and these girls will be mobilised by the existing community mobilizers. Health workers and teachers, and others involved in the vaccinations will be urged to inform the vaccinated girls when and where they should receive their subsequent doses and the importance of completing the 3 vaccination doses. The MOH through Uganda National Expanded Program (UNEPI) on Immunisation will be responsible for forecasting, ordering and national distribution of vaccines. The amount of vaccine for the HPV vaccination will be estimated according to the size of the target population which is 1.6% of the total population determined by the Uganda Bureau of Statistics (UBOS). Each district will receive an additional 5% vaccine supply to account for possible vaccine wastage. However during the training sessions emphasis will be placed on minimizing vaccine wastage. The implementation of the HPV program is coordinated by MOH and Ministry Of Education; both constitute the national technical working groups. At district level the District Health Office (DHO) will work with the District Education Office (DEO) to plan and conduct training of health workers and teachers to deliver the vaccination. The target group for the HPV vaccine introduction will be girls who are at least 10 years of age and not yet sexually active. The HPV demonstration project showed that majority of the 10 year old girls are in Primary 4. Also the Ministry of Education policy recommends the starting age of Primary 1 at 6 years and therefore majority of the girls in Primary 4 will be 10 years old. The Universal Primary Education (UPE) has enabled majority of the girls to attend school. The HPV vaccination will therefore target girls who are in Primary 4 (P.4) for those found at school or 10 year old girls who are not attending school and are in the community. Irrespective of the strategy, provide a description of existing health services and/or health education currently being provided to young adolescents (both girls and/or boys) within the 9-13 year old age group: a. For health services (this can include: what health services are provided, to which age/sex group, whether it’s mandatory or voluntary, regularly or ad-hoc, in school or out of school, who provides these (government, NGOs), how often, what is the uptake in the community, how is it perceived by the community.) The school health program ensures that school children and staff are healthy and creates an environment conducive for learning, growth and development of children. The 2008 School Health Policy is under review and adolescent health is among the priorities. The school health manuals in accordance with the existing policy had been developed and distributed to all schools. The new Policy covers public and private schools, from early childhood development centrs up to secondary and technical schools, and clearly defines the roles of various ministries, parents, students and other stakeholders. The main responsibilities are with the Ministry of Education and Sports, including the implementation of the Health Promoting School Initiative (HPSI) by the teachers, recruitment and employment of school health nurses –and the establishment of basic health and nutrition services through these nurses-, the construction of toilets and pit latrines etc. However, in the absence of school health nurses, health centre staff provides both curative services (at health centres) and promotive and preventive services, including immunization (at schools). The School Health Program initially employed in schools to teach on sexual and reproductive health by health care providers declined over years. There were efforts by Ministry of Education and Sports to integrate Adolescent Sexual Reproductive Health (ASRH) into the main stream curriculum. This intervention was piloted in 5 primary schools of 5 districts but required to be rolled out in the whole country through the Pre-service training. The Education Sector is one of the key sectors promoting Health for All (HFA) by promoting life-long healthy lifestyles. The Government of Uganda through the Ministry of Education and Sports and other Development partners has continued to invest heavily in a number of components of school health programme designed to improve adolescent growth, personal hygiene, nutrition, water and sanitation and HIV/AIDS amongst others. In 2011, Uganda developed a National adolescent health strategic plan of 2011-2015 to improve the health services of the adolescents using experiences from the two innovations mentioned above. The services are voluntary however there is a deliberate effort to sensitize all adolescents to ensure equity in access and utilization of services. The plan describes outputs and activities to be implemented at national, district and community levels in order to meet the strategic objectives with a focus on the following priority areas: 1. Policy and legal framework with the main purpose of advocacy to influence legislation, policies, program and strategies to promote adolescent health and development 2. Coordination, networking and partnerships 3. School Health 4. Adolescent Friendly Services 5. Sexual Abuse and gender based violence 6. Psychosocial services for Adolescents 7. STI/HIV/AIDS and Adolescents 8. Harmful traditional/cultural practices 9. Advocacy, Research, Monitoring and Evaluation 10. Capacity building for adolescent health program and services. At the community health education is conducted by the health workers from the catchment health facilities in conjunction with the Village Health Teams. Community health education is scheduled with the community. b. For health education (this can include: the topic, whether it is national, sub-national, in school or out of school, who provides the education, how often, is it in the school curriculum, are there NGOs providing these? How is it perceived by the community? Has there been an evaluation and if so, how was it evaluated and what were the findings?) Health education/ promotion will operate at the sub-national level both at the school; through inclusion in curriculum and a component in teacher training; and out of school at the household level; through Village Health Teams (VHTs), Scouts / Girl guides, Local Councils (LC1s), and mass media. Although mothers are the primary target at household level, recent research and experiences have shown that there are structural barriers to women’s decision making. Hence, the household will be further segmented to include other decision makers; such as mothers, husbands/fathers, grandparents, aunties, mother in laws and father-in-laws. Please describe the communications plan for HPV vaccination strategy (what activities will be done to educate and raise awareness of the vaccination plan to the target population, their parents/guardians, the wider community, community leaders, groups of influence, etc; who will provide this education and what materials will be used; how often will these activities occur vis-a-vis the proposed vaccination schedule.) In order to achieve the communication and behavioral objectives, a three pronged Communication for Development approach with three main strategies will be used, namely 1. Programme Communication 2. Social mobilization 3. Advocacy 1. Programme Communication Health promotion will target the specific behavioral barriers at the school and family/household level and create awareness through the following interventions: IPC through IEC materials The teachers (in school) and the VHTs (out of school) will have the main responsibility for IPC using IEC packages (including school curriculum). The IEC packages will include pictorial cards and informative leaflets covering important aspects of Immunization; IEC materials in addition to being used in school counseling for girls and individual and group counseling for parents and guardians, can also be used for training purposes. Information materials will also be developed for promotional activities conducted by health workers, VHTs, Scouts/Girl Guides and other volunteers. Mass Media: Mass Media will be used to make Public Service Announcements (PSA) by government agencies. These are very important in keeping messages in public eyes. Short spots, PSA and jingles to promote the vaccine will be developed for airing on radio and TV. PSA messages will create awareness and understanding regarding importance of HPV vaccine. Involvement of goodwill ambassadors: The involvement of goodwill ambassadors for promotion of social causes has been found very effective and bears positive results the world over. Well-known and popular personalities and media stars possess charisma and charm that is needed to add visibility and credibility to the cause. In a bid to make the new vaccine communication more persuasive and relevant to the target audiences, a panel of goodwill ambassadors belonging to different walks of life (sports stars, media celebrities, religious leaders and doctors) will be selected in consultation with partners to promote new vaccine. Programme Communication Activities: · Training / Orientation of teachers and VHTs on key messages for immunization · Awareness raising through school sessions for the girls. · Individual/Group counseling sessions for parents. · Awareness raising through Public Service Announcements, TV, talk shows, Radio spots/jingles, DJ mentions, children’s voices and testimonies. · Dissemination of messages in newspapers through articles and strip adverts. · Sensitization sessions with Goodwill Ambassadors · Promotional visits by Goodwill Ambassador with communities 2. Social mobilization; with specific focus on hard to reach Social mobilizationwill operate at the district, sub district and village level. In addition to parents, it will target local politicians, religious leaders, traditional leaders, opinion leaders, community groups, and teachers. Social mobilization is not only crucial for sustainable behavioral change, it is also an effective strategy for community empowerment and participation. It will create awareness and seek to change people’s behavior at village level and will entail the following activities: Formation of Alliances/Support Groups The District Health Management Team (DHMT) with the help of local volunteers (teachers/health-workers) will be responsible for forming support groups at the community level, to advocate and participate in program activities. The support groups will include local religious leaders, health workers, teachers, NGO/CBO representatives. These support groups will provide an excellent venue for imparting knowledge on new vaccine. These groups will meet on a regular basis and plan how to provide solutions with mutual understanding and sharing of experience. Community Based Participatory Activities: Activities will be organized and supervised by DHMTs. IPC through the VHTs supported byIEC materials will be the main channels of communication for these activities. Informative/educational materials will be designed and developed for various members of the support groups. The materials developed for traditional and religious leaders will be designed to directly address any cultural constraints and false religious beliefs, and will be in the form of fact sheets and videos. The teachers will be involved in school based interactive/informative activities for promotion of the new vaccine in schools by actively involving school children. Social Mobilization Activities: · Community sessions and dialogue/group discussions with various target groups organized by DHMTs/DHE · Alliances formed with community leaders, NGOs, religious/cultural leaders · Community based media activities; music, dance and drama performances as well as puppet shows. · Establishment of community radio listeners’ groups by VHTs to mobilize the communities, listen and participate in radio discussion programmes on immunization · Conducting sensitization sessions with religious, traditional and community leaders · Conducting sensitization sessions with teachers to create awareness · School based activities conducted by teachers · Additional activities may include street theatre, community meetings, sports days, school-based activities, and seminars, celebration of important health events e.g. World Health Day, Child Days Plus 2.8.3. Advocacy: Advocacy will target individuals involved at all levels of policy and decision making. At the National level it will target ministers, MPs, and other relevant people in the ministries. At the District level it will target the district councils and heads of departments. The district level advocacy will entail dialogue with District Health Officers (DCOs), heads of departments and councilors. Media agencies and their representatives at national and district levels will also be targeted. Newspaper articles, seminars and workshops/meetings will be employed to make policy makers more aware of the magnitude of risks. The advocacy component will focus on the following: Capacity Building: Build the capacity of policy makers, parliamentarians at national and district level for implementing the advocacy strategy. Also, advocacy capacity of the NGOs and the media will be strengthened to effectively publicize and promote the newvaccine. Awareness Raising: Raise awareness of government officials and affiliated partners about the consequences of lowcoverage, and ways and means of achieving targets. Advocacy Activities: · Develop/adapt advocacy kit for political leaders, traditional and religious leaders at national and district levels. · Conduct high level advocacy meetings to get support and commitment of political, religious and traditional leaders. · Seek endorsement statements from credible authorities in government, traditional and religious organizations and medical professionals in support of new vaccine. · Meetings district leaders, heads of departments, religious and traditional leaders and key partners. · Launch the Communication strategy by a key figure in government, either the First Lady or Minister of Health. · Capacity building of policy makers to develop supportive policy and implementation · Sensitization/Capacity Building sessions with media representatives Specific activities for Hard to reach; · Identify the hard to reach and hard to convince/serve populations and their locations · Rapid assessment on the reasons why particular special groups do not believe in and utilize immunization services. · Identification of grassroots NGOs and FBOs and engage them to mobilize the hard to reach communities. · Identification of leaders of groups opposed to immunization e.g. traditional and religious leaders and engage them in dialogue · Engagement of urban families resisting immunization to address concerns about immunization · Involvement of urban authorities in planning, implementation and monitoring of immunization services · Intensive use of mass media and community radio with emphasis on interactive radio discussion programmes especially on local FM radio stations · Intensive community mobilization using film vans, street bashes/road shows to mobilize and sensitize communities. · Establish outreaches and or mobile service teams to cover hard to access populations · Formation of District Communication Committee · Identification of focal person within the District Health Management Team (Health Education Officer/other) · Identification of local volunteers (teacher/health-worker) and formation of support groups at community level and advocate and participate in program activities Training and capacity building The implementation of the communication strategy requires strengthening communication capacity in immunization at all levels. Training of Trainers (TOT): Master trainers will be trained at the national level in social mobilization/advocacy, design and implementation of the strategy. They will conduct further trainings in all districts. These will be the Ministry of health national trainers Training of District Health Management Teams (District Health Educator, District Health Inspector and District Health Visitor): Capacity building of the district health management teams in communication is crucial for the implementation of the Immunization social mobilization strategy at the district/implementation level. This will not be a one- time activity but a series of participatory workshops will be conducted to equip them with the necessary communication and mobilization skills for immunization. VHTs, LC1s, Chiefs, religious leaders, teachers, Traditional Birth Attendants and health assistants: For sustained behavior change at community and household level, interpersonal communication and counseling skills of the service providers at community level such as VHTs and LC1s are extremely important. They will be trained to enhance their interpersonal communication and counseling skills, and in the use of IEC materials related to immunization. They will also receive basic training in community mobilization to form local alliances/support groups. Please select strategy that the country will choose to deliver the HPV vaccine: Mixed strategy School-based strategy Uganda strategy to deliver HPV vaccine does not include a "School-based strategy" INTRUCTIONS Description should include: Primary/secondary/tertiary, grades in each category, majority age in each grade Number of schools in the country (public/government schools, private school, or other categorization if possible and relevant for the country) What is the school year (which month to which month) When are the school holidays? (Approximated months, days if possible) When are the major examinations? (Approximated month) Uganda’s formal education system is divided into four distinct levels namely: Pre-Primary, Primary, Secondary and Post-Secondary or Tertiary. The number of years spent varies; Pre-Primary (3 years), Primary (7 years), Secondary (6 years) and Tertiary (2-5 years). This means that for a child who enters school and completes his or her education program up to university spends a total of not less than 16 years at school. This provides an excellent opportunity for an individual to learn, get healthy, grow and develop. Since the introduction of the Universal Primary in1997, the number of children enrolled and attending school has increased substantially, from 2.5 million in 1997 to nearly 8.2 million in 17,865 primary school by 2010 (EMIS), the total number of females enrolled in primary schools as per EMIS 2010, was 4, 195,400 compared to 4,179,248 males. The school holidays usually happen during the first week of May for first term (beginning 1st week of February), last week of August for second term (beginning last week of May) and first week of December (beginning last week of September) for the third and last term in a year. Please specify whether girls will be vaccinated by selection of a Specific age Table 6.1.2 a Number of Base year Target year 2012 2015 Target population of girls in chosen age 68,263 825,308 Girls of chosen age enrolled in schools

If girls are to be vaccinated by a specific grade, please specify grade and provide the below data relative to the target grade: Table 6.1.2 b Age of girls in grade Number of girls in grade / age % of girls in targeted population 8 years old 61,500 8 9 years old 119,000 16 10 years old 156,800 21 11 years old 158,700 21 12 years old 122,500 16 13 years old 77,100 10 14 years old 38,300 5 TOTAL girls 9-13 years old 634,100 86 TOTAL girls 14 years old and above 38,300 5 TOTAL 733,900 100 Note: (1) To add new Age of girls in grade, click on the New item icon in the Action line. Use the Delete item icon to delete a specific Age of girls in Grade. Please provide a source for the enrolment data (e.g., national statistics office, MOE, recent census, school registers, etc.) The source of data is Ministry of Education census of 2012 How will the school-based strategy capture those girls not in school? (Will out-of-school girls be invited to join school-attending girls on the days of vaccination? Will separate outreach sessions be scheduled for them? Will existing outreach posts be used? Will out-of-school girls be asked to come to the local health center? Will vaccination nurses do home visits?) The Ten year old eligible girls who are not attending school will access HPV vaccination through a) Pre-Planned stand alone month of HPV Immunisation services: This will be delivered through Static (Health facility) and Community outreaches. By policy all health facilities with a fridge conduct daily immunisation and at least 4 community outreaches per month. b) National CDP a period of accelerated Child Survival intervention is conducted every April and October. During these months schools and communities are mobilized for increased health. The second dose will be administered as part of the routine immunization outreach and static delivery strategies. c) Communication and Advocacy: This will be intensified during the months of HPV vaccination. The available community structures will be targeted such as community and religious leaders, and school administration d) Social mobilization and Sensitization: Intensified period of social mobilization using IEC, radio, local structure, sensitization through health education in the communities and health facilities, e) Monitoring and supportive supervision: this will strengthen the capacities of health workers to improve performance. Data utilization to reach targeted and missed girls If any, please describe special considerations to be made for marginalised or migrating populations? Considerations for the marginalised and migrating populations: Community-based outreach sites, including health centers will be primary conduit to reach the marginalized and migrating populations Planning with the communities and utilization of the local community structures to guide the vaccination Social mobilization and awareness use of family health days in districts that are under this support Health center-based strategy Please describe the health system and services for the target population at the health centers:(This can include: Number and type of health centers in the country by level (national, sub-national, district), (by public/government, private, or other categorization relevant for the country and if available). What services for 9-13 year old girls are routinely available in these health centers? What are the general operating day/times for service delivery in the health centers? How vaccinations are delivered in the existing health centers? By whom, to what populations, etc.) Public health services in Uganda are delivered through VHTs, Health Centre (HC) IIs, HC IIIs, HC IVs and Hospitals. There are a total 4394 health facilities, 2,622 are Government, 774 are Private Not For Profit and 998 Private For Profit (HSSIP 2010/11 – 2014/15). The services provided to the 9-13 years are Health Prevention, Promotive and Curative services which include; Immunization (TT) and De-worming Adolescent Friendly Services (Sexual Abuse and gender based violence , Psychosocial services for Adolescents) STI/HIV/AIDS and Adolescents Harmful traditional/cultural practices Capacity building for adolescent health program and services Treatment of minor and major illnesses All the health facilities operate 24 hours except health centre II which operates for 8 hours. All the heath facilities provide Adolescent health services which include curative, preventive and promotive health activities in the 8 hours of day time. In a total of 4,394 health facilities a total of 2,602 health facilities are providing routine immunization and have fridges. The routine immunization is provided in each health facility target catchment area and immunization is administered by trained Health workers at all the immunisation sites (Static and Outreach). How will the health centre-based strategy capture all the girls who are eligible? The health facility serves both the community and the schools in the catchment area. It serves as the focal point for planning distribution and delivery of health services to this catchment population’ Increased utilization of service by the eligible girls in the community will be through: Mapping and registration of the eligible girls and Utilization of catchment population data to plan the service delivery Communication targeting community structure will be intensified during the months of HPV vaccination. Social mobilization and Sensitization will be intensified using IEC, radio, local structure, sensitization through health education in the communities and health facilities. The Village Health Teams will conduct follow up of missed girl’s and mobilize entire communities for service uptake. Monitoring and supportive supervision both internal and from higher health levels will be conducted and this will strengthen the capacities of health workers to improve performance If applicable, please describe special considerations to be made for marginalised or migrating populations? Community-based outreach sites, including health centers will be primary conduit to reach the marginalized and migrating populations. Planning with the communities and utilization of the local community structures to guide the vaccination Social mobilization and awareness Family health days and child days plus

| 6.2. Requested vaccine (HPV quadrivalent, 1 dose(s) per vial, LIQUID) As reported in the cMYP, the country plans to introduce HPV quadrivalent, using HPV quadrivalent, 1 dose(s) per vial, LIQUID. When is the country planning to conduct this vaccine? April 2015 Please note that, due to a variety of factors, the launch date may vary compared to the date stipulated in the application. GAVI will work closely with countries and their partners to address these issues. 6.2.1. Co-financing information If you would like to co-finance an amount higher than the minimum, please provide information in Your co-financing row. Country group Low Year 1 Year 2 2015 2016 Minimum co-financing 0.20 0.20 Your co-financing (please change if higher) 0.20 0.20 6.2.2. Specifications of vaccinations with new vaccine Data from Year 1 Year 2 2015 2016 Number of children to be vaccinated with the first dose Table 5.2 # 557,083 783,581 Number of children to be vaccinated with the third dose Table 5.2 # 495,185 698,409 Immunisation coverage with the third dose Table 5.2 # 80.00 % 82.00 % Country co-financing per dose Table 6.2.1 $ 0.2 0.2 |  |
| --- | --- |

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$) 2015 2016 Number of vaccine doses # 94,200 113,700 Number of AD syringes # 0 0 Number of re-constitution syringes # 0 0 Total value to be co-financed by the Country [1] $ 439,000 529,500 [1] The co-financing amount for low-income countries indicates costs for the vaccines and any freight charges. The total co-financing amount does not contain the costs and fees of the relevant Procurement Agency, such as contingency buffer and handling fees. Information on these extra costs and fees will be provided by the relevant Procurement Agency as part of the cost estimate to be requested by the Country. 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$) 2015 2016 Number of vaccine doses # 2,099,500 2,533,100 Number of AD syringes # 2,342,100 2,807,400 Number of re-constitution syringes # 0 0 Total value to be co-financed by GAVI $ 9,887,000 11,928,500

6.2.5. New and Under-Used Vaccine Introduction Grant Calculation of Vaccine Introduction Grant for the HPV quadrivalent, 1 dose(s) per vial, LIQUID Year of New Vaccine Introduction Girls in cohort (From Table 5.2) Share per Girls in cohort in US$ Total in US$ 2015 618,980 2.40 1,485,552 The Grant will be based on a maximum award of $2.40 per infant in the birth cohort with a minimum starting grant award of $100,000 Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan). The GAVI new vaccine introduction grant will be utilized by the country to support the most critical start up activities as in country resource mobilization is done by use of the introduction plan. The grant will support the following activities: 1. Training of operational level health workers: this will be done in a cascade manner first at the national level to train a pool of trainers of trainers, this group will also include participants from Ministry of education, training school institutions and this will be followed by training at the regional level a pool of another trainers of trainers who will include members from the district health team and district education team. This set of two pools will then train the operational level health workers at the sub county level. 2. Printing of the operational field guides at least a copy per participant 3. Advocacy and sensitization targeting the key stakeholders at the national and district level through print media and meetings 4. Preventative cold chain maintenance at the district level by both national and district cold chain focal persons 5. Support of core teams from the national and district level to supervise and monitor the quality of training at the operational level and the actual vaccination exercise. 6. Vaccine distribution at the district level. Please summarise in the table below the full costs of preparing for and introducing the vaccine, and specify which items are expected to be covered with the one-time GAVI grant. Please note that the country will be required to submit a detailed budget for the Vaccine Introduction Grant prior to release of funds. Cost (and finance) to introduce the HPV quadrivalent, 1 dose(s) per vial, LIQUID US$ Cost Category Total cost for preparation of and delivery of campaign in US$ Funded with GAVI introduction grant in US$ Training 978,988 978,988 Social Mobilization, IEC and advocacy 1,054,868 477,160 Cold Chain Equipment & Maintenance 69,805 0 Vehicles and Transportation 80,556 0 Programme Management 139,318 87,343 Surveillance and Monitoring 87,000 87,000 Human Resources 0 0 Waste Management 173,216 0 Technical Assistance 540,416 78,187 Other (please specify) Micro planning at regional, district and sub county level for both health and education sector 255,640 255,640 Total 3,379,807 1,964,318 Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs. A part from the Government of Uganda and GAVI funding, additional funding will be mobilised from in country health development partners mainly; <?xml:namespace prefix = o /> UNICEF to support social mobilization activities, WHO to support supervision and monitoring; USAID to support training workshops, SIDA, DFID to support training, PATH, JICA to support cold chain capacity, Merck Company to support mobilization, RED Cross to support social mobilization

7. NVS Preventive Campains No NVS Prevention Campaign Support this year

8. Procurement and Management 8.1 Procurement and Management of New and Under-Used Vaccines Routine Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC). a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF): Procurement and management will follow the existing vaccine procurement mechanism whereby the Government of Uganda (GOU), through the National Medical Stores (NMS), provides funds to UNICEF country office that procures vaccines from WHO pre-qualified suppliers. Similarly GAVI supported vaccines will also be procured through UNICEF as per procedure of the existing government arrangement. All this is governed by an MOU signed annually between GOU and UNICEF. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document l Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used. l The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality. Not applicable c) Please indicate how funds should be transferred by the GAVI Alliance (if applicable) The mechanism for transferring funds will be outlined in the Financial Management Assessment Aide Memoire signed between GAVI Alliance and Government of Uganda, this arrangement will be followed. d) Please indicate how the co-financing amounts will be paid (and who is responsible for this) A vote for HPV vaccine co-financing will be included in the MoH annual budget. Funds will be released from Ministry of Finance, Planning and Economic Development to National Medical Stores (NMS). Upon approval by Permanent Secretary of MoH, National Medical Stores will transfer funds to UNICEF that manages the procurement. e) Please describe the financial management procedures that will be applied for the management of the NVS cash support, including procurement. According to GAVI categorization, Uganda is among the countries that contribute 0.2 dollars per dose of the vaccine. Funds for PCV, HPV and Rota have been catered for within the MOH MTEF. These funds will be disbursed to UNICEF which is the procurement agent for all vaccines. Other introductory funds from GAVI will be managed in-country using IFMS (Integrated Financial Management System). f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP) All EPI data will be recorded and reported using the existing Health Management Information tools (HMIS). The existing tools have already been revised to incorporate information on the new vaccines and gender segregation. During the next review of HMIS tools scheduled to start in 2014, all additional data for HPV seggregating data by age will be incoporated. HMIS monthly reports are submitted from the districts to MoH electronically using the E HMIS (DHIS2) by the 15 th day of the following month where data is aggregated. Monthly reports are aggregated to compile annual reports. The information is incorporated into the WHO/UNICEF Joint Reporting Format which is submitted annually by the 15th April of the following year. Periodically (every 5 years) nationwide coverage surveys and Demographic Health surveys are done to verify immunization coverage. The monitoring indicators of the new vaccine to be introduced have been included in the updated cMYP 2012-2016, August 2013 (attached) g) If applying for measles second dose, does the country wish to have the support in cash or in-kind? Cash 8.2 Procurement and Management for NVS Preventive Campaign(s) No NVS Prevention Campaign Support this year

8.3 Vaccine Management (EVSM/EVM/VMA) Under the new guidelines, it is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 36 months. Did the country have Effective Vaccine Management (EVM) in the past? Yes When was the EVM conducted? July 2011 Please attach the most recent EVM report (DOCUMENT NUMBER : 20,21,22), the corresponding EVM improvement plan (DOCUMENT NUMBER : 21) and progress on the EVM improvement plan (DOCUMENT NUMBER : 22). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes When is the next Effective Vaccine Management (EVM) Assessment planned? July 2014 8.4 Waste management Please describe the country’s waste management plan for immunisation activities (including campaigns). Include details on the safe handling, storage, transportation and disposal of immunisation waste. Uganda has a Health care waste Management policy and three disposal methods are common for immunization waste: <?xml:namespace prefix = o /> a) Burying In this method of disposal, waste is placed in a pit and covered with soil. The site for the waste pit is at least 50 meters away from any water source to avoid contamination of the source and the pit is usually located on land that is not used for agriculture or development. b) Burning Waste is placed in a pit and burned on a regular basis (at least once a week, according to the volume of waste and the size of the pit). The waste is burned thoroughly and ashes covered with earth. Pits are 1-2 meters wide and to the depth of 2-5 meters, but at least 1.5 meters above water table. The pit is usually fenced off to restrict unauthorized access and located away from public areas. Kerosene is added to the waste before starting the fire to avoid explosions. c) Incineration This method is used in some districts in particular at district and regional referral hospitals.

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

10. List of documents attached to this proposal 10.1. List of documents attached to this proposal Document Number Document Section Mandatory File Signature health Fin.pdf 1 MoH Signature (or delegated authority) of Proposal File desc: Date/time: 9/14/2013 6:37:07 AM Size: 598634 Signature health Fin.pdf 2 MoF Signature (or delegated authority) of Proposal File desc: Date/time: 9/14/2013 6:37:49 AM Size: 598634 Signature Edu.pdf 3 MoE signature (or delegated authority) of HPV Proposal 4.1.1 File desc: Date/time: 9/14/2013 6:38:43 AM Size: 308980 Signature HPAC members.JPG 3 Signatures of ICC or HSCC or equivalent in Proposal File desc: Date/time: 9/14/2013 6:45:33 AM Size: 778417 HSSIP Compact Uganda final.pdf 4 Terms of Reference for the ICC 4.1.2 File desc: Date/time: 9/14/2013 6:05:45 AM Size: 790449 Minutes endorsing proposal.pdf 4 Minutes of ICC/HSCC meeting endorsing Proposal File desc: Date/time: 9/14/2013 5:58:05 AM Size: 5297690 UGANDA EPI cMYP 2012-2016_update_2013.doc 5 comprehensive Multi Year Plan - cMYP File desc: Date/time: 9/14/2013 8:15:19 AM Size: 1464832 Minutes of NITAG meeting endorsing proposal.doc 5 Minutes of NITAG meeting endorsing proposal 4.2 File desc: Date/time: 9/13/2013 4:27:44 AM Size: 26112 cMYP_V3.3_July_2013_UGANDA2.xlsm 6 cMYP Costing tool for financial analysis File desc: Date/time: 9/13/2013 8:13:03 AM Size: 2309761 Uganda Plan for Introduction of HPV 2013.doc 7 Plan for NVS introduction (if not part of cMYP) 5.1 File desc: Date/time: 9/14/2013 8:42:31 AM Size: 835072 HPAC MINUTES - AUGUST.pdf 7 Minutes of last three ICC/HSCC meetings File desc: Date/time: 9/13/2013 3:39:03 AM Size: 8720319 EVM-DVS-Improvement-Plan-Uganda-D1-22 Sept-2011 (1).xls 8 Improvement plan based on EVM File desc: Date/time: 9/14/2013 8:54:09 AM Size: 200704 Minutes of three most recent NITAG meetings.doc 9 Minutes of three most recent NITAG meetings 4.2.1 File desc: Date/time: 9/13/2013 4:29:29 AM Size: 26112 FINAL_Uganda_HPV_demo_project summary.pdf 9 HPV summary of the evaluation methodology 5.1.1 File desc: Date/time: 9/13/2013 8:27:59 AM Size: 1013966 Plan for Cervical Cancer and control 2010 -2014.pdf 10 HPV roadmap or strategy 6.1.1 File desc: Date/time: 9/13/2013 8:38:12 AM Size: 5019329 Evidence of introduction of RCV.doc 11 Evidence of introduction of RCV in routine programme 7.c.3 File desc: Date/time: 9/13/2013 9:05:55 AM Size: 26112 Final DQS report september 2013.pdf 13 Data quality assessment (DQA) report 5.1.5 File desc: Date/time: 9/13/2013 7:40:06 AM Size: 894873 DQA improvement Plan.doc 14 DQA improvement plan 5.1.5 File desc: Date/time: 9/13/2013 7:50:24 AM Size: 26112 Progress report on implementation of DQA.doc 15 Progress report on implementation of DQA improvement plan 5.1.5 File desc: Date/time: 9/13/2013 7:51:14 AM Size: 26112 Campaign target population.doc 18 Campaign target population documentation 7.x.1 File desc: Date/time: 9/13/2013 9:01:33 AM Size: 26112 EVM_Uganda_report_Final.doc 20 EVM report 8.3 File desc: Date/time: 9/13/2013 9:14:32 AM Size: 3668992 Sept 2013-UNEPI Progress of implementation of EVM-NVS-Improvement-Plan (1).xls 22 EVM improvement plan progress report 8.3 File desc: Date/time: 9/14/2013 8:48:54 AM Size: 43008

11. Annexes Annex 1 - NVS Routine Support Annex 1.1 - NVS Routine Support (HPV quadrivalent, 1 dose(s) per vial, LIQUID) Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$ 2015 2016 Number of vaccine doses # 94,200 113,700 Number of AD syringes # 0 0 Number of re-constitution syringes # 0 0 Total value to be co-financed by the Country [1] $ 439,000 529,500 Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$ 2015 2016 Number of vaccine doses # 2,099,500 2,533,100 Number of AD syringes # 2,342,100 2,807,400 Number of re-constitution syringes # 0 0 Total value to be co-financed by GAVI $ 9,887,000 11,928,500

Table Annex 1.1 C: Summary table for vaccine HPV quadrivalent, 1 dose(s) per vial, LIQUID ID Data from 2015 2016 Number of surviving infants Table 5.2 # 1,721,179 1,776,257 Number of children to be vaccinated with the first dose Table 5.2 # 557,083 783,581 Number of children to be vaccinated with the third dose Table 5.2 # 495,185 698,409 Immunisation coverage with the third dose Table 5.2 % 80.00 % 82.00 % Number of doses per child Parameter # 3 3 Estimated vaccine wastage factor Table 5.2 # 1.05 1.05 Number of doses per vial Parameter # 1 1 AD syringes required Parameter # Yes Yes Reconstitution syringes required Parameter # No No Safety boxes required Parameter # No No g Vaccine price per dose Table Annexes 4A $ 4.5 4.5 cc Country co-financing per dose Table 6.4.1 $ 0.2 0.2 ca AD syringe price per unit Table Annexes 4A $ 0.0465 0.0465 cr Reconstitution syringe price per unit Table Annexes 4A $ 0 0 cs Safety box price per unit Table Annexes 4A $ 0.58 0.58 fv Freight cost as % of vaccines value Table Annexes 4B % 4.00 % 4.00 % fd Freight cost as % of devices value Parameter % 0 0

Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1) Formula 2015 Total Government GAVI A Country co-finance 4.29 % B Number of children to be vaccinated with the first dose Table 1 557,083 23,922 533,161 C Number of doses per child Vaccine parameter (schedule) 3 D Number of doses needed B x C 1,671,249 71,766 1,599,483 E Estimated vaccine wastage factor Wastage factor table 1.05 F Number of doses needed including wastage D x E 1,754,812 75,355 1,679,457 G Vaccines buffer stock (F – F of previous year) * 0.25 438,703 18,839 419,864 I Total vaccine doses needed (((F + G) / Vaccine package size) + 1) * Vaccine package size 2,193,615 94,198 2,099,417 J Number of doses per vial Vaccine parameter 1 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 2,342,047 0 2,342,047 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 N Cost of vaccines needed I x g 9,871,268 423,887 9,447,381 O Cost of AD syringes needed K x ca 108,906 0 108,906 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0 0 0 R Freight cost for vaccines needed N x fv 345,495 14,837 330,658 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 10,325,669 438,723 9,886,946 U Total country co-financing I 3 cc 438,723 V Country co-financing % of GAVI supported proportion U / T 4.29 % Table Annex 1.1 D: Estimated numbers for HPV quadrivalent, 1 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 2) Formula 2016 Total Government GAVI A Country co-finance 4.29 % B Number of children to be vaccinated with the first dose Table 1 783,581 33,649 749,932 C Number of doses per child Vaccine parameter (schedule) 3 D Number of doses needed B x C 2,350,743 100,945 2,249,798 E Estimated vaccine wastage factor Wastage factor table 1.05 F Number of doses needed including wastage D x E 2,468,281 105,992 2,362,289 G Vaccines buffer stock (F – F of previous year) * 0.25 178,368 7,660 170,708 I Total vaccine doses needed (((F + G) / Vaccine package size) + 1) * Vaccine package size 2,646,749 113,656 2,533,093 J Number of doses per vial Vaccine parameter 1 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 2,807,314 0 2,807,314 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 0 0 0 N Cost of vaccines needed I x g 11,910,371 511,450 11,398,921 O Cost of AD syringes needed K x ca 130,541 0 130,541 P Cost of reconstitution syringes needed L x cr 0 0 0 Q Cost of safety boxes needed M x cs 0 0 0 R Freight cost for vaccines needed N x fv 416,863 17,901 398,962 S Freight cost for devices needed (O+P+Q) x fd 0 0 0 T Total fund needed (N+O+P+Q+R+S) 12,457,775 529,350 11,928,425 U Total country co-financing I 3 cc 529,350 V Country co-financing % of GAVI supported proportion U / T 4.29 %

Annex 2 - NVS Routine – Preferred Second Presentation No NVS Routine – Preferred Second Presentation requested this year

Annex 3 - NVS Preventive campaign(s) No NVS Prevention Campaign Support this year

| Annex 4 Table Annex 4A: Commodities Cost Vaccine Presentation 2015 2016 DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 1.986 1.927 DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 1.986 1.927 DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 1.986 1.927 HPV bivalent, 2 dose(s) per vial, LIQUID 2 4.600 4.600 HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 4.500 4.500 Measles second dose, 10 dose(s) per vial, LYOPHILISED 10 0.296 0.322 Meningococcal type A, 10 dose(s) per vial, LYOPHILISED 10 0.582 0.611 MR, 10 dose(s) per vial, LYOPHILISED 10 0.565 0.591 Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 3.500 3.500 Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 3.500 3.500 Rotavirus, 2-dose schedule 1 2.550 2.550 Rotavirus, 3-dose schedule 1 3.500 3.500 Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 0.923 0.923 Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 0.923 0.923 Supply Form 2015 2016 AD-SYRINGE SYRINGE 0.047 0.047 RECONSTIT-SYRINGE-PENTAVAL SYRINGE 0.037 0.037 RECONSTIT-SYRINGE-YF SYRINGE 0.037 0.037 SAFETY-BOX SAFETYBOX 0.580 0.580 Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised) Table Annex 4B: Freight cost as percentage of value Vaccine Antigen Vaccine Type No Threshold 500,000$ <= > DTP-HepB-Hib HEPBHIB 25.50 % 6.40 % HPV bivalent HPV 3.50 % HPV quadrivalent HPV 3.50 % Measles second dose MEASLES 14.00 % Meningococcal type A MENINACONJUGATE 10.20 % MR MR 13.20 % Pneumococcal (PCV10) PNEUMO 3.00 % Pneumococcal (PCV13) PNEUMO 6.00 % Rotavirus ROTA 5.00 % Yellow Fever YF 7.80 % Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine. Vaccine 2015 2016 HPV quadrivalent, 1 dose(s) per vial, LIQUID 0.2 0.2 |  |
| --- | --- |

Table Annex 4D: Wastage rates and factors The following table shows the wastage rates for routine and campaign vaccines, set for 2015. Vaccine dose(s) per vial Maximum Vaccine wastage rate* Benchmark Wastage Rate** DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 5 % DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 25 % 15 % DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 10 % HPV bivalent, 2 dose(s) per vial, LIQUID 2 10 % HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5 % Measles second dose, 10 dose(s) per vial, LYOPHILISED 10 40 % Meningococcal type A, 10 dose(s) per vial, LYOPHILISED 10 10 % MR, 10 dose(s) per vial, LYOPHILISED 10 25 % Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 10 % Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 5 % Rotavirus, 2-dose schedule 1 5 % Rotavirus, 3-dose schedule 1 5 % Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 40 % Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 10 % Comments: * Source - WHO indicative wastage rates ** Source - Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat Note: HPV demonstration project wastage rates are the same as the vaccine Table Annex 4E: Vaccine maximum packed volumes Kindly note that this table is for reference purposes only and includes GAVI- and non GAVI-supported vaccines. Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella freeze dried MR lyophilized SC 1 1 26.1 26.1 Measles-Rubella freeze dried MR lyophilized SC 1 2 13.1 13.1 Measles-Rubella freeze dried MR lyophilized SC 1 5 5.2 7 Measles-Rubella freeze dried MR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP-Hib liquid IM 3 1 32.3 DTP-HepB liquid + Hib freeze-dried DTP-Hib liquid IM 3 10 2.5 DTP-HepB liquid + Hib freeze-dried DTP-HepB+Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB+Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized SC 2 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 3 10 15 Japanese Encephalitis JE_lyo lyophilized SC 3 10 8.1 8.1 Japanese Encephalitis JE_lyo lyophilized SC 3 5 2.5 2.9 Japanese Encephalitis JE_lyo lyophilized SC 3 1 12.6 11.5 Japanese Encephalitis JE_liq liquid SC 3 10 3.4 Rota vaccine Rota_lyo lyophilized Oral 2 1 156 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 PFS 55.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 1 21 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Papilomavirus vaccine HPV liquid IM 3 1 15 Human Papilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5

12. Banking Form In accordance with the decision on financial support made by the GAVI Alliance, the Government of Uganda hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): MINISTRY OF HEALTH Address: P.O.BOX 7272 City Country: KAMPALA Telephone no.: +256-414-340-872 Fax no.: +256-414-231-584 Currency of the bank account: USD For credit to: Bank account's title: GAVI VACCNE FUND Bank account no.: 000140088400002 Bank's name: BANK OF UGANDA Is the bank account exclusively to be used by this program? True By who is the account audited? AUDITOR GENERAL Signature of Government's authorizing official Seal Name: DR. ASUMAN LUKWAGO Title: PERMANENT SECRETARY Signature: Date: 13/09/2013 FINANCIAL INSTITUTION Bank Name: BANK OF UGANDA Branch Name: MAIN Address: P.O.BOX 7120 City Country: KAMPALA, UGANDA Swift Code: UGAUGKA Sort Code: ABA No.: Telephone No.: +256-414-258-441 FAX No.: +256-414-259-343 CORRESPONDENT BANK (In the United States) CITI BANK (CITI NEW YORK) MAIN CITI BANK NA, 111, WALL STREET NEW YORK, USA CITIUS33 1212-816-7086 I certify that the account No 000140088400002 is held by MINISTRY OF HEALTH at this banking institution The account is to be signed jointly by at least 3 (number of signatories) of the following authorized signatories: 1 Name: DR ASUMAN LUKWAGO Title: PERMANENT SECRETARY 2 Name: S.S. KYAMBADDE Title: UNDER SECRETARY 3 Name: MWAMBU WYCLIFFE Title: ASSISTANT COMMISSIONER ACCOUNTS Name of bank's authorizing official Signature: Date: Seal: