Application Form for Country Proposals

Measles Supplementary Immunization Activities (SIAs)

available for Afghanistan, DR Congo, Ethiopia, Nigeria, Pakistan and Chad

Submitted by

The Government of the Democratic Republic of Congo.

Date of submission: 12.11.12

Deadline for submission: November 12, 2012

(Or a date otherwise agreed with the GAVI Secretariat)

Please submit the Proposal using the form provided.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI alliance partner institution. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE

GRANT TERMS AND CONDITIONS

Countries will be expected to sign and agree to the following GAVI Alliance terms and conditions in the application forms. These clauses may also be included in a grant agreement to be agreed upon between GAVI and the country.

FUNDING USED SOLELY FOR APPROVED PROGRAMMES

The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance for this application will be used and applied for the sole purpose of fulfilling the programme(s) described in this application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for this application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the SIAilability of funds.

AMENDMENT TO THIS PROPOSAL

The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in this application. The GAVI Alliance will document any change approved by the GAVI Alliance, and this application will be amended.

RETURN OF FUNDS

The Country agrees to reimburse to the GAVI Alliance, all funding amounts that are not used for the programme(s) described in this application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.

SUSPENSION/ TERMINATION

The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in this application, or any GAVI Alliance-approved amendment to this application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in this application if a misuse of GAVI Alliance funds is confirmed.

ANTICORRUPTION

The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with this application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.

AUDITS AND RECORDS

The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.

The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this application is accurate and correct and forms a legally binding obligation on the Country, under the Country’s law, to perform the programmes described in this application.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARENCY AND ACCOUNTABILITY POLICY

The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and will comply with its requirements.

ARBITRATION

Any dispute between the Country and the GAVI Alliance arising out of or relating to this application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English.

For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.

The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in this application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in this application.

Use of commercial bank accounts

The eligible country government is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support, including HSS, ISS, CSO and vaccine introduction grants. The undersigned representative of the government confirms that the government will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.

# Application Specification

Vaccine: Measles, 10 doses/vial, lyophilised.

Q1.	Please specify the timing (week/month and year) of the planned SIA, and the year of the next projected SIA.

• Ecuador Block, Eastern Province (Early September 2013), North Kivu and South Kivu (End of November 2013)

• Katanga Block, Maniema (February 2014), Western Kasai and Eastern Kasai (April 2014).

• Kinshasa Block, Bas Congo, Bandundu (July 2014)

# Executive Summary

Q2.	Q2.The objective of GAVI’s assistance for measles SIAs is to strengthen the impact of the comprehensive package of support offered by the GAVI Alliance partners to sustainably prevent measles deaths. The comprehensive support is designed to:

- Strengthen health systems to deliver routine immunizations, including MCV1 (e.g. Health Systems  Strengthening resources),

- Improve the sustainability of national financing for measles immunization and other vaccines (e.g. Financial commitments from the country; vaccine co-financing)

- Support the routine delivery of the second dose of measles-containing vaccine (MCV2), and

- Reduce morbidity and mortality from rubella through the introduction of measles-rubella (MR) vaccine.

Please provide a summary of the ways through which the proposal addresses the objective above.

From 2010 to this day, the DRC has been witnessing new outbreaks of the measles epidemic that affect all the provinces. In 2011, the country recorded more than 130,000 cases of measles. Between the first and the 53rd week of 2012 (week 1 – week 53), more than 73,314 cases among which 22,084 cases were in the age bracket of more than 5 years, being 30%. Concerning the deaths, 2,023 measles related deaths were reported among which 279 were among children over 5 years old, being 13.8%. Chart 1: Comparison of changes specific to measles from 2008 to 2012 among children under 5 years and over 5 years Chart 1 traces the comparison of changes in the lethality specific to measles from 2008 to 2012 among children under 5 years and over 5 years. We note that this lethality varied between 1,5% and 3.4% among children under 5 years and between 0 and 1.3% among children over 5 years. There is also a large number of deaths in 2011 and 2012, coinciding with the resurgence of measles in the country. Even among children between 5 and 15 years, 279 deaths were reported in 2012. This increased lethality observed in 2012 was due to poor case management. (Source: IDS-RDC_9 janvier 2013) Figure 1 : Development of the measles epidemic from 2007 to 2012 Fig.1 shows that the measles epidemic that was initially concentrated in the eastern part of the country is widespread throughout the country in 2012. Chart 2: Development of suspected cases and deaths from measles per week between 2004 and 2012 Catch-up campaigns conducted between 2002 and 2006 have reduced the number of cases significantly. During the period from 2007 to 2010, the country has not experienced major epidemics following the implementation of campaigns and regular monitoring of quality. The epidemic that began in July 2010 was caused by the failure of implementation of the follow-up campaign's schedule during this period. This shows that the country has a positive experience with the implementation of measles control strategies. Table I: Comparative development by province of suspected cases of measles among children under 5 years and over 5 years between 2010 and 2012, DRC (Source IDS 4th Division) Province 2010 2011 2012 case<5 years case>5 years case<5 years case>5 years case<5 years case>5 years Bandundu 33 32 496 167 4061 2750 Lower Congo 25 0 456 219 457 400 Equator 135 71 201 202 6788 2971 West Kasai 34 15 736 317 2264 1417 East Kasai 139 24 27794 11787 4070 3048 Katanga 2582 776 58155 16133 7081 2231 Kinshasa 55 36 297 166 754 592 Maniema 16 3 7653 1763 1261 418 North Kivu 75 31 65 46 491 214 Western Province 160 94 2560 1078 23503 7887 South Kivu 361 146 2918 833 500 156 Totals 3615 1228 101331 32711 51230 22084 Table 1 above shows a significant increase in suspected measles cases in the country from 2011. Moreover, it is worth noting the increase in the proportion of cases in children over 5 years. In effect, this proportion increased from 24.4% in 2011 to 30.1% in 2012. Chart 3: Progress of routine vaccine coverage per antigen, 2005 to 2011 Measles epidemics are largely related to weak routine vaccination in the country which resulted in an increase of children susceptible to measles. In addition, the implementation of catch-up and monitoring campaigns planned since 2002 has encountered funding difficulties having accomplished either at the non-realization of 2009 and 2010 campaigns, or the achievement of poor quality measles vaccination campaigns. The opposite graph shows the development of the vaccine coverage by antigen, according to estimates by the WHO-UNICEF, reflecting the weakness of routine vaccination in the country. These WHO-UNICEF estimates coincide more with the statistics gotten from the national investigation on vaccine coverage, organized in May 2012 for children between 12 - 23 months. Table II: : Statistics of the 2012 VCS and WHO-UNICEF 2011 CV estimates Antigens VCS 2012 WHO-UNICEF JRF 2011 DTP1 85% 79% DPT3 77% 70% OPV3 82% 78% MV 75% 71% Chart 4: Province by province MV vaccine coverage according to the 2012 VC survey. The routine MV coverage fluctuates between 54% in Western Kasai and 88 % in the Kinshasa, Bandundu and North Kivu provinces. This puts the national average at 75%. The low national MV vaccine coverage accounts for the vulnerability of various groups of children to measles and considering the effectiveness of the measles vaccine (85 %), only 64% of immunized children could be protected thus leaving 36% of the children exposed and unprotected in 2011. This gives a joint total of 61% vulnerable children in an environment where the measles virus continues to spread wildly. In addition, the non-compliance of the follow-up campaigns schedule promoted the outbreak of measles epidemics from 2010. Vaccination campaigns against measles conducted in 2011 and 2012, partly labelled follow up or response campaigns were unable to protect children against measles epidemics. This is due in part to the poor control of funding, the overlapping with other activities, the late response, the poor quality of supervision campaigns, etc. The DRC would like to use the opportunity provided by GAVI support through its entire program, especially the support given to anti-measles SIAs, not only to organize quality measles immunization campaigns, but also to strengthen the routine immunization system (including measles immunization) in a bid to reduce the the measles related morbidity and mortality. Strategies used are strengthening of routine EPI, the organization of quality regular follow up campaigns and the strengthening of surveillance, the permanent availability of the vaccine. The country plans to conduct quality campaigns with the following features: timely start (at least 8 months before) of preparations for the campaign ensure timely quality training of intermediate and operational level actors (revision of modules, training support from the central level up to the operational level) permanent availability of vaccines and inoculation materials upward micro-planning starting from the country's health areas with focus on children not or insufficiently reached (micro-planning approach village by village) consolidation of health micro plans at health area level validation of basic micro plans and feedback in time (at least 3 months) at all levels and correct adjustment of the budget if possible development and implementation of a logistics and detailed cold chain plan timely deployment (at least 7 days before the campaign) of supervisors with adequate profile in the health zones completion of rapid convenience surveys during the campaign by the supervisors completion of post-campaign surveys with emphasis on the reasons for the non-vaccination of children. Ensure good coordination and strong leadership for these campaigns at the national, provincial and health zone level well before the campaign, during and after. Commitment of local political and administrative authorities and community leaders in social mobilization activities before the start of activities. This proposal is based: On organizing follow-up measles immunization campaigns targeting children from 6 to 14 months taking the actual epidemiological context of the measles situation into account. The strengthening of routine EPI before, during and after the follow-up campaigns using all the opportunities offered by the funding from the government, GAVI and other the vaccination partners. This is in line with the current CMYP. In concrete terms, this strengthening will be as follows: Before the campaigns: Organize the quality micro-planning of measles SIAs identifying unvaccinated children and reviewing the micro planning of routine EPI; Benefit from training providers to strengthen the capacity on injection safety, MAPI management and communication; Strengthen logistics with the acquisition of rolling stock and cold chain equipment; During the campaigns: Strengthen communication for the vaccination of children not immunized or immunized inadequately; Recover children lost from the routine and ensure their vaccination. After the campaigns. Perform the post-campaign coverage surveys in targeted health zones in order to estimate the true coverage of SIAs and the reasons for the non-vaccination of children. This information will be used to improve the level of routine EPI and its implementation. The strengthening of logistics with new acquisitions in cold chain equipment (204 solar refrigerators and 19 cold rooms) funded by the World Bank, of which the 1st batch is expected in February 2013, 60 refrigerators, 2000 vaccine carriers and 1900 coolers by UNICEF. This promotes the completion of follow up campaigns in 24 months. The cold chain requirements are: 4064 Refrigerators, 513 freezers, 4104 coolers, 97,628 vaccine carriers, 472,592 storage tanks. Existing equipment: 3180 refrigerators, 448 freezers, 2039 coolers, 31,591 vaccine carriers, 37,029 storage tanks (although the real needs are expressed during different micro-planning workshops). The Gap is therefore: 985 refrigerators, 65 freezers, 2,565 coolers, 66,037 vaccines carriers 435,563 storage tanks. On the GAP identified above, 515 refrigerators will be met by this project, 200 by the World Bank. However, 210 refrigerators, 106 freezers, 64,037 vaccine carriers, 1,665 coolers, 435,563 storage tanks may be filled by the reallocation of GAVI-RSS funds available in the country. Table III: Cold chain equipment needs PROVINCE No. HZ No. Refrig Required No. Freezers Required Refrig Freezer GAP Refr GAP Freezer CV in Ref CV in Freezer Bandundu 52 416 52 339 50 77 2 81% 96% West Kasai 44 352 44 264 48 88 0 75% 109% Katanga 67 536 67 460 64 76 3 86% 96% Maniema 18 144 18 134 26 10 0 93% 144% North Kivu 28 192 28 285 57 0 0 148% 238% Lower Congo 31 248 31 149 27 99 4 60% 87% Equator 69 552 69 359 50 193 19 65% 72% East Kasai 51 408 51 337 33 71 18 83% 65% Kinshasa 35 280 35 184 36 96 0 66% 103% Eastern Prov 83 664 83 389 36 275 47 59% 43% South Kivu 34 272 34 280 21 0 13 103% 62% Total 513 4064 513 3180 448 985 106 84% 101% Source: EPI-DRC logistics, January 2013 Table IV: Needs for coolers, vaccines carriers and storage tanks for the follow up MV campaign 2013-2014 Taking into account the spread of the epidemic in the country, the intervention approach by block was chosen to facilitate the population's rapid acquisition of collective immunity. Therefore 3 blocks were formed: • Ecuador Block, Eastern Province (Early September 2013), North Kivu and South Kivu (End of November 2013) • Katanga Block, Maniema (February 2014), Western Kasai and Eastern Kasai (April 2014). • Kinshasa Block, Bas Congo, Bandundu (July 2014) The total cost of this project amounts to US$ 51,290,021. The DRC seeks for this support an amount from GAVI of: $ US 46,286,411 of which Measles vaccines and injection equipment: $ US 20,397,767 Operational costs: U$ 25,888,643 If the proposal is approved by GAVI, this campaign series will start from July 2013 and will end in August 2014. From 2015, the epidemiological profile will guide the choice of targets for follow-up campaigns.

# Signatures of the Government and National Coordinating Bodies

Government

The Government of the Democratic Republic of Congo would like to expand the existing partnership with the GAVI Alliance to further prevent measles deaths and for the improvement of the infant routine immunization programme of the country, and specifically hereby requests GAVI support for measles vaccine (lyophilized, 10doses/via) for supplementary immunization activities.

The Government of the Democratic Republic of Congo commits itself to developing national immunization services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan and the Plan of Action as presented in this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

The Government of the Democratic Republic of Congo acknowledges and accepts the GAVI Alliance Grant Terms and Conditions included in the Application Form for Country Proposals for Measles Supplementary Immunization Activities.

Please note that this application will not be reviewed or approved by GAVI’s Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.

| Minister of Health (or delegated authority) | Minister of Finance (or delegated authority) |
| --- | --- |
| Name | His Excellency Félix KABANGE NUMBI, Minister of Public Health | Name | His Excellency Patrice KITEBI Minister Delegate for Finances |
| Date |  | Date |  |
| Signature |  | Signature |  |

This proposal has been compiled by (these persons may be contacted in case the GAVI Secretariat has queries on this document):

| Full name | Position | Telephone | Email |
| --- | --- | --- | --- |
| Dr Audry MULUMBA | EPI Director | 0998363739 | audrywakamba@yahoo.fr |
| Dr Paul LAME | EPI Assistant Director | 0810603329 | lamepaul@yahoo.fr |
| Dr Calixte SHIDI | EPI Measles focal point | 0815142308 | Shidicalixte5@yahoo.fr |
| Dr Obama Ricardo | WHO, Measles focal point | 0819500111 | obamar@cd.afro.who.int |
| Dr Sylvie LUKETA | UNICEF, Immunization Specialist | 0815060854 | sluketa@unicef.org |
| Dr Augustin MILABYIO | MCHIP, Consultant | 0810699775 | augbm@yahoo.fr |
| Dr André TONDA | Immunization Advisor, MCHIP | 0999396473 | andretonda2@hotmail.com |

National Coordinating Body/ Inter-agency Coordinating Committee for Immunization

We the members of the Inter-Agency Coordinating Committee for Immunization (ICC), Health Sector Coordinating Committee (HSCC), or equivalent committee met on this 2nd November 2012 in Kinshasa to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting during which the proposal was approved are attached as document.

| Name/Title | Agency/Organization | Signature |
| --- | --- | --- |
| Dr Pierre LOKADI OPETHA, Secretary General | Ministry of Health |  |
| Dr Audry MULUMBA, EPI Director | EPI |  |
| Dr Paul LAME, Assistant EPI Director | EPI |  |
| Dr Calixte SHIDI, Measles FP | EPI |  |
| Dr Guillaume NGOIE, support CD | EPI |  |
| Mr Claude MANGOBO, Logistics CD | EPI |  |
| Dr Helene MAMBU, SVI Focal Point, DRC | Sabin Vaccine Institute |  |
| Dr Tiekoura Coulibaly | WHO |  |
| Dr Obama Ricardo | WHO |  |
| Mrs Yolande MASEMBE | WHO |  |
| Dr Granga Daouya | UNICEF |  |
| Dr Ba Abderrahmane | UNICEF |  |
| Dr Sylvie LUKETA | UNICEF |  |
| Bonny SUMAILI | UNICEF |  |
| Dr Andre TONDA, MCHIP Focal Point | MCHIP |  |
| Dr Augustin MILABYIO, Consultant | MCHIP |  |
| Dr Joseph KONGOLO, EPI Focal Point | MSH/PROSANI |  |

# Immunization Programme Data

Please provide in the table below the reported national annual coverage data for the first dose of measles-containing vaccine (MCV1) from the WHO/UNICEF Joint Reporting Form for the three most recent years. Also provide survey estimates of national MCV1 coverage for the three most recent years, if available.

Table 4.1. Reported MCV1 coverage

| Trends of reported national MCV1 coverage |
| --- |
|  | WHO/UNICEF Joint Reporting Form | Survey |
| Year | 2009 | 2010 | 2011 | 2010 | 2012 |
| Survey type |  |  |  | MICS | ECV-OMS |
| Total population in the target age group[Type text] | 2 490 794 | 2 565 517 | 2 642 483 | 2384 | 6694 |
| Number immunized | 2 144 725 | 2 239 464 | 2 243 746 | 1597 | 5020 |
| MCV1 Coverage (%) | 86% | 87% | 85% | 67% | 75 % |
| Wastage rate (%) for MCV1 | 24% | 24% | 15% | NA | NA |

Please provide in the table below reported national (or sub-national if applicable) coverage estimates for the three most recent measles SIAs. Also provide post-campaign survey coverage estimates, if available.

Table 4.2. Measles SIA coverage

| Past measles SIA coverage |
| --- |
|  | Reported | Survey |
| Year | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 |
| Type of survey |  |  |  | NA | NA | Investigation post camp. |
| Target age group | 6-59 months old | 6-59 months old | 6 months to 14 yrs | NA | NA | 6 months to 14 yrs |
| Total population in the target age group[Type text] | 2 615 795 | 1 226 792 | 16 890 826 | NA | NA | 15601 |
| Geographic extent (national, sub national) | Sub-national | Sub-national | Sub-national | NA | NA | Sub-national (2 Provinces) |
| Number immunized | 2 641 554 | 1 259 363 | 16 793 925 | NA | NA | 14420 |
| Measles SIA Coverage (%) % | 101% | 103% | 99% | NA | NA | 92 % |
| Wastage rate (%) for measles SIA |  |  |  | NA | NA | NA |

# Targets and Plans for Measles SIAs and Increasing Routine MCV Coverage

Table 5.1. Target figures for Measles SIA (Please ensure targets are consistent with Section 7 and the Plan of Action in Section 9)

|  | Target | Target (if applicable, for phased* SIA)[Insert date] |
| --- | --- | --- |
|  | 2013 | 2014 |
| Target age group | 6 m to 14 years | 6 m to 14 years |
| Total population in the target group (nationally) | 37,030,886 | 38,141,812 |
| % of population targeted for the SIA | 40% | 62% |
| Number to be immunized with measles vaccine during the SIA | 14,731,988 | 23,594,969 |

*Phased: If a portion of the country is planned (e.g. 1/3 of the country each year for 3 years)

Table 5.2  Targets for routine MCV coverage over the duration of the Plan of Action (Please ensure targets are consistent with the Plan of Action in Section 9)

|  | Target | Target |
| --- | --- | --- |
|  | 2013 | 2014 |
| Routine MCV1 Coverage | 85% | 88% |
| Routine MCV2 Coverage (if applicable) | NA | NA |

Q5.1	Q5.1Please provide a detailed justification, based upon measles epidemiology, if the application requests support to vaccinate an age-range outside 9 months to 5 years through the SIA.[Type text]

The strategy adopted by the country to target children aged 6 months to 14 years for vaccination against measles is justified by the elements below: Indeed, from the in depth analysis of the measles epidemiology in the country, it appears that a follow-up campaign targeting children aged 6 months to 14 years is necessary to control the measles situation. In 2012, only 60% of confirmed cases were aged between 6 months and 4 years, 77% were aged 6 months to 9 years. Otherwise, 84% of confirmed cases were aged 6 months -14 years (see table below). Table V: Number of measles Igm+ cases by age group, S52-2012 Age Number of confirmed measles cases Total confirmed cases Cumulative percentage of confirmed cases 6-11months 82 82 8% 1 year 175 257 24% 2 years 138 395 36% 3 years 111 506 47% 4 years 145 651 60% 5 years 26 677 62% 6 years 54 731 67% 7 years 43 774 71% 8 years 37 811 75% 9 years 24 835 77% 10 years 28 863 80% 11 years 16 879 81% 12 years 18 897 83% 13 years 8 905 83% 14 years 10 915 84% Chart 7: Comparative development of proportions of ages affected by measles between 2011 and 2012 The WHO-UNICEF directives recommend vaccination against measles for children from 6 months in emergency contexts. In the DRC, where measles is highly endemic and taking into account the combination of factors such as the existence of pockets of unvaccinated children, malnutrition and limited access to primary health care, it is advisable to vaccinate children from 6 months. As shown in the opposite graph, the 2012 epidemic affected a higher proportion of children over 5 years compared to the 2011 epidemic. This is due to the fact that 2011 measles vaccination campaigns mainly targeted children under 5. This would explain the change in the epidemiological profile in 2012. This is corroborated with the analysis of the Measles IgM+ cases that show that in 2011 the proportion of cases over 10 years was 7.2%, while in 2012 this proportion was exceeded by almost double to 16.9 %. This data means that measles outbreaks are not interrupted with measles campaigns only targeting children under 10 years.

Q5.2	Q5.2If available, please summarize the targets in the national measles elimination plan OR provide the plan as an attachment. [Type text]

Considering the measles epidemic situation in the DRC, which is a cause for concern and falls within the framework of regional objectives, a plan to eradicate measles has been prepared and it covers the 2012-2020 period. This plan has the following objectives; GENERAL OBJECTIVE To contribute in the reduction of measles cases to less than one per one million inhabitants. Specific objectives Achieve a routine immunization coverage of at least 90 percent among children between 9 to 24 months by 2020 Introduce the second dose of MV by 2016 Achieve an immunization coverage of 95 percent amongst children from 6 to 59 months during monitoring campaigns in targeted provinces every year by 2020. Achieve immunization coverage of 95 percent amongst children from 6 to 15 months in during monitoring campaigns in targeted provinces every year by 2020. Strengthen measles surveillance by 2020.

# Financial Support

The information in this section including proposed commitments in Sections 6.3 and 6.4 will inform the discussion between the country and GAVI regarding amounts and types of GAVI support.

  - Government financial support for past Measles SIA

Countries should provide information on the total funding, and amount per targeted person, provided by the government for vaccines and for operational costs for at least the last measles SIA. This should be the actual expenses but if not available, the final budget should be referred to. Please also provide information on funding provided by partners.

Table 6.1. Share of financing for last measles SIA

| Item | Category | Governments funding (US$) | Partner support (US$) |
| --- | --- | --- | --- |
| Vaccines and injection supplies | Total amount | 0 | 4.615.179 |
|  | Amount per target person | 0 | 0,27* |
| Operational costs | Total amount | 66.004 | 7.585.156 |
|  | Amount per target person | 0,004 | 0,45 |

Year of SIA: 2011

Estimated target population: 16.890.826

Statistics provided on the basis of real expenses

*Operational costs financed by MSF, not taken into account

Support for past measles routine vaccines

Countries should provide information on the budget provided by the government for routine measles vaccines and injection supplies for the past 5 years, in total amount and amount per child immunized. Please also provide information on funding provided by partners.

Table 6.2. Share of financing for routine measles

| Year | Category | Governments funding (US$) | Partner support (US$) |
| --- | --- | --- | --- |
| 2007 | Total amount | 0 | ND |
|  | Amount per child immunized | 0 | ND |
| 2008 | Total amount | 0 | 1 123 179 |
|  | Amount per child immunized | 0 | 0,62 |
| 2009 | Total amount | 0 | 682 276 |
|  | Amount per child immunized | 0 | 0,32 |
| 2010 | Total amount | 138 992 | 880 825 |
|  | Amount per child immunized | 0 | 0,39 |
| 2011 | Total amount | 0 | 782 996 |
|  | Amount per child immunized | 0 | 0,35 |

Proposed support for upcoming Measles SIA

Countries should provide information on the proposed total funding commitment, and amount per targeted person, that will be provided by the government for vaccines and supplies, and for operational costs, for the measles SIA for which GAVI support is being requested. If planning a phased SIA with varying contributions, the table may be repeated for each phase. GAVI's support will not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the government funds (refer to the Plan of Action and/or cMYP). GAVI will not replace government funding. Each country is required to contribute towards the costs of immunizing its children against measles, using the past government contributions to measles SIAs as the reference point.

Please provide additional details below on operational costs summarized in Table 6.3a.

Table 6.3b. Amount (and financing) for the upcoming measles SIA operational costs

Financial support for activities to strengthen routine measles and immunization coverage in the Plan of Action

Q6.4.	Please describe the amount, use, and timeframe over which the government will financially contribute, considering the objectives of the available support from GAVI and costs of the proposed Plan of Action.

The government will take charge of all the traditional vaccines (MV, BCG, OPV, TT) as from 2013. It will benefit from the support of other partners in terms of operational costs for the setting up of routine immunization (supervision, monitoring, communication, planning) Financing expected from the government is estimated at 29,692,585 between 2013 and 2015 and includes: The purchase of traditional vaccines: USD 12,068,473 The purchase of inoculation material: USD 3,732,877 Co-financing of new vaccines: USD 13,891,235 Financing from GAVI shall be used for the preparatory and implementation stages as well as the setting up and continuation of campaigns to strengthen routine immunization. Logistics for the campaign (cold chain equipment, incinerators, transportation equipment etc.) will help reinforce routine EPI.

# Procurement

Measles vaccines and related equipment are financed by GAVI shall be procured through UNICEF.

Using the estimated total for the target population, please describe the estimated supplies needed for the measles SIA in the table below. If the SIA is phased, please repeat the table and provide the estimated supplies needed for each phase. Please ensure estimates are consistent with Tables 5.1 and 6.3a.

Table 7. Procurement information by funding source in 2013

|  |  | Proportion from government funds | Proportion from partner funds | Proportion from GAVI funds |
| --- | --- | --- | --- | --- |
| Required date for supplies to arrive | May |  |  |  |
| SIA Date | September and November 2013 |  |  |  |
| Number of vaccine doses for target population | 17,031,648 |  |  |  |
| Number of vaccine doses for wastage | 2,554,747 |  |  |  |
| Total number of vaccine doses | 19,586,395 | 0% | 0% | 100% |
| Number of syringes | 19,586,395 | 0% | 0% | 100% |
| Number of reconstitution syringes | 1.958,640 | 0% | 0% | 100% |
| Number of safety boxes | 215,450 | 0% | 0% | 100% |

Table 7. Procurement information by funding source in 2014

|  |  | Proportion from government funds | Proportion from partner funds | Proportion from GAVI funds |
| --- | --- | --- | --- | --- |
| Required date for supplies to arrive | February |  |  |  |
| SIA Date | February, April and July 2014 |  |  |  |
| Number of vaccine doses for target population | 27,292,577 |  |  |  |
| Number of vaccine doses for wastage | 4,093,886 |  |  |  |
| Total number of vaccine doses | 31,386,464 | 0% | 0% | 100% |
| Number of syringes | 31,386,464 | 0% | 0% | 100% |
| Number of reconstitution syringes | 3,186,647 | 0% | 0% | 100% |
| Number of safety boxes | 345,251 | 0% | 0% | 100% |

# Fiduciary Management Arrangement Data

Q8.	Q8.Please indicate whether funds for operational costs as requested in Section 6 should be transferred to the government or WHO and/or UNICEF and when funding is expected to be needed in country. Attach banking form if funding should be transferred to the government. Please note that WHO and/or UNICEF may require administrative fees of approximately 7% which would need to be covered by the operational funds.

The financing channel remains the same, funds from the government pass through the management and support unit which is placed under the Ministry of Public Health.

Please provide all of the data in table below. It may be submitted as a separate file if preferred.

| Information to be provided by the recipient organization/country |
| --- |
| 1. Name and contact information of the recipient organization(s) | To be filled by the financial department |
| 2. Experiences of the recipient organization with GAVI, World Bank, WHO, UNICEF, GFATM or other donors-financed operations (e.g. receipt of previous grants) | Yes or No? If YES, please state the name of the grant, years and grant amount: GAVI several years of experience World Bank 30.000.000 $ WHO: several years of experience UNICEF: several years of experience And other execution partners including Rotary, PROSANI etc. provide the following information: and provide the following: What are the main conclusions with regard to use of funds? The funds were used appropriately. for on-going Grants: Most recent financial management (FM) and procurement performance rating? Recent evaluation was carried out in 2012 by an audit firm known as STRONG which carried out an audit of GAVI funds from 2008 to 2011 and submitted its findings to GAVI Financial management (FM) and procurement implementation issues? Till date, we have not had any difficulties with regards to the putting in place of mechanisms for financial management and contract award. |
| 3. Amount of the proposed grant (US Dollars) | See details of the budget in the tables above. |
| 4. Information about financial management (FM) arrangements for Measles SIA: |
| Will the resources be managed through the government standard expenditure procedures channel? | Resources can be managed by consulting GAVI funds management mechanisms |
| Does the recipient organization have an FM or Operating Manual that describes the internal control system and FM operational procedures? | Yes, the procedures manual for the management of administrative and financial resources of the Ministry of Health is available and it describes the internal control system. EPI has an internal audit service which is also operational. |
| What is the budgeting process? | A budget spending plan is submitted to the strategic ICC for approval and after validation, the budget is executed. However, the monthly evaluation of expenditure shall be done by the technical ICC |
| What accounting system is used or to be used, including whether it is a computerized accounting system or a manual accounting system? | The accounting system uses ''SOMMA COMPTA'' software which is more advanced as compared to the software proposed (known as “TROMPO”) which will soon be operational. |
| What is the staffing arrangement of the organization in accounting, auditing, and reporting? (number of personnel, qualification; experience) | Head of the administrative and finance department; Bachelor’s degree in financial management Head of the financial department, Degree in financial management. Accountant, graduate in financial management 2 Auditors, both degree holders |
| What is the bank arrangement? Provide details of the bank account opened at the Central Bank or in a commercial bank and the list of authorized signatories include titles | All financial operations must pass through the following banks: Raw-Bank: account N° 01009961101-45, 01009961102-42, 01009961103-39; TMB (Trust Merchant Bank): 1201-5241957-01-62, 1201-5241957-02-63 There are two signatories Dr Audry MULUMBA, Doctor and EPI director Head of Financial and Administrative department. Mrs KAWENDE FATUMA |
| What are the basic flows of funds arrangements in place or to be used to ensure timely disbursement of funds to Implementing Entities and to beneficiaries? | The two banks we are working with are well renowned and the program has never had any problems as concerns the disbursement of funds. |
| Does the implementing entity keep adequate records of financial transactions, including funds received and paid, and of the balances of funds held? | The implementing entity has and keeps updated records, notably the cash and bank records, withdrawal and deposit vouchers and bank records as well as detailed files of property acquired from partners. |
| How often does the implementing entity produce interim financial reports? | Intermediary financial reports are done on a monthly basis for they have assessed during the sub-committee meetings which hold monthly. |
| Are the annual financial statements audited by an external audit firm or Government audit institution (e.g. Auditor General Department…)? | Annual financial statements are audited by an external audit firm as is the case with GAVI funds and those of other partners. For example, UNICEF funds are audited by the audit bench, government funds are audited by government inspectors while audit for the program is conducted internally. |
| 5. Information about procurement management arrangements for the Measles SIA: |
| Which public contract award system is used or can be used for SVA against measles? (national procedures for contract award or specific procedures) | These are the national procurement procedures stated in the Ministry of Public Health’s financial management procedures manual and also in the GAVI funds management mechanism. |
| Does the recipient organization have a procurement plan or a procurement plan will be prepared for the Measles SIA? | As far as investment is concerned, a procurement plan already exists but it will be applied for SIAs against measles. |
| Is there a functioning complaint mechanism? | The mechanism for the management of complaints has not yet been set up but this will be done for SIAs against measles. |
| What is the staffing arrangement of the organization in procurement? Does the implementing entity have an experienced procurement specialist on its staff? | The implementing entity has an experienced procurement specialist who is: The head of general services: Holder of a degree in Law |
| Are there procedures to inspect for quality control of goods, works, or services delivered? | During procurement, quality and quantity control procedures of goods are respected. The programme has a budget and control department which is in charge of quality and quantity control. |

# List of documents to attach to this proposal

  - Minutes of the ICC or equivalent, endorsing the proposal

  - Current cMYP reflecting comprehensive strategies to strengthen routine immunization coverage, based on the Health Sector Strategic Plan, and valid for at least one year from the proposed date of SIAs; or timing can be agreed with the Secretariat for the next updating.

  - A detailed plan of action and budget for the measles SIA and MCV1 strengthening activities, for example based upon the WHO Measles Planning and Implementation Field Guide, including specific activities:

    - To strengthen routine MCV1 coverage in order to increase population level immunity and hence the interval between SIAs

    - To implement the SIA

    - What will be undertaken as part of the planning and implementation of the measles SIA that will strengthen routine immunization capacity and service delivery

    - To evaluate the implementation of the routine strengthening activities done during the SIA

    - To assess through the a survey the coverage achieved through the SIA

    - Covering the period from beginning of support requested in this application until just prior to the next anticipated measles or measles-rubella (MR) SIA, or 2017, whichever is earlier. If it is planned to cover a portion of the country each year (Phased), the PoA should cover the period until the entire national cohort has been immunized.

  - National measles elimination plan, if available

  - Banking form, if applicable

Nota Bene:

- In the case where the taking into account of vaccinated children aged 6 months to 10 years is retained for measles follow up campaigns from 2013 to 2014, the restructured budget is presented in the following manner:

In 2013

| Budget Post 2013 | Expected total cost in USD | Government funding | WHO funding | UNICEF funding | GAVI operational cost funding ($ USD) |
| --- | --- | --- | --- | --- | --- |
| Human resources | $ 2,191,432 |  |  |  | $ 2,191,432 |
| Management tools | $ 64,200 |  | $ 64,200 |  |  |
| Strengthening of logistics | $ 1,638,376 | $ 600,000 |  |  | $ 1,038,376 |
| Micro planning and Training | $ 870,326 |  |  |  | $ 870,326 |
| Follow-up supervision and evaluation | $ 183,640 | $ 183,640 |  |  |  |
| Post campaign surveys | $ 200,000 |  | $ 200,000 |  |  |
| Input distribution | $ 290,000 |  |  | $ 290,000 |  |
| Social mobilization | $ 265,450 |  |  | $ 265,450 |  |
| Administrative costs (7%) | $ 399,240 |  |  |  | $ 399,240 |
| Transfer fees | $ 152,567 |  |  |  | $ 152,567 |
| Vaccines and injection material | $ 5,779,874 |  |  |  | $ 5,779,874 |
| TOTAL | $ 12,035,103 | $ 783,640 | $ 264,200 | $ 555,450 | $ 10,431,813 |

Target population: 10,568,600

In 2014

| Budget Post 2014 | Expected total cost in USD | Government funding | WHO funding | UNICEF funding | GAVI operational cost funding ($ USD) |
| --- | --- | --- | --- | --- | --- |
| Human resources | $ 3,471,853 |  |  |  | $ 3,471,853 |
| Management tools | $ 89,700 |  | $ 89,700 |  |  |
| Strengthening of logistics | $ 6,252,601 |  |  |  | $ 6,252,601 |
| Micro planning and Training | $1,451,596 |  |  |  | $1,451,596 |
| Follow-up supervision and evaluation | $ 282,120 | $ 282,120 |  |  |  |
| Post campaign surveys | $ 700,000 |  | $ 700,000 |  |  |
| Input distribution | $ 435,000 |  |  | $ 435,000 |  |
| Social mobilization | $ 403,205 |  |  | $ 403,205 |  |
| Administrative costs (7%) | $ 916,025 |  |  |  | $ 916,025 |
| Transfer fees | $ 350,053 |  |  |  | $ 350,053 |
| Vaccines and injection material | $ 9,540,909 |  |  |  | $ 9,540,909 |
| Total | $ 23,893,062 | $ 282,120 | $ 789,700 | $ 838,205 | $ 21,983,037 |

Target population: 17,025,615

- Vaccination scenario of children aged 6 to 59 months

# Footnotes

For further information on vaccines, please visit: http://www.who.int/immunization standards/ vaccine quality/PQ vaccine list en/en/index.html

Please note: The IRC may review previous applications to GAVI.

Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question