Application Form for Country Proposals

Measles Supplementary Immunisation Activities (SIAs)

Available for Afghanistan, Chad, DR Congo, Ethiopia, Nigeria, Pakistan

Submitted by

The Government of [Nigeria]

Date of submission: [15th February 2013]

Deadline for submission:  15th  February  2013

(Or a date otherwise agreed with the GAVI Secretariat)

Please submit the Proposal using the form provided.

Enquiries to: proposals@gavialliance.orgor representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE

GRANT TERMS AND CONDITIONS

Countries will be expected to sign and agree to the following GAVI Alliance terms and conditions in the application forms, which may also be included in a grant agreement to be agreed upon between GAVI and the country:

FUNDING USED SOLELY FOR APPROVED PROGRAMMES

The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance for this application will be used and applied for the sole purpose of fulfilling the programme(s) described in this application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for this application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.

AMENDMENT TO THIS PROPOSAL

The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in this application. The GAVI Alliance will document any change approved by the GAVI Alliance, and this application will be amended.

RETURN OF FUNDS

The Country agrees to reimburse to the GAVI Alliance, all funding amounts that are not used for the programme(s) described in this application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.

SUSPENSION/ TERMINATION

The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in this application, or any GAVI Alliance-approved amendment to this application.  The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in this application if a misuse of GAVI Alliance funds is confirmed.

ANTICORRUPTION

The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with this application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.

AUDITS AND RECORDS

The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.

The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds.  If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.

CONFIRMATION OF LEGAL VALIDITY

The Country and the signatories for the government confirm that this application is accurate and correct and forms a legally binding obligation on the Country, under the Country’s law, to perform the programmes described in this application.

CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARENCY AND ACCOUNTABILITY POLICY

The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and will comply with its requirements.

ARBITRATION

Any dispute between the Country and the GAVI Alliance arising out of or relating to this application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English.

For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance.  For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.

The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in this application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death.  Country is solely responsible for all aspects of managing and implementing the programmes described in this application.

Use of commercial bank accounts

The eligible country government is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support, including HSS, ISS, CSO and vaccine introduction grants.  The undersigned representative of the government confirms that the government will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.

# Application Specification

Vaccine: Measles, 10 doses/vial, lyophilised

Q1.	Please specify the timing (week/month and year) of the planned SIA, and the year of the next projected SIA.

17th-21st August   2013  -  Northern States

21st 25th September  2013  -  Southern States[

Indicate the week

# Executive Summary

Q2.	The objective of GAVI’s assistance for measles SIAs is to strengthen the impact of the comprehensive package of support offered by the GAVI Alliance partners to sustainably prevent measles deaths. The comprehensive support is designed to:

- Strengthen health systems to deliver routine immunisations, including MCV1 (eg. Health Systems  Strengthening resources),

- Improve the sustainability of national financing for measles immunisation and other vaccines (eg. Financial commitments from the country; vaccine co-financing)

- Support the routine delivery of the second dose of measles-containing vaccine (MCV2), and

- Reduce morbidity and mortality from rubella through the introduction of measles-rubella (MR) vaccine.

Please provide a summary of the ways through which the proposal addresses the objective above.

Nigeria has the largest population at risk of measles infections in Africa, with highly densely populated cities such as Lagos, Kano, Ibadan, Port Harcourt, Bauchi, Kaduna and Enugu. It also has large populations in hard to reach areas which make immunization service delivery difficult.

Between 2000 and 2005 Nigeria reported 649,105 measles cases nationally through the national surveillance system.  In December 2005 and October 2006 a sub national catch up campaign was conducted in 19 northern states and  17 southern states respectively. Two follow up campaigns were conducted in 2008 and 2011. However, between 2006 and 2009 the number of measles declined to 2,697 cases. The recent resurgence of measles resulting in 8,243 cases in 2010 and 11,043 cases in 2011 further justifies the ultimate need for another follow up campaign in 2013 in Nigeria.

The country because of its large population at risk and vast land mass and previous experience from the catch up and follow-up campaigns would conduct the measles SIA in phases in 2013. Phase one proposed for August 2013 would cover the 19 Northern states and the FCT with a total of 15,978,622 eligible children aged 9-59 months. The second phase of the campaign is to be conducted in the 17 southern states with a total  of 13,698,004 eligible children aged 9-59 months a month after the Northern phase. In total, 29,676,626 children are eligible for the 2013 follow up campaign. In terms of vaccine requirement 35,611,960 doses of measles vaccines would be required for the 2013 follow up campaign based on the target population and a 17% wastage rate.

The estimated cost of the campaign in 2013 is US$ 38,842,333 for the procurement of vaccine and operational costs; (Vaccine cost stood at US$ 12,339,795, Operational cost is US$ 26,502,538. Overall the cost per person vaccinated in Nigeria will be 1.31 USD. The Government of Nigeria (GoN) is committed to raise $18,716,546 necessary to cover the cost for vaccines, devices and part of the operational costs. The GoN would welcome GAVI Alliance support to bridge the gap of $20,125,787 for the campaign to cover the remaining operational costs.

Goals and Objectives:

The goal of the measles follow up campaign is to reduce the national measles mortality by at least 95% compared with 2000 estimates; accelerate/support measles elimination targets; and to prevent the risk of major outbreaks through immunizing at least 95% of the population at risk in each LGA by 2020.

Specifically the target is to,

- Vaccinate at least 95% of those aged 9 months to 59 months at risk of measles infection with measles vaccine during the follow up campaign regardless of previous vaccination history.

- Use the follow up campaigns to strengthen the health system in the broader context (routine immunization, cold chain capacity and supply chain, waste management, strengthen outbreak response, laboratory capacity, data management, planning at LGA/Ward/Health Facility levels).

- Strengthen the pharmaco-vigilance system for monitoring adverse events following immunization

- Strengthen laboratory based surveillance system for measles

The key components of the follow up campaign includes: planning phase with the establishment of a national coordinating body and inter-sectoral technical committees; conducting resource mobilization activities; developing training materials; review of field guides, logistics and data management tools; conducting post coverage survey; organizing state, LGA and ward micro-planning and implementation training; developing a waste management and AEFI plans and conducting social mobilization activities. In addition post implementation activities that include mop up and keep up vaccinations in identified wards/LGAs.

The completion of the cold chain expansion and rehabilitation at the national and zonal levels, provides Nigeria with sufficient cold storage capacity for the measles vaccines for all the phases of the campaign including the routine immunization system. Currently, the combined installed positive storage capacity at the national level (National Strategic Cold Store and the 6 Zonal cold Stores) is 225,144 liters positive and 53,991 liters negative.

The country has established a pharmaco-vigilance system following the recent MenAfrivac campaign and this has further strengthened the infrastructure for measles case and laboratory based surveillance. In addition, the measles control program will be leveraged to strengthen critical components of the health system more broadly;

- Strengthening planning for Routine Immunization and use SIA Micro plans to update target population for RI services.

- Conduct needs assessment and includes key topics to reinforce routine immunization skills in SIA training.

- Foster strong relationship with media for accurate, supportive coverage of RI

- Update inventory, distribute new equipment to meet needs for SIA and RI

- Re-inforce health worker skills on measles case detection and reporting.

Building on the experience with successful MenAfriVac, Measles and Polio campaigns, and in light of the acute community awareness of measles, demand for measles preventive vaccination is expected to be high. A post-implementation coverage survey will be conducted within four to eight weeks of the conclusion of the campaign.

# Signatures of the Government and National Coordinating Body

  - The Government

The Government of Nigeria would like to expand the existing partnership with the GAVI Alliance to further prevent measles deaths and for the improvement of the infant routine immunisation programme of the country, and specifically hereby requests GAVI support for measles vaccine (lyophilised, 10doses/via) for supplementary immunisation activities.

The Government of Nigeria commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan and the Plan of Action as presented in this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

The Government of Nigeria acknowledges and accepts the GAVI Alliance Grant Terms and Conditions included in the Application Form for Country Proposals for Measles Supplementary Immunisation Activities.

Please note that this application will not be reviewed or approved by GAVI’s Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Prof Onyebuchi Christian CHUKWU | Name | Dr Ngozi OKONJO –IWEALA |
| Date |  | Date |  |
| Signature |  | Signature |  |

This proposal has been compiled by (these persons may be contacted in case the GAVI Secretariat has queries on this document):

| Full name | Position | Telephone | Email |
| --- | --- | --- | --- |
| Dr A.J. OTERI Dr Bassey Okposen | Deputy Director GAVI Focal Point Chief Medical Officer/GAVI Focal point(New) | +2348026724545 +2348023199898 | josephoteri@yahoo.co.uk basenokng@yahoo.com |
| Dr Nneka ONWU | Chief Medical Officer/Head Non Polio SIAs | +2348023024254 | nnekaonwu@yahoo.com |

  - National Coordinating Body/ Inter-agency Coordinating Committee for Immunisation

We the members of the Inter-Agency Coordinating Committee for Immunisation (ICC), Health Sector Coordinating Committee (HSCC), or equivalent committee, met on this date, 8TH November 2012  to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as document number: 8th November,2012]

| Name/Title | Agency/Organisation | Signature |
| --- | --- | --- |
| Prof. Onyebuchi C Chukwu, Honourable Minister of Health | Federal Ministry of Health |  |
| Dr Muhammad Ali- Pate, Hon. Minister of State for Health | Federal Ministry of Health |  |
| Mrs. Fatima Bamidele, Permanent Secretary | Federal Ministry of Health |  |
| Dr Mansur Kabir, Director Public Health | Federal Ministry of Health |  |
| Dr Ado J.G Muhammad, Executive Director | National Primary Health Care Development Agency |  |
| Dr Alex Gasasira, OIC, WHO | WHO |  |
| Mr Ibrahim Fall, Ag. Country Representative | UNICEF |  |
| Dr Dinesh Nair | World Bank |  |
| Alhaji Abdu Garba | USAID |  |
| Dr Anthony Ayeke, International Aid/Cooperation Officer | EC Delegation |  |
| Dr Owen Wiwa, Country Director | Clinton Health Access Initiative |  |
| Dr Ben Anyene, National Immunization Policy Advisor | PRRINN-MCH |  |

# Immunisation Programme Data

Please provide in the table below the reported national annual coverage data for the first dose of measles-containing vaccine (MCV1) from the WHO/UNICEF Joint Reporting Form for the three most recent years. Also provide survey estimates of national MCV1 coverage for the three most recent years, if available.

Table 4.1. Reported MCV1 coverage

| Trends of reported national MCV1 coverage |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | WHO/UNICEF Joint Reporting Form |  |  | Survey |  |  |
| Year | 2009 | 2010 | 2011 | 2003(NICs) | 2006(NICs) | 2010(NICs) |
| Survey type |  |  |  | MCV1 | MCV1 | MCV1 |
| Total population in the target age cohort | 5,546,453 | 5,558,414 | 6,115,146 |  |  |  |
| Number vaccinated | 4,969,502 | 5,369,764 | 5,932,299 |  |  |  |
| MCV1 Coverage (%) | 90 | 97 | 97 | 25.3% | 32.7% | 63.6% |
| Wastage rate (%) for MCV1 |  |  |  |  |  |  |

Please provide in the table below reported national (or sub-national if applicable) coverage estimates for the three most recent measles SIAs. Also provide post-campaign survey coverage estimates, if available.

Please Note:  No post campaign coverage surveys have been done for the past  measles SIAs..

Table 4.2. Measles SIA coverage

| Past measles SIA coverage |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Reported |  |  | Survey |  |  |
| Year | 2006 | 2008 | 2011 |  |  |  |
| Type of survey |  |  |  |  |  |  |
| Target age group | 9 months to 15 years | 9months to 59 months | 9 to 59 months |  |  |  |
| Total population in the target age group | 31,478,681 | 25,245,739 | 27,876,145 |  |  |  |
| Geographic extent (national, subnational) | Subnational | National | National |  |  |  |
| Number vaccinated | 26,358,790 | 28,275,225 | 28,483,970 |  |  |  |
| Measles SIA Coverage (%) | 90% | 113% | 102% |  |  |  |
| Wastage rate (%) for measles SIA | 18.3% | --- | 6.79% |  |  |  |

# Targets and Plans for Measles SIAs and Increasing Routine MCV Coverage

Table 5.1. Target  figures for Measles SIA (Please ensure targets are consistent with Section 7 and the Plan of Action in Section 9)

|  | Target | Target (if applicable, for phased* SIA) | Target (if applicable, for phased* SIA) |
| --- | --- | --- | --- |
|  | [Aug/Sept 2013 | [Insert date] | [Insert date] |
| Target age group | 9months-59months |  |  |
| Total population in the target group (nationally) | 29,676,626 |  |  |
| % of population targeted for the SIA | 100% |  |  |
| Number to be vaccinated with measles vaccine during the SIA | 29,676,626 |  |  |

*Phased: If a portion of the country is planned (e.g. 1/3 of the country each year for 3 years)

Table 5.2. Targets for routine MCV coverage over the duration of the Plan of Action (Please ensure targets are consistent with the Plan of Action in Section 9)

|  | Target | Target | Target | Target |
| --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |
| Routine MCV1 Coverage | 75% | 78% | 82 % | 85% |
| Routine MCV2 Coverage (if applicable) | N/A | N/A |  |  |

Q5.1	Please provide a detailed justification, based upon measles epidemiology, if the application requests support to vaccinate an age-range outside 9 months to 5 years through the SIA.

NOT APPLICABLE

Q5.2	If available, please summarise the targets in the national measles elimination plan OR provide the plan as an attachment.

Type Text At the end of 2012 - Finalized a strategic plan for measles elimination and successfully apply for measles SIAs support to GAVI. - Mapped all LGAs with the highest burden of measles completed for immunization strengthening activities (vulnerability studies) - Continued to strengthen on-going case based surveillance and data systems for measles as well as case management At the end of 2013 - Accelerated routine immunization coverage of infants with first dose measles only vaccines to 78% in every district in accordance with the 2011- 2015 cMYP - Implemented keep-up vaccination strategy in all LGAs where measles resurge vaccinating missed opportunities for all antigens especially OPV - Conducted the highest quality of measles follow up campaign (integrated with polio and vitamin A) in September and November with post campaign mop-ups to ensure all LGAs attain 95% coverage

# Financial Support

The information in this section including proposed commitments in Sections 6.3 and 6.4 will inform the discussion between the country and GAVI regarding amounts and types of GAVI support.

  - Government financial support for past Measles SIA

Countries should provide information on the total funding, and amount per targeted person, provided by the government for vaccines and for operational costs for at least the last measles SIA. This should be the actual expenses but if not available, the final budget should be referred to. Please also provide information on funding provided by partners.

Table 6.1. Share of financing for last measles SIA

| Item | Category | Government funding (US$) | Partner support (US$) |
| --- | --- | --- | --- |
| Vaccines and injection supplies | Total amount | 14,060,000 | NIL |
|  | Amount per target person | 0.45 | NIL |
| Operational costs | Total amount | 17,802,702 | 700,000 (WHO) |
|  | Amount per target person | 0.57 | 0.03 |

Year of SIA: 2011

Estimated target population:  27,876,145 (using population growth factor from projected 2006 census)

Note: The downward decline in the target population is due to the fact that the earlier submission was based on the previous measles campaign coverage; but the revised document is based on projected target population of the 2006 census following inputs from partners.

Are the amounts provided based on actual expenses or final budget?

They were based  on the  Final budget.

Support for past measles routine vaccines

Countries should provide information on the budget provided by the government for routine measles vaccines and injection supplies for the past 5 years, in total amount and amount per child immunized. Please also provide information on funding provided by partners.

Table 6.2. Share of financing for routine measles

| Year | Category | Governments funding (US$) | Partner support (US$) |
| --- | --- | --- | --- |
| 2011 | Total amount | 2,030,859 | 0 |
|  | Amount per child immunized | 0.34 | 0 |
| 2010 | Total amount | 2,264,785 | 0 |
|  | Amount per child immunized | 0.42 | 0 |
| 2009 | Total amount | 2,469,406 | 0 |
|  | Amount per child immunized | 0.50 | 0 |
|  | Total amount |  | 0 |
| 2008 | Amount per child immunized |  | 0 |
|  | Total amount |  | 0 |
| 2007 | Amount per child immunized |  | 0 |

  - Proposed support for upcoming Measles SIA

Countries should provide information on the proposed total funding commitment, and amount per targeted person, that will be provided by the government for vaccines and supplies, and for operational costs, for the measles SIA for which GAVI support is being requested. If planning a phased SIA with varying contributions, the table may be repeated for each phase. GAVI's support will not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the government funds (refer to the Plan of Action and/or cMYP). GAVI will not replace government funding. Each country is required to contribute towards the costs of immunising its children against measles, using the past government contributions to measles SIAs as the reference point.

Table 6.3a. Proposed financing for the upcoming measles SIA for which GAVI support is requested.

Estimated target population:  29,676,626 - (100% of target population to be covered)

Please provide additional details below on operational costs summarised in Table 6.3a.

Table 6.3b. Amount (and financing) for the upcoming measles SIA operational costs

| Cost Category | Total projected cost ($US) | Government funds (US$) | Partner funds (US$) | GAVI operational funds (US$) |
| --- | --- | --- | --- | --- |
| Vaccines and devices | 12.339,795 | 12,339,795 | 0 | 0 |
| Vaccination personnel allowances | 12,672,994 | 0 | 0 | 12,672,994 |
| Planning/ Training / Evaluation | 1,516,157 | 102,217 | 0 | 1,413,947 |
| Data Tools & Other Planning Materials | 1,023,801 | 1,023,801 | 0 | 0 |
| Social Mobilization | 2,474,836 | 224,226 | 0 | 2,250,610 |
| Logistics & Cold Chain Management | 6,907,283 | 4,391,117 | 0 | 2,516,166 |
| Measles Surveillance & Coverage Survey | 961,665 | 304,848 | 0 | 656,817 |
| Other Operational Costs | 945,802 | 330,548 | 0 | 615,254 |
| TOTAL | 38,842,333 | 18,716,546 |  | 20,125,787 |

- Expected shortfall to be mobilised from Partners.

  - Financial support for activities to strengthen routine measles and immunisation coverage in the Plan of Action

Q6.4.	Please describe the amount, use, and timeframe over which the government will financially contribute, considering the objectives of the available support from GAVI and costs of the proposed Plan of Action.

Government of Nigeria is expected to provide a total of USD 18,716,546 ( USD 6,376,751 as operational costs and USD 12,339,795 million for vaccines and devices) as its financial obligation towards the campaign. Keep up vaccination: Keep up vaccinations will be conducted post implementation in wards with pool of susceptible children. This Keep up vaccination would be an organized outreach conducted within the health facility catchment area therefore making it an entry point for routine Immunisation. The Federal Ministry of Health weekly epidemiological report and routine measles monthly data would be the marker to the location of pool of susceptibles. The wards /LGA would be categorized based on monthly routine data, a routine coverage of < 80% aggregated over three months and suspected or confirmed case of measles is an indicator for keep up vaccination. The measles follow up campaign ward disaggregated immunization data will also be used in identifying viable sites for enhanced routine immunization outreach services and these will be explored during the keep up vaccination exercise This information will be utilized by the identified Measles focal point/ Surveillance/Outbreak and Response team in LGA/State through the Zonal coordinator to plan for an immediate vaccination in the affected wards/LGA. The plan will utilize: - Micro-plan (target population, estimated number of households per catchment area, maps) - Measles quarterly coverage(HF catchment area) - Surveillance report(Measles cases) - SIA ward disaggregated immunization coverage The implementers of the vaccination in the LGA/Ward would include the Zonal Technical Officer(ZTO) assigned to the LGA, the LIO, Health Educator, Two(2) Health workers(vaccinator/Recorder) and Four(4) Community Leaders(WDC chairman, secretary, Traditional leader, Women leader).The operational level is the ward usually with a population range of 5,000 - 15,000. The target population will include children 9 months to 23 months of age irrespective of their previous vaccination status. The outreach location may be divided into six(6) sites with a daily work schedule of 2 sites /day (Work load - 200 children/day). The communities will be sensitized prior to the vaccination exercise, at least two community dialogues sessions will be held. This dialogue will seek to obtain consensus for the outreach, set date and time and mobilize the various households for the exercise. It will also sensitize the communities on community surveillance and the various antigens on the EPI schedule. At the outreach, children aged 9months to 23 months will be given measles vaccine irrespective of previous immunization status, in addition other due vaccines and vitamin A will be administered.(‘supermarket approach’) The data will be recorded and reported in the health facility data tool. This activity would be implemented quarterly post implementation of the 2013 Follow up campaign proposed for August and September 2013. The Financial cost of the Keep up vaccination per year is US$ 330,548 and till 2015 it comes to US$ 991,645. Health Systems Strengthening (HSS): Activities under HSS will include training, logistics, cold chain and waste management which have a cost implication of US$ 7,253,467.

# Procurement

Measles vaccines and supplies supported by GAVI shall be procured through UNICEF.

Using the estimated total for the target population, please describe the estimated supplies needed for the measles SIA in the table below. If the SIA is phased, please repeat the table and provide the estimated supplies needed for each phase. Please ensure estimates are consistent with Tables 5.1 and 6.3a.

Table 7. Procurement information by funding source

|  |  | Proportion from government funds | Proportion from partner funds | Proportion from GAVI funds |
| --- | --- | --- | --- | --- |
| Required date for supplies to arrive | June 2013 |  |  |  |
| SIA Date | AUG/SEPT 2013 |  |  |  |
| Number of vaccine doses for target population | 29,676,626 |  |  |  |
| Number of vaccine doses for wastage | 5,935,325 |  |  |  |
| Total number of vaccine doses | 35,611,951 | 100% | Nil | [ Nil |
| Number of syringes | 32,644,288 | [100% | [Nil | Nil |
| Number of reconstitution syringes | 3,917,315 | 100% | [Nil | Nil |
| Number of safety boxes | 383,897 | 100% | Nil | Nil |

# Fiduciary Management Arrangement Data

Q8.	Please indicate whether funds for operational costs as requested in Section 6 should be transferred to the government or WHO and/or UNICEF and when funding is expected to be needed in country. Attach banking form if funding should be transferred to the government. Please note that WHO and/or UNICEF may require administrative fees of approximately 7% which would need to be covered by the operational funds.

Operational funds for the campaign should be transferred to the government of Nigeria using the existing GAVI accounts. Transfers meant for WHO and UNICEF will be transferred to them on instruction from GAVI

Please provide all of the data in table below. It may be submitted as a separate file if preferred.

| Information to be provided by the recipient organization/country |  |  |  |
| --- | --- | --- | --- |
| 1. Name and contact information of the recipient organization(s) | NATIONAL PRIMARY HEALTH CARE DEVELOPMENT AGENCY PLOTS 681/682 Port Harcourt Crescent, Off Gimbiya St, Area 11,Garki,FCT NIGERIA E mail :nphcdaabuja@yahoo.com |  |  |
| 2. Experiences of the recipient organization with GAVI, World Bank, WHO, UNICEF, GFATM or other donors-financed operations (e.g. receipt of previous grants) | Yes If YES, please state the name of the grant, years and grant amount: Nigeria has had grant from GAVI for Men A campaign in 2011 and provide the following: for completed Grants: - What are the main conclusions with regard to use of funds? for on-going Grants: - Most recent financial management (FM) and procurement performance rating? - Financial management (FM) and procurement implementation issues? |  |  |
| 3. Amount of the proposed grant (US Dollars) | US$ 20,125,787 |  |  |
| 4. Information about financial management (FM) arrangements for Measles SIA: |  |  |  |
| - Will the resources be managed through the government standard expenditure procedures channel? | Yes |  |  |
| - Does the recipient organization have an FM or Operating Manual that describes the internal control system and FM operational procedures? | Yes |  |  |
| - What is the budgeting process? | Annual cycle |  |  |
| - What accounting system is used or to be used, including whether it is a computerized accounting system or a manual accounting system? | Manual |  |  |
| - What is the staffing arrangement of the organization in accounting, auditing, and reporting? | The Agency has adequate accounting and auditing and reporting mechanisms as provided under the civil service guidelines. |  |  |
| - What is the bank arrangement? Provide details of the bank account opened at the Central Bank or in a commercial bank and the list of authorized signatories include titles | The agency has dedicated bank accounts in government approved commercial banks which has been communicated to the GAVI Alliance secretariat. The signatories to the GAVI ISS account is the ED NPHCDA and the chairman of Rotary plus |  |  |
| - What are the basic flows of funds arrangements in place or to be used to ensure timely disbursement of funds to Implementing Entities and to beneficiaries? | Once funds are approved, conversion to the local currency is done using the prevailing apex bank rates. e transaction is used and it takes a minimum of two days to get to the beneficiary account |  |  |
| - Does the implementing entity keep adequate records of financial transactions, including funds received and paid, and of the balances of funds held? | Yes records of financial transactions are kept and properly backed up. |  |  |
| - How often does the implementing entity produce interim financial reports? | Quarterly |  |  |
| - Are the annual financial statements audited by an external audit firm or Government audit institution (e.g. Auditor General Department…)? | It is audited by an external accounting firm and government internal audit. |  |  |
| 5. Information about procurement management arrangements for the Measles SIA: |  |  |  |
| - What procurement system is used or will be used for the Measles SIA? | The government procurement system will be used |  |  |
| - Does the recipient organization have a procurement plan or a procurement plan will be prepared for the Measles SIA? | There is a procurement plan but an additional procurement plan will be prepared for the measles SIA |  |  |
| - Is there a functioning complaint mechanism? | Yes (SERVICOM) |  |  |
| - What is the staffing arrangement of the organization in procurement? Does the implementing entity have an experienced procurement specialist on its staff? | There is a unit under the office of the executive director and is headed by a director with other complement staff of relevant disciplines. |  |  |
| - Are there procedures to inspect for quality control of goods, works, or services delivered? | Yes, there are independent verifier office headed by a consultant |  |  |

# List of documents to attach to this proposal

  - Minutes of the ICC or equivalent, endorsing the proposal

  - Current cMYP reflecting comprehensive strategies to strengthen routine immunisation coverage, based on the Health Sector Strategic Plan, and valid for at least one year from the proposed date of SIAs; or timing can be agreed with the Secretariat for the next updating.

  - A detailed plan of action and budget for the measles SIA and MCV1 strengthening activities, for example based upon the WHO Measles Planning and Implementation Field Guide, including specific activities:

    - To strengthen routine MCV1 coverage in order to increase population level immunity and hence the interval between SIAs

    - To implement the SIA

    - What will be undertaken as part of the planning and implementation of the measles SIA that will strengthen routine immunisation capacity and service delivery

    - To evaluate the implementation of the routine strengthening activities done during the SIA

    - To assess through the a survey the coverage achieved through the SIA

    - Covering the period from beginning of support requested in this application until just prior to the next anticipated measles or measles-rubella (MR) SIA, or 2017, whichever is earlier. If it is planned to cover a portion of the country each year (Phased), the PoA should cover the period until the entire national cohort has been vaccinated.

  - National measles elimination plan, if available

  - Banking form, if applicable

For more information on vaccines : http://www.who.int/immunization standards/ vaccine quality/PQ vaccine list en/en/index.html

Note : The IRC may review previous applications to GAVI.

Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question