|  |  |  |  |  | [V2.8]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Response To Conditions. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Ethiopia. |  |  |  |  |  |  |  |
| Date of submission: 1/23/2013. |  |  |  |  |  |  |  |
| Deadline for submission: 2/1/2013. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2011. |  |  |  |  |  |  |
|  |  |  | End Year. | 2015. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of December 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Preventive Campaign Support; Meningogoccal, 10 dose(s) per vial, LIQUID; 2013; 2015.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (Meningogoccal campaign). 6. New and Under-Used Vaccines (NVS Routine). 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for Meningogoccal, 10 dose(s) per vial, LIQUID campaign support. 7.2.1 Summary for Meningogoccal campaign support. 7.2.2 Grant Support for Operational Costs of the Meningogoccal Campaign. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for Meningogoccal, 10 dose(s) per vial, LIQUID campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine Meningogoccal, 10 dose(s) per vial, LIQUID. Table Annex 3.1 D Estimated numbers for Meningogoccal, 10 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. Ethiopia lies in the African Meningitis Belt which extends from the Red Sea in the East to the Atlantic ocean in the West, in 1981 there were 50,000 cases and nearly a thousand deaths and in 1989 there were 46,000 cases and 1,700 deaths due to meningococcal meningitis. Major epidemics usually occur every 8 to 12 years and the last report was in 2001 when 6,964 cases had been reported with 330 deaths. Amhara, SNNPR and Oromia regions are the most affected ones that reported largest cases during the outbreaks occurred in the past. In January 2012, a risk assessment was done using district prioritization tool and result showed regional risk level of 5 high risk, 3 moderate risk and 3 low risk regions for meningitis outbreak. A strategic decision was made to conduct the campaign in phased way taking into account the quantitative output of the risk assessment; vaccine availability and logistical feasibility. The immunization is intended to cover the entire country, with a cumulated target of 58,427,373 populations from 1-29 years and a need of 64.3 million doses total. The vaccination will be phased over three years, starting 2013, and covering 19 million persons in 2013, 24.5 million in 2014 and 15 million in 2015 respectively. The vaccine introduction plan was also very much appreciated by the ICC and preparatory activities will start immediately once GAVI support is approved. Key preparatory activities include strengthening the existing national new vaccine coordination core committee and establishing the same at subnational levels, developing training materials, logistics and data management tools; organizing national and subnational trainings; conducting advocacy and social mobilization activities and AEFI monitoring and case based surveillance. In order to have sufficient cold chain space for the Meningitis A vaccine, additional cold chain equipment will be put in place and actions will be taken to fill gaps seen in the recent rapid cold chain assessment done in 2011. The last Vaccine Management Assessment (VMA) was done in 2009 following which 5000 refrigerators and cold boxes were procured and distributed, three new cold rooms constructed in two regions and two central level cold rooms upgraded; cold chain training was given to immunization officers and cold chain focal persons at various levels. The country is also planning to conduct the next effective vaccine management assessment (EVMA) in 2013. The estimated total budget of the campaign in 2013-2015 is USD 78390434 which includes 40,412,657 for material (vaccine and supplies) cost and 37,977,777 ($ 0.65 per target) is accounted for operational cost. The Government of Ethiopia would welcome GAVI support of the amount of money required to cover the operational cost. Vaccinesand injection materials will also be supported by GAVI and the country appreciates the GAVI support to fully finance the material needs..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Ethiopia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | Meningogoccal, 10 dose(s) per vial, LIQUID preventive campaigns. |  |
| The Government of Ethiopia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January.. |  |  |
| The payment for the first year of co-financed support will be around March 2013 for Meningogoccal, 10 dose(s) per vial, LIQUID.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Dr. Tedros Adhanom; Name; Mr. Sufian Ahmed. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. ASCHALEW TEKA; Immunization Officer; +251911336737; aschalewt@et.afro.who.int. BEZAWIT GETACHEW; Nattionla Immunization coordinator; +251911167430; bezicho4005@gmail.com. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 27/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Ato Nahusenay Areaya/Program Coordinator; Rotary International Ethiopia. Dr Teodros Bekele / Urban Health Promotion and Disease Prevention Directorate Director/National Program Coordinator-Maternal ,Newborn, child Adolescent Health; FMOH Ethiopia. Dr Kesetebirhan Admasu/ State Minister of Health; FMOH Ethiopia. Dr Khaled Bessaoud/ WHO Representative; WHO Ethiopia. Dr. Filimona Bisrat/Program Coordinator; CCRDA/CORE Group. Dr. Peter Salama /UNICEF Representative; UNICEF Ethiopia. Dr. Teklay Kidane /Immunization coordinator; Clinton Health Access Initiative. Dr. Tesfaye Bulto/Program director; USAID(IFHP). Mrs Mesret Yetube /pastoralist Health Promotion and Disease Prevention Directorate Director; FMOH Ethiopia. Ms Miheret Hiluf /Agrarian Health Promotion and disease Prevention Directorate Director; FMOH Ethiopia. Ms Roman Tesfaye /Policy Plan and Finance Directorate Director; FMOH Ethiopia. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; ICC. Year of constitution of the current committee; 1996. Organisational structure (e.g., sub-committee, stand-alone); stand alone. Frequency of meetings; Quarterly. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; State Minister of Health/FMOH Ethiopia; Dr. Kestebirhan Admasu. Secretary; Immunization Officer/WHO; Dr. Aschalew Teka. Members; Policy Plan and Finance Directorate Director/FMOH; Ms Roman Tesfaye. Urban Health Promotion and Disease Prevention Directorate Director/National Program Coordinator-Maternal ,Newborn,child Adolesent Health/FMOH; Dr Teodros Bekele. Agrarian Health Promotion and disease Prevention Directorate/ Director/ FMOH; Ms Miheret Hiluf. pastoralist Health Promotion and Disease Prevention Directorate/FMOH; Mrs Mesret Yetube. WHO Representative; Dr Khaled Bessaoud. UNICEF Representative; Dr. Peter Salama. CHAI; Dr. Teklay Kidane. CCRDA/CORE Group; Dr Filimona Bisrat. Rotary; Ato Nahusenay Areaya. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| · Coordination of partners' effort in support ofGovernment activities · Provides technicalinformation and updates on routine and supplementary activities · Promote resource mobilization with in the country and externally for routineimmunizations and supplemental activities · Review multi year and annual plans. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Include new members to represent regions and also newly established agencies under MOH(PFSA) working on vaccine storageand distribution. 2.; Facilitate the establishment and revitalization of functioning ICC at sub national levels .. 3.; Provide orientation program on financial sustainability, co-financing, and global situation on immunization funding. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG; Not applicable. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone). Frequency of meetings.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members.

Major functions and responsibilities of the NITAG.

There is no NITAG established in the coutnry.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.; Not applicable. 2.; Not applicable. 3.; Not applicable.

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2012 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 86,841,347; 2012; CSA 2007. Infant mortality rate (per 1000); 59; 2010; EDHS 2011. Surviving infants[1]; 2,953,628; 2012; 2005 woreda based planning. GNI per capita (US$); 400; 2011; World Bank. Total Health Expenditure (THE) as a percentage of GDP; 7; %; 2011; Annual report. General government expenditure on health (GGHE) as % of General government expenditure; 10; %; 2012; MOFED Annual report.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. Ethiopia designed a 20 year comprehensive Health Sector Development Plan (HSDP) to be implemented in four cycles. The current HSDP IV cycle guides the planning and budgeting process for the period 2010/11-2011/15. Core plan is prepared at national level and the indicative is shared to regions where additional local priorities might be included and comprehensive plan is prepared at lower level which is then communicated to the next higher level.. Please indicate the name and date of the relevant planning document for health. HSDP-IV 2010/11 up to 2014/15. Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). Yes! The current cMYP (2011-2015) is aligned with HSDP IV in both timing andcontent and some changes such as delay in ROTA vaccine introduction due tosupply shortage are re-planned to show current status. Please indicate the national planning budgeting cycle for health. National budget cycle runs from July 7- July 6 every year.. Please indicate the national planning cycle for immunisation. National planning cycle also runs from July 7-July 6 every year where indicative core plan is prepared at National level followed by comprehensive sub-national plans. The planning approach uses a mix of bottom up and top down approach.. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. Data on sex is collected at health facility level in the EPI registration book but as such it is not included in the regular reporting.. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. The vaccine will be given for both males and females and data will be collected on the gender ofvaccinated persons. Data will be analyzed at the end of the day by field supervisors who would see if the vaccine administration matches the sex distribution of the population. If a significant skew is observed they will bring it to the attention of next level supervisors and take appropriate actions to rectify the situation. Women association and women development army at all levels will be involved in the campaign activity to mobilize women to utilize the vaccine. There will be a half day orientationwith community members which will be used to understand community concerns and address issues as necessary. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. As documented in the national DHS and other studies such as national survey on social and behavioral determinants of immunization service utilization among care takers , there is no significant difference in immunization service utilization between males and females. However evidence from the above both studies show that income influences service utilization and data from DHS 2010 dictate that 52% of children in the highest quintiles are fully immunized compared to 17% in the lowest quintiles.. Country should provide an outline of all preparatory activities for vaccine(s) introduction. Activities Target Date Submission of Proposal to GAVI 28 August 2012 Anticipation of approval from GAVI February 2013 Procurement of addition cold chain – Order placement March 2013 Finalization of the field guideline for the campaign March 2013 Printing of the field guideline for the campaign and instruments for recording and reporting April 2013 Development of Social Mobilization plan April 2013 Development of Logistic distribution plan May 2013 Development of supervision plan including third party monitoring June 2013 Training of Tutors August 2013 Training of the staff at Regional and lower level September 2013 Receipt of vaccines and supplies September 2013 Social mobilization activities to begin September 2013 Federal level activities including dispatch of vaccines to states Sept-Oct 2013 Field activities for campaign Phase 1 October 2012 Post campaign Evaluation Phase 1 November 2013.

5.2. Baseline and Annual Targets (NVS Routine Support)

No NVS Routine Support is requested.

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (Meningogoccal campaign). Cohort for Meningogoccal is population 1-29 years old.. Table 5.3.1 Baseline NVS preventive campaign figures for Meningogoccal.. Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2012; 2013; 2014; 2015. Total births; 3,085,983; 3,163,133; 3,242,211; 3,323,266. Total population 1-29 years old; 58,427,373; 58,427,373; 58,427,373; 58,427,373. Target population vaccinated with Meningococcal; 0; 18,926,853; 24,429,665; 15,070,855. Meningococcal (campaign) coverage (%) [1]; 0.00 %; 32.39 %; 41.81 %; 25.79 %. Wastage rate in base year and thereafter (%) for Meningococcal (campaign); 10; 10; 10; 10. Wastage factor in base year and thereafter for Meningococcal; 1.11; 1.11; 1.11; 1.11.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

No NVS Routine Support is requested.

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Meningococcal Meningitis; Setting priority for the introduction of the Men A conjugate vaccine in Ethiopia using the DPT*; January 2012; recommended preventive campaign for the entire country.

If Meningogoccal vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Not applicable.

7.2.Requested for Meningogoccal, 10 dose(s) per vial, LIQUID campaign support 7.2.1. Summary for Meningogoccal campaign support. Please give a summary of the cMYP and/or the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan sections that refer to the introduction of Meningogoccal, 10 dose(s) per vial, LIQUID campaign. Outline the key points that informed the decision-making process (data considered etc):. Ethiopia lies in the African Meningitis Belt which extends from the Red Sea in the East to the Atlantic Ocean in the West. It has suffered major epidemics of meningococcal meningitis, a bacterial disease of the central nervous system, in 1981 there were 50,000 cases and nearly a thousand deaths and in 1989 there were 46,000 cases and 1,700 deaths. Between June and August 2000, there was an outbreak in Addis Ababa with over 850 cases and 33 deaths. Major epidemics usually occur every 8 to 12 years and the last report was in 2001 when 6,964 cases had been reported with 330 deaths. Amhara, SNNPR and Oromia regions are the most affected ones that reported largest cases during the outbreaks occurred in the past. Sero type A of Nisseria Meningitidis was the responsible agent for the outbreaks reported at all times with only few other serotypes isolated Meningitis is one of the weekly reportable diseases and there is a system of enhanced meningococcal surveillance in the country and cases are reported through IDSR. Men A conjugate vaccine provides a long lasting immunity against the antigen which is most often associated with Meningitis in the belt regions and it can also be used in individuals 1-29 years. The use of the conjugated Men A vaccine in Burkina Faso, Mali and Niger showed to have significant impact in reducing cases. After introduction of the vaccine In 2010/2011 in these countries, no cases of meningitis were reported in vaccinated individuals. In Ethiopia risk assessment was done to roll out meningitis campaign using district prioritization tool. The assessment was based on data from IDSR and outbreak investigations in 9 regions and 2 city administrations (entire country). Zonal level risk assessment was done and the finding was scaled up to determine regional risk level. The quantitative assessment output showed that 5 of the regions are at high risk, 5 at moderate risk and the remaining 3 at low risk for meningitis outbreak. (see figure below) The impact of Men A vaccine in reducing mortality and halting outbreaks as was demonstrated in other African countries also provides good evidence to introduce the vaccine in Ethiopia to prevent further outbreaks in the future. The strategic approach of vaccine introduction in the country follows a phased approach to be completed over 3 years. The decision is based on availability of vaccine for Ethiopia over 2013 to 2015; the quantitative risk assessment output as well as expert opinions accounting for factors such as population movements, crisis and quality of surveillance. In particular, the decision accounts for the greater risk of meningitis identified in the Western part of Ethiopia, the opportunity to expand the front of immunity against Nm A by the North Sudanese border , the need to protect populations in areas where outbreak aggravating factors exist by the South Sudanese border and the ability of Addis Ababa city administration to detect outbreak early and respond appropriately to the epidemic given the strong capacity of the surveillance system in the capital city. Accordingly Phase 1 campaign in 2013 covers the most western part of the country and zones directly bordering Sudan and South Sudan will be targeted. The total target population is 18,926 853 and 20,819, 538 doses of vaccines needed (10% wastage rate) The second phase in 2014 continues towards southern and central parts of the country targeting 24, 429 665 people and requires 26,872,632 doses of vaccine, The third campaign will be in 2015 for 15,070,855 population and 16,577,941 vaccine doses is required. The country had successfully conducted quality Polio and measles SIAs and demonstrated reach experience in implementing campaign activities. Accordingly Planning, meeting and discussions at National and sub national level will be made In good time before vaccine introduction.. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. There are activities already started in 2011 such as immunization safety and waste management assessment, preparation of AEFI guideline and conducting TOT trainings on AEFI surveillance and these activities will be finalized in 2012. Training on AEFI will be conducted for health workers; provision of safe injection materials and supportive supervision will be done to ensure that safe injection and proper waste management practices are in place including waste disposal using incinerators One AD-Syringe will be used for each vaccinated individual and safety box will be made available. Since a large volume of injection will be given during the campaign, the preparatory plan will include identifying available disposal capacity as well as improving gaps identified so that adequate waste management capacity will be ensured at all levels. The experience of conducting successful SIAs would be an input that can be used in planning for AEFI and waste management. There will be adequate monitoring of AEFI and supervisors and vaccinators will be trained on AEFI. Currently the available cold chain space at National store is adequate to receive doses of meningitis for each phase in addition to routine vaccine supply with the assumption that all the available cold chain space at national level will be used for vaccine storage only. However there are constraints at regional level and the plan is to distribute supply directly from the centers for zones not far from the capital Addis Ababa. The result of cold chain capacity is as shown below and the detail is separately attached. National level cold chain capacity assessment Detail Year Remark (conclusion of national store adequacy and assumptions) Available capacity at national level 2012 284,000 liters Required storage capacity for routine vaccine (traditional, new and underutilized) per quarter 63,123 liters is required in 2013 before Rota introduction In 2013 Men A SIAs will be done before Rota introduction and measles SIAs 91,970 liters in 2014 after Rota introduction 94,362 liters 2015 Remaining capacity above routine 2013 2014 2015 220,877 ltrs 192,030 ltrs 189,638 ltrs Capacity needed for Men A per Phase Phase I Phase II Phase III 53,151 ltrs 61,735 ltrs 42,227 ltrs Capacity gap for Men A Phase I Phase II Phase III No Gap No Gap No Gap Cold chain inventory was done in 2008 and VMA was done in August 2009. Recommendations were made to improve the gaps identified then. The following major activities were implemented to fill identified gaps. 1) Series of trainings were conducted Ø Vaccine management trainings to MOH staffs, all regional EPI focal persons, cold store managers and majority of the EPI focal persons of the zonal health departments. Ø More than 100 health staffs from regional and zonal levels trained on cold chain maintenance for one month. This training was cascaded down to lower level and more than 700 hundred health staffs from each woreda office trained on cold chain maintenance for 10 days. Ø Provided MLM training to EPI managers working at national, central and zonal levels. 2) Cold chain expansion Ø More than 5000 refrigerators, 5000 cold boxes and 5000 vaccine carriers procured and delivered to health facilities. Ø Two big cold rooms upgraded for vaccine storage purpose at central level Ø Three new cold rooms installed in three different locations of the country Ø Three new cold rooms will be installed at regional level very soon The future strategy designed at country level to deal with handling of vaccine and cold chain issues will be Integration of EPI logistics with other medical supplies coordinated under Pharmaceutical Fund and Supply Agency (PFSA). See detail of plans for cold room construction, procurement of refrigerators, cold boxes in the attached document number 4.. 7.2.2. Grant Support for Operational Costs of the Meningogoccal Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of Meningogoccal support; Target population vaccinated (from Table 5.3); Share per population 1-29 years old in US$; Total in US$. 2013; 18,926,853; 0.65; 12,302,454. 2014; 24,429,665; 0.65; 15,879,282. 2015; 15,070,855; 0.65; 9,796,056.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the Meningogoccal, 10 dose(s) per vial, LIQUID campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 2,756,169; 2,756,169. Social Mobilization, IEC and advocacy; 4,298,130; 4,298,130. Cold Chain Equipment & Maintenance; 1,021,040; 1,021,040. Vehicles and Transportation; 366,938; 366,938. Programme Management; 195,990; 195,990. Surveillance and Monitoring; 125,000; 125,000. Human Resources; 2,380,374; 2,380,374. Waste Management; 100,000; 100,000. Technical Assistance; 26,333; 26,333. Planning; 559,294; 559,294. Volunteer incentives; 0. Other (please specify). Other Costs; 473,170; 473,170. Total; 12,302,438; 12,302,438... Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2014; 2014. Training; 1,872,650; 1,872,650. Social Mobilization, IEC and advocacy; 1,471,227; 1,471,227. Cold Chain Equipment & Maintenance; 2,856,833; 2,856,833. Vehicles and Transportation; 1,745,842; 1,745,842. Programme Management; 290,348; 290,348. Surveillance and Monitoring; 1,110,991; 1,110,991. Human Resources; 3,499,674; 3,499,674. Waste Management; 793,565; 793,565. Technical Assistance; 141,791; 141,791. Planning; 592,480; 592,480. Volunteer incentives; 1,503,881; 1,503,881. Other (please specify). Total; 15,879,282; 15,879,282... Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2015; 2015. Training; 1,155,835; 1,155,835. Social Mobilization, IEC and advocacy; 908,069; 908,069. Cold Chain Equipment & Maintenance; 1,763,290; 1,763,290. Vehicles and Transportation; 1,077,566; 1,077,566. Programme Management; 179,208; 179,208. Surveillance and Monitoring; 685,724; 685,724. Human Resources; 2,155,132; 2,155,132. Waste Management; 489,803; 489,803. Technical Assistance; 87,516; 87,516. Planning; 365,690; 365,690. Volunteer incentives; 928,223; 928,223. Other (please specify). Total; 9,796,056; 9,796,056..... Please describe others sources of funding if available to cover your full needs.. The government contributes through social mobilization and human resources which is not costed in the application...

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

No NVS Routine Support is requested.

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for Meningogoccal, 10 dose(s) per vial, LIQUID campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. The Government of Ethiopia has an existing partnership with UNICEF which is the procuring agent for vaccines and injection safety materials for both routine immunization and campaigns. This existing partnership will be extended further for procurement of Meningococcal A conjugate 10 dose Lypholized vaccine to be used for the campaign. Pharmaceutical Fund and Supply Agency of Ethiopia (PFSA) clears the supplies once the goods are shipped to Ethiopia. PFSA is also responsible for the distribution of vaccines to sub national levels.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. The campaign will be conducted in a phased approach over 3 years starting from 2013 and ending at 2015. The campaign will begin from the highest risk areas, western part of the country, and moves towards the east covering the entire country over 3 years . S/No PHASE I (October 2013) PHASE II (October 2014) PHASE III (October 2015) Region No of Zones Target Population (1-29 Years) Region No of Zones Target Population (1-29 Years) Region No of Zones Target Population (1-29 Years) 1 AMHARA 7 8193413 Addis Ababa 10 2086009 Afar 5 1091301 2 Benishangul 5 657297 Oromia 14 12329587 Amhara 4 4776885 3 Gambella 4 296583 SNNPR 18 10014078 Dire Dawa 1 473900 4 Oromia 7 6150859 Hareri 1 75732 5 SNNPR 4 1815437 Oromia 2 3613999 6 Tigray 3 1813263 Somali 9 3490203 7 Tigray 3 1548836 8 Total 30 18926852 TOTAL 42 24429674 Total 25 15070856. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan). - Coverage will be reported through administrative structure as well as end of campaign coverage survey - Standard material will be prepared for data collection and reporting. - Rapid convenient survey will be done to identify poorly covered areas - Independent monitors will be deployed.

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? August 2009. Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes. When was the last EVSM conducted? January 2003. Did the country have Effective Vaccine Management (EVM) in the past? No. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. The country conducted VMA in August 2009 and the finding was presented to the ICC members in the presence of the director general of Ministry of Health and report was shared with all stakeholders. Report is also attached with this application. As per the recommendations of the EVM report the following activities were implemented - EPI managers and vaccine store men from most ofthe regions and districts trained on vaccine management. - For each district at least one health staff hasbeen trained on cold chain equipment maintenance. - Three new cold rooms constructed in two regions - Two central levels cold rooms have been upgraded for vaccine storage purpose. - Electronic vaccine stock management tools have been installed in the regional vaccine stores - More than 5000 new EPI refrigerators, 5000 coldboxes and 5000 vaccine carriers procured and distributed to facilities.. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? August 2013. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. Signature_MoH&MoF.docx. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 1/23/2013 7:29:32 AM. Size: 521066. Signature_MoH&MoF.docx. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 1/23/2013 7:28:34 AM. Size: 521066. ICC Signature.JPG. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 8/30/2012 9:01:20 AM. Size: 385812. ICC Minute.zip. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/30/2012 9:04:27 AM. Size: 1417556. Ethiopia cMYP_updated 20 July 2012 final (2).doc. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/30/2012 11:15:31 AM. Size: 2343424. ETHIOPIA_cMYP_Costing_Tool_Vs 2 6_En_20 JULY 2012.xls. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/28/2012 9:39:16 AM. Size: 3571200. ETHIOPIA_Men A introduction workplan.doc. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 8/30/2012 4:36:12 AM. Size: 1221632. VMAreport_4 draft final.docx. 8; Improvement plan based on EVM; File desc:. Date/time: 8/28/2012 10:18:35 AM. Size: 273808. support doc for clarification_230113.zip. 14; Summary of response to conditions; 3; File desc:. Date/time: 1/23/2013 7:33:37 AM. Size: 690683.

11. Annexes.

Annex 1 - NVS Routine Support.

No NVS Routine Support is requested.

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (Meningogoccal, 10 dose(s) per vial, LIQUID). Table Annex 3.1 C: Summary table for CAMPAIGN Meningogoccal, 10 dose(s) per vial, LIQUID.. Data from; 2013; 2014; 2015. Total campaign population; Table 5.3.1; #; 58,427,373; 58,427,373; 58,427,373. Immunization coverage; Table 5.3.1; %; 32.00 %; 42.00 %; 26.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 18,926,853; 24,429,665; 15,070,855. Number of doses per persons; Parameter; #; 1; 1; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.11; 1.11; 1.11. Number of doses per vial; Parameter; #; 10; 10; 10. AD syringes required; Parameter; #; Yes; Yes; Yes. Reconstitution syringes required; Parameter; #; No; No; No. Safety boxes required; Parameter; #; No; No; No. Vaccine price per dose; Table Annexes 4A; $; 0.52; 0.52; 0.52. AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0. Safety box price per unit; Table Annexes 4A; $; 0.58; 0.58; 0.58. Freight cost as % of vaccines value; Table Annexes 4B; %; 10.00 %; 10.00 %; 10.00 %. Freight cost as % of devices value; Parameter; %; 0; 0; 0...

Table Annex 3.1 D: Estimated number of Meningogoccal, 10 dose(s) per vial, LIQUID associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013; 2014; 2015. B; Number of persons to be vaccinated with the first dose; 18,926,853; 24,429,665; 15,070,855. C; Number of doses per persons; 1; 1; 1. D; Number of doses needed; B x C; 18,926,853; 24,429,665; 15,070,855. E; Estimated vaccine wastage factor; Wastage factor table; 1.11; 1.11; 1.11. F; Number of doses needed including wastage; D x E; 21,008,807; 27,116,929; 16,728,650. G; Vaccines buffer stock; (F – F of previous year); 0; 0; 0. I; Total vaccine doses needed; F + G; 21,009,307; 27,117,429; 16,729,150. J; Number of doses per vial; Vaccine parameter; 10; 10; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 21,008,807; 27,116,929; 16,728,650. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 0.52; 0.52; 0.52. O; Cost of AD syringes needed; K x ca; 976,909.5255; 1,260,937.1985; 777,882.225. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0; 0; 0. R; Freight cost for vaccines needed; N x fv; 0; 0; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 11,901,749.5255; 15,362,001.1985; 9,477,041.225... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.524; 0.555; 0.578; 0.606. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.037; 0.037; 0.037; 0.037. RECONSTIT-SYRINGE-YF; SYRINGE; 0.037; 0.037; 0.037; 0.037. SAFETY-BOX; SAFETYBOX; 0.580; 0.580; 0.580; 0.580. |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |
| Vaccine. |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. Meningogoccal, 10 dose(s) per vial, LIQUID; 10 %; 1.11. |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Ethiopia hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:. |  |
| Is the bank account exclusively to be used by this program?. |  |
| By who is the account audited?. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:. Title:. Signature:. Date:. |  |
| FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:. | CORRESPONDENT BANK. (In the United States). |
| I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:. |  |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |  |