GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Sao Tome and Principe

Date of submission: 01.06.2011 07:43:19

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2012 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMS The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the program(s) described in the Country’s application. Any significant change from the approved program(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the program(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the program(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programs described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programs described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programs described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programs described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programs described in its application.

Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |
| New Vaccines Support | Measles, 10 doses/vial, Lyophilised | 2013 | 2015 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunization

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunization

4.1.3. The Inter-Agency Coordinating Committee for Immunization

4.2. National Immunization Technical Advisory Group for Immunization

4.2.1. The NITAG Group for Immunization

5. Immunization Program Data

5.1. Basic facts

5.2. Current immunization schedule

5.3. Trends of immunization coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunization budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of immunizations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of immunizations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Measles, 10 doses/vial, Lyophilised

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Measles, 10 doses/vial, Lyophilised

Table 1.1  D - Estimated number of doses for vaccine Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget

Annex 1.2 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.2  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Resume

The Government of Sao Tome and Principe are fully aware of their responsibilities towards women and children and further to agreements signed with the international community to fulfill its responsibilities in the Millennium Development Goals (MDG) with regard to reducing poverty and promoting economic growth and social development, have adopted the Comprehensive Multi Year Plan Analysis (cMYPA) 2012-2015 of  the EPI in order to mobilize resources to set up immunization activities and other measures essential to the survival and development of children.

The present long term plan 2012-2015 of the EPI of Sao Tome and Principe is set out in the following way;

- Introduction,

- Country in general,

- Organization of national health system,

- Analysis of the EPI situation

- Strengths, weaknesses, opportunities and hazards,

- National priorities,

- EPI vision,

- Strategies,

- Schedule of Activities,

- Analysis of costs and program financing,

- The EPI evaluation system,

- Action plan 2012

The analysis of the situation is presented based on the basic components of the immunization system; the five operational components;

  - Provision of services,

  - Integrated epidemiological monitoring of the illness,

  - Logistics,

  - Supply and quality of vaccines,

  - Communication,

And the three support components;

- management,

- development of capacity

- financing

The main objective of the 2012-2015 EPI is to contribute to the reduction in morbidity and mortality linked to preventable diseases by means of immunization.

The national objectives are presented in different stages:

Figure 1: National objectives and stages of EPI 2012-2015

Immunization coverage objectives

Type of vaccine                         2012              2013              2014            2015

Standard vaccine                       %                    %                  %                 %

Traditional vaccine

BCG                                             99                   99                  99                99

TT pregnant women                95                   98                  98                98

Measles                                     95                   98                  98                98

Polio (OPV3)                              98                    98                   98               98

Measles 2nd dose                                               80                   80               80

Under - used vaccines

Yellow fever                                 95                     98                  98               98

DTP-HepB-Hib (3)                         98                     98                  98               98

New vaccines

PCV-13                                            98                     98                 98               98

ROTAVIRUS                                                                                   98               98

NB: the introduction of new vaccine could lead to a slight decrease in the vaccine coverage. Despite this, measures will be taken to maintain the coverage at 98%.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Sao Tome and Principe would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunization program of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid , Measles 10 doses/vial Lyophilised introduction.

The Government of Sao Tome and Principe commits itself to developing national immunization services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of April .

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) | Minister of Finance (or delegated authority) |
| --- | --- |
| Name | Angela DA COSTA PINHEIRO | Name | Americo D’ OLIVEIRA DOS RAMOS |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Maria Elizabeth CARVALHO | Head of Expanded Program on Immunization/EPI | 00239 2242002 | bethmaria74@hotmail.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunization

We the members of the ICC, HSCC, or equivalent committee[1] met on the 11.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Manuela F. DA COSTA | Directorate of Health Care |  |  |
| Maria Tomé PALMER | National Red Cross Society |  |  |
| Luis Manuel BONFIM | UNICEF |  |  |
| François NGUESSAN | WHO |  |  |
| José Manuel CARVALHO | UNFPA |  |  |
| Catarina DUARTE | Cooperation Portuguese |  |  |
| Edgar Manuel A. DAS NEVES | Institut Marquês de Valle Flor |  |  |
| Neusa Raquel DA COSTA LIMA | Directorate of Planning and Finance, Ministry of Health |  |  |
| António MARQUES LIMA | Adviser to the Ministry of Health |  |  |
| Maria Elizabeth CARVALHO | Expanded program of Immunization |  |  |
| Geisel MENEZES | Ministry of Finance and Cooperation |  |  |
| Maria Quaresma DOS ANJOS | WHO |  |  |
| Vladmir SOUSA | EPI |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Maria Elisabeth Carvalho | Title | EPI Manager |
| --- | --- | --- | --- |
| Tel no | 00239 - 2242002 |  |  |
| Fax no | 00239 - 2242009 | Address | Ministére de la Santé et des Affaires Sociales, PSR, Avenida kwame Nkruma, Sao Tomé, BP - 98 |
| Email | bethmaria74@hotmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners and NGOs) supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | CCIA |
| --- | --- |
| Year of constitution of the current committee | 2002 |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings | 3 meetings per year |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair | Minister of Health and Social Affairs | Angela da Costa Pinheiro |
| Secretary | Assessor of the Minister | António Marques Lima |
| Members | Directorate of Health Care | Manuela F. DA COSTA | Action |
|  | WHO | François NGUESSAN |  |
|  | Cooperation Portuguese | Catarina DUARTE |  |
|  | Institut Marquês de Valle Flor | Edgar Manuel A. DAS NEVES |  |
|  | Directorate of Planning and Finance, Ministry of Health | Neusa Raquel DA COSTA LIMA |  |
|  | Expanded Program on Immunization | Maria Elizabeth CARVALHO |  |
|  | Ministry of Finance and Cooperation | Geisel MENEZES |  |
|  | UNICEF | Tanya RADOSAVLJEVIC |  |
|  | National Red Cross Society | Paulo NEVES |  |
|  | UNFPA | Victoria D'ALVA |  |

Major functions and responsibilities of the committee

- Coordination of different activities - Mobilization of ressources - Monitoring and Evaluation of the activities of EPI and finanice management.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Promulgating ICC with other partners |
| --- | --- |
| 2. | Adoption of the annual schedule of work for ICC |
| 3. | Annual Assessment of the ICC activities. |

# National Immunization Technical Advisory Group for Immunization

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | NA | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunization

Profile of the NITAG

| Name of the NITAG | NA |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair | NA |  |
| Secretary |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

NA

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | NA |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunization Program Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunization (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 5

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure | Year | Source |
| --- | --- | --- | --- |
| Total population | 163,783 |  | 2010 | INE |
| Infant mortality rate (per 1000) | 38 |  | 2009 | INE |
| Surviving Infants[1] | 5,468 |  | 2010 | INE |
| GNI per capita (US$) | 1,320 |  | 2009 | INE |
| Total Health Expenditure (THE) as a percentage of GDP | 7.21 | % | 2010 | INE |
| General government expenditure on health (GGHE) as % of General government expenditure | 10.90 | % | 2010 | INE |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The planning document is the National Strategic Plan for Poverty Reduction (2002 - 2015). The health care planning document is the National Development Plan for Health being updated.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes

Please indicate the national planning budgeting cycle for health

Planning for 5 years with an annual budget.

Please indicate the national planning cycle for immunization

2012 - 2015

Please indicate if sex disaggregated data (SDD) is used in immunization routine reporting systems

No

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

No

# Current immunization schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes |  |  |
| measles | 9 months | Yes |  |  |
| yellow Fever | 9 months | Yes |  |  |
| DTC+HepB+Hib | 6 weeks | Yes |  |  |
| VPO | 6 weeks | Yes |  |  |
| Vitamin A | 6 to 59 months | Yes |  |

# Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  |  | 2010 | 2009 |  |  |  | 2010 |
| BCG |  | 99 | 96 |  | Tuberculosis | 15 |  |
| DTP | DTP1 |  | 99 | 94 |  | Diphtheria | 0 |  |
|  | DTP3 |  | 98 | 87 |  | Pertussis | 0 |  |
| Polio 3 |  | 98 | 84 |  | Polio | 0 |  |
| Measles (first dose) |  | 92 | 87 |  | Measles | 0 |  |
| TT2+ (Pregnant women) |  | 87 |  |  | NN Tetanus | 0 |  |
| Hib3 |  | 98 | 84 |  | Hib[2] | 0 |  |
| Yellow Fever |  | 92 | 87 |  | Yellow fever | 0 |  |
| HepB3 |  | 98 | 87 |  | HepBsero-prevalence[1] | 9 |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  | 90 |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 80 |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Demographic and Health Survey (DHS), 2009

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |
| --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 5,569 | 5,783 | 5,898 | 6,016 | 6,137 |  |  |
| Total infants' deaths | 101 | 170 | 173 | 177 | 183 |  |  |
| Total surviving infants | 5,468 | 5,613 | 5,725 | 5,839 | 5,954 |  |  |
| Total pregnant women | 6,388 | 6,633 | 6,766 | 6,901 | 7,039 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 5,511 | 5,783 | 5,898 | 6,016 | 6,139 |  |  |
| BCG coverage (%)[1] | 99% | 100% | 100% | 100% | 100% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 5,193 | 5,520 | 5,610 | 5,722 | 5,837 |  |  |
| OPV3 coverage (%)[2] | 95% | 98% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 5,318 | 5,577 | 5,668 | 5,781 | 5,896 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 5,193 | 5,520 | 5,610 | 5,722 | 5,837 |  |  |
| DTP3 coverage (%)[2] | 95% | 98% | 98% | 98% | 98% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 5,577 | 5,668 | 5,781 | 5,896 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 5,332 | 5,610 | 5,722 | 5,837 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 95% | 98% | 98% | 98% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 5,001 | 5,351 | 5,610 | 5,722 | 5,837 |  |  |
| Measles coverage (%)[2] | 91% | 95% | 98% | 98% | 98% |  |  |
| Infants vaccinated (to be vaccinated) with 2nd dose of Measles | 0 | 0 | 4,580 | 4,671 | 4,765 |  |  |
| Pregnant women vaccinated with TT+ | 6,385 | 6,616 | 6,619 | 6,750 | 6,885 |  |  |
| TT+ coverage (%)[4] | 100% | 100% | 98% | 98% | 98% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery | 5,515 | 6,303 | 6,415 | 6,544 | 6,675 |  |  |
| Vit A supplement to infants after 6 months | 17,530 | 18,172 | 18,420 | 18,789 | 19,875 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 2% | 1% | 1% | 1% | 1% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of immunizations with the same vaccine in the same period.

# Summary of current and future immunization budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Vaccines (routine vaccines only) | 68,713 | 174,304 | 336,442 | 337,513 | 402,758 |  |  |  |  |
| Traditional vaccines | 9,948 | 11,851 | 13,869 | 15,896 | 18,200 |  |  |  |  |
| New and underused vaccines | 58,765 | 162,453 | 322,573 | 321,617 | 384,558 |  |  |  |  |
| Injection supplies | 3,639 | 7,904 | 9,400 | 10,950 | 12,557 |  |  |  |  |
| Personnel | 39,634 | 44,814 | 62,561 | 64,454 | 65,741 |  |  |  |  |
| Salaries of full-time NIP health workers (immunization specific) | 1,342 | 2,737 | 2,792 | 2,848 | 2,905 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 38,292 | 42,077 | 59,769 | 61,606 | 62,836 |  |  |  |  |
| Transportation | 10,243 | 11,457 | 11,780 | 12,540 | 12,938 |  |  |  |  |
| Maintenance and overheads | 7,123 | 32,730 | 19,028 | 22,295 | 25,825 |  |  |  |  |
| Training | 0 | 17,340 | 10,404 | 15,918 | 5,412 |  |  |  |  |
| Social mobilisation and IEC | 0 | 15,300 | 15,606 | 15,918 | 16,236 |  |  |  |  |
| Disease surveillance | 753 | 3,060 | 5,202 | 6,367 | 5,412 |  |  |  |  |
| Program management | 279,075 | 136,233 | 75,080 | 116,733 | 54,122 |  |  |  |  |
| Other | 135,177 | 75,771 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Recurrent Costs | 544,357 | 518,913 | 545,503 | 602,688 | 601,001 |  |  |  |  |
| Routine Capital Costs |
| Vehicle |  |  |  |  |  |  |  |  |  |
| Cold chain equipment |  | 55,999 |  |  |  |  |  |  |  |
| Other capital equipment |  | 118,118 | 4,162 | 42,448 | 46,112 |  |  |  |  |
| Subtotal Capital Costs | 0 | 174,117 | 4,162 | 42,448 | 46,112 |  |  |  |  |
| Campaigns |
| Polio |  |  |  |  |  |  |  |  |  |
| Measles |  | 130,306 |  |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 0 | 130,306 | 0 | 0 | 0 |  |  |  |  |
| GRAND TOTAL | 544,357 | 823,336 | 549,665 | 645,136 | 647,113 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunization program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
|  | GAVI,GOV, UNICEF, | 496,722 | 468,590 | 477,321 | 532,502 | 529,412 |  |  |  |  |  |
| Routine Capital Costs |  |
|  | GAVI,GOV | 47,635 | 224,440 | 72,344 | 112,634 | 117,701 |  |  |  |  |  |
| Campaigns |  |
|  | WHO, UNICEF, GOV |  | 130,306 |  |  |  |  |  |  |  |  |
| GRAND TOTAL | 544,357 | 823,336 | 549,665 | 645,136 | 647,113 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

The actual storage capacity in the cold chain is sufficient to accommodate vaccines even with two annual supplies of the DTP-HepB-Hib vaccine. However, with the introduction in 2012 of the new PCV vaccine and the purchase of vaccines for the follow up campaign for measles, extra capacity is necessary. This gap could be filled with the acquisition of a 10m3 cold room at central level at an estimated cost including installation of 50 000 USD. The expenses relating to this purchase have actually been submitted to the government from present until 2011, a decision taken by the CCIA during its meeting on 11 May. This additional storage capacity will allow the country to guarantee the storage of all vaccines even with the introduction of the 2nd dose of the measles vaccine in 2013 and the anti-rotavirus vaccine in 2014 with a comfortable margin up to 2015. At intermediary level the capacity for storage is adequate even with the introduction of new vaccines during the period of aid.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

The country has undergone an experience in the introduction of new vaccines and under used vaccines. Actually, with the support of GAVI, the vaccines against hepatitis B (monovalent) and yellow fever were introduced in September 2003 and pentavalent in 2009 in the standard EPI program. All these vaccines have followed DTP and have been successfully introduced. Given the scale of infections linked to pneumococcus in the sub regions and throughout the country and given the recommendations made by the WHO relating to the second dose of measles, the country plans to introduce the pneumococcus vaccine in 2012 and the second measles dose in 2013.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (Liters or m3) Liters | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 833 | 888 | 1,162 | 1,207 |  |  |  |  |
| B | Existing net positive cold chain capacity (Liters or m3) Liters | # | 540 | 540 | 540 | 540 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 2 | 2 | 3 | 3 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 1 | 1 | 1 | 1 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | 293 | 348 | 622 | 667 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 39,584 |  |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

All immunization expenses, mainly for the purchase of base vaccines and for the vaccines with co finance are, up to 20 000 USD financed by the State each year. The shares of co finance from the government are provided through UNICEF.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| ND |  |  |  |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |
| --- | --- |
| Insufficient storage capacity in district areas before introduction Follow up system of Fridge /tag indicators for freezing of vaccines not operational Insufficient training of personnel on management of vaccines and cold chain | Provision of two refrigerators at central level. Expected support of WHO and UNICEF. Training station in preparation |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Vaccine anti pneumococcus PCV 13 liquid, mono dose Measles vaccine II, 10 dose bottle, lyophilic

# 6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

As reported in the cMYP, the country plans to introduce Measles, 10 doses/vial, Lyophilised vaccine.

# 6.3.2. Co-financing information

No Co-financing for Measles

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 20% | 20% | 20% |  |  |  |  |  |
| Equivalent wastage factor | 1.25 | 1.25 | 1.25 |  |  |  |  |  |

# 6.3.4. Specifications of immunizations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 5,610 | 5,722 | 5,837 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 4,580 | 4,671 | 4,765 |  |  |  |  |  |
| Immunization coverage with the third dose | Table 1 | # | 97.99% | 98.00% | 98.03% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.25 | 1.25 | 1.25 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.00 | 0.00 | 0.00 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 0 | 0 | 0 |  |  |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 |  |  |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 |  |  |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 0 | 0 | 0 |  |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 7,200 | 5,900 | 6,000 |  |  |  |  |  |
| Number of AD syringes | # | 6,700 | 5,300 | 5,400 |  |  |  |  |  |
| Number of re-constitution syringes | # | 800 | 700 | 700 |  |  |  |  |  |
| Number of safety boxes | # | 100 | 75 | 75 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 2,500 | 2,000 | 2,000 |  |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Measles, 10 doses/vial, Lyophilised

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 5,898 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Measles, 10 doses/vial, Lyophilised (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 27,000 | 20,000 |
| Social Mobilization, IEC and Advocacy | 17,160 | 17,160 |
| Cold Chain Equipment & Maintenance | 29,334 | 10,000 |
| Vehicles and Transportation | 5,022 | 5,000 |
| Program Management | 42,656 | 15,000 |
| Surveillance and Monitoring | 52,110 | 15,000 |
| Human Resources | 21,178 | 0 |
| Waste Management | 63,506 | 0 |
| Technical assistance | 10,000 | 0 |
| Advanced Strategie | 10000 | 10000 |  |
| Recovery of loss incurred | 10000 | 7840 |  |
| Totals | 287,966 | 100,000 |

# 6.4.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Intermediate |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.4.4. Specifications of immunizations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 5,577 | 5,668 | 5,781 | 5,896 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 5,332 | 5,610 | 5,722 | 5,837 |  |  |  |  |
| Immunization coverage with the third dose | Table 1 | # | 94.99% | 97.99% | 98.00% | 98.03% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 1,200 | 1,200 | 1,300 | 1,500 |  |  |  |  |
| Number of AD syringes | # | 1,300 | 1,200 | 1,400 | 1,600 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25 | 25 | 25 | 25 |  |  |  |  |
| Total value to be co-financed by country | $ | 4,500 | 4,500 | 5,000 | 6,000 |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 20,800 | 16,900 | 17,100 | 17,200 |  |  |  |  |
| Number of AD syringes | # | 22,200 | 17,800 | 18,100 | 18,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 250 | 200 | 200 | 225 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 78,000 | 63,500 | 64,000 | 64,500 |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 5,783 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 27,000 | 20,000 |
| Social Mobilization, IEC and Advocacy | 17,160 | 17,160 |
| Cold Chain Equipment & Maintenance | 29,334 | 10,000 |
| Vehicles and Transportation | 5,022 | 5,000 |
| Program Management | 42,656 | 15,000 |
| Surveillance and Monitoring | 52,110 | 15,000 |
| Human Resources | 21,178 | 0 |
| Waste Management | 63,506 | 0 |
| Technical assistance | 10,000 | 0 |
| Advanced Strategy | 10000 | 10000 |  |
| REcovery of loss incurred | 10000 | 7840 |  |
| Totals | 287,966 | 100,000 |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The support of UNICEF for the purchase of vaccines

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunization commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

NA

- Please describe the introduction of the vaccines (refer to cMYP)

The country has experience in the introduction of new and under used vaccines. The anti pneumococcal vaccine will be introduced on 1st January 2012 throughout the whole of the country in line with present immunization timescales. There will be no follow up immunization.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The GAVI funds will be transferred into a special account according to the Finance Ministry.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The Finance Ministry will provide a share through UNICEF

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

From the monthly health structure reports like other antigens and declared by WHO/UNICEF (JRF) and the annual GAVI report.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? October  - 2007

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? October  - 2007

If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°8)

A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

When is the next Effective Vaccine Management (EVM) Assessment planned? September   - 2011

Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

# Annexes

# Annex 1

# Annex 1.1 – Measles, 10 doses/vial, Lyophilised

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 0 | 0 | 0 |  |  |  |  |
| Number of AD syringes | # |  | 0 | 0 | 0 |  |  |  |  |
| Number of re-constitution syringes | # |  | 0 | 0 | 0 |  |  |  |  |
| Number of safety boxes | # |  | 0 | 0 | 0 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 0 | 0 | 0 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 7,200 | 5,900 | 6,000 |  |  |  |  |
| Number of AD syringes | # |  | 6,700 | 5,300 | 5,400 |  |  |  |  |
| Number of re-constitution syringes | # |  | 800 | 700 | 700 |  |  |  |  |
| Number of safety boxes | # |  | 100 | 75 | 75 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 2,500 | 2,000 | 2,000 |  |  |  |  |

Table 1.1  C - Summary table for Measles, 10 doses/vial, Lyophilised

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 5,725 | 5,839 | 5,954 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 4,580 | 4,671 | 4,765 |  |  |  |  |
| Immunization coverage with the last dose | Table 1 | # |  | 97.99% | 98.00% | 98.03% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 5,610 | 5,722 | 5,837 |  |  |  |  |
| Number of doses per child |  | # |  | 1 | 1 | 1 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.25 | 1.25 | 1.25 |  |  |  |  |
| Number of doses per vial |  | # |  | 10 | 10 | 10 |  |  |  |  |
| AD syringes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 0.240 | 0.240 | 0.240 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.00 | 0.00 | 0.00 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  | 0.038 | 0.038 | 0.038 |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 | 2014 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 4,580 | 0 | 4,580 | 4,671 | 0 | 4,671 |
| C | Number of doses per child | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 4,580 | 0 | 4,580 | 4,671 | 0 | 4,671 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |
| F | Number of doses needed including wastage | D * E | 5,725 | 0 | 5,725 | 5,839 | 0 | 5,839 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,432 | 0 | 1,432 | 29 | 0 | 29 |
| I | Total vaccine doses needed | F + G | 7,157 | 0 | 7,157 | 5,868 | 0 | 5,868 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 6,674 | 0 | 6,674 | 5,218 | 0 | 5,218 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 795 | 0 | 795 | 652 | 0 | 652 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 83 | 0 | 83 | 66 | 0 | 66 |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,718 | 0 | 1,718 | 1,409 | 0 | 1,409 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 354 | 0 | 354 | 277 | 0 | 277 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 31 | 0 | 31 | 25 | 0 | 25 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 54 | 0 | 54 | 43 | 0 | 43 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 172 | 0 | 172 | 141 | 0 | 141 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 44 | 0 | 44 | 35 | 0 | 35 |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,373 | 0 | 2,373 | 1,930 | 0 | 1,930 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 4,765 | 0 | 4,765 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 4,765 | 0 | 4,765 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.25 | 1.25 | 1.25 |  |  |  |
| F | Number of doses needed including wastage | D * E | 5,957 | 0 | 5,957 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 30 | 0 | 30 |  |  |  |
| I | Total vaccine doses needed | F + G | 5,987 | 0 | 5,987 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 5,323 | 0 | 5,323 |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 665 | 0 | 665 |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 67 | 0 | 67 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,437 | 0 | 1,437 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 283 | 0 | 283 |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 26 | 0 | 26 |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 43 | 0 | 43 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 144 | 0 | 144 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 36 | 0 | 36 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 1,969 | 0 | 1,969 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,200 | 1,200 | 1,300 | 1,500 |  |  |  |  |
| Number of AD syringes | # | 1,300 | 1,200 | 1,400 | 1,600 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25 | 25 | 25 | 25 |  |  |  |  |
| Total value to be co-financed by the country | $ | 4,500 | 4,500 | 5,000 | 6,000 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 20,800 | 16,900 | 17,100 | 17,200 |  |  |  |  |
| Number of AD syringes | # | 22,200 | 17,800 | 18,100 | 18,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 250 | 200 | 200 | 225 |  |  |  |  |
| Total value to be co-financed by the country | $ | 78,000 | 63,500 | 64,000 | 64,500 |  |  |  |  |

Table 1.2  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 5,613 | 5,725 | 5,839 | 5,954 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 5,332 | 5,610 | 5,722 | 5,837 |  |  |  |  |
| Immunization coverage with the last dose | Table 1 | # | 94.99% | 97.99% | 98.00% | 98.03% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 5,577 | 5,668 | 5,781 | 5,896 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 6.14% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 5,577 | 298 | 5,279 | 5,668 | 349 | 5,319 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 16,731 | 894 | 15,837 | 17,004 | 1,045 | 15,959 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 17,568 | 939 | 16,629 | 17,855 | 1,097 | 16,758 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 4,392 | 235 | 4,157 | 72 | 5 | 67 |
| I | Total vaccine doses needed | F + G | 21,960 | 1,173 | 20,787 | 17,927 | 1,102 | 16,825 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 23,447 | 1,252 | 22,195 | 18,955 | 1,165 | 17,790 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 261 | 14 | 247 | 211 | 13 | 198 |
| N | Cost of vaccines needed | I * vaccine price per dose | 76,860 | 4,104 | 72,756 | 62,745 | 3,855 | 58,890 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 1,243 | 67 | 1,176 | 1,005 | 62 | 943 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 168 | 9 | 159 | 136 | 9 | 127 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 3,843 | 206 | 3,637 | 3,138 | 193 | 2,945 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 142 | 8 | 134 | 115 | 8 | 107 |
| T | Total fund needed | (N + O + P + Q + R + S) | 82,256 | 4,392 | 77,864 | 67,139 | 4,124 | 63,015 |
| U | Total country co-financing | I * country co-financing per dose | 4,392 |  |  | 4,124 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 6.14% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 | 2015 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 6.94% |  |  | 8.01% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 5,781 | 402 | 5,379 | 5,896 | 473 | 5,423 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 17,343 | 1,205 | 16,138 | 17,688 | 1,418 | 16,270 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 18,211 | 1,265 | 16,946 | 18,573 | 1,489 | 17,084 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 89 | 7 | 82 | 91 | 8 | 83 |
| I | Total vaccine doses needed | F + G | 18,300 | 1,271 | 17,029 | 18,664 | 1,496 | 17,168 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 19,350 | 1,344 | 18,006 | 19,735 | 1,582 | 18,153 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 215 | 15 | 200 | 220 | 18 | 202 |
| N | Cost of vaccines needed | I * vaccine price per dose | 64,050 | 4,447 | 59,603 | 65,324 | 5,234 | 60,090 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 1,026 | 72 | 954 | 1,046 | 84 | 962 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 138 | 10 | 128 | 141 | 12 | 129 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 3,203 | 223 | 2,980 | 3,267 | 262 | 3,005 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 117 | 9 | 108 | 119 | 10 | 109 |
| T | Total fund needed | (N + O + P + Q + R + S) | 68,534 | 4,758 | 63,776 | 69,897 | 5,600 | 64,297 |
| U | Total country co-financing | I * country co-financing per dose | 4,758 |  |  | 5,600 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 6.94% |  |  | 8.01% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ | 250’000 $ | 2’000’000 $ |
| --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Intermediate - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |
| Measles, 10 doses/vial, Lyophilised |  | 0.00 | 0.00 | 0.00 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 7 | Yes |
| Improvement plan based on EVM |  | 8 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 10 |  |
| Banking details |  | 9 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name | New file | Actions |
| --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\signatures ministre sante.2011.pdf Date/Time: 31.05.2011 07:32:33 Size: 281 KB |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\signatures ministre finance.2011.pdf Date/Time: 31.05.2011 06:55:37 Size: 281 KB |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\signatures CCIA 11.05.2011.pdf Date/Time: 31.05.2011 07:23:39 Size: 254 KB |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\CCIA 11.05.2011.pdf Date/Time: 31.05.2011 07:23:39 Size: 743 KB |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: PPAC version du 01-06-11.doc Date/Time: 01.06.2011 06:28:45 Size: 2 MB |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: gavi+2011_cMYP_Costing_Tool_Vs+2+5_Fr_STP26052011.xls Date/Time: 01.06.2011 10:07:02 Size: 3 MB |  |  |
| 7 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\3 REUNION CCIA.pdf Date/Time: 31.05.2011 08:00:06 Size: 1 MB |  |  |
| 8 | File Type: Improvement plan based on EVM * File Desc: | File name: GEV.doc Date/Time: 01.06.2011 06:28:45 Size: 25 KB |  |  |
| 9 | File Type: Banking details File Desc: | File name: C:\Documents and Settings\stp02fp.UNDPST.001\Ambiente de trabalho\gavi 2011\etablissement financiere.pdf Date/Time: 31.05.2011 07:48:45 Size: 538 KB |  |  |
| 10 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Plan d'Introduction du PCV-13 et VAR 2_24-05-11.doc Date/Time: 06.06.2011 05:37:41 Size: 767 KB |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Sao Tome and Principe hereby requests that a payment be made via electronic bank transfer as detailed below: |  |
| --- | --- |
| Name of Institution (Account Holder): |  |  |
| Address: |  |  |
| City Country: |  |  |
| Telephone no.: |  | Fax no.: |  |  |
| Currency of the bank account: |  |  |
| For credit to: |  |
| Bank account's title: |  |  |
| Bank account no.: |  |  |
| Bank's name: |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |
| --- |
| 1 |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: