GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Djibouti

Date of submission: 31.05.2011 13:26:05

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 |  |  |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 1.2 - Rotavirus 2-dose schedule

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.2  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Established since 1984, the Expanded Program on Immunization (EPI) has gone through several stages. Between 1984 and 1990, the program's performance achieved the highest coverage, that is, 87% of DTP3.

From 1991 to 1994 because of the civil war nearly two thirds of the country was totally deprived of essential health care, including immunization activities. The lull recorded 1995 onwards has allowed immunization campaigns to resume that have generated a slight increase in immunization coverage.	

It is from 2000 that the program was launched again by the national authorities. This stimulus covered all program activities and has carried on till today.

In recent years the country has made considerable progress in improving the health system. 
The principal focus points of health-care developed are:

The establishment of community pharmacies	
The reorganization of districts in health regions

The financial participation of users,

The development of human resources ,

The autonomy of the major public institutions,

The strengthening priority health programs including the EPI.

However, much remains to be done in the field of immunization to help significantly reduce mortality and morbidity.

Infant mortality remains high with a rate of 67 per thousand live births according to EDIM (Djibouti survey on multiple indicators) 2006.
The main causes of hospitalization and death among children are: pneumonia, diarrheal diseases, malnutrition.

According to the Countdown report (WHO/CHERG2010), diarrhea and pneumonia kill 18% to 16% of children in the Republic of Djibouti respectively.

In terms of vaccination coverage significant efforts have been made since the relaunch of the Expanded Program on Immunization in 2000.

These incremental coverage improvements were demonstrated by:

-The PAPFAM survey conducted in 2002 showed that 53.1% of children have received the DPT3, 39.2% the Polio and 58% of children under 23 months were vaccinated against measles.

-In 2006, the EDIM report states DTP3 56, 8% and 65% measles.

-The vaccine coverage survey conducted in June 2008 revealed that 83% of children under one year received the 3 DTCP doses and 73% the first ROUVAX dose.

In order to accelerate the significant reduction of mortality and morbidity in young children, the Health Department introduced the Pentavalent vaccine (DTP+Hib+HepB) in 2007.

Government co-financing to supply PENTAVALENT will begin in 2012.

The 2010 annual report of Expanded Program of Immunization routine activities shows coverage of 88% for the PENTAVALENT and 85% against measles.	

With this experience, the Health Department decided to prepare the proposal to introduce two other new vaccines: the pneumococcal vaccine (PVC13) in 2012 and the anti rotavirus vaccine in 2013. The preparation of the proposal began in February 2011.

The Ministry of Health is supported in all stages of the application process by its traditional partners (WHO and UNICEF).

According to analysis by the Johns Hopkins University in September 2009 with support from GAVI, in Djibouti invasive pneumococcal diseases are responsible for 2178 cases of pneumonia, meningitis and other invasive diseases each year.

Fatality rates are 15% for pneumonia and 66% for meningitis.

With a coverage of 90% and 85% efficiency of the vaccine against pneumococcus, 76% of deaths from these diseases could be prevented each year.

The introduction of the vaccine against pneumococcal disease will contribute to achieving MDG 4 and will also reduce the burden of pneumococcal disease among adults in reducing naso-pharyngeal carriage of streptococci and thus reduce the spread of disease by herd immunity.

On the other hand, the anti rotavirus vaccine combined with prevention measures (basic hygiene and oral rehydration therapy) the infant-juvenile mortality will be significantly reduced in Djibouti.

In this context, the EPI multi-year plan is updated with the support of UNICEF covering the period 2011-2015.

A cold chain capacity needs evaluation is conducted in April 2011 with support from WHO. The current capacity of the cold chain sufficient until 2012 is enhanced by 10 refrigerators and 6 freezers. A 20m3 cold room is planned with the World Bank at central level by the end of 2011.

The cost of the introduction of the anti pneumococcal vaccine in the first year is estimated at 338,965 USD including government co-financing.

But the introduction of two new vaccines (the anti pneumococcal in 2012 and the anti rotavirus in 2013) will drastically contribute to the reduction of the mortality current rate of among children under 1 year by less than 2/ 3.

The objective of the EPI is to achieve a vaccination coverage of 95% for the anti pneumococcal vaccine and 90% for the anti rotavirus vaccine by the end of 2015.

To achieve this goal, the Ministry of Health is committed to improving immunization services throughout the country through the systematic implementation of all the strategies developed in the EPI's 2011-2015 multi-year action plan.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Djibouti would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid , Rotavirus 2-dose schedule introduction.

The Government of Djibouti commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of March.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) | Minister of Finance (or delegated authority) |
| --- | --- |
| Name | ALI YACOUB MAHAMOUD | Name | ILYAS MOUSSA DAWALEH |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Mr ABDALLAH AHMED HADE | NATIONAL COORDINATION, EPI | MOBILE : (00253) 825900 BUREAU (00253) 351491 | abdallahhade@yahoo.fr |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 10.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr SALEH BANOITA TOURAB Secretary General, MH | Ministry of Health |  |  |
| Dr RIDA JEBENIANI IP representative | WHO |  |  |
| Dr MOKHTAR OMAR AHMED Child survival and develop. Specialist | UNICEF |  |  |
| Dr MARCEL MBYA medical officer | HCR |  |  |
| Dr JIDIA STEPHANO Director | AMDA |  |  |
| Mme MOUMINA HOUMED Director Health Promotion | Ministry of Health |  |  |
| Mme FATOUMA MOHAMED KAMIL Director Health Regions | Ministry of Health |  |  |
| Mr ABDOULRAHMAN MOHAMED ABOUBAKER Director DEPCI | Ministry of Health |  |  |
| Mr ABDALLAH AHMED HADE EPI national coordinator | Ministry of Health |  |  |
| Mr ABDO ALI MOHAMED EPI Communication | Ministry of Health |  |  |
| Mme AICHA ADBARA IBRAHIM Planning Officer | Ministry of Health |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | ABDALLAH AHMED HADE | Title | EPI NATIONAL COORDINATOR |
| --- | --- | --- | --- |
| Tel no | 00(253) 351491 |  |  |
| Fax no | 00 (253) 3506647 | Address | Republique de Djibouti. Ministere de la santé. BP.1974 Téléphone:00(253)351491 Djibouti. |
| Email | abdallahhade@yahoo.fr |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-agency Coordination Committee ( ICC). |
| --- | --- |
| Year of constitution of the current committee | 2001 |
| Organisational structure (e.g., sub-committee, stand-alone) | Autonomous organization representing the Ministry of Health, civil society, partners (WHO ; UNICEF), and NGOs. |
| Frequency of meetings | Quarterly or when summoned by the President |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair | Secretary General, MH. Ministry of Health . | Dr SALEH BAOITA TOURAB |
| Secretary | United Nations Children’s Fund Representative, UNICEF | Dr JOSEFA MARRATO |
| Members | EPI Coordinator, Ministry of Health | ABDALLAH AHMED HADE | Action |
|  | WHO EPI Representative | DR RIDA JEBENIANI |  |
|  | Director – Health Promotion, Ministry of health | Ms. MOUMINA HOUMED |  |
|  | Representant HCR | Okimba |  |
|  | Director – Health regions, Ministry of Health | Ms. FATOUMA MOHAMED KAMIL |  |
|  | Director of study ; international planning and coordination Ministry of health , | M.ABDOULRAHMAN MOHAMED ABOUBAKER |  |
|  | EPI Communication Ministry of Health | ABDO ALI MOHAMED |  |
|  | Secretary general, Union of Djibouti Women UNFD | Ms. DEGMO DJAMA |  |
|  | AMDA Director | JIDIA STEPHANO |  |
|  | Maternal and Child Health Director Ministry of Health | MOUNIRA ALI |  |
|  | Director, Institute of Public Health Ministry of Health | Dr AMMAR AHMED ABDO |  |
|  | Child Survival and Development Specialist UNICEF | Dr MOKTAR OMAR AHMED |  |
|  | Child Survival and Development Officer UNICEF | Dr MOHAMADOU BACHIR MBODJ |  |

Major functions and responsibilities of the committee

-Determine priority actions of the EPI, -Monitor strategy implmentation, -Participate in financial resource mobilization, -Provide technical support to EPI

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | -Report on the progress in EPI activities. This involves verifying strengths and weaknesses of the EPI in different fields especially training, communication, and vaccine management. |
| --- | --- |
| 2. | - Define the mission of teams within the ICC for implementing recommendations. The committee formed sub working groups to help EPI in planning and implementation of recommendations translated into an action plan. |
| 3. | -Strengthen the monitoring system for EPI activities through meetings and workshops. To optimize success, meetings will be planned. The objective of these meetings is to know about developments in the activities to bring about timely adjustments during and after the execution period. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 05.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 5.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Mr Abdallah Ahmed Hade | Title | EPI Coordinator |
| --- | --- | --- | --- |
| Tel no | Mobile 00253 825900 or 253 35 14 91 |  |  |
| Fax no | 00253 35 06 47 | Address | Ministry of Health |
| Email | abdallahhade@yahoo.fr |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | National Immunization Technical Advisory Group for Immunization |
| --- | --- |
| Year of constitution of the current NITAG | 2010 |
| Organisational structure (e.g., sub-committee, stand-alone) | autonomous committee |
| Frequency of meetings | once every three months |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair | Director, Armed forces health centers | Dr Ahmed Hassan Boulaleh |
| Secretary | Health Economist; Technical Advisor to the Ministry of Health | Dr Mahyoub Mohamed |
| Members | Specialist in infectious and tropical diseases | Dr Houssein Youssouf | Action |
|  | Chief Physician, Social Protection Body | Dr Mahamoud Mohamed Ismael |  |
|  | Health center doctor | Dr Meeke Mohamed Moussa |  |
|  | Laboratory Officer Ministry of Health | Mohamed Hassan Ali |  |
|  | Director, Institute of Public Health, Ministry of Health | Dr Ammar Ahmed Abdo |  |
|  | Chief Pediatrician, Peltier General Hospital | Dr Ahmed Robleh Abdilleh |  |
|  | Child Survival and Development Specialist UNICEF | Dr MOKTAR OMAR AHMED |  |
|  | Child Survival and Development Officer UNICEF | Dr MOHAMADOU BACHIR MBODJ |  |
|  | Medical officer WHO | Dr Ridha Djebeniani |  |

Major functions and responsibilities of the NITAG

Defined DGTCV roles are : -give technical advice on the subject to the Government -formulate btter policies and strategies. -Monitor the program on immunization, collection, and important data identification program, -Inform about the latest scientific developments in vaccines and diseases preventable with the help immunization.

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | -organize meetings for information and training of halth professions to raise their interest in prevention by immunization. |
| --- | --- |
| 2. | -promotion on immunization by using public public institutions and social organizations in the proximity. The NITAG can be an effective catalyst for spreading the message on vaccines and immunization |
| 3. | -make a plea for implementing a reliable edipemiological surveillance system. To help the political people make decisions NITAG should have reliable and timely information |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 5

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure | Year | Source |
| --- | --- | --- | --- |
| Total population | 818,159 |  | 2009 | Preliminary report on population census |
| Infant mortality rate (per 1000) | 67 |  | 2006 | EDIM |
| Surviving Infants[1] | 24,427 |  | 2010 | Annual report |
| GNI per capita (US$) | 1,280 |  | 2009 | World Bank |
| Total Health Expenditure (THE) as a percentage of GDP | 15.00 | % | 2010 | Mnistry of Health |
| General government expenditure on health (GGHE) as % of General government expenditure | 54.20 | % | 2010 | Medium term health expense card 2009 – 2012 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

National Health Development plan (PNDS) prepared in 2008 extends upto 2010. It is a reference document for budget and action planning by the Ministry of Health. This plan was revised in September and October 2010. Another plan is being prepared since 2011 for the next 5 years starting end of 2010. Parallel to this PNDS, the Ministry Health prepares a budgtized action plan every year. These plans are executed by different programs and services of the Ministry of health under the supervision of the Department of study, planning and international cooperation.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The Ministry of Health has put together multi-year plan in 2006 for immunization 2007-2011. This plan was reviewed and actualized. A new plan was prepared for the period 2011-2015. This five-year plan is in line with the document.

Please indicate the national planning budgeting cycle for health

At the end of each year, the Ministry of Health puts forth budget proposals to the Ministry of Finance. The Ministry of Finance organizes budgetary among different Ministries. After a discuaaion, the annual budget of the Ministry of health is adopted by the Government. This budget is available at the beginning of each year. The budget coming from an external source is discussed, approved, and signed at the Ministry of External Affairs and International Cooperation. The expenses are incurred by the Ministry of Health under the direction and control of the external expenses department of the Ministry of Finance.

Please indicate the national planning cycle for immunisation

The expanded program on immunization prepares its annual plan of action from the five-year plan (PNDS) and sends it to the Ministry of Health. This plan is then discussed with different partners (WHO-UNICEF-WB) to prepare annual and half-yearly action plans. The Ministry of health and the partners mobilize funds for implementation of these plans. The expanded program on immunization responsible for execution of these plans organizes meetings with different committees (interagency coordination committee, national immunization technical advisory group for immunization, immunization monitoring committee) to follow-up on all these activites.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Until now, the systematically collected EPI data is not categorized by gender. There is no social circle differences in offering immunization services. On the contrary, some information is likely to come to light during the gender-wise coverage survey.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

-

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | birth | Yes | In 2011(September) , first dose of hepatitus will be given at birth |  |
| Penta | 6 weeks , 10 weeks , 14 weeks | Yes |  |  |
| Polio | birth, 6weeks , 10weeks , 14weeks | Yes |  |  |
| DTP | 15 months | Yes |  |  |
| Measles | 9months | Yes | In 2011 second dose in the 15th months |  |
| Vitamin A | 6 months onwards . | Yes |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2009 | 2010 |  | 2008 |  | 2009 | 2010 |
| BCG | 90 | 90 |  | 93 | Tuberculosis |  |  |
| DTP | DTP1 | 90 | 90 |  | 91 | Diphtheria | 0 | 0 |
|  | DTP3 | 88 | 88 |  | 83 | Pertussis | 0 | 0 |
| Polio 3 | 88 | 88 |  | 83 | Polio | 0 | 0 |
| Measles (first dose) | 84 | 85 |  | 73 | Measles | 48 | 7 |
| TT2+ (Pregnant women) | 70 | 69 |  | 65 | NN Tetanus |  |  |
| Hib3 | 88 | 88 |  | 83 | Hib[2] |  |  |
| Yellow Fever |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 | 88 | 88 |  | 83 | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) | 80 | 85 |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

VACCINE COVERAGE SURVEY 2008 WITH TARGET GROUP OF 0-23 MONTHS

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |
| --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 26,181 | 27,776 | 28,609 | 29,467 | 30,351 |  |  |
| Total infants' deaths | 1,754 | 1,861 | 1,917 | 1,975 | 2,034 |  |  |
| Total surviving infants | 24,427 | 25,915 | 26,692 | 27,492 | 28,317 |  |  |
| Total pregnant women | 26,181 | 27,776 | 28,609 | 29,467 | 30,351 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 23,563 | 25,554 | 26,607 | 27,699 | 28,834 |  |  |
| BCG coverage (%)[1] | 90% | 92% | 93% | 94% | 95% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 21,496 | 23,324 | 24,290 | 25,568 | 26,902 |  |  |
| OPV3 coverage (%)[2] | 88% | 90% | 91% | 93% | 95% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 21,985 | 23,583 | 24,557 | 26,118 | 27,184 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 21,496 | 23,324 | 24,290 | 25,568 | 26,902 |  |  |
| DTP3 coverage (%)[2] | 88% | 90% | 91% | 93% | 95% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 10% | 10% | 10% | 10% | 10% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 23,583 | 24,557 | 26,118 | 27,184 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 23,324 | 24,290 | 25,568 | 26,902 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 90% | 91% | 93% | 95% |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  |  | 21,888 | 23,644 | 25,769 |  |  |
| Target population vaccinated with last dose of Rotavirus |  |  | 21,354 | 23,369 | 25,486 |  |  |
| Rotavirus coverage (%)[2] | 0% | 0% | 80% | 85% | 90% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 20,763 | 23,065 | 24,023 | 25,293 | 26,902 |  |  |
| Measles coverage (%)[2] | 85% | 89% | 90% | 92% | 95% |  |  |
| Pregnant women vaccinated with TT+ | 18,607 | 20,598 | 21,457 | 23,537 | 25,799 |  |  |
| TT+ coverage (%)[4] | 71% | 74% | 75% | 80% | 85% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 20,763 | 23,755 | 24,023 | 25,293 | 26,902 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 2% | 1% | 1% | 2% | 1% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Vaccines (routine vaccines only) | 266,031 | 601,804 | 981,575 | 964,330 | 1,025,641 |  |  |  |  |
| Traditional vaccines | 34,031 | 48,619 | 47,994 | 50,360 | 52,728 |  |  |  |  |
| New and underused vaccines | 232,000 | 553,185 | 933,581 | 913,970 | 972,913 |  |  |  |  |
| Injection supplies | 17,976 | 29,662 | 29,747 | 31,488 | 33,319 |  |  |  |  |
| Personnel | 183,840 | 278,287 | 341,793 | 348,630 | 355,602 |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 176,040 | 266,426 | 329,059 | 335,641 | 342,353 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 7,800 | 11,861 | 12,734 | 12,989 | 13,249 |  |  |  |  |
| Transportation | 46,989 | 69,914 | 71,672 | 73,473 | 67,778 |  |  |  |  |
| Maintenance and overheads | 119,082 | 187,805 | 203,479 | 218,622 | 163,703 |  |  |  |  |
| Training |  | 95,457 | 106,121 | 54,122 | 87,222 |  |  |  |  |
| Social mobilisation and IEC | 5,000 | 74,909 | 82,827 | 44,921 | 53,769 |  |  |  |  |
| Disease surveillance |  | 78,654 | 87,985 | 98,876 | 110,883 |  |  |  |  |
| Program management |  | 81,463 | 92,426 | 68,690 | 81,126 |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 638,918 | 1,497,955 | 1,997,625 | 1,903,152 | 1,979,043 |  |  |  |  |
| Routine Capital Costs |
| Vehicle | 20,400 | 40,784 | 45,844 | 51,091 | 29,589 |  |  |  |  |
| Cold chain equipment | 38,045 | 88,825 | 115,573 | 143,127 | 129,734 |  |  |  |  |
| Other capital equipment | 31,400 | 40,596 | 40,596 | 40,596 | 40,596 |  |  |  |  |
| Subtotal Capital Costs | 89,845 | 170,205 | 202,013 | 234,814 | 199,919 |  |  |  |  |
| Campaigns |
| Polio | 407,707 | 346,211 | 363,106 | 380,837 | 399,445 |  |  |  |  |
| Measles | 0 |  | 0 |  |  |  |  |  |  |
| Yellow Fever | 0 | 0 | 0 | 0 |  |  |  |  |  |
| MNT campaigns | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Other campaigns | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Subtotal Campaign Costs | 407,707 | 346,211 | 363,106 | 380,837 | 399,445 |  |  |  |  |
| GRAND TOTAL | 1,136,470 | 2,014,371 | 2,562,744 | 2,518,803 | 2,578,407 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Traditional vaccines | UNICEF | 34,031 | 48,619 | 47,994 | 50,360 | 52,728 |  |  |  |  |  |
| New vaccines; under-used and injection material | GAVI | 249,976 | 582,847 | 963,328 | 945,458 | 1,006,232 |  |  |  |  |  |
| Personnel | MH/UNICEF | 183,840 | 278,287 | 341,793 | 348,630 | 355,602 |  |  |  |  |  |
| Transport | MH/UNICEF | 46,989 | 69,914 | 71,672 | 73,473 | 67,778 |  |  |  |  |  |
| Maintenance and general expenses | MH/UNICEF | 119,082 | 187,805 | 203,479 | 218,622 | 163,703 |  |  |  |  |  |
| Training | UNICEF/GAVI |  | 95,457 | 106,121 | 54,122 | 87,222 |  |  |  |  |  |
| IEC social mobilization | UNICEF | 5,000 | 74,909 | 82,827 | 44,921 | 53,769 |  |  |  |  |  |
| Surveillance | WHO |  | 78,654 | 87,985 | 98,876 | 110,883 |  |  |  |  |  |
| Program management | MH/UNICEF/GAVI |  | 81,463 | 92,426 | 68,690 | 81,126 |  |  |  |  |  |
| Routine Capital Costs |  |
|  | UNICEF/MH/World Bank | 89,845 | 170,205 | 202,213 | 234,814 | 199,919 |  |  |  |  |  |
| Campaigns |  |
|  | WHO/UNICEF/MH |  |  |  |  |  |  |  |  |  |  |
|  | UNICEF | 266,000 | 187,540 | 197,142 | 206,475 | 216,261 |  |  |  |  |  |
|  | WHO | 141,707 | 157,970 | 165,964 | 174,361 | 183,184 |  |  |  |  |  |
| GRAND TOTAL | 1,136,470 | 2,013,670 | 2,562,944 | 2,518,802 | 2,578,407 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Decentralization of the health-care system is one of the priorities for the Ministry of Health. It is a necessity to ensure not only equality but also to devolve the managerial burden of actors/players allowing better health-care coverage. The country is divided into six (6) administrative regions: a region centered on the capital (Djibouti) and 5 other interior regions (Ali Sabieh, Arta, Dikhil, Obock, and Tadjoura).Health-care services in Djibouti are provided at three levels: the peripheral level that includes health posts, the intermediary level that represents the regional hospitals and community health centers, and finally reference hospitals at the central level. Immunization services are available to all levels of the health system - public, semi-private and private – on a daily basis. Since 2006 vaccines have never been out of stock and vaccine orders are placed through joint planning with WHO and UNICEF. The vaccines are stored at the central depot with monthly distribution to health centers. Regular monitoring is done once a week by the central team. At regional level vaccine distribution takes place every two months with regular and supportive quarterly supervision. Health-care regions distribute vaccines to health posts once a month. The capacity of the cold chain was strengthened in 2006 and covers virtually the entire country. The cold chain equipment in good working condition and with a long shelf life, are of two types: in the capital and in the regional hospitals. Power supply is of electrical origin. As for the health posts in health-care regions, they are run on solar energy. To ensure proper storage of vaccines, the central depot and community health centers are equipped with generators. The installed equipment complies with WHO-UNICEF standards. Maintenance is carried out every 6 months by the program with support of UNICEF to ensure proper functioning of the cold chain. AT THE CENTRAL LEVEL: The expanded program on immunization provides a central depot with two cold rooms, one with positive capacity of 4,140 liters and one a negative of 3,750 liters. . Similarly at the central level, there are 7 refrigerators with a capacity of 645 liters and 9 freezers with a capacity of 1,150 liters. with a total capacity of 4,785 positive liters and 4,900 negative liters, In addition to this equipment a positive cold room with a gross capacity of 20 m3 is scheduled for 2011 with the help of funding from the World Bank. This will cover all storage needs at the central level with the introduction of new vaccines. AT THE INTERMEDIATE LEVEL: The current storage capacity available in the health regions is of 1,320 positive liters and 360 negative liters. In addition to this equipment, the expanded program on immunization has received ten refrigerators from the World Bank with a total capacity of 922 liters and 6 freezers with a total capacity of 766 liters which will be distributed to health regions. The evaluation of the cold chain conducted with support from UNICEF shows that storage capacity is sufficient at all levels, to meet the needs for both, the existing vaccines as well as for the introduction of new vaccines According to the last cold chain evaluation carried out , the storage capacity is sufficient at all levels, to meet the needs both for existing vaccines as well as for the introduction of new vaccines

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

The World Health Organization informs the member countries about the immunization policy, available vaccines, priorities, and support in order to introduce them. The Djibouti government then decided to broaden the range of antigens by introducing it into the national immunization program. The anti pneumococcal vaccine and the anti rotavirus can reduce the high mortality and morbidity rates among children less than 5 years. In fact, mortality rate among children under 5 years in Djibouti was estimated at 16% for pneumonia and 18% for diarrhea (Countdown 2010 WHO / CHERG). In 2010, the Ministry of Health report showed that pneumonia was the leading cause of consulting a doctor with 25% of cases, and diarrhea in second place with 19% in children under 5 years old (Mother and Child Health Directorate). Pneumonia and diarrhea remain the two main causes of consulting a doctor, hospitalization, and death in this age group according to hospital data. Also, the decision to introduce new vaccines has been endorsed by the Inter-Agency Coordination Committee (ICC Report attached) during the various meetings held since February 2011.The decision making process involved several steps: - the coordination committee made recommendations to the Department of Health for accelerating the introduction of two new vaccines with the view of reducing mortality from these diseases in children less than 5 years. In fact, this initiative aims to contribute to the achievement of Goal 4 of the Millennium Development Goals by 2015. - National Immunization Technical Advisory Group (NITAG) meeting to make recommendations to this effect. - Meeting with the Health Minister to present the implementation plan of new vaccines. - Plea to the Finance Minister for co-financing with the support of the Health Minister. - Inter-Agency Coordinating Committee (ICC) meetings to finalize the proposal before submission to GAVI.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (liters or m3) Liters | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 3,410 | 4,705 | 4,908 |  |  |  |  |  |
| B | Existing net positive cold chain capacity (liters or m3) Liters | # | 4,685 | 4,685 | 4,685 |  |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 2 | 2 |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 1 | 1 | 1 |  |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -1,275 | 20 | 223 |  |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 0 |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The budget line related to Djibouti's share for new vaccines will be included in the Ministry of Health's national budget. In this regard, commitment is obtained at the highest level of government. The Ministry of Health, in coordination with the Ministry of Finance through the national treasury, will be responsible for the payment of the amount of share. The funds on the purchase of vaccines chapter will be transferred to GAVI through the UNICEF office in Djibouti.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Pneumonia | Annual report of Maternal and Child Health Department | 2010 | 25% of consultation cases at the regional health structures in the interiors and in Djibouti City |  |
| Diarrhia | Annual report of Maternal and Child Health Department | 2010 | 19% of consultaition cases at the regional health structures in the interiors and in Djibouti City |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |
| --- | --- |
| cold chain capacity: | - the storage capacity of the national depot has been enhanced by the installation of positive cold storage rooms with a capacity of 4,140 liters and a negative capacity of 3,750 liters -regular maintenance and automatic start in the generator at Enguela’s national depot. -appropriate preventive maintenance of the cold chain equipment. -implementation of functional stock sheets and order sheets in training of health workers which allowed supply and monitoring of vaccine management. -Systematic use of sheets/ order forms, for monitoring temperature and delivery. -Installation of solar systems in all health posts. - Establishment of a regular cold chain maintenance system. |  |
| skills of the health-care staff | -Training of health-care professionals and establishing proper equipment maintenance to sustain the significant efforts made under the program -manager training in methods of needs assessment and strengthened coordination. - Training/retraining of health workers on vaccine management, immunization practices and vaccine safety, and dangers of freezing vaccines. In addition, a ministerial circular on the conservation and use of vaccines has been distributed and posted in all immunization services. -training immunization workers in drop-out rates and wastage rates of the new pentavalent vaccine -training through supervision to consolidate the acquired skills. |  |
| Communication and social mobilization | -Developing a communication strategy. Production of adapted educational media (flip chart, posters, commercials, leaflets, posters etc...) according to the communication need. - Strengthening of information and sensitization activities - Training staff in matters of interpersonal communication. -Social mobilization through media (Radio, TV, print.) |  |
| Monitoring and evaluation | - Regular training through supervision - regular and frequent monitoring from the beginning of the introduction period to observe and check storage of vaccines, immunization practice, and interpersonal communication - Service notes only for the use of vaccine storage refrigerators in health-care facilities. - post introduction evaluation made and recommendations and lessons learnt have been implemented |  |
| Post introduction Pentavalent Evaluation in Djibouti | Monitoring of the evaluation recommendations (Follow up PIE Recommendations ) A. At the national level • Planning a budget line for co-financing the purchase of new vaccines being discussed at the highest level (Finalized) • The National immunization technical advisory group (NITAG) is established by ministerial directive • The briefings and meetings were organized at all health-care regions on decentralization of responsibilities and management of immunization activities. • A ministerial circular on vaccination guidelines and injection safety is distributed and displayed in all health centers. A communication plan is developed in May 2009 B. At the regional level, the Centers and Health posts • Training programs have been strengthened on the following topics: - Calculation of coverage - Wastage rates - Monitoring immunization activities - Vaccine Management • The data on target populations (annual and monthly target) were distributed and displayed in all health centers. • A communication plan is developed in May 2009 • IEC training has been organized for associations and health personnel. Educational media on vaccines have been produced. |  |
| Post introduction of Pentavalent evaluation in Djibouti (continued): Experiences from the introduction of the Pentavalent vaccine: • The introduction of the new vaccine was an opportunity to strengthen the EPI (PEV) in its entirety: Advocacy with decision makers, negotiations with the Ministry of Finance on the establishment of a budget line for co-financing the contribution for the purchase of new vaccines. • It is necessary that all guidelines are written and distributed at all health facilities. • The secondary evaluation of introduction of the new vaccine has also shown the strengths and improvements needed in the Expanded Program on Immunization at a given point of time • Importance of developing the New vaccine introduction plan at the national level which should not be static but that must adapt to the regional context and be available at all levels of health facilities • To monitor side effects of each new vaccine, it is important to develop forms, to develop national guidelines for AEFI (MAPI), make them available at all health facilities, and train health personnel in this regard. • When introducing a new vaccine, it is important to train health personnel in general but also in interpersonal communication for getting the message across to mothers and fight rumors. Take into account public communication, and also social mobilization • In Djibouti the new vaccine was well accepted by health professionals and the community not only as a new vaccine but also as a vaccine that protects against hepatitis and meningitis (well known by mothers and which have local language names) • The fact there has been no change in the immunization schedule has facilitated the introduction and presentation of the vaccine which is in liquid form and has two doses • For future introductions of new vaccines in Djibouti, as observed in post introduction evaluation, it is important to differentiate the newly introduced vaccines from traditional vaccines. In this context, it is desirable to find a name in the local language, easy for the community to remember, for each new vaccine included in the EPI, This will later facilitate post introduction evaluation, and also monitoring the Adverse Events Following Immunization (AEFI or MAPI), mothers’ memory and health workers’ memory regarding the new vaccine introduced. • The lesson for the future from the experience of the introduction is in Djibouti , as in Sudan, the importance of training health personnel while adding the anti pneumococcal and anti rotavirus vaccine to the EPI schedule |  |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

--anti pneumococcal vacci(conjugate)OCV13, one dose per vial, liquid. -anti rotavirus, one dose per tube, liquid. .

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Intermediate |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 23,583 | 24,557 | 26,118 | 27,184 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 23,324 | 24,290 | 25,568 | 26,902 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 90.00% | 91.00% | 93.00% | 95.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 5,000 | 4,800 | 5,800 | 7,000 |  |  |  |  |
| Number of AD syringes | # | 5,300 | 5,100 | 6,200 | 7,400 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 75 | 75 | 75 | 100 |  |  |  |  |
| Total value to be co-financed by country | $ | 19,000 | 18,000 | 22,000 | 26,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 87,900 | 73,400 | 77,800 | 79,600 |  |  |  |  |
| Number of AD syringes | # | 93,900 | 77,600 | 82,300 | 84,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,050 | 875 | 925 | 950 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 329,500 | 275,000 | 291,000 | 298,000 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 27,776 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 18,000 | 15,000 |
| Social Mobilization, IEC and Advocacy | 45,000 | 30,000 |
| Cold Chain Equipment & Maintenance | 25,000 | 15,000 |
| Vehicles and Transportation | 20,000 | 15,000 |
| Programme Management | 10,000 | 10,000 |
| Surveillance and Monitoring | 15,000 | 15,000 |
| Human Resources | 10,000 | 0 |
| Waste Management | 5,000 | 0 |
| Technical assistance | 0 | 0 |
|  | 0 | 0 |  |
| Totals | 148,000 | 100,000 |

# 6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Intermediate |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.23 | 0.26 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.23 | 0.26 |  |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 21,888 | 23,644 | 25,769 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 21,354 | 23,369 | 25,486 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 80.00% | 85.00% | 90.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.23 | 0.26 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 2,200 | 2,800 | 3,800 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25 | 50 | 50 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 11,500 | 12,000 | 14,500 |  |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 55,300 | 47,900 | 51,500 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 625 | 550 | 575 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 291,000 | 201,500 | 195,000 |  |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 28,609 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 20,000 | 15,000 |
| Social Mobilization, IEC and Advocacy | 45,000 | 25,000 |
| Cold Chain Equipment & Maintenance | 15,000 | 15,000 |
| Vehicles and Transportation | 25,000 | 20,000 |
| Programme Management | 5,000 | 5,000 |
| Surveillance and Monitoring | 15,000 | 15,000 |
| Human Resources |  | 5,000 |
| Waste Management | 5,000 |  |
| Technical assistance | 100,000 |  |
| Totals | 230,000 | 100,000 |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The fund to support the introduction of new vaccines will be transferred into the account of the Ministry of Health. This account is managed by the EPI manager and the Financial and Administrative Director of the Ministry of Health. A table on the use of funds is approved by the Secretary General of Ministry of Health. All expenses incurred are submitted to the Inter-agency Coordinating Committee for approval. The Expanded Program on Immunization has the responsibility to send fund utilization report to GAVI. The supply of new vaccines and injection equipment will be effectuated annually through UNICEF as with other vaccines.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

-

- Please describe the introduction of the vaccines (refer to cMYP)

The goal of the Expanded Program on Immunization in Djibouti is to reduce mortality and morbidity from diseases preventable with immunization. In Djibouti, the infant-child mortality is 94 per thousand live births according to EDIM 2006. According to the same study 67 per thousand live births die before their first birthday. With this in mind, the Ministry of Health has decided to expand the range of antigens by introducing two new vaccines (anti pneumococcal and anti rotavirus).The introduction of new vaccines is a priority for the Ministry of Health and the government. The specific objective of the introduction of new vaccines is to reduce mortality and morbidity due to acute respiratory infections caused by streptococcus pneumonia and diarrhea caused by the rotavirus. In fact worldwide, nearly 9.7 million children die annually before their fifth birthday. Every day, over 26,000 children in this age group die from causes that are preventable according to the UNICEF 2008 progress report. Pneumonia is responsible for approximately 19% of deaths among these children. In the Mediterranean region (EMRO), diarrhea and pneumonia kill 17% and 14% of children respectively according to the WHO Countdown report. According to the report of Countdown to 2015 (WHO/ CHERG 2010), diarrhea and pneumonia kill 18% and 16% of children in Djibouti. According to an analysis by the Johns Hopkins University with support from GAVI, in Djibouti, invasive pneumococcal diseases are responsible for 2178 cases of pneumonia, meningitis, and other invasive diseases each year. Fatality rates are 15% for pneumonia and 66% for meningitis. With a coverage of 90% and an efficiency of 85% of the vaccine against pneumococcus, 76% of deaths from these diseases could be prevented every year. Pneumonia and the diarrheal diseases are the two leading causes of hospitalization and death among children under 5 in the country. According to the Ministry of Health HIS (Health Information System) 2009 Annual Report, pneumonia and diarrhea are the main reasons for consultation in children under 5 years in Djibouti city and in the districts. These pathologies represented 57% of consultation cases in 2009. To cope with this reality the Ministry of Health with the support of WHO and UNICEF has implemented a strategy of taking charge of the acute respiratory infections with help of antibiotics, at the community level. For executing this strategy the Ministry of Health has recruited a hundred community health workers who were trained for a year. These community health workers, in addition to this activity provide a promotional service package to the rural community including active research and promotion of vaccination. The Ministry of Health intends to introduce the vaccine against pneumococcus in January 2012 and the vaccine against rotavirus in January 2013. These vaccines can be incorporated into the immunization schedule of the expanded program on immunization with the Pentavalent. The expected coverage by 2015 for these new vaccines will be 95% for pneumococcus and 90% for rotavirus. Monitoring indicators for the introduction plan for these new vaccines are: -The numbers of children immunized for the third time with the pneumococcal vaccine and with the second dose of the anti rotavirus vaccine; - Dropout rate (between the first and third dose of the vaccine against pneumococcus and between the first and second doses of the vaccine against rotavirus) - Wastage rate. The introduction plan for the new vaccines takes into account all activities for a better use of these new vaccines, and to achieve the above objectives. These activities are -increase vaccine coverage of target populations including remote and difficult to reach populations. -strengthen outreach to open remote rural areas. -strengthen and decentralize training supervision to enable health region managers to regularly monitor immunization activities in general and that of new vaccines in particular. -Reduce wastage rate and ensure vaccine safety - increase the systematic use of routine immunization services. These vaccines will be incorporated into the immunization schedule of the expanded program on immunization. -Vaccine against pneumococcal disease at 6, 10, and 14 weeks. -Vaccine against the rotavirus at 6 and 10 weeks. Vaccine management will also be strengthened through training of staff at all levels on the use and management of new vaccines. All monitoring and management tools (data collection sheet, schedules; immunization card, health card, stock management card, immunization registry, vaccine purchase orders, monthly reports, vaccine monitoring forms) will be revised and adapted to new vaccines. All health workers will be trained on the use of these new formats. The supply of new vaccines will be done through UNICEF as with other vaccines. The vaccine against pneumococcus will be administered with self-locking syringes and safety boxes will available to ensure maximum vaccine safety. All health centers providing immunization services have incinerators and all health workers will be trained / retrained on vaccine safety techniques. All training material on the new vaccines will be updated. Health professionals will be monitored on the job after formal training. The educational material as well as the key messages concerning new vaccines are developed and distributed through all channels of existing media. Information campaigns, awareness, and communication will be conducted before the introduction of new vaccines across the country. The existing monitoring system will be strengthened and a monitoring tool for the pneumococcus and rotavirus will be established with support from the WHO. The data collected by this system will be used to evaluate the impact of the introduction of new vaccines. In addition to these data, seroprevalence surveys of rotavirus and pneumococcal will be conducted periodically to evaluate the impact of new vaccines. At the same time, a vaccine coverage survey will be conducted in 2013.A post introduction evaluation is planned in late 2012. The results (strengths, weaknesses, recommendations and lessons learned) of the post introduction evaluation of DTP-Hib-HepB have been used to improve the preparation and introduction of new vaccines. Similarly, the result of the post anti pneumococcal introduction evaluation expected before end of 2012 will enable to better target and improve the introduction of anti rotavirus.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The funds to support new vaccines will be transferred to countries using the same channel as that for the Pentavalent, using the same bank details attached to documents.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The Republic of Djibouti government in coordination with the Ministry of Finance and Economy, and the Ministry of Health are responsible for paying the co-financing amount to GAVI Alliance. The funds will be transferred to GAVI Alliance through the Djibouti UNICEF office.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

All monitoring and management tools (data collection sheet, schedules; immunization card, stock management card, immunization register, vaccine purchase orders, monthly reports, vaccine monitoring forms) will be revised and adapted to new vaccines and all personnel will be trained in the use of these new media. These updated media will be duplicated and made available at all levels. The coverage of new vaccines will be monitored using the micro planning tools, for tracking and monitoring (target population, vaccine coverage, dropout rates, utilization rates, cumulative curve, lost from sight monitoring schedule). These data will be compiled in the routine EPI monthly activity reports. These reports are generated, collected and analyzed by health posts and the HMC at district level, by community health centers, by para-public and private services in the capital. These data are also analyzed regularly at the central level for the concerned services. Regular supervisory training will be conducted at all the new centers and verify accuracy and reliability of transmitted data. Monitoring tools will be updated and will include the new vaccines. These activities and tools will enable monitoring of the coverage of new vaccines as well as dropout rates.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? August  - 2009

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? April   - 2011

If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°20)

A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

After a vaccine management evaluation of February 2006, the cold chain was strengthened by the establishment of two cold rooms (positive and negative). All health posts at the health district and health region level within the country were equipped with cold chain equipment powered by solar energy. HMC (hospital medical centers) of regional hospitals provide immunization activities and are very well equipped with electric cold chain equipment. Health centers in the capital are also well equipped with electric cold chain equipment. With the support of UNICEF, the program regularly performs half-yearly cold chain maintenance. Immunization staff and Expanded Program on Immunization personnel are regularly trained/retrained in vaccine management, in micro planning of immunization activities, and the use of collection tools, in the AEFI (adverse events following immunization), and in maintaining the solar energy powered cold chain. A positive cold room is also provided at the central level at the end of the year 2011 with funds from the World Bank. To strengthen vaccine distribution and management, 50 motorcycles were made available for health regions and health posts financed with the support of UNICEF/ USAID.

When is the next Effective Vaccine Management (EVM) Assessment planned? April   - 2011

Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

The ICC committee expresses its satisfaction over continuous effort of the team composed of UNICEF, WHO and MH in the preparation of the proposal document. The ICC committee recommends: - maintaining the dynamics of the team for eventual execution of the introduction plan for the new vaccines. -developing an effective communication strategy. -preparing mass training of health-care personnel per category in order to reach the Maximum number of health workers. - producing relevant and appropriate IEC material. -organizing the launch by involving higher-level decision makers (e.g. the President, the First Lady, the Prime Minister etc.)

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 5,000 | 4,800 | 5,800 | 7,000 |  |  |  |  |
| Number of AD syringes | # | 5,300 | 5,100 | 6,200 | 7,400 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 75 | 75 | 75 | 100 |  |  |  |  |
| Total value to be co-financed by the country | $ | 19,000 | 18,000 | 22,000 | 26,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 87,900 | 73,400 | 77,800 | 79,600 |  |  |  |  |
| Number of AD syringes | # | 93,900 | 77,600 | 82,300 | 84,200 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,050 | 875 | 925 | 950 |  |  |  |  |
| Total value to be co-financed by the country | $ | 329,500 | 275,000 | 291,000 | 298,000 |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 25,915 | 26,692 | 27,492 | 28,317 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 23,324 | 24,290 | 25,568 | 26,902 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 90.00% | 91.00% | 93.00% | 95.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 23,583 | 24,557 | 26,118 | 27,184 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 6.14% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 23,583 | 1,260 | 22,323 | 24,557 | 1,509 | 23,048 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 70,749 | 3,778 | 66,971 | 73,671 | 4,525 | 69,146 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 74,287 | 3,967 | 70,320 | 77,355 | 4,752 | 72,603 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 18,572 | 992 | 17,580 | 767 | 48 | 719 |
| I | Total vaccine doses needed | F + G | 92,859 | 4,959 | 87,900 | 78,122 | 4,799 | 73,323 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 99,147 | 5,295 | 93,852 | 82,627 | 5,075 | 77,552 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 1,101 | 59 | 1,042 | 918 | 57 | 861 |
| N | Cost of vaccines needed | I * vaccine price per dose | 325,007 | 17,355 | 307,652 | 273,427 | 16,794 | 256,633 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 5,255 | 281 | 4,974 | 4,380 | 270 | 4,110 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 705 | 38 | 667 | 588 | 37 | 551 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 16,251 | 868 | 15,383 | 13,672 | 840 | 12,832 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 596 | 32 | 564 | 497 | 31 | 466 |
| T | Total fund needed | (N + O + P + Q + R + S) | 347,814 | 18,572 | 329,242 | 292,564 | 17,969 | 274,595 |
| U | Total country co-financing | I * country co-financing per dose | 18,572 |  |  | 17,969 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 6.14% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 | 2015 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 6.94% |  |  | 8.01% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 26,118 | 1,814 | 24,304 | 27,184 | 2,178 | 25,006 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 78,354 | 5,440 | 72,914 | 81,552 | 6,533 | 75,019 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 82,272 | 5,713 | 76,559 | 85,630 | 6,860 | 78,770 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,230 | 86 | 1,144 | 840 | 68 | 772 |
| I | Total vaccine doses needed | F + G | 83,502 | 5,798 | 77,704 | 86,470 | 6,927 | 79,543 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 88,339 | 6,134 | 82,205 | 91,456 | 7,327 | 84,129 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 981 | 69 | 912 | 1,016 | 82 | 934 |
| N | Cost of vaccines needed | I * vaccine price per dose | 292,257 | 20,291 | 271,966 | 302,645 | 24,245 | 278,400 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 4,682 | 326 | 4,356 | 4,848 | 389 | 4,459 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 628 | 44 | 584 | 651 | 53 | 598 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 14,613 | 1,015 | 13,598 | 15,133 | 1,213 | 13,920 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 531 | 37 | 494 | 550 | 45 | 505 |
| T | Total fund needed | (N + O + P + Q + R + S) | 312,711 | 21,711 | 291,000 | 323,827 | 25,941 | 297,886 |
| U | Total country co-financing | I * country co-financing per dose | 21,711 |  |  | 25,941 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 6.94% |  |  | 8.01% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Rotavirus 2-dose schedule

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 2,200 | 2,800 | 3,800 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 25 | 50 | 50 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 11,500 | 12,000 | 14,500 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 55,300 | 47,900 | 51,500 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 625 | 550 | 575 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 291,000 | 201,500 | 195,000 |  |  |  |  |

Table 1.2  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 26,692 | 27,492 | 28,317 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 21,354 | 23,369 | 25,486 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # |  | 80.00% | 85.00% | 90.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 21,888 | 23,644 | 25,769 |  |  |  |  |
| Number of doses per child |  | # |  | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # |  | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # |  | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.20 | 0.23 | 0.26 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 | 2014 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.80% |  |  | 5.47% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 21,888 | 833 | 21,055 | 23,644 | 1,293 | 22,351 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 43,776 | 1,666 | 42,110 | 47,288 | 2,585 | 44,703 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 45,965 | 1,749 | 44,216 | 49,653 | 2,715 | 46,938 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 11,492 | 438 | 11,054 | 922 | 51 | 871 |
| I | Total vaccine doses needed | F + G | 57,457 | 2,186 | 55,271 | 50,575 | 2,765 | 47,810 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 638 | 25 | 613 | 562 | 31 | 531 |
| N | Cost of vaccines needed | I * vaccine price per dose | 287,285 | 10,929 | 276,356 | 202,300 | 11,059 | 191,241 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 409 | 16 | 393 | 360 | 20 | 340 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 14,365 | 547 | 13,818 | 10,115 | 553 | 9,562 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 41 | 2 | 39 | 36 | 2 | 34 |
| T | Total fund needed | (N + O + P + Q + R + S) | 302,100 | 11,492 | 290,608 | 212,811 | 11,633 | 201,178 |
| U | Total country co-financing | I * country co-financing per dose | 11,492 |  |  | 11,633 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.80% |  |  | 5.47% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 6.86% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 25,769 | 1,769 | 24,000 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 51,538 | 3,538 | 48,000 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 54,115 | 3,715 | 50,400 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,116 | 77 | 1,039 |  |  |  |
| I | Total vaccine doses needed | F + G | 55,231 | 3,792 | 51,439 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 614 | 43 | 571 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 198,832 | 13,649 | 185,183 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 393 | 27 | 366 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 9,942 | 683 | 9,259 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 40 | 3 | 37 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 209,207 | 14,362 | 194,845 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 14,361 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 6.86% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ | 250’000 $ | 2’000’000 $ |
| --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Intermediate - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.20 | 0.23 | 0.26 | 0.30 |  |  |  |
| Rotavirus 2-dose schedule |  | 0.20 | 0.23 | 0.26 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 6 | Yes |
| cMYP Costing tool for financial analysis |  | 5 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 7, 8, 9 | Yes |
| Improvement plan based on EVM |  | 20 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 13, 14 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 10 |  |
| Banking details |  | 11, 12 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name | New file | Actions |
| --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\2011-05-31 signature Ministre propostion\signatures Ministre S propostion 001.jpg Date/Time: 31.05.2011 10:06:05 Size: 1 MB |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\2011-05-31 signature Ministre propostion\signatures Ministre S propostion 001.jpg Date/Time: 31.05.2011 10:07:09 Size: 1 MB |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: Members of the Inter-agency Committee | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\2011-05-31 signature NV\signature CCIA 001.jpg Date/Time: 31.05.2011 10:12:45 Size: 1 MB |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: ICC Committee meeting 10 Mai 2011 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\Comité de Coordination Inter Agence avalisant.docx Date/Time: 31.05.2011 10:14:41 Size: 23 KB |  |  |
| 5 | File Type: cMYP Costing tool for financial analysis * File Desc: Multi-Year Plan 2011 - 2015 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\cMYP\280511DjibCMYPcosting Amman.xlsx Date/Time: 31.05.2011 10:16:35 Size: 1 MB |  |  |
| 6 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: Multi-Year Plan 2011 - 2015 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\cMYP\300511 Djibouti CMYP.doc Date/Time: 31.05.2011 10:18:12 Size: 1 MB |  |  |
| 7 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: ICC 2011 meeting | File name: G:\APR -SNV 2011\doc . joindre\CR 2011\Comité de Coordination Inter Agenc1.docx Date/Time: 31.05.2011 10:24:18 Size: 19 KB |  |  |
| 8 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: ICC meeting 2011 | File name: G:\APR -SNV 2011\doc . joindre\CR 2011\Comité de Coordination Inter Agence2011.docx Date/Time: 31.05.2011 10:24:59 Size: 18 KB |  |  |
| 9 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: réunion ICC | File name: G:\APR -SNV 2011\doc . joindre\CR 2011\Comité de Coordination Inter Agence.docx Date/Time: 31.05.2011 10:25:33 Size: 24 KB |  |  |
| 10 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: Pneumococcal and Rotavirus introduction plan | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\PlanIntroPneumoRotafinal 2011.docx Date/Time: 31.05.2011 10:38:40 Size: 464 KB |  |  |
| 11 | File Type: Banking details File Desc: Bank form /Signature | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\2011-05-21 banque signatue\banque signatue 001.jpg Date/Time: 31.05.2011 10:40:41 Size: 789 KB |  |  |
| 12 | File Type: Banking details File Desc: Bank form / signature | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\2011-05-21 banque signature\banque signature 002.jpg Date/Time: 31.05.2011 10:45:24 Size: 731 KB |  |  |
| 13 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: JRF 2009 | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\JRF_data_pour_2009_fran%C3%A7ais(1).xls Date/Time: 31.05.2011 10:49:33 Size: 374 KB |  |  |
| 14 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: JRF 2010 | File name: G:\APR -SNV 2011\doc . joindre\SNV2011\JRF_data_pour_2010_français.xls Date/Time: 31.05.2011 10:50:22 Size: 262 KB |  |  |
| 15 | File Type: other File Desc: Survey MICS 2006 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\EDIM_06.pdf Date/Time: 31.05.2011 11:02:34 Size: 348 KB |  |  |
| 16 | File Type: other File Desc: Health MTEF 2009-2012 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\RAPPORT DE PRESENTATION DU CDMT SANTE 2009-2012_VF.doc Date/Time: 31.05.2011 11:06:32 Size: 557 KB |  |  |
| 17 | File Type: other File Desc: Vaccine coverage 2008 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\Rapport final de couverture vaccinale.pdf Date/Time: 31.05.2011 11:09:53 Size: 374 KB |  |  |
| 18 | File Type: other File Desc: EVM May 2011 | File name: G:\APR -SNV 2011\doc . joindre\APR2010\Rapport GEV Djibouti-Version finale.doc Date/Time: 31.05.2011 11:09:53 Size: 1 MB |  |  |
| 19 | File Type: other File Desc: Introduction report PENTAVALENT 2009 | File name: G:\APR -SNV 2011\doc . joindre\attachments_2011_05_29.zip Date/Time: 31.05.2011 11:18:48 Size: 275 KB |  |  |
| 20 | File Type: Improvement plan based on EVM * File Desc: EVM Report | File name: G:\APR -SNV 2011\doc . joindre\GEV.docx Date/Time: 31.05.2011 11:39:33 Size: 23 KB |  |  |
| 21 | File Type: other File Desc: Minutes of the NITAG meeting | File name: G:\compte rendu GTCV.docx Date/Time: 31.05.2011 12:29:16 Size: 16 KB |  |  |