GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

United Republic of Tanzania

Date of submission: 16.06.2011 07:28:47

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2010 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 | Rotavirus 3-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 1.2 - Rotavirus 2-dose schedule

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.2  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

The Government of the United Republic of Tanzania (Mainland and Zanzibar) plans to introduce the Pneumococcal vaccine (PCV 13), in the single dose fully liquid formulation as first choice and PCV10 as second choice into the national immunization programme in 2012. Pneumococcal vaccine becomes the third vaccine to be introduced in the country with GAVI support since 2002. 

This is consistent with the two separate comprehensive Multi-Year Plans (cMYP) for 2010-2015 (Tanzania Mainland and Zanzibar) which clearly outlines the priorities of the immunization programme and objectives and strategies to achieve these. Key activities have been planned and costed to address the identified priorities, and financing has been analysed and sustainability strategies proposed. The Governments of Tanzania (both Mainland and Zanzibar) have budget lines for vaccines which are “ring-fenced” and separated for other funding allocated to the programmes.

In response to conditional approval from GAVI granted in 2010, expansion of cold chain storage capacity has been addressed. Two additional Walk in Cold Rooms with capacity of 40m3 have been installed at MSD increasing positive storage capacity at MSD to 40,000 litres as of April 2011. Procurement of six (6) more WICR with capacity of 40m3 is underway, with expected installation by the end of December 2011. This will increase at MSD the positive cold storage capacity to 97,144 litres which is adequate to enable quarterly shipments of all traditional and new vaccines up to 2015 including Pneumococcal (PCV13) and Rotavirus vaccine.

Disposal of immunization injections, used needles and syringes is a priority for the country to ensure that the recipient, health worker, community and the environment are safe. Both MOHSW have Health Care Waste Management Plan and Policy Guidelines which include handling and disposal of all injectable with those used by the EPI. The same policy will be applied during the PCV introduction.

This Introduction Plan specifically addresses the aspect of Pneumococcal introduction into the immunization programme. It outlines key activities to be conducted in preparation for introduction of the vaccine and a timeline for the different activities. It also provides a budget for all non-vaccine costs related to the activities defined in this plan, as well as the cost-share provision of USD0.20 per infant in the birth cohort in the introduction year. 

As provided in the guidelines on new vaccines introduction, this plan addresses the following key areas: 
•	Summary of the cMYP referring to the introduction of new and underused vaccines
•	Summary of cold chain capacity and its expansion plan showing the readiness to accommodate new vaccines.
•	How co-financing and financial sustainability will be achieved, also indicating portion of supply to be procured by the country and GAVI 
•	Pneumococcal disease burden in the country
•	Lessons learned from the introduction of Hepatitis B and pentavalent in the country 
•	List of the vaccines to be introduced with support from GAVI and specifications of vaccine
•	Concise information on key activities prior introduction: revision of recording and reporting tools, training of health workers, advocacy and social mobilisation, monitoring and supervision and Post Introduction Evaluation (PIE)
•	Timeline of activities related to Pneumococcal introduction. 

The non-vaccine costs associated with introducing Pneumococcal in 2012 amount to $2,147,000 and Introduction of Rota in 2013 amount to USD 2,010,000. The number of children in the projected birth cohort in 2012 is 1,919,383. The Government of Tanzania therefore requests GAVI to approve the new vaccine introduction grant and remit the sum of $575,815 to facilitate introduction of the Pneumococcal vaccine in 2012 and USD 582,500 to facilitate introduction of the Rotavirus vaccine in 2013.

The ICC meeting on 6th May 2011 endorsed this application.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of United Republic of Tanzania would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid , Rotavirus 2-dose schedule introduction.

The Government of United Republic of Tanzania commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of October.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) | Minister of Finance (or delegated authority) |
| --- | --- |
| Name | Hon.Dr. Hadji Hussein MPONDA | Name | Hon. Mustafa MKULO |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. Dafrossa C. LYIMO | EPI Programme Manager -MOHSW | +255715565568 | dafrossac@gmail.com |  |
| Mr.Christopher KAMUGISHA | WHO EPI Focal person | +255756959544 | kamugishac@tz.afro.who.int |  |
| Mr. Pamphil SILAYO | UNICEF EPI Focal Person | +255754749563 | psilayo@unicef.org |  |
| Mr. Kabelwa KAGARUKI | EPI Cold Chain and Logistic officer -MOHSW | +255755072212 | kabelwakagaruki@yahoo.com |  |
| Dr. Eliphase KAMUGISHA | UNICEF-Child health specialist - Zanzibar | +255784689862 | ekamugisha@unicef.org |  |
| Mr. Yusuf Haji MAKAME | EPI Programme Manager -MOHsW, Zanzibar | +255777422021 | yussufhaji2002@yahoo.co.uk |  |
| Mr.Abdul Ameir SALEH | EPI Cold Chain and Logistic officer- Zanzibar | +255754302611 | addulepiznz@zanlink.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 06.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr. Rufaro CHATORA | WHO Country Representative |  |  |
| Dr. Dorothy ROZGA | UNICEF Country Representative |  |  |
| Christopher ARMSTRONG | CIDA Health Lead |  |  |
| Dr. Emmanuel MALANGILA | SHS World Bank |  |  |
| Ms. Jane LWEIKIZA | Tanzania Red Cross Society |  |  |
| Dr. Raz.STEVENSON | MCH Focal USAID |  |  |
| Dr. Deo MTASIWA | Chief Medical Officer MOHSW |  |  |
| Dr. Donan MMBANDO | Director of Preventive Services - MOHSW |  |  |
| Dr. Kandy MUZE | Paediatric Association of Tanzania |  |  |
| Mr. Michael MWALUKASA | Prime Minister Office Regional Administrative and Local Government (PMORALG) |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr Dafrossa C LYIMO | Title | EPI Programme Manager |
| --- | --- | --- | --- |
| Tel no | +255715565568 |  |  |
| Fax no | +255222450089 | Address | Ministry of Health and Social Welfare EPI programme Box 9083 Dar es salaam Tanzania |
| Email | dafrossac@gmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-agency Coordinating Committee |
| --- | --- |
| Year of constitution of the current committee | 2000 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand- alone committee |
| Frequency of meetings | 4 times per year |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair | Permanent Secretary, Ministry of Health and Social Welfare | Ms. Blandina NYONI |
| Secretary | EPI Programme Manager, Ministry of Health and Social Welfare | Dr. Dafrossa LYIMO |
| Members | WHO Country Representative | Dr.Rufaro ChATORA | Action |
|  | UNICEF Country Representative | Dr. Dorothy ROZGA |  |
|  | CIDA Health Lead | Christopher ARMSTRONG |  |
|  | SHS World Bank | Dr. Emmanuel MALANGALILA |  |
|  | Tanzania Red Cross Society | Ms. Jane LWEIKIZA |  |
|  | MCH Focal USAID | Dr.Raz STEVENSON |  |
|  | Chief Medical Officer MOHSW | Dr. Deo MTASIWA |  |
|  | Director of Preventive Services - MOHSW | Dr. Donan MMBANDO |  |
|  | Paediatric Association of Tanzania | Dr. Kandy MUZE |  |
|  | Prime Minister Office Regional Administrative and Local Government (PMORALG) | Mr. Michael MWALUKASA |  |

Major functions and responsibilities of the committee

• Foster solid partnerships by coordinating all inputs and resources available from inside and outside the country in order to maximize resources for the good of the child. The ICC partnership provided itself a positive force in supporting Routine Immunization and Supplemental Immunization Activities (SIAs). • Review and endorse work plans; Country Multi Year Plans (cMYPs), EPI annual plans, Supplemental Immunization Activities (SIAs) plans of action, Surveillance plans. • Mobilization of resources. • Enhance transparency and accountability by reviewing use of funds and other resources. • Encourage information-sharing and feedback as possible to all levels in the country and interested partners. • Address issues are geared to strengthen immunization services, the introduction of new vaccines and preventive responses of outbreaks

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Regular quarterly meetings |
| --- | --- |
| 2. | Incorporation of all decision makers in the MoHSW and health stakeholders including development partners |
| 3. | The use of technical working groups to review and recommend specific issues of different specialities and submitted to the technical committee of sector wide approach |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |
| --- | --- | --- |
| Chair |  |  |
| Secretary |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 5

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure | Year | Source |
| --- | --- | --- | --- |
| Total population | 43,219,497 |  | 2010 | Tanzania National Bureau of statistics |
| Infant mortality rate (per 1000) | 51 |  | 2010 | Tanzania Demographic Health survey (TDHS) 2010 report |
| Surviving Infants[1] | 1,639,847 |  | 2010 | EPI log forecasting tool |
| GNI per capita (US$) |  |  |  |  |
| Total Health Expenditure (THE) as a percentage of GDP | 5.30 | % |  |  |
| General government expenditure on health (GGHE) as % of General government expenditure | 6.30 | % |  |  |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

Ministries of Health and Social Welfare develop annual plans and all Councils develop the Council Comprehensive Health Plans (CCHP) which includes EPI activities. All these contribute to the National budget which is endorsed by the national parliament. Ministries of Health and Social Welfare annual planning and budgeting (Medium Term Expenditure Framework (2009/10 - 2011/12), and Council Comprehensive Health Plan (2011/12) are guided by 3rd Health Sector Strategic Plan (HSSP3)2009-2015 and Primary Health Services Development Program (2007-2017). The HSSP3 provides an overview of the priority strategic directions across the health sectors which are guided by the National Health Policy, Vision 2025, National Strategy for Growth and Poverty Reduction in Tanzania Mainland (MKUKUTA) and MKUZA in Zanzibar and MDGs.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The cMYP is aligned with these documents by timing and content. Timing HSSP III 2009 to 2015 and cMYP 2010 to 2015 Content: In the HSSP III strategy 1: District Health Services and strategy 7: Maternal Newborn and Child health address the introduction of new vaccines and improvement of coverage. The introduction of new vaccines activities are reflected in the cMYP

Please indicate the national planning budgeting cycle for health

One year planning cycle from 1st July to 30th June

Please indicate the national planning cycle for immunisation

One year planning cycle from 1st January to 31st December

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

To date, it is not done in the immunization routine reporting system. However in the Health Management Information System there is plan to include gender dis aggregation. The surveillance tools segregate data by gender and the reported measles and diarrhoea cases due to rota shows no significant different between males and female. This means that both male and female children are equally reached. Boys and girls are treated the same in the health services.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

Provision of immunization services is equally done to both female and male children. Currently there is no evidence of mortality and morbidity of vaccine preventable diseases affecting one gender than the other.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes |  |  |
| Polio | Tanzania Mainland: OPV 0 at birth; OPV1 at 4wks; OPV2 at 8wks; OPV3 at 12wks | Yes | By January 2012 schedule will change to OPV 0 is at birth;OPV1 at 6wks; OPV2 at 10wks; OPV3 at 14wks |  |
| Polio | Zanzibar: Penta1 at 6wks; Penta2 at 10wks; Penta3 at 14wks | Yes |  |  |
| Penta | Tanzania Mainland: Penta1 at 4wks; Penta2 at 8wks; Penta3 at 12wks | Yes | By January 2012 schedule will change to Penta 1 at 6wks;Penta 2 at 10wks; and penta 3 at 14wks |  |
| Penta | Zanzibar: Penta1 at 6wks; Penta2 at 10wks; Penta3 at 14wks |  |  |  |
| Measles | 9 months |  |  |  |
| TT | First contact; one month; six month; one year; one year |  |  |  |
| Vitamin A | 9mths; 15mths and 21mths | Yes |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2009 | 2010 | 2008 | 2010 |  | 2009 | 2010 |
| BCG | 93 | 99 | 98 | 95 | Tuberculosis |  |  |
| DTP | DTP1 |  | 98 |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 85 | 91 | 95 | 88 | Pertussis | 0 | 0 |
| Polio 3 | 88 | 94 |  |  | Polio | 0 | 0 |
| Measles (first dose) | 91 | 92 | 85 | 85 | Measles | 1,574 | 167 |
| TT2+ (Pregnant women) | 74 | 73 |  |  | NN Tetanus | 6 | 5 |
| Hib3 |  |  |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 |  |  |  |  | HepBsero-prevalence[1] |  | 0 |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Post campaign coverage survey (2008), Tanzania Demographic Health survey (TDHS) preliminary Report September 2010

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |
| --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 1,822,119 | 1,919,383 | 1,974,937 | 2,031,933 | 2,090,575 |  |  |
| Total infants' deaths | 92,446 | 97,889 | 96,883 | 97,703 | 100,522 |  |  |
| Total surviving infants | 1,729,673 | 1,821,494 | 1,878,054 | 1,934,230 | 1,990,053 |  |  |
| Total pregnant women | 1,822,119 | 1,919,383 | 1,974,937 | 2,031,933 | 2,090,575 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 1,798,279 | 1,882,075 | 1,936,548 | 1,992,430 | 2,049,927 |  |  |
| BCG coverage (%)[1] | 99% | 98% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 1,576,656 | 1,730,420 | 1,784,152 | 1,837,518 | 1,890,550 |  |  |
| OPV3 coverage (%)[2] | 91% | 95% | 95% | 95% | 95% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 1,637,458 | 1,783,527 | 1,838,914 | 1,893,928 | 1,948,596 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 1,523,657 | 1,712,204 | 1,784,151 | 1,837,519 | 1,890,550 |  |  |
| DTP3 coverage (%)[2] | 88% | 94% | 95% | 95% | 95% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 10% | 10% | 10% | 10% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.11 | 1.11 | 1.11 | 1.11 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 1,105,709 | 1,782,573 | 1,838,058 | 1,891,103 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 1,014,635 | 1,745,011 | 1,799,912 | 1,851,853 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 56% | 93% | 93% | 93% |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  |  | 1,143,676 | 1,838,058 | 1,891,103 |  |  |
| Target population vaccinated with last dose of Rotavirus |  |  | 1,051,351 | 1,799,912 | 1,851,853 |  |  |
| Rotavirus coverage (%)[2] | 0% | 0% | 56% | 93% | 93% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 1,545,536 | 1,677,312 | 1,729,389 | 1,781,108 | 1,832,504 |  |  |
| Measles coverage (%)[2] | 89% | 92% | 92% | 92% | 92% |  |  |
| Pregnant women vaccinated with TT+ | 1,335,412 | 1,471,444 | 1,574,404 | 1,622,707 | 1,669,552 |  |  |
| TT+ coverage (%)[4] | 73% | 77% | 80% | 80% | 80% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 7% | 4% | 3% | 3% | 3% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Vaccines (routine vaccines only) | 17,223,603 | 50,418,714 | 101,504,940 | 122,957,490 | 137,166,883 |  |  |  |  |
| Traditional vaccines | 2,236,970 | 2,824,077 | 4,000,205 | 4,326,168 | 4,793,570 |  |  |  |  |
| New and underused vaccines | 14,986,633 | 47,594,637 | 97,504,735 | 118,631,322 | 132,373,313 |  |  |  |  |
| Injection supplies | 844,169 | 1,443,075 | 2,031,301 | 2,264,113 | 2,524,260 |  |  |  |  |
| Personnel | 17,499,072 | 18,396,714 | 18,772,290 | 19,167,220 | 19,560,501 |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 2,065,380 | 2,191,519 | 2,235,350 | 2,280,057 | 2,325,658 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 15,433,692 | 16,205,195 | 16,536,940 | 16,887,163 | 17,234,843 |  |  |  |  |
| Transportation | 2,175,330 | 3,070,400 | 3,825,511 | 4,587,387 | 2,882,540 |  |  |  |  |
| Maintenance and overheads | 22,746,791 | 23,689,319 | 24,196,111 | 24,721,677 | 25,244,077 |  |  |  |  |
| Training | 697,040 | 770,250 | 807,844 | 850,650 | 895,753 |  |  |  |  |
| Social mobilisation and IEC | 860,894 | 965,286 | 1,013,407 | 1,063,513 | 1,116,644 |  |  |  |  |
| Disease surveillance | 1,372,770 | 1,931,617 | 2,027,881 | 2,127,570 | 2,232,952 |  |  |  |  |
| Program management | 1,560,129 | 1,739,206 | 1,824,900 | 1,914,712 | 2,009,891 |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 64,979,798 | 102,424,581 | 156,004,185 | 179,654,332 | 193,633,501 |  |  |  |  |
| Routine Capital Costs |
| Vehicle | 1,980,260 | 2,838,898 | 3,601,167 | 4,390,843 | 2,869,064 |  |  |  |  |
| Cold chain equipment | 8,497 | 123,472 | 380,125 | 333,923 | 63,416 |  |  |  |  |
| Other capital equipment | 61,100 | 62,322 | 62,322 | 62,322 | 62,322 |  |  |  |  |
| Subtotal Capital Costs | 2,049,857 | 3,024,692 | 4,043,614 | 4,787,088 | 2,994,802 |  |  |  |  |
| Campaigns |
| Polio |  |  |  | 2,476,776 |  |  |  |  |  |
| Measles |  |  |  | 11,857,555 |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |
| MNT campaigns | 120,407 |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 120,407 | 0 | 0 | 14,334,331 | 0 |  |  |  |  |
| GRAND TOTAL | 67,150,062 | 105,449,273 | 160,047,799 | 198,775,751 | 196,628,303 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Vaccines | Government | 3,182,440 | 4,919,344 | 7,414,097 | 8,117,336 | 8,581,846 |  |  |  |  |  |
|  | GAVI | 14,041,162 | 25,957,585 | 61,595,159 | 78,242,579 | 84,818,680 |  |  |  |  |  |
|  | MERCK |  | 19,541,785 | 32,495,683 |  |  |  |  |  |  |  |
| Injection supplies | Government | 429,054 | 926,456 | 691,795 | 779,197 | 877,879 |  |  |  |  |  |
|  | GAVI | 415,115 | 433,252 | 1,189,944 | 1,310,810 | 1,438,361 |  |  |  |  |  |
|  | MERCK |  | 83,367 | 149,562 |  |  |  |  |  |  |  |
| Personnel | Government | 5,284,632 | 2,379,194 | 2,566,099 | 1,890,141 | 381,545 |  |  |  |  |  |
|  | Sub-national | 12,136,320 | 15,772,734 | 15,984,189 | 17,032,873 | 18,898,930 |  |  |  |  |  |
|  | UNICEF | 18,160 | 35,084 | 138,608 | 62,340 | 170,376 |  |  |  |  |  |
|  | DANIDA | 59,960 | 127,033 | 83,394 | 100,000 | 62,586 |  |  |  |  |  |
| Transportation | Government | 9,936 | 16,080 | 20,795 | 21,211 | 12,189 |  |  |  |  |  |
|  | Sub-national | 2,157,445 | 3,041,455 | 3,788,079 | 4,549,206 | 2,860,600 |  |  |  |  |  |
|  | UNICEF | 7,949 | 12,864 | 16,636 | 16,969 |  |  |  |  |  |  |
|  | DANIDA |  |  |  |  | 9,751 |  |  |  |  |  |
| Maintenance and overhead | Government | 10,089 | 12,216 | 16,012 | 21,128 | 27,065 |  |  |  |  |  |
|  | Sub-national | 22,736,701 | 23,677,103 | 24,180,099 | 24,700,550 | 25,217,012 |  |  |  |  |  |
| Short-term training | Government | 10,000 | 10,000 | 12,985 |  | 10,000 |  |  |  |  |  |
|  | WHO | 300,000 | 748,308 | 784,859 | 826,643 | 870,678 |  |  |  |  |  |
|  | UNICEF | 387,040 | 11,942 | 10,000 | 24,007 | 15,075 |  |  |  |  |  |
| IEC/social mobilization | Government |  | 10,000 |  |  |  |  |  |  |  |  |
|  | UNICEF | 860,894 | 955,285 | 1,013,407 | 1,063,513 | 1,116,644 |  |  |  |  |  |
| Disease surveillance | WHO | 1,372,770 | 1,931,617 | 2,027,880 | 2,127,570 | 2,232,952 |  |  |  |  |  |
| Programme management | Government | 1,560,129 | 1,739,205 | 1,824,900 | 1,914,712 | 2,009,891 |  |  |  |  |  |
| Routine Capital Costs |  |
| Vehicles | WHO | 1,919,060 |  |  |  |  |  |  |  |  |  |
|  | GAVI |  | 96,965 | 132,863 |  |  |  |  |  |  |  |
|  | ADB |  |  |  | 135,521 | 79,494 |  |  |  |  |  |
| Cold chain equipment | Government |  | 123,472 | 370,415 | 321,206 | 61,736 |  |  |  |  |  |
|  | UNICEF | 8,497 |  |  | 12,718 | 1,681 |  |  |  |  |  |
|  | ADB |  |  | 9,710 |  |  |  |  |  |  |  |
| Other capital expenditure | Government |  | 8,160 | 54,162 | 62,322 | 54,162 |  |  |  |  |  |
|  | WHO |  | 54,162 | 8,160 |  |  |  |  |  |  |  |
|  | UNICEF |  |  |  |  |  |  |  |  |  |  |
|  | ADB |  |  |  |  | 8,160 |  |  |  |  |  |
| Campaigns |  |
| Polio | Government | 15,000 |  |  | 954,572 |  |  |  |  |  |  |
|  | Sub-national | 53,100 |  |  |  |  |  |  |  |  |  |
|  | WHO |  |  |  | 575,000 |  |  |  |  |  |  |
|  | UNICEF | 105,407 |  |  | 947,204 |  |  |  |  |  |  |
| Measles | Government |  |  |  | 3,941,450 |  |  |  |  |  |  |
|  | Sub-national |  |  |  | 1,959,181 |  |  |  |  |  |  |
|  | WHO |  |  |  | 2,085,000 |  |  |  |  |  |  |
|  | UNICEF |  |  |  | 1,959,181 |  |  |  |  |  |  |
|  | Measles Partners |  |  |  | 3,871,924 |  |  |  |  |  |  |
| GRAND TOTAL | 67,080,860 | 102,624,668 | 156,579,492 | 159,626,064 | 149,817,293 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Central vaccine store (CVS) is located at Medical Store Department in Dar es Salaam and caters for Tanzania Mainland and Zanzibar. CVS currently has sufficient positive storage level for the traditional vaccine storage, including pentavalent (which has been converted from single dose vials to 10 dose vials as of March 2011). Two (2) additional Walk in Cold Rooms (WICR) with capacity of 40m3 each have been installed, making available positive storage capacity at MSD to 40,000 litres as of April 2011 even after introduction of pneumococcal vaccine in 2012 the positive storage capacity will be sufficient based on 4 shipments. The procurement process for additional six (6) WICR with capacity of 40m3 each has commenced and are expected to be installed by the end of December 2011. This will increase the positive cold storage capacity to 97,144 litres which is adequate to accommodate also Rotavirus vaccine (Rotarix). Plans are being developed to procure additional cold rooms at national level to accommodate anticipated other new vaccine introduction (such as 2nd doses of measles) through UNDAP and GAVI HSS funds by mid-2012 and to reduce the number of shipments. There are 26 Regional vaccine stores (RVS) in Tanzania mainland. To ensure that each region has enough storage capacity by March 2012, one WICR will be installed with standby water cooled generator of a capacity of 40 kVA in each region: 7 regions will be installed with 40m3 and 19 regions will be installed 30m3. The current Ice Lined Refrigerators which are in the RVS will be transferred to the councils to increase their storage capacities. Regional vaccine stores will have a storage capacity for up to three months stock with 25% buffer stock. Zanzibar has enough positive storage capacity for traditional vaccines. Procurement of two new WICR with capacity of 10m3 each has commenced and will be installed by the end of 2011 at Unguja and Pemba to accommodate the incoming new vaccine. In Mainland and Zanzibar, there are 161 councils of which 143 (88.8%) have council vaccine stores. The remaining 18 council’s vaccine stores are yet to be established because they are new established. Storage capacity at this level can last for three months. Additional positive storage capacity at this level will be increased through the UNDAP and GAVI HSS funds. All districts in Zanzibar have enough storage capacity.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

In both cMYP there are sections titled New Vaccine Introduction (Section 4 table 9 and 10 Tanzania mainland and Zanzibar section 5,6 table 8 and 9), and clear explain which type of vaccines will be introduced, burden of the disease and in the section of pririorities, objective and milestone introduction of new vaccines are well captured. Also in the Intrduction plans more details are given

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 109,837 | 199,337 | 234,518 | 263,940 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 40,000 | 40,000 | 40,000 | 40,000 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 3 | 5 | 6 | 7 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -12,541 | 9,834 | 18,630 | 25,985 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 185,207 | 432,151 | 246,943 | 123,472 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The major provider of secured funding is the governement which contributes about 80% of the total costs of antigens and operational costs. The increasing propotion of health expenditures from total government expenditure from 9% in 2006/09 to 14% in 2009/10 is an indication of government commitment to continue allocating more resources to the health sector that may increase the possibility of more allocation to the costing of implementing immunization activities. The stability of economic growth at the level of 6.2% over a period of the past three years is also a condition to rely upon. The current initiatives that has began by involving MoHSW planning and budget section will be consilidated by meeting with them on annual basis during the preparation of the budget. Furthermore, the present efforts by the MoHSW to improve both technical and allocative efficiency creates another possibility for increase resources

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hib/spn | WHO Burden of disease assessment | 2008 | 215,072 cases, Incidence rate 3,688/100,000, Deaths 14,356. |  |
| Rotavirus |  | 2010 | Sentinel sites data: 1,014 stool specimens 38% positive for rotavirus infection |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |
| --- | --- |
| Storage capacity for single dose vial of Pentavalent vaccine was inadequate however it minimizes wastage | 1.Increased frequency of shipment from 4 to 12 2.Fast chain of distributing vaccines to lower levels 3.Increased distribution frequency 4.Increased vaccine packaging transportation |  |
| Training of health workers should be conducted early to allow smooth preparations and avoid rushing. | Early planning and disbursement of funds for training |  |
| A post introduction evaluation revealed that the cold chain assessment done prior to introduction of DPT -HepB in 2002 was the best practice. | A Vaccine Management Assessment was conducted in 2007 and cold chain capacity was also evaluated. Introduction of SMT/CCTI was done. However assessment at the health facility need to be done to benefit the introduction of new vaccines and is planned in December 2009 |  |
| Adoption of Multi Dose Vial Policy at introduction of DPT-HepB helped to reduce wastage | Training on use of the two dose vials will help to ensure safety and reduce wastage |  |
| The support of introduction of new vaccines at USD 0.30 per birth cohort is not enough however is better than a 100,000 USDs | Mobilize additional funds from Government and partners |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Pneumococcal (PCV13), 1 doses/vial, Liquid Rotavirus 2-dose schedule vaccine

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,105,709 | 1,782,573 | 1,838,058 | 1,891,103 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,014,635 | 1,745,011 | 1,799,912 | 1,851,853 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 55.70% | 92.92% | 93.06% | 93.06% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 232,500 | 328,400 | 311,600 | 320,400 |  |  |  |  |
| Number of AD syringes | # | 248,300 | 348,600 | 329,500 | 338,800 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,775 | 3,875 | 3,675 | 3,775 |  |  |  |  |
| Total value to be co-financed by country | $ | 871,000 | 1,230,000 | 1,167,000 | 1,200,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 4,121,300 | 5,819,900 | 5,522,100 | 5,678,400 |  |  |  |  |
| Number of AD syringes | # | 4,400,400 | 6,179,100 | 5,839,800 | 6,005,000 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 48,850 | 68,600 | 64,825 | 66,675 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 15,437,000 | 21,796,500 | 20,680,000 | 21,265,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 1,919,383 | 0.30 | 576,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 475,025 | 314,050 |
| Social Mobilization, IEC and Advocacy | 1,052,058 | 147,750 |
| Cold Chain Equipment & Maintenance |  |  |
| Vehicles and Transportation | 467,497 | 57,100 |
| Programme Management |  |  |
| Surveillance and Monitoring | 83,104 | 57,100 |
| Human Resources |  |  |
| Waste Management |  |  |
| Technical assistance |  |  |
| Revision of recording and reporting materials | 70214 |  |  |
| Totals | 2,147,898 | 576,000 |

# 6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,143,676 | 1,838,058 | 1,891,103 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,051,351 | 1,799,912 | 1,851,853 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 55.98% | 93.06% | 93.06% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 114,200 | 200,800 | 211,200 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,275 | 2,250 | 2,350 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 600,500 | 845,000 | 800,000 |  |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 2,888,000 | 4,023,700 | 3,788,100 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 32,075 | 44,675 | 42,050 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 15,184,500 | 16,931,000 | 14,348,500 |  |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 1,974,937 | 0.30 | 592,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 475,025 | 314,050 |
| Social Mobilization, IEC and Advocacy | 526,029 | 164,250 |
| Cold Chain Equipment & Maintenance |  |  |
| Vehicles and Transportation | 467,497 | 57,100 |
| Programme Management |  |  |
| Surveillance and Monitoring | 83,104 | 57,100 |
| Human Resources |  |  |
| Waste Management |  |  |
| Technical assistance |  |  |
| Totals | 1,551,655 | 592,500 |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

1.The support of procurement of new and under-used vaccine will be channeled direct to UNICEF to procure vaccines and injection supplies on behalf of the country. 2. The funds financed by the government will be also sent to UNICEF for this purpose.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

All vaccine, injection materials and cold chain equipment are procured through UNICEF 2. Tanzania Food and Drug Authority ( TFDA) a National Regulatory Authority, Licensed and inspect vaccines to be used in the country to ensure quality.

- Please describe the introduction of the vaccines (refer to cMYP)

Pneumococcal is planned to be introduced in June 2012 and Rota vaccine in January 2013. This is in line with the cMYP for 2010-2015. The introduction of pneumococcal and rota has been discussed with stakeholders at different fora and decision was taken by Government to introduce both vaccines. In the case of pneumococcal vaccine, the SWAp technical committee endorsed the decision of Government on 16 April 2008, and The ICC meeting endorsed the application for introduction of Pnemococcal and rota vaccine on 6th May 2011. The new vaccine introduction plans, which are part of these documents submitted specifically, addresses the pneumococcal and rota introduction into the immunization programme. Both outlines key activities to be conducted in preparation for introduction of the vaccines and includes timeline for the different activities and budget for all non vaccines costs to the activities. Consistent with the guidelines on new vaccines introduction, the plans addresses the following key areas 1. Summary of the cMYP referring to the introduction of new and underused vaccines 2. Summary of cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion plan has been financed and implemented. 3. How financial sustainability and co-financing will be achieved 4. The Hib/spn disease burden and rotavirus disease burden 5. Lesson learned from the introduction of pentavalent in the country 6. List of the vaccines to be introduced with support from GAVI and presentation 7. Data of Pneumococcal and rota vaccines on the specification of vaccinations with new vaccines, portion of supply to be procured by the country and portion of supply to be procured by GAVI. 8. Concise information on other key activities; revision of recording and reporting tools, training of health workers, advocacy and social mobilization, monitoring and supervision and post introduction evaluation. The plan concludes with a timeline of activities related to pneumococcal and rota vaccine introduction

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

New vaccine introduction grant will be transferred to WHO account as for the current account used for the funds for GAVI ISS

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The co-financing will be paid by government using Medium Term Expenditure Framework (MTEF) funds on a yearly basis. The program will integrate co-financing budget in the vaccine budget.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The coverage of the new vaccine will be monitored through the routine EPI reporting system. Section 2.4.4cMYP Immunization data are generated at the health facility level. Health facilities are encouraged to use data especially monitoring immunization coverage and diseases. Timely transfer of data to district and then regions is encouraged to allow timely correction of weakness. National level receives data from region monthly and during annual evaluation meeting. Data compilation analysis and utilization is done at each level. To improve quality of data DQS are conducted especially during supervisory visit as highlighted in the section 2.4.1 "Tanzania adopted DQS tool in 2006 thereafter countrywide training was conducted to health providers from regional level to health facility level. The plan is to integrate DQS activities into routine supervision activity. To validate reported immunization coverage periodic coverage survey and EPI review are conducted refer cMYP section 2.4.5 and 2.4.3

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? December  - 2009

If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

1.VMA report was shared with all stakeholders 2.Vaccine management guidelines were developed, printed, disseminated and distributes to all levels. 3.Situation analysis of cold chain storage capacity was done 4.Expansion of cold storage capacity at National level and reginal and distric levels on going. 5.Stock management tool(SMT)introduced to some districts. Extending to other districts in the plan 6.Fridge Tags for temeperature monitoring introduced to all levels,and fridge tag users guideline writen in KISWAHILI (National language) were developed and distributed to all intermediate levels

When is the next Effective Vaccine Management (EVM) Assessment planned? November  - 2012

Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 232,500 | 328,400 | 311,600 | 320,400 |  |  |  |  |
| Number of AD syringes | # | 248,300 | 348,600 | 329,500 | 338,800 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,775 | 3,875 | 3,675 | 3,775 |  |  |  |  |
| Total value to be co-financed by the country | $ | 871,000 | 1,230,000 | 1,167,000 | 1,200,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 4,121,300 | 5,819,900 | 5,522,100 | 5,678,400 |  |  |  |  |
| Number of AD syringes | # | 4,400,400 | 6,179,100 | 5,839,800 | 6,005,000 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 48,850 | 68,600 | 64,825 | 66,675 |  |  |  |  |
| Total value to be co-financed by the country | $ | 15,437,000 | 21,796,500 | 20,680,000 | 21,265,500 |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 1,821,494 | 1,878,054 | 1,934,230 | 1,990,053 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 1,014,635 | 1,745,011 | 1,799,912 | 1,851,853 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 55.70% | 92.92% | 93.06% | 93.06% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 1,105,709 | 1,782,573 | 1,838,058 | 1,891,103 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,105,709 | 59,041 | 1,046,668 | 1,782,573 | 95,193 | 1,687,380 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 3,317,127 | 177,122 | 3,140,005 | 5,347,719 | 285,578 | 5,062,141 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 3,482,984 | 185,978 | 3,297,006 | 5,615,105 | 299,857 | 5,315,248 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 870,746 | 46,495 | 824,251 | 533,031 | 28,465 | 504,566 |
| I | Total vaccine doses needed | F + G | 4,353,730 | 232,473 | 4,121,257 | 6,148,136 | 328,322 | 5,819,814 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 4,648,540 | 248,214 | 4,400,326 | 6,527,633 | 348,588 | 6,179,045 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 51,599 | 2,756 | 48,843 | 72,457 | 3,870 | 68,587 |
| N | Cost of vaccines needed | I * vaccine price per dose | 15,238,055 | 813,653 | 14,424,402 | 21,518,476 | 1,149,126 | 20,369,350 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 246,373 | 13,156 | 233,217 | 345,965 | 18,476 | 327,489 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 33,024 | 1,764 | 31,260 | 46,373 | 2,477 | 43,896 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 761,903 | 40,683 | 721,220 | 1,075,924 | 57,457 | 1,018,467 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 27,940 | 1,492 | 26,448 | 39,234 | 2,096 | 37,138 |
| T | Total fund needed | (N + O + P + Q + R + S) | 16,307,295 | 870,746 | 15,436,549 | 23,025,972 | 1,229,628 | 21,796,344 |
| U | Total country co-financing | I * country co-financing per dose | 870,746 |  |  | 1,229,628 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 | 2015 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,838,058 | 98,163 | 1,739,895 | 1,891,103 | 100,996 | 1,790,107 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 5,514,174 | 294,489 | 5,219,685 | 5,673,309 | 302,988 | 5,370,321 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 5,789,883 | 309,213 | 5,480,670 | 5,956,975 | 318,137 | 5,638,838 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 43,695 | 2,334 | 41,361 | 41,773 | 2,231 | 39,542 |
| I | Total vaccine doses needed | F + G | 5,833,578 | 311,547 | 5,522,031 | 5,998,748 | 320,368 | 5,678,380 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 6,169,235 | 329,473 | 5,839,762 | 6,343,742 | 338,793 | 6,004,949 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 68,479 | 3,658 | 64,821 | 70,416 | 3,761 | 66,655 |
| N | Cost of vaccines needed | I * vaccine price per dose | 20,417,523 | 1,090,413 | 19,327,110 | 20,995,618 | 1,121,287 | 19,874,331 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 326,970 | 17,463 | 309,507 | 336,219 | 17,957 | 318,262 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 43,827 | 2,341 | 41,486 | 45,067 | 2,407 | 42,660 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 1,020,877 | 54,521 | 966,356 | 1,049,781 | 56,065 | 993,716 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 37,080 | 1,981 | 35,099 | 38,129 | 2,037 | 36,092 |
| T | Total fund needed | (N + O + P + Q + R + S) | 21,846,277 | 1,166,716 | 20,679,561 | 22,464,814 | 1,199,750 | 21,265,064 |
| U | Total country co-financing | I * country co-financing per dose | 1,166,716 |  |  | 1,199,750 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Rotavirus 2-dose schedule

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 114,200 | 200,800 | 211,200 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 1,275 | 2,250 | 2,350 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 600,500 | 845,000 | 800,000 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 2,888,000 | 4,023,700 | 3,788,100 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 32,075 | 44,675 | 42,050 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 15,184,500 | 16,931,000 | 14,348,500 |  |  |  |  |

Table 1.2  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 1,878,054 | 1,934,230 | 1,990,053 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 1,051,351 | 1,799,912 | 1,851,853 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # |  | 55.98% | 93.06% | 93.06% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 1,143,676 | 1,838,058 | 1,891,103 |  |  |  |  |
| Number of doses per child |  | # |  | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # |  | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # |  | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 | 2014 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.80% |  |  | 4.75% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,143,676 | 43,504 | 1,100,172 | 1,838,058 | 87,365 | 1,750,693 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 2,287,352 | 87,008 | 2,200,344 | 3,676,116 | 174,729 | 3,501,387 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 2,401,720 | 91,359 | 2,310,361 | 3,859,922 | 183,465 | 3,676,457 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 600,430 | 22,840 | 577,590 | 364,551 | 17,328 | 347,223 |
| I | Total vaccine doses needed | F + G | 3,002,150 | 114,198 | 2,887,952 | 4,224,473 | 200,792 | 4,023,681 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 33,324 | 1,268 | 32,056 | 46,892 | 2,229 | 44,663 |
| N | Cost of vaccines needed | I * vaccine price per dose | 15,010,750 | 570,989 | 14,439,761 | 16,897,892 | 803,168 | 16,094,724 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 21,328 | 812 | 20,516 | 30,011 | 1,427 | 28,584 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 750,538 | 28,550 | 721,988 | 844,895 | 40,159 | 804,736 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 2,133 | 82 | 2,051 | 3,002 | 143 | 2,859 |
| T | Total fund needed | (N + O + P + Q + R + S) | 15,784,749 | 600,430 | 15,184,319 | 17,775,800 | 844,895 | 16,930,905 |
| U | Total country co-financing | I * country co-financing per dose | 600,430 |  |  | 844,895 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.80% |  |  | 4.75% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.28% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 1,891,103 | 99,853 | 1,791,250 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 3,782,206 | 199,705 | 3,582,501 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 3,971,317 | 209,690 | 3,761,627 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 27,849 | 1,471 | 26,378 |  |  |  |
| I | Total vaccine doses needed | F + G | 3,999,166 | 211,160 | 3,788,006 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 44,391 | 2,344 | 42,047 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 14,396,998 | 760,176 | 13,636,822 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 28,411 | 1,501 | 26,910 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 719,850 | 38,009 | 681,841 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 2,842 | 151 | 2,691 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 15,148,101 | 799,834 | 14,348,267 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 799,834 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.28% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ | 250’000 $ | 2’000’000 $ |
| --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |
| Rotavirus 2-dose schedule |  | 0.20 | 0.20 | 0.20 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5, 6 | Yes |
| cMYP Costing tool for financial analysis |  | 7, 8 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 9, 10, 17, 18 | Yes |
| Improvement plan based on EVM |  | 16 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 13 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  | 14, 15 |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 11, 12 |  |
| Banking details |  | 19 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name | New file | Actions |
| --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: Application Minister of Health Signature.pdf Date/Time: 13.05.2011 08:15:51 Size: 314 KB |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: Application Minister of Finance Signature.pdf Date/Time: 13.05.2011 08:31:06 Size: 314 KB |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: ICC Members Signatories on Application of New Vaccines.pdf Date/Time: 13.05.2011 08:32:53 Size: 525 KB |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: 57th ICC endorsed Application of new vaccines.pdf Date/Time: 13.05.2011 08:34:59 Size: 2 MB |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: Tanzania Mainland cMYP 2010-2015.doc Date/Time: 10.05.2011 09:50:21 Size: 1 MB |  |  |
| 6 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: Zanzibar cMYP 2010-2015.doc Date/Time: 10.05.2011 09:55:54 Size: 1 MB |  |  |
| 7 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: Tanzania Mainland cMYP Costing Tool 2010-2015.xls Date/Time: 10.05.2011 09:59:02 Size: 3 MB |  |  |
| 8 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: Zanzibar cMYP Costing Tool 2010-2015.xls Date/Time: 10.05.2011 10:02:32 Size: 3 MB |  |  |
| 9 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: 55th ICC Meeting Minutes.pdf Date/Time: 13.05.2011 08:55:32 Size: 1 MB |  |  |
| 10 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: 56th ICC Meeting Minutes.pdf Date/Time: 13.05.2011 09:00:01 Size: 1 MB |  |  |
| 11 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Introduction plan for pneumococcal 2012.doc Date/Time: 10.05.2011 10:07:05 Size: 287 KB |  |  |
| 12 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Introduction plan for rotavirus 2013.doc Date/Time: 10.05.2011 10:07:45 Size: 275 KB |  |  |
| 13 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: | File name: JRF 2010 TANZANIA Final -120411.xls Date/Time: 10.05.2011 10:09:40 Size: 452 KB |  |  |
| 14 | File Type: National policy on injection safety File Desc: Infection Prevention Control Guide Tanzania | File name: C:\Documents and Settings\user\Desktop\injection prevention guide\Infection Prevention Control Guideline - Tanzania -.pdf Date/Time: 14.05.2011 08:24:29 Size: 843 KB |  |  |
| 15 | File Type: National policy on injection safety File Desc: Infection prevention Control Pocket Guide ,Tanzania | File name: C:\Documents and Settings\user\Desktop\Application DOCuments attached\Infection Prevention Control Pocket guide TZ 2011.pdf Date/Time: 14.05.2011 08:30:52 Size: 3 MB |  |  |
| 16 | File Type: Improvement plan based on EVM * File Desc: Tanzania EPI annual Plan including VMA implementation plan | File name: E:\Tanzania , EPI ANNUAL PLAN 2011.doc Date/Time: 25.05.2011 09:42:37 Size: 658 KB |  |  |
| 17 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Meeting of 54th ICC meeting | File name: 2010,+54th+ICC+Meeting.doc Date/Time: 16.06.2011 07:18:12 Size: 64 KB |  |  |
| 18 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: Signatures for 54th ICC meeting | File name: 54th+ICC+Meeting+signatures.pdf Date/Time: 16.06.2011 07:19:36 Size: 131 KB |  |  |
| 19 | File Type: Banking details File Desc: Banking details - via WHO (e-mail confirmation) | File name: Tanzania Banking details.htm Date/Time: 17.06.2011 04:08:21 Size: 29 KB |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of United Republic of Tanzania hereby requests that a payment be made via electronic bank transfer as detailed below: |  |
| --- | --- |
| Name of Institution (Account Holder): |  |  |
| Address: |  |  |
| City Country: |  |  |
| Telephone no.: |  | Fax no.: |  |  |
| Currency of the bank account: |  |  |
| For credit to: |  |
| Bank account's title: |  |  |
| Bank account no.: |  |  |
| Bank's name: |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |
| --- |
| 1 |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: