Revision 5

February 2005

The Government of

Republic of Angola

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI) and The Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# Synopsis of the proposal including the specific requests for support from GAVI and The Vaccine Fund. The figures essential for the calculation of award amounts should be presented here, including: baseline data, current DTP3 coverage and targets for increased coverage, strategies for reaching all children, requested number of doses of vaccine(s) and their presentations (drawn from the tables in this form). Summarise also the nature of ICC participation in developing this proposal.

The Government of the Republic of Angola places great importance on the provision of sound health care services to its population. The Expanded Program on Immunization is one of the Ministry of Health priority programs.

With the implementation of the Reaching Every District (RED) approach in 59 out of 164 districts, the Angolan Expanded Program on Immunization has made great strides in improving immunization program performance.  National DPT3 coverage has increased by 13 percentage points in the last year from 46% in 2003 to 59 % in 2004.  Strategies used include training of personnel at all levels, the development of sound district micro plans, improved monitoring and supervision, and improved vaccine and cold chain management.

In order to build upon its successes the government of Angola would like to provide additional life saving vaccines through its routine vaccination program. The Republic of Angola is therefore requesting assistance from GAVI to introduce two new vaccines into the routine system, Hepatitis B and Haemophilus Influenzae type b.  The first preference is to introduce these combined with DPT as a pentavalent vaccine.  If the pentavalent vaccine is not available, the second choice is DPT + Hepatitis B combination vaccine.

The Republic of Angola has an area of 1.246.700 km2, its total population estimated for the year 2005 is 17,681,600 inhabitants including the following:

Births                                       :    884,080 (5% Estimated Birth Rate for 2005)

Infant Mortality Rate               :    150 ‰ live births (MICS-2001)

Survival infants                        :    751,468

Pregnant women                      :     884,080 (5% of total population)

Women of Child bearing age   :    3,713,136 (21% of total population)

Annual population growth        :    2.8%

| New vaccines requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Pentavalent (first choice) | 2 | January 2006 | 3,215,568 | 2,856,940 |
| Tetravalent (second choice) | 10 | January 2006 | 3,852,888 | 3,423,181 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

The ICC has been very involved in the all aspects of the program including the preparation of this Application and fully endorses its content.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of the Republic of Angola commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...

Title:	Vice Minister of Health.

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| Ministry of Health | Vice Minister |  |
| Ministry of Health | National Director of Public Health |  |
| WHO | WHO Representative |  |
| UNICEF | UNICEF Representative |  |
| Rotary | Chairperson Rotary/Polioplus |  |
| USAID | Health Officer |  |
| CORE Group | Country Director |  |
| RED Cross Society | Health Delegate |  |

In case the GAVI Secretariat have queries on this submission, please contact:

Dr. Fátima Valente, National Immunization Section Chief, Rua 1º Congresso nº67

Tel.No.:  244-2-391226

Fax No.: 244-2- 391226

E-mail: pav.ang@ebonet.net

Or:

Dr. Daniel Kertesz	Team leader, EPI/WHO

Tel. No.: 244-2 -392180

Fax No.: 244-2- 332314

E-mail: kerteszd@ao.afro.who.int

Or:

Dr. Guy Clarysse, Health and Nutrition Chief, UNICEF

Tel. No.: 244-2 331010

E-mail: gclarysse@unicef.org

In case the GAVI Secretariat have queries on this submission, please contact :

Name: ……………………………	Title/Address: ……………………………….

Tel.No.: ………………………….   		            ………………………………..

- Immunization-related fact sheet

| Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 17,681, 600 (Projected for 2005) | GNP per capita | 740$ US (2003 WB indicators) |
| Surviving Infants* | 751,468 | Infant mortality rate | 150/ 1000 (2001 multiple indicators survey) |
| Percentage of GDP allocated to Health | 16.9% (2001) | Percentage of Government expenditure for Health Care | 6% |

* Surviving infants = Infants surviving the first 12 months of life

| Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trends of immunization coverage (in percentage) |  |  |  |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| Vaccine |  |  | Reported |  | Survey |  |  |  | Disease | Number of reported cases |  |
|  |  |  | 2003 | 2004 * | 2003 | Age group | 2004 | Age group |  | 2003 | 2004 |
| BCG |  |  | 62% | 72% | NA | NA | NA | NA | Tuberculosis | 37,052 | 36,480 |
| DTP | DTP1 |  | 68% | 75% | NA | NA | NA | NA | Diphtheria | 16 | 0 |
|  | DTP3 |  | 46% | 59% | NA | NA | NA | NA | Pertussis | 2654 | 1,675 |
| OPV3 |  |  | 45% | 57% | NA | NA | NA | NA | Polio | 0 | 0 |
| Measles |  |  | 62% | 64% | NA | NA | NA | NA | Measles | 1196 | 29 |
| TT2+ (Pregnant women) |  |  | 72% | 72% | NA | NA | NA | NA | NN Tetanus | 117 | 100 |
| Hib3 |  |  | NA | NA | NA | NA | NA | NA | Hib | NA | NA |
| Yellow Fever |  |  | 52% | 60% | NA | NA | NA | NA | Yellow fever | 0 | 0 |
| HepB3 |  |  | NA | NA | NA | NA | NA | NA | HepB seroprevalence (if available) | NA | 9.2%** |
| Vit A supplementation (Routine) |  | Mothers ( < 6 weeks after delivery ) | NA | 21% | NA | NA | NA | NA |  |  |  |
|  |  | Infants under-1 ( > 6 months) | NA | 17% | NA | NA | NA | NA |  |  |  |

* Surviving infants = Infants surviving the first 12 months of life

** National HIV/ HepB sentinel Survey (pregnant women). Set 2004.

The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: DPT-3: 59% EPI- MoH National Information System. The only source of data. ………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

Summary of health system development status relevant to immunization:

Angola’s Ministry of Health is in process of transition from the emergency to the development. The main strategic lines of action are:

- The expansion of the health network (recovery of priority services, provision of essential drugs and improvement of human resources).

- To continue with the decentralization process from the central to the provincial and municipal level including planning and strategic decision-making.

- Strengthening the financing and administrative systems (preparation of regulations envisaged under the basic health law; preparation of a model for financing on budget management; improvement in coordination and the revitalization of the health information system).

- Building capacity for primary health care through strengthening of the programmes against the major diseases; Malaria, HIV/AIDS, Immuno-preventable diseases Tuberculosis, support for reproductive health programmes.

- Strengthening training and health education programmes, improvement in the nutritional status of the population.

For the health services delivery to the population, the three levels of care were structured:

1. Primary health care level composed of health centers and health post;

2. Secondary health care level composed of general hospitals and

3. Tertiary health care level composed of highly specialized hospitals (provincial and national hospitals)

In the last three years the health facility network is improved remarkably, having rehabilitated or constructed many infrastructures. Nevertheless still important sectors of the population do not have access to basic health services.

Table 2A     Angola Public Health Facility Network. December 2004

| Type of Health Facility | Number of Functioning Health Facilities |
| --- | --- |
| Health posts | 1049 |
| Health centers | 294 |
| Municipal and provincial hospitals | 75 |
| National hospitals | 8 |
| TOTAL | 1.426 |

Source: Ministry of Health. EPI, Epidemiological Surveillance Division.

Vaccination services are provided in about 730 health facilities (51%), this is an increase of almost 100% from 2001.  In addition, vaccination services are provided by mobile and outreach teams that originate from the provincial, district and health facility levels to provide services to the hard-to-reach populations.

| - Attached are the relevant section(s) of strategies for health system development | Document number 01 |
| --- | --- |

4. TProfile of the Inter Agency Co-ordinating Committee (ICC)

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.

4.1 Profile of the ICC

- Name of the ICC: Inter-agency Coordinating Committee (ICC)

- Date of constitution of the current ICC: November 1995.

- Organisational structure (e.g., sub-committee, stand-alone):

Since its constitution, the ICC was focused only on immunization, particularly polio eradication activities. The role of the ICC was later broadened to include other immunization activities including measles SIAs and routine immunization.

Having found the ICC very useful in coordination of resources and efforts among the MOH and various partners, the Ministry of Health in 2004 decided to further broaden the mandate of the ICC to include other health programmes. The Chairperson for the ICC is the Honourable Vice-Minister of Health.

The committee has 3 technical committees, as follow:

- Child Health Committee

- Women’s Health Committee

- Disease Control Committee

Under each of these technical committees there are sub-committees including:

- Health promotion.

- Logistics.

- Surveillance.

- Frequency of meetings: Monthly.

Composition:

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Vice Minister/Ministry of Health | Dr. José Vieira Dias Van-Dunem |
| Deputy Coordinator | Director of National Public Health | Dra. Adelaide Carvalho |
| Secretary | National Deputy Director of the Directorate of Public Health/ MOH | Dr. João Cunha |
| Members | - Representative/WHO - Representative/UNICEF - President CNPPI/Rotary - Program Director/ USAID - Sec. Dir./CORE Group - International Red Cross - Dir. Dep.Epidemiology/MoH - Chief of Repr.Health/ MoH - Chief of Child and Adolescent Health Section/ MoH - Chief of Health Promotion/ MoH - Chief of Department of Disease Control/ MoH - EPI Team Leader/ WHO - Chief of Health and Nutrition Section/ UNICEF - Director of Provincial Health/ MoH Luanda | - Dr. Fatoumata Diallo - Dr. Mario Ferrari - Ing. Sylvia Nagy - Dr. Cathy Bowles - Dr. Antonio Dias - Dr. Martin Acosta - Dra. Ana Vaz - Dra. Elsa Ambriz - Dra. Aida de Meneses - Dra. Filomena Wilson - Dr. Filomeno Fortes - Dr. Daniel Kertesz - Dr. Guy Clarisse - Dr. Vita Vemba |

Note: The ICC is in process of re- organization witch will include representatives from UNFPA, World Bank, European Union and  Associations of National and International NGOS.

4.2 Functioning of the ICC structure

Major functions and responsibilities of the ICC relating to EPI: (see terms of reference document number 02)

- Coordination

- Resource mobilization

- Follow up programme implementation

- Review annual plans and budgets

- Advocacy and promotion of social mobilization

- Provide recommendations

Attached is the supporting document:

| - Terms of reference of the ICC | Document number…2…. |
| --- | --- |

- Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Ensure that regular meetings are held as planned and that an agenda of the ensuing meeting is circulated in advance of the meeting date and time.

- Ensure that the minutes of ICC are circulated to members in time

- Ensure that the ICC is periodically briefed about the level of implementation of planned immunization and surveillance activities in order to enlist their support at all levels.

- Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal :

- The drop-out rate: as a sign of improvement in the immunization services, the ICC looks at the reduction of drop-out rate in multi-dose antigens (DTP1-DTP3)

- Completeness of district (municipal) reporting to central level

- Vaccine stock out at various levels:

Attached are the supporting documents:

| - ICC’s work plan for the next 12 months | Document number…3…. |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program | Document number…4…. |

# 5. Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, Reviews, and Studies of Immunization Services for Current Reference

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Multiple Indicator Cluster Survey | UNICEF, NIS | 2001 |
| Evaluation of AFP surveillance | MOH,WHO,USAID & CDC, UNICEF | 10/2002 |
| National EPI Program Review | UNICEF, WHO, CDC, USAID, AN University | 03/2003 |
| RED Assessment | WHO, UNICEF | 10/2004 |

- The three major strengths identified in the assessments:

- Improved AFP surveillance performance

- Improved EPI monitoring system

- Improved routine coverage in 2004

- The three major problems identified in the assessments:

- Quality and frequency of supervision at health facilities

- Cold chain maintenance

- Utilization of data for decision making

- The three major recommendations in the assessments:

- To maintain the investment in financial and human resources for immunization.

- Improve quality and frequency of supervision at municipal and health facility levels.

- Improve capacity of local personnel to collect and utilize data

- Attached are complete copies (with an executive summary) of:

| - the most recent assessment reports on the status of immunization services | Document number …5A, 5B |
| --- | --- |
| - A list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress…. | Document number……6. |

- Components or areas of immunization services that are yet to be reviewed (or studied).

| ##### Component or area | Month/Year |
| --- | --- |
| Injection Safety Assessment | 10/ 2005 |
| Vaccine Management Assessment | 05/2005 |
| Waste management assessment | 10/2005 |
| Data Quality Auditing (DQA) | 09/2005 |
| Data Quality Self Assessment (DQS) | 04-12/2005 |

- Components or areas of immunization services that are yet to be reviewed (or studied).

# 6. Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has updated the multi-year immunization plan or adjusted the health sector plan.

| - Attached is a complete copy (with an executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…7…. |
| --- | --- |

| Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…) |  |  |
| --- | --- | --- |
| Type of technical support | Period for the support | Desired from which agency |
| External Technical support from partners | 2005-2008 | WHO, UNICEF, CORE, CDC, USAID |

| Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  |  |  |  | Comments |
|  |  | Entire country |  | Only part of the country |  |  |  |
| BCG | At birth | X |  |  |  |  |  |
| Polio | At birth, 2, 4 & 6 Months | X |  |  |  |  |  |
| DTP | At 2, 4 & 6 Months | X |  |  |  |  |  |
| Measles | At 9 Months | X |  |  |  |  |  |
| Yellow Fever | At 9 Months | X |  |  |  |  |  |
| TT | Pregnant and women at childbearing age (15-45 Years) | X |  |  |  |  |  |
| Pentavalent | At 2, 4 & 6 Months | X |  |  |  |  | New vaccine, start January 2006 |
| Vitamin A | 6-59 months | X |  |  |  |  |  |

- Summary of major action points and timeframe for improving immunization coverage:

| Major Action Points | Responsible Office | Timeframe |
| --- | --- | --- |
| Training of staff and improved supportive supervision which will aim at reducing missed opportunities for vaccination, improve quality of services and immunization safety, | MOH, WHO, UNICEF, CORE | 2005-2007 |
| Expansion of vaccination services: a) by opening more fixed vaccination post in areas of the country recently accessible; b) by expanding and regularizing out-reach and mobile immunization services. | MOH, WHO, UNICEF, CORE | 2005- 2007 |
| Ensure vaccine availability at all times through planed distribution and monthly monitoring of stock at all levels. | MOH, WHO, UNICEF, CORE | 2006-2007 |
| Strengthening advocacy and social communication | MOH, WHO, UNICEF, CORE | 2005-2007 |

Table 4: Baseline and annual targets

| Number of |  | Baseline and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI/VF application | Year 1 of Programme implementation | Year 2 of Programme implementation | Year 3 of Programme implementation | Year 4 of Programme implementation | Year 5 of Programme implementation | Year 6 of Programme implementation |
|  |  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Births |  | 860,000 | 884,080 | 908,834 | 934,282 | 960,441 | 987,334 | 1,014,979 | 1,043,399 |
| Infants’ deaths |  | 129,000 | 132,612 | 136,325 | 140,142 | 144,066 | 148,100 | 152,247 | 156,510 |
| Surviving infants |  | 731,000 | 751,468 | 772,509 | 794,139 | 816,375 | 839,234 | 862,732 | 886,889 |
| Pregnant women |  | 860,000 | 884,080 | 908,834 | 934,282 | 960,441 | 987,334 | 1,014,979 | 1,043,399 |
| Infants vaccinated with BCG |  | 617,275 | 663,060 | 727,067 | 747,425 | 816,375 | 839,234 | 913,481 | 939,059 |
| BCG coverage* |  | 72% | 75% | 80% | 80% | 85% | 85% | 90% | 90% |
| Infants vaccinated with OPV3 |  | 419,279 | 526,028 | 579,382 | 635,311 | 653,100 | 713,349 | 733,322 | 798,200 |
| OPV3 coverage** |  | 57% | 70% | 75% | 80% | 80% | 85% | 85% | 90% |
| Infants vaccinated with DTP3*** |  | 430,479 | 526,028 | NA | NA | NA | NA | NA | NA |
| DTP3 coverage** |  | 59% | 70% | NA | NA | NA | NA | NA | NA |
| Infants vaccinated with DTP1*** |  | 550,253 | 751,406 | NA | NA | NA | NA | NA | NA |
| Wastage[1] rate in base-year and planned thereafter (estimated) |  | 30% | 25% | NA | NA | NA | NA | NA | NA |
| Infants vaccinated with 3rd dose of DPT-HepB+Hib** |  | NA | NA | 579,382 | 635,311 | 653,100 | 713,349 | 733,322 | 798,200 |
| DPT-HepB+Hib 3 Coverage** |  | NA | NA | 75% | 80% | 80% | 85% | 85% | 90% |
| Infants vaccinated with 1st dose of DPT-HepB+Hib* |  | NA | NA | 772,509 | 840,854 | 864,397 | 937,967 | 964,230 | 1,043,399 |
| Wastage1 rate in base-year and planned thereafter |  | NA | NA | 10% | 10% | 10% | 10% | 10% | 10% |
| Infants vaccinated with Measles |  | 475,15 | 563,601 | 618,007 | 635,311 | 693,919 | 713,349 | 776,459 | 798,200 |
| Measles coverage** |  | 65% | 75% | 80% | 80% | 85% | 85% | 90% | 90% |
| Pregnant women vaccinated with TT-2 + |  | 617,022 | 663,060 | 681,626 | 747,425 | 768,353 | 839,234 | 862,732 | 939,059 |
| TT-2 + coverage |  | 72% | 75% | 75% | 80% | 80% | 85% | 85% | 90% |
| Vit A supplementa-tion | Mothers (< 6 weeks from delivery) | 177,105 | 663,060 | 727,067 | 794,139 | 816,375 | 888,600 | 913,481 | 991,229 |
|  | Infants (6-59 months) | 750,83 | 1,893,699 | 1,946,723 | 2,168,000 | 2,228,704 | 2,467,347 | 2,536,433 | 2,793,700 |

* Number of infants vaccinated out of total births

** Number of infants vaccinated out of surviving infants

*** Indicate total number of children vaccinated with either DTP alone or combined

| Table 5: Estimate of annual DTP drop out rates (Pentavalent for 2006-2011) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual rates and targets |  |  |  |  |  |  |  |
| YEAR | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 20% | 15% | 10% | 10% | 10% | 10% | 10% | 10% |

- Planning and constraints for the Polio Eradication Initiative:

As part of the efforts being made for the eradication of polio, Angola started conducting national immunization days (NIDs) in 1996. The last polio case was detected in 2001.  The rounds of NIDs were being synchronized with countries in the sub-region (Namibia, Zambia, DRC, Congo-Brazzaville, Gabon e Sao Tome e Principe) from 2001 to 2003.

The OPV vaccination coverage during the NIDs in 2004 was 99%, and 106% for first and second rounds respectively.

Surveillance for acute flaccid paralysis (AFP) is a part of the national integrated disease surveillance system. Moreover, at national level non polio AFP detection rate in 2004 was 1.5 per 100,000 children under the age of 15; the rate of adequate stool sample collection was 85%.

The National Certification Committee and the National Expert Committee on Poliomyelitis were created and is functioning from 2002.  The National Committee on Certification has elaborated and sent to AFRO a report on Polio free Status.

Constraints for polio eradication

- Low routine OPV coverage

- Limited and uncertainties of funds for PEI activities

- Inaccessibility of certain areas due to the existence of land mines and lack of roads and bridges in parts of the country.

# 7. Injection safety

7.1 	Summary of the injection safety strategy for immunization (for all proposals):

- Use of Auto-disabled syringes and safety boxes since 1997

- Training of health workers for the proper use of AD and appropriate disposal

- Plans to build at least one incinerator in each province and for each major hospital

- Plans for an injection safety assessment in October 2005.

- Introduction of AEFIs monitoring system planned for 2005.

  - For countries submitting a proposal for Injection Safety Support.  Summarise the most important findings of a recent assessment of Injection Safety and Waste Disposal. The relevant documents are attached

Not Applicable

| - Situation Analysis of Injection Safety and Waste Disposal or Report of the most recent Injection Safety and Waste Disposal Assessment | Document number… |
| --- | --- |
| - Update of the implementation status of recommendations from recent injection safety assessment or injection safety components from a broader review. | Document number… |
| - Policy on Injection Safety and Waste Disposal or a Draft Policy awaiting endorsement | Document number… |
| - A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan. | Document number… |

7.3	Injection safety equipment (For countries submitting a request for injection safety support). GAVI’s support is only for three years of routine immunization.

The following tables calculate the amount of supplies requested for injection safety:

|  |  | Table 6.1: Estimated supply for safety of vaccination with ………... vaccine ( Use one table for each vaccine BCG(1 dose), DTP(3 doses), TT(2 doses) 1, Measles(1 dose) and Yellow Fever(1 dose), and number them from 6.1 to 6.5) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Formula |  | 20… | 20… |  | 20… |  | 20… |  | 20… |  |  |
|  |  | A | Number of children to be vaccinated 2 | # |  |  |  |  |  |  |  |  |  |  |  |
|  |  | B | Percentage of vaccines requested from The Vaccine Fund 3 | % |  |  |  |  |  |  |  |  |  |  |  |
|  |  | C | Number of doses per child | # |  |  |  |  |  |  |  |  |  |  |  |
|  |  | D | Number of doses | A x B/100 x C |  |  |  |  |  |  |  |  |  |  |  |
|  |  | E | Standard vaccine wastage factor 4 | Either 2.0 or 1.6 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | F | Number of doses ( incl. wastage) | A x B/100 x C x E |  |  |  |  |  |  |  |  |  |  |  |
|  |  | G | Vaccines buffer stock 5 | F x 0.25 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | H | Number of doses per vial | # |  |  |  |  |  |  |  |  |  |  |  |
|  |  | I | Total vaccine doses | F + G |  |  |  |  |  |  |  |  |  |  |  |
|  |  | J | Number of AD syringes (+ 10% wastage) requested | (D + G) x 1.11 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | K | Reconstitution syringes (+ 10% wastage) requested 6 | I / H x 1.11 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | L | Total of safety boxes (+ 10% of extra need) requested | (J + K) / 100 x 1.11 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 GAVI/The Vaccine Fund supports the procurement of AD syringes to deliver two doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of two doses for Pregnant Women (estimated as total births) 2 To insert the number of infants that will complete vaccinations with all scheduled doses of a specific vaccine. 3 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended. 4 A standard wastage factor of 2.0 for BCG and of 1.6 for DTP, Measles, TT, and YF vaccines is used for calculation of INS support 5 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. 6 It applies only for lyophilized vaccines; write zero for other vaccines. |  |  |  |  |  |  |  |  |  |  |  |  |  |

7.4 	For countries requesting GAVI/The Vaccine Fund to provide funds in lieu of the supply calculated above.

List of activities of the injection safety plan funded by The Vaccine Fund and by other sources:

| Source of fund | ###### Injection Safety activity | Month of start of fund utilization |
| --- | --- | --- |

(Use as many rows as necessary

# 8. New and under-used vaccines

- Summary of those aspects of the comprehensive multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Pages 10 and 26 of the Multi Year Plan address the introduction of Hepatitis B and Haemophilus Influenzae Type b vaccines in Angola.  The MYP calls for the introduction of the 2 vaccines by the year 2006.  Please see also the Introduction Plan for "Pentavalent" DTP-HepB-Hib Vaccine into the Angolan EPI Programme. (Document Number 8).

- Assessment of burden of relevant diseases (if available) :

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| HepB | National sentinel surveillance for pregnant women (MoH, CDC, WHO, UNICEF) | 2004 | 9.2% prevalence |
| Hib | Bacterial Meningitis in Angola, Lancet | 2003 | 28% of bacterial isolates from children with bacterial meningitis were Hib+ |

- (For Europe and Asia countries requesting support for Hib Vaccines). WHO advise on Hib introduction is attached:

| - WHO advise on introduction of Hib in this country | Document number…… |
| --- | --- |

- (if new or under-used vaccines have been already introduced)

Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

Although Angola has not introduced new vaccines, the country has recently experienced great success in improving routine coverage through district level micro-planning, improved supervision, and provision of outreach and mobile services using the RED approach.

- Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :

A UNICEF international staff member is now support the development a national plan for cold chain rehabilitation and maintenance at all levels.  Support is also available in 2005 to replace the national cold rooms and expand the storage capacity at the provincial levels and to train personnel at the provincial and municipal levels.

- First preference: required number of doses and presentations of requested new and under-used vaccines. (For each one of the requested first preference of  new and under-used vaccine, please use provided formulae)

Table 7.1: Estimated number of doses of DTP-HepB-Hib (Pentavalent vaccine)

|  |  | Formula | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated with the first dose 1 | # | 772509 | 840854 | 864397 | 937967 | 964230 | 1043399 |
| B | Percentage of vaccines requested from The Vaccine Fund 2 | % | 100 | 100 | 100 | 100 | 100 | 0 |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
|  | Number of doses (total) | A x C | 2317527 | 2522561 | 2593191 | 2813902 | 2892690 | 3130197 |
| D | Number of doses (GAVI) | A x B/100 x C | 2317527 | 2522561 | 2593191 | 2813902 | 2892690 | 0 |
| E | Estimated vaccine wastage factor | see list in table  | 1,11 | 1,11 | 1,11 | 1,11 | 1,11 | 1,11 |
|  | Number of doses ( incl. wastage) Total |  | 2572455 | 2800043 | 2878442 | 3123431 | 3210886 | 3474519 |
| F | Number of doses ( incl. wastage) GAVI | D x E | 2572455 | 2800043 | 2878442 | 3123431 | 3210886 | 0 |
|  | Vaccines buffer stock (Total) |  | 643114 | 56897 | 19600 | 61247 | 21864 | 65908 |
| G | Vaccines buffer stock GAVI | F (-F of previous year) x 0.25 | 643114 | 56897 | 19600 | 61247 | 21864 | 0 |
| H | Number of doses per vial | # | 2 | 2 | 2 | 2 | 2 | 2 |
|  | Total vaccine doses needed |  | 3215568 | 2856940 | 2898041 | 3184678 | 3232750 | 3540427 |
| I | Total vaccine doses requested of GAVI | F + G | 3215568 | 2856940 | 2898041 | 3184678 | 3232750 | 0 |
|  | Number of AD syringes (+ 10% wastage) Total |  | 3286311 | 2863199 | 2900197 | 3191416 | 3235155 | 3547677 |
|  |  | Formula | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| J | Number of AD syringes (+ 10% wastage) GAVI | (D + G) x 1.11 | 3286311 | 2863199 | 2900197 | 3191416 | 3235155 | 0 |
|  | Reconstitution syringes (+ 10% wastage) Total |  | 1784640 | 1585602 | 1608413 | 1767497 | 1794176 | 1964937 |
| K | Reconstitution syringes (+ 10% wastage) GAVI | I / H x 1.11 | 1784640 | 1585602 | 1608413 | 1767497 | 1794176 | 0 |
|  | Total of safety boxes (+ 10% of extra need) total |  | 56288 | 49382 | 50046 | 55044 | 55826 | 61190 |
| L | Total of safety boxes (+ 10% of extra need) GAVI | (J + K) / 100 x 1.11 | 56288 | 49382 | 50046 | 55044 | 55826 | 0 |

| - Table  : Wastage rates and factors Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial, 25% for a liquid vaccine in a10 or 20-dose vial, 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial, and to reduce it in the following years. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

- Summary of major action points and timeframe for reduction of vaccine wastage.  If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate:

- Implementation of multi-dose vial policy

- Training of health workers

- Improve monitoring of vaccine management

- Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1)

The second preference is Tetravalent DTP-HepB (liquid).

Table 7.2: Estimated number of doses of DTP-HepB (Tetravalent vaccine)

|  |  | Formula | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated with the first dose 1 | # | 772509 | 840854 | 864397 | 937967 | 964230 | 1043399 |
| B | Percentage of vaccines requested from The Vaccine Fund 2 | % | 100 | 100 | 100 | 100 | 100 | 0 |
| C | Number of doses per child | # | 3 | 3 | 3 | 3 | 3 | 3 |
|  | Number of doses (total) | A x C | 2317527 | 2522561 | 2593191 | 2813902 | 2892690 | 3130197 |
| D | Number of doses (GAVI) | A x B/100 x C | 2317527 | 2522561 | 2593191 | 2813902 | 2892690 | 0 |
| E | Estimated vaccine wastage factor | see list in table  | 1,33 | 1,33 | 1,33 | 1,33 | 1,33 | 1,33 |
|  | Number of doses ( incl. wastage) Total |  | 3082311 | 3355007 | 3448944 | 3742490 | 3847278 | 4163162 |
| F | Number of doses ( incl. wastage) GAVI | D x E | 3082311 | 3355007 | 3448944 | 3742490 | 3847278 | 0 |
|  | Vaccines buffer stock (Total) |  | 770578 | 68174 | 23484 | 73386 | 26197 | 78971 |
| G | Vaccines buffer stock GAVI | F (-F of previous year) x 0.25 | 770578 | 68174 | 23484 | 73386 | 26197 | 0 |
| H | Number of doses per vial | # | 10 | 10 | 10 | 10 | 10 | 10 |
|  | Total vaccine doses needed |  | 3852888 | 3423181 | 3472428 | 3815876 | 3873475 | 4242133 |
| I | Total vaccine doses requested of GAVI | F + G | 3852888 | 3423181 | 3472428 | 3815876 | 3873475 | 0 |
|  | Number of AD syringes (+ 10% wastage) Total |  | 3427796 | 2875716 | 2904509 | 3204890 | 3239965 | 3562177 |
| J | Number of AD syringes (+ 10% wastage) GAVI | (D + G) x 1.11 | 3427796 | 2875716 | 2904509 | 3204890 | 3239965 | 0 |
|  | Reconstitution syringes (+ 10% wastage) Total |  | 0 | 0 | 0 | 0 | 0 | 0 |
| K | Reconstitution syringes (+ 10% wastage) GAVI | I / H x 1.11 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Total of safety boxes (+ 10% of extra need) total |  | 38049 | 31920 | 32240 | 35574 | 35964 | 0 |
| L | Total of safety boxes (+ 10% of extra need) GAVI | (J + K) / 100 x 1.11 | 38049 | 31920 | 32240 | 35574 | 35964 | 0 |

| - Attached is the plan of action for introduction of vaccinations with new or under-used vaccines (if already contained within the national multi-year plan, indicate pages) | Document number…8 |
| --- | --- |

# 9. Financial analysis and planning

Assured long term financing is crucial for maintaining program improvements and sustaining the introduction of new vaccines.  Meeting the financial requirements of improved and expanded immunization programs has proven to be the biggest challenge that countries and their partners face.  The financial analysis of the estimated cost of immunization (including the introduction of a new vaccine) is summarised in three major areas for the next years (see the document attached hereby):

- Rigorous analyses of the current and projected future costs for the program for the next years;

- Projected financing from all sources for the same time period;

- Description of the highest priority actions that the government/ will take to fill any resource gaps.

  - For countries that have already completed a Financial Sustainability Plan (FSP):

| - The attached document is an update of the program costs, financing projections and the plan of action for addressing the financial gap (if already contained within the national, comprehensive multi-year plan, indicate pages) | Document number…… |
| --- | --- |

  - For countries that have not completed a FSP:

| - The attached document summarises the results of most recent efforts to conduct the needed financial analyses and prepare a FSP. (if already contained within the national, comprehensive multi-year plan, indicate pages) | Document number 8 (see points number 2.7 and 4 )…… |
| --- | --- |

See new vaccine introduction plan, ICC minutes (Doc Number 4)

Please follow the latest version of the financial analysis tool which is available @ http://www.who.int/immunization_financing/tools/annexes/en/

10.

- Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Republic of Angola, kindly requests the Alliance and its partners to provide financial and technical assistance required to successful introduce new vaccines to benefit Angolan children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):

- Support for Immunization Services                       		  YES           NO

- Support for New and Under-used vaccines                                  YES           NO

- Support for Injection Safety                                                          YES           NO

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 20…according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely ………… (number of children). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 2) with their proposal.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: (fill in only what is being requested from the Vaccine Fund in line with tables 7.1, 7.2…)

| Table 8: New vaccines requested from GAVI and the Vaccine Fund (fill in the annual amount of row “I” of table 7.1. Specify one additional row for each presentation of any vaccine as per tables 7.2, 7.3, …) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccine presentation | Number of doses per vial | Starting month and year | Number of doses requested for first calendar year | Number of doses requested for second calendar year * |
| Pentavalent (first choice) | 2 | January 2006 | 3,215,568 | 2,856,940 |
| Tetravalent (second choice) | 10 | January 2006 | 3,852,888 | 3,423,181 |
| * Vaccines will also be requested for following years as described in tables 7.1, 7.2… |  |  |  |  |

- Vaccines will be procured (tick only one) :

By UNICEF                                               By GOVERNMENT

- (If vaccines are proposed to be procured by the Government) 	Process and procedures of the National Regulatory Authority to control the purchase and delivery of vaccines into the country, including weaknesses, constraints and planned measures to improve the control system:

- (In case you are approved, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of new vaccines) Please submit the attached “Banking Form”( Annex 2) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund..

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

(Tick one choice only):		The amount of supplies listed in table 9

The equivalent amount of funds

| Table 9: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and YF, requested from GAVI and the Vaccine Fund for three years (fill in the total sums of rows “J, K and L” of tables 6.1, 6.2, 6.3, 6.4 and 6.5). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM |  | 20.. | 20.. | 20.. | 20.. |
| J | Total AD syringes | for BCG |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |
| K | Total of reconstitution syringes |  |  |  |  |  |
| L | Total of safety boxes |  |  |  |  |  |

- (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 2) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.

# Additional comments and recommendations from the ICC

Due to the rising benefits in favour of child survival and the high cost of the pentavalent vaccine, its introduction in the Country requires entirely financing support of GAVI for the first 5 years. In this period, the government and partners will develop sustainable mechanisms for further funding. In addition to the Government contribution commitment, there is the possibility of creating a "National Fund for Vaccines" with possible contributions of companies operating in the country.

Table 1

Table 2

ANNEX  1

Index of documents attached

| Section of proposal | Document Subject | Document number |
| --- | --- | --- |
| 3 | A copy of the relevant section(s) of strategies for health system development | 1… |
| 4 | a) The terms of reference of the ICC | 2… |
|  | b) The ICC’s work plan for the next 12 months | 3… |
|  | c) The minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections | 4… |
| 5 | a) Most recent, national assessment report(s) on the status of immunization services | 5 A 5 B |
|  | b) Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation. | 6… |
| 6 | A complete copy (with executive summary) of the comprehensive Multi-Year Immunization Plan or of the relevant pages of the health sector plan | 7… |
| 7 | - The Situation Analysis of Injection Safety and Waste Disposal or Report of the most recent Injection Safety and Waste Disposal Assessment Note : Injection Safety and Waste Management assessment will be done in October 2005 | … |
|  | b) An update of the implementation status of recommendations from recent injection safety assessment or injection safety components from a broader review. |  |
|  | c) The Policy on Injection Safety and Waste Disposal or a Draft Policy awaiting endorsement | … |
|  | d) The plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or relevant pages of the health plan. Note: Is planned to be done after the Injection Safety Assessment | … |
| 8 | a) WHO’s advise on introduction of Hib in this country (for European and Asian countries) | NR |
|  | b) Plan of Action for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | 8… |
| 9 | Updated Financial Sustainability Plan (or a summary of the relevant financial analysis for preparation of the FSP) Note : Financial Sustainability Plan is planned for first quarter 2006. | ……… |

ANNEX  2

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  | Ministério da Saúde |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  | Luanda – Angola |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: | José Vieira Dias Van-Dúnem |  |  |  |  |  |  |  | Seal: |  |
| #### Title: | Vice Ministro da Saúde |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Formula to calculate DTP vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of DTP doses distributed for use according to the supply  records with correction for stock balance at start and end of the supply period; B =  the number of DTP vaccinations.

GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

Please submit hard copy documents with an identical electronic copy whenever possible