GAVI Alliance

APPLICATION FORM FROM

Chad

SEPTEMBER 2007

For support:

to the new liquid DTP-HepB-Hib vaccine

September 2007

Please return a signed copy of the document to:

GAVI Alliance Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10,

Switzerland.

Enquiries to: Dr Ivone Rizzo, irizzo@gavialliance.org or representatives of a GAVI

partner agency.  All documents and attachments must be in English or French.

## CONTENTS

| SECTION | SUPPORT | PAGE |
| --- | --- | --- |
| 1. | Executive summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies | ALL | 4 |
| 3. | Immunization Programme Data | ALL | 8 |
| 4. | Immunization Services Support (ISS) | ISS | 17 |
| 5. | Injection Safety Support (INS) | INS | 18 |
| 6. | New and Under-Used Vaccine Support (NVS) | NVS | 20 |
| 7. | Additional comments and recommendations from the National Coordinating Body (ICC) | ALL | 28 |
| 8. | Documents required for each type of support | ALL | 30 |
| Annex 1 – Banking form | ISS + NVS |  |
| Annex 2 – Excel Spreadsheet | NVS |  |

## Executive Summary

The new considerations and policies of the GIVS are identified in the four strategic pillars that consist of 24 strategies, one of which provides for the adoption of new vaccines and new technologies.

# The government of the Republic of Chad has decided to introduce new vaccines: Haemophilus influenzae b (Hib) and Viral Hepatitis B (HepB) vaccines in pentavalent form (DTP-HepB -Hib) beginning 1 July 2008. To this end, it is submitting this application to the GAVI Secretariat. This application was prepared by the EPI Technical Committee, consisting of: the technical staff of the Ministry of Public Health, the Ministry of Finance and Information Systems, the Ministry of Planning and the Economy (DGAS, DSRV, PEV, BIEC, DAFM, etc.), the WHO and UNICEF in charge of immunisation. This application was validated by the Inter-Agency Coordinating Committee on 25 September 2007.

The Haemophilus influenzae b and Viral Hepatitis B vaccines in pentavalent form (DTP-HepB-Hib) are vaccines in liquid form contained in a single-dose vial.

# Chad has been receiving GAVI Fund support since 2003 to strengthen immunisation services, for injection safety, and for expanding under-used vaccines in the routine EPI: the Yellow Fever vaccine.

With this support from GAVI, EPI/Chad performances have improved as shown in the tables below:

Table 1: Trend in vaccine coverage

| Antigens | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 | 24% | 20% | 28% | 31% | 27% | 40% | 47% | 50% | 57% | 77% |
| VAR | 30% | 21% | 41% | 38% | 35% | 55% | 61% | 56% | 70% | 81% |
| VAA | 30% | 26% | 38% | 39% | 35% | 52% | 40% | 49% | 63% | 73% |

National immunisation coverage for DTP3 is up from 47% in 2003 to 77% in 2006.

Table 2: Trend in district performance

| Performances | 2002 | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- |
| Districts with DTP3 equal to or greater than 80% | 4 | 4 | 6 | 7 | 23 |
| Districts with DTP3 between 50% and 80% | 9 | 16 | 17 | 23 | 19 |
| Districts with DTP3 less than 50% | 39 | 32 | 30 | 24 | 12 |
| Total of reporting districts | 52 | 52 | 53 | 54 | 54 |

The number of health districts with immunisation coverage greater than 80% is increasing gradually.

Although immunisation coverage is improving, the DTP drop out rate and wastage rate remains high. These rates are 21% and 68% respectively in 2006.

The country intends to continue to improve EPI performances. Thus, in the 2008-2012 Complete Multi-Year Plan, Chad proposes to achieve and maintain 90% immunisation coverage per antigen at the national level and at least 80% in all the districts by 2012. Chad also intends to pursue the introduction of new vaccines in the EPI, namely the Hib and HepB infection vaccines in 2008, for which there is an introduction plan.

The epidemiological context of Hib and HepB in the sub-region and in Chad argues in favour of introducing these vaccines.

Currently available storage capacity for preserving vaccines at the regional level is quite sufficient for the regions. There are three cold chambers at the central level and three sub-national warehouses that will be set up by end-2007 and will be used to supply the Health Regions.

The status quo provides us with 69% cold-chain coverage. To reach 100% coverage by 2012, the plan is to expand coverage by 8% per year for the missing responsibility zones (RZs), in addition to replacing the ageing cold chain.

Because of the DTP inventory that is still available in the field and the residual inventory throughout the first six months of 2008, pentavalent vaccine administration should begin on 1 July 2008. This vaccine will follow the usual DTP immunisation schedule, which is administered at 6, 10 and 14 weeks for the three doses required for children under one year old.

The 2008-2012 Complete Multi-Year Plan includes a section on the financial viability strategies of the program, the most important of which will involve strengthening advocacy with the government so that vaccine independence is sustainable.

As part of the new GAVI co-financing policy, Chad will use the current procurement procedure through the UNICEF system for providing its share of the pentavalent vaccine, pending the finalisation of the restructuring of the Pharmaceuticals Clearinghouse (Centrale Pharmaceutique d’Achat - CPA). A budget line item is planned for this purpose in the Ministry of Public Health’s budget.

The principal implementation strategies recommended for successfully introducing the pentavalent vaccine are:

- Setting up a sustainable immunisation financing mechanism;

- Improving the supply of services and accessibility to immunisation services;

- Strengthening staff capacities;

- Revising the monitoring tools;

- Steady supply of vaccines and injection supplies;

- Improving injection safety (including incinerating waste) and vaccine management (reducing wastage rates);

- Strengthening cold-chain capacity;

- Strengthening behaviour change communication/social mobilisation;

- Strengthening collaboration, coordination and partnerships;

- Strengthening epidemiological surveillance with confirmation in the laboratory, including AEFI surveillance.

- Strengthening human resources;

- Operations research.

The total amount of the plan is $99,797,925

The quantities of the vaccine requested from the fund, their estimated cost and the government’s and GAVI’s share of the co-financing are summarised in the table below (Table 2.1.a):

2. Signatures of the Government and National Coordinating Bodies

## Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of the Republic of Chad would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for the introduction of the new vaccine: DTP-HepB-Hib pentavalent.

The Government of the Republic of Chad commits itself to developing national immunisation services on a sustainable basis in accordance with the comprehensive Multi-Year Plan presented with this document.  The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Table N° 2.1a of page 4 of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance: USD 18,340,000. Table N° 6.4 of page 25 of this application shows the government financial commitment for the procurement of this new vaccine (NVS support only).

| Table 2.1a : Targets and budgets for introducing the first vaccine: DTP-HepB-Hib (antigen) immunisation with presentation of one dose |
| --- |
| Total supplies |  | Base Year 2006 | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| National target of the number of children to be vaccinated | # | 245,033 | 310,722 | 331,661 | 348,696 | 358,459 | 368,496 |
| Total number of vaccine doses required | # |  | 1,295,436 | 1,150,706 | 1,167,309 | 1,199,993 | 1,233,592 |
| Total number of AD syringes required | # |  | 0 | 0 | 0 | 0 | 0 |
| Total number of re-constitution syringes necessary | # |  | 0 | 0 | 0 | 0 | 0 |
| Total number of safety boxes necessary | # |  | 0 | 0 | 0 | 0 | 0 |
| Total budget | Price per dose of vaccine * | $ |  | 3,600 | 3,600 | 3,200 | 3,000 | 2,800 |
|  | Total funds necessary | $ |  | 4 ,710,204 | 4,183,966 | 3,772,743 | 3,635,967 | 3,488,599 |
| Co-financing for which the country is responsible | Co-financing per dose | $ |  | 0.20 | 0.20 | 0.20 | 0.30 | 0.30 |
|  | Total payments made by the country | $ |  | 259,500 | 230,500 | 233,500 | 360,000 | 370,500 |
| Support requested from GAVI | Payment made by GAVI per dose | $ |  | 0.80 | 0.80 | 0.80 | 0.70 | 0.70 |
|  | Total payments made by GAVI | $ |  | 4,451,500 | 3,954,000 | 3,539,500 | 3,276,000 | 3,119,000 |

| Table 2.1b: Targets and budgets for introducing the second vaccine: NA (antigen) immunisation with …….…………………….. (presentation of the vaccine) |
| --- |
| Total supplies |  | Base Year | Year 1 2008 | Year 2 2009 | Year 3 20… | Year 4 20… | Year 5 20… |
| National target of the number of children to be vaccinated | # | NA | NA | NA | NA | NA | NA |
| Total number of vaccine doses required | # | NA | NA | NA | NA | NA | NA |
| Total number of AD syringes required | # | NA | NA | NA | NA | NA | NA |
| Total number of re-constitution syringes necessary | # | NA | NA | NA | NA | NA | NA |
| Total number of safety boxes necessary | # | NA | NA | NA | NA | NA | NA |
| Total budget | Price per dose of vaccine * | $ | NA | NA | NA | NA | NA | NA |
|  | Total funds necessary | $ | NA | NA | NA | NA | NA | NA |
| Co-financing for which the country is responsible | Co-financing per dose | $ | NA | NA | NA | NA | NA | NA |
|  | Total payments made by the country | $ | NA | NA | NA | NA | NA | NA |
| Support requested from GAVI | Payment made by GAVI per dose | $ | NA | NA | NA | NA | NA | NA |
|  | Total payments made by GAVI | $ | NA | NA | NA | NA | NA | NA |

| Minister of Health: | Minister of Finance: |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Name: Pr. AVOCKSOUMA DJONA ATCHENEMOU | Name: Mr ABAKAR MALLAH MOURCHA |
| Date: …………………………………… | Date: …………………………………… |

National Coordinating Body: Inter-Agency Immunisation Coordinating Committee:

We the members of the ICC/HSCC met on 25 September 2007 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER 01

| Name/Title | Institution/Organisation | Signature |
| --- | --- | --- |
| Pr AVOCKSOUM DJONA ATCHENEMOU Chair | Ministry of Public Health |  |
| Mr DJEDOSSOUM NAOUNDANGAR Vice Chair | Ministry of Public Health |  |
| Mr MOUNDOUNA ERNEST 1st Rapporteur | Ministry of Public Health |  |
| Dr GARBA TCHANG SALOMON 2nd Rapporteur | Ministry of Public Health |  |
| Mr ABAKAR MALLAH MOURCHA Member | Secretary of State for Finance and Information Technology, in Charge of the Budget |  |
| Mrs NGARMBATINA ODJIMBEYE SOUKATE Member | Minister of Social Action, National Solidarity and the Family |  |
| Pr YAO KASSANKOGNO Member | WHO Representative in Chad |  |
| Mrs MARIAM COULIBALY N’DIAYE Member | UNICEF Representative in Chad |  |
| MAHAMAT ANNOUR WADAK Member | 8th EDF Health Project |  |
| DOMINIQUE BOUILLIN Member | French Cooperation |  |
| Dr AHMAT ALI HISSEIN Member | National Polio Plus Commission |  |
| Dr NDEKOUNDAM NGANGRO MOSUREL Member | Ministry of Public Health |  |
| Mr HARBA KHAMIS Member | Ministry of Public Health |  |
| Dr BRAHIM HAMIT Member | Ministry of Public Health |  |
| Dr KONO NOUDJABAYE SEPHORA Member | Ministry of Public Health |  |
| Dr OUMAR ABDELHADI Member | Ministry of Public Health |  |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: GARBA TCHANG SALOMON | Title: EPI Coordinator |
| --- | --- |
| Tel.: (00235) 252 52 26 | Address: Ministry of Public Health BP 440 Ndjamena /Chad |
| Fax : (00235) 251 48 21 |  |
| E-mail: garbasal@yahoo.fr |  |

The GAVI Secretariat is unable to return documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and CSOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC/HSCC).  The ICC/HSCC are responsible for coordinating and guiding the use of the GAVI ISS and NVS support.  Please provide information about the ICC/HSCC in your country in the spaces below.

Profile of the ICC/HSCC

Name of the ICC/HSCC: Inter-Agency Coordinating Committee

Date of constitution of the current ICC/HSCC: August 2007

Organisational structure (e.g., sub-committee, stand-alone): Stand-alone

Frequency of meetings: Four meetings per year based on the articles of association, and special meetings

Composition: Function Title / Organisation Organisation Chair Ministry of Public Health Pr AVOCKSOUMA DJONA ATCHENEMOU Vice Chair Ministry of Public Health DJEDOSSOUM NAOUNDANGAR 1st Rapporteur Ministry of Public Health MOUNDOUNA ERNEST 2nd Rapporteur Ministry of Public Health Dr GARBA TCHANG SALOMON Members Minister of Finance and Information Technology Minister of Social Action, National Solidarity and the Family Minister of the Economy and Planning WHO Representative UNICEF Representative World Bank Representative UNFPA Representative Ambassador, Head of the European Commission Delegation Ambassador of the United States of America Chair, National Polio Plus Commission French Cooperation Representative Director General of Health Activities Chief of the 8th EDF Project Director General of Resources and Planning Director General of the Regional Health Project Director of Reproductive Health and Immunisation Director of Planning …………. Mr ABAKAR MALLAH MOUCHA Mrs NGARMBATINA ODJIMBEYE SOUKATE Mr OUSMANE M. BREME Pr YAO KASSANKOGNO Mrs MARIAM COULIBALY N’DIAYE Mr YACINE DIALLO SE GILLES DESESQUELLES Dr AHMAT ALI HISSEIN Dr DOMINIQUE BOUILLIN NDEIKOUNDAM NGANGRO MOSUREL MAHAMAT NOUR WADAK Mr HARBA KHAMIS Dr BRAHIM HAMIT Dr KONO NOUDJALBAYE Séphora Dr OUMAR ABDELHADI ………….

Major functions and responsibilities of the ICC: The ICC’s mission is to:

- Approve the Immunisation Division’s annual action plan, including the projects to organise National Immunisation Days and to strengthen epidemiological surveillance;

- Coordinate the interventions among the different partners on the one hand, and between the partners and the EPI’s national structures on the other hand;

- Mobilise the resources necessary to carry out the immunisation activities;

- Evaluate the performance of the action plan and the implementation of its different aspects.

Three major strategies to enhance the ICC/HSCC’s role and functions in the next 12 months:

1. Strengthen advocacy and resource mobilisation;

2. Expand the ICC to other programmes and partners of the Ministry of Health;

3. Strengthen coordination at the provincial and district levels in the context of strengthening the health system.

## 3. Immunisation Programme Data

Please complete the tables below, using data from available sources.  Please identify the source of the data, and the date. Where possible use the most recent data, and attach the source document.

  - Please refer to the Comprehensive Multi-Year Plan for Immunisation (or equivalent plan), and attach a complete copy (with an executive summary) as DOCUMENT NUMBER 02.

  - Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms on Vaccine Preventable Diseases and attach them as DOCUMENT NUMBER 3.

  - Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

Table 3.1: Basic facts for the year 2006 (the most recent; specify dates of data provided)

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population | 9,552,843 | 2006 | DCAP |
| Infant mortality rate (per 1000) | 102 per thousand | 2004 | EDST2 |
| Surviving Infants* | 391,666 | 2006 | DCAP |
| GNI per capita (US$) | 389.8 | 2005 | INSEED |
| Percentage of GDP allocated to Health | 4.2% | 2006 | INSEED |
| Percentage of Government expenditure on Health | 4.2% | 2006 | INSEED |

* Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country:

Please indicate the name and date of the relevant planning document for health: National Health Policy adopted in May 2007.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content etc)? Yes, the cMYP is aligned in this national document. Its budget is taken from the Ministry of Health’s programme budget, which is prepared based on the Medium-Term Expenditure Framework.

Please indicate the national planning budgeting cycle for health: The Ministry of Public Health’s programme budget is prepared for the period from 2007 to 2009.

______________________________________________________________________________

Please indicate the national planning cycle for immunisation: The national planning cycle for immunisation in Chad follows a bottom-up scheme. In the responsibility zones, the micro plans are prepared each year by the health committees, which are comprised of health care workers, the community and local partners;

The district makes a summary of the responsibility zone micro plans. This summary, in the form of an annual operational plan, is submitted for approval to the District Health Council chaired by the prefect of the Department.

At the regional level, a summary is made of the district operational plans as well by the framework team of the regional health delegation. The delegation’s action plan that comes out of this summary is submitted for approval to the Regional Health Council, chaired by the Governor of the region.

The central level prepares a five-year strategic plan and an annual plan that includes the plans of the regional Health Delegations. The EPI Technical Support Committee finalises these plans and then they are submitted to the ICC for approval.

Table 3.2: 	Current Immunisation Schedule: Traditional, New Vaccines and Vitamin A Supplement (refer to cMYP pages 15)

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Indicate by an “x” if given in: | Indicate by an “x” if given in: |
| --- | --- | --- | --- |
|  |  | Entire country | Entire country |  |
| BCG | At birth | X |  |  |
| Polio 0 | From birth to D14 | X |  |  |
| DTPHepB1 + polio1 | 6th week | X |  |  |
| DTPHepB2 + polio2 | 10th week | X |  |  |
| DTPHepB3 + polio3 | 14th week | X |  |  |
| Vit A 100,000 IU and Mebendazole | 6th week | X |  |  |
| VAR | 9th month until 12 months | X |  |  |
| Vit A 200,000 IU and Mebendazole | 12th month and then every 6 months until age 5 | X |  |  |

Table 3.3: Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (in percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2005 | 2006 | 200… | 200… |  | 2005 | 2006 |
| BCG | 71% | 85% |  |  | Tuberculosis* | not available | not available |
| DTP | DTP 1 | 81% | 98% |  |  | Diphtheria | not available | not available |
|  | DTP 3 | 58% | 77% |  |  | Pertussis | not available | not available |
| Polio 3 | 57% | 73% |  |  | Polio | 2 | 1 |
| Measles (first dose) | 70% | 83% |  |  | Measles | 2 | 13 |
| TT2+ (Pregnant women) | not available | 60% |  |  | NN Tetanus | NA | NA |
| Hib3 | NA |  |  |  | Hib ** | NA | NA |
| Yellow Fever | 63% | 74% |  |  | Yellow fever | 0 | 0 |
| HepB3 | NA |  |  |  | hepB sero-prevalence* | NA | NA |
| Vit A supplement | Mothers (<6 weeks post-delivery) | not available | 20% |  |  |  |  |  |
|  | Infants (>6 months) | not available |  |  |  |  |  |  |

* * If available

** Note: JRF asks for Hib meningitis.

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to.

Table 3.4: Baseline and annual targets (pages 47 and 48 of the cMYP)

| Nombre | Baseline and annual targets |
| --- | --- |
|  | Base year 2006 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Births | 361,797 | 416,326 | 429,232 | 442,539 | 456,257 | 470,401 |
| Infants’ deaths |  |  |  |  |  |  |
| Surviving infants | 317,675 | 365,555 | 376,887 | 388,570 | 400,616 | 413,035 |
| Pregnant women (4.2%) | 212,642 | 429,527 | 442,842 | 456,570 | 470,724 | 485,316 |
| Target population vaccinated with BCG | 306,762 | 347,277 | 358,043 | 368,068 | 378,374 | 388,968 |
| BCG coverage* | 85% | 95% | 95% | 95% | 95% | 95% |
| Target population vaccinated with OPV3 | 231,080 | 310,722 | 331,661 | 348,696 | 378,374 | 388,968 |
| OPV3 coverage** | 73% | 85% | 88% | 90% | 95% | 95% |
| Target population vaccinated with DTP3*** | 245,033 | 164,500 |  |  |  |  |
| DTP3 coverage** | 77% | 45% | NA | NA | NA | NA |
| Target population vaccinated with DTP1*** | 311,690 | 347,277 | NA | NA | NA | NA |
| Wastage rate in base-year and planned thereafter (DTP1-DTP3) | 30% | 5% | 5% | 5% | 5% | 5% |
| Target population vaccinated with 3rd dose of …DTPHepB-Hib……….. | NA | 146,222 | 331,661 | 348,696 | 378,374 | 388,968 |
| …………. Coverage** | NA | 40% | 88% | 90% | 95% | 95% |
| Target population vaccinated with 1st dose of Yellow Fever | 235,198(74%) | 310,722 | 331,661 | 348,696 | 378,374 | 388,968 |
| Wastage1 rate in base-year and planned thereafter | 36% | 30% | 25% | 20% | 20% | 20% |
| Target population vaccinated with 1st dose of Measles | 262,084 | 310,722 | 331,661 | 348,696 | 378,374 | 388,968 |
| Target population vaccinated with 2nd dose of Measles | NA |  |  |  |  |  |
| Measles coverage** | NA |  |  |  |  |  |
| Pregnant women vaccinated with TT+ | 212,642 | 292,444 | 320,354 | 348,696 | 378,374 | 388,968 |
| TT+ coverage**** | 60% | 80% | 85% | 90% | 95% | 95% |
| Vit A supplement | Mothers (<6 weeks from delivery) | 70,611(20%) | NA | NA | NA | NA | NA |
|  | Infants (>6 months) | 77% | 80% | 82% | 85% | 90% | 90% |
| Annual DTP Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 25% of the HDs have less than 10% | 50% of the HDs have less than 10% | 70% of the HDs have less than 10% | 80% of the HDs have less than 10% | 90% of the HDs have less than 10% | 100% of the HDs have less than 10% |
| Annual Measles Drop out rate (for countries applying for YF) | NA | NA | NA | NA | NA | NA |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Table 3.5: Summary of current and future immunisation budget (or refer to cMYP pages 62 and 63)

| Cost category | Base Year 2006 | 2008 | 2009 | 2010 | 2011 | 2012 | Total 2008 - 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | US$ | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines | 752,395 | 2,967,906 | 4,545,869 | 4,396,384 | 4,509,678 | 4,388,381 | 20,808,218 |
| - Traditional vaccines | 430,132 | 513,826 | 419,466 | 419,342 | 434,971 | 447,150 | 2,234,754 |
| - New and underused vaccines | 322,263 | 2,454,079 | 4,126,403 | 3,977,042 | 4,074,707 | 3,941,231 | 18,573,463 |
| Injection supplies | 108,984 | 232,708 | 274,104 | 289,145 | 311,680 | 320,407 | 1,428,043 |
| Personnel | 340,241 | 390,157 | 417,503 | 435,296 | 453,634 | 472,530 | 2,169,120 |
| - Salaries of full-time health workers | 72,558 | 97,203 | 105,255 | 107,360 | 109,507 | 111,697 | 531,023 |
| - Per-diems for outreach vaccinators/mobile teams | 83,048 | 93,281 | 105,690 | 117,247 | 129,223 | 141,632 | 587,072 |
| - Per-diems for supervision | 184,634 | 199,672 | 206,559 | 210,690 | 214,903 | 219,202 | 1,051,025 |
| Transportation | 30,080 | 30,684 | 31,321 | 31,964 | 32,541 | 33,217 | 159,727 |
| - Fixed strategy and delivery of vaccines | 18,983 | 19,364 | 19,764 | 20,168 | 20,536 | 20,960 | 100,792 |
| - Advanced and mobile strategy | 11,097 | 11,320 | 11,557 | 11,796 | 12,005 | 12,257 | 58,935 |
| Maintenance and overhead | 1,166,852 | 1,212,969 | 1,255,265 | 1,306,521 | 1,198,239 | 1,240,002 | 6,212,996 |
| Cold chains | 677,707 | 711,729 | 733,330 | 765,955 | 702,577 | 723,301 | 3,636,893 |
| Other equipment | 56,107 | 59,540 | 71,403 | 81,022 | 26,927 | $38,592 | 277,484 |
| Buildings | 433,038 | 441,699 | 450,533 | 459,544 | 468,734 | 478,109 | 2,298,619 |
| Short-term training | 93,860 | 119,570 | 72,663 | 74,116 | 75,599 | 77,111 | 419,059 |
| Social mobilisation and IEC | 65,307 | 66,613 | 67,945 | 69,304 | 70,690 | 72,104 | 346,657 |
| Disease control and surveillance | 313,904 | 224,883 | 229,380 | 233,968 | 238,647 | 243,420 | 1,170,298 |
| Programme management | 14,689 | 14,983 | 25,997 | 15,588 | 15,900 | 141,294 | $213,762 |
| Other recurring costs |  | 98,757 | 21,229 | 21,653 | 22,086 | 22,528 | 186,254 |
| Sub-total for recurring costs | 2,886,313 | 5,359,228 | 6,941,278 | 6,873,940 | 6,928,694 | 7,010,994 | 33,114,133 |
| Vehicles | 70,031 | 3,782 | 61,288 | 21,639 |  | 65,040 | 151,749 |
| Cold chain equipment | 46,200 | 976,535 | 550,722 | 801,508 | 861,025 | 1,131,136 | 4,320,926 |
| Other capital costs | 22,286 | 5,883 | 105,433 | 106,121 | 100,328 | 151,569 | 469,334 |
| Sub-total for capital | 138,517 | 986,200 | 717,443 | 929,269 | 961,354 | 1,347,745 | 4,942,010 |
| Routine sub-total | 3,024,830 | 6,345,428 | 7,658,721 | 7,803,209 | 7,890,048 | 8,358,739 | 38,056,143 |
| Polio | 2,250,757 | 4,185,762 | 1,316,566 | 1,147,003 |  |  | 6,649,331 |
| Vaccines | 802,561 | 643,968 | 199,179 | 170,630 |  |  | 1,013,778 |
| Operating costs | 1,448,196 | 3,541,794 | 1,117,386 | 976,372 |  |  | 5,635,553 |
| Measles | 2,068,099 | 3,700,768 |  |  | 4,131,894 |  | 7,832,663 |
| Vaccines and injection supplies | 1,297,474 | 1,431,558 |  |  | 1,508,158 |  | 2,939,716 |
| Operating costs | 770,625 | 2,269,210 |  |  | 2,623,736 |  | 4,892,947 |
| NN tetanus |  | 9,238,247 | 9,701,626 | 10,158,860 | 10,637,908 |  | 39,736,641 |
| Vaccines and injection supplies |  | 654,674 | 674,969 | 693,868 | 713,297 |  | 2,736,809 |
| Operating costs |  | 8,583,573 | 9,026,657 | 9,464,991 | 9,924,611 |  | 36,999,832 |
| Sub-total for campaign costs | 4,318,856 | 1,7124,777 | 11,018,192 | 11,305,862 | 14,769,802 |  | 54,218,634 |
| Grand total | 7,343,686 | 23,470,205 | 18,676,913 | 19,109,071 | 22,659,850 | 8,358,739 | 92,274,777 |

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners.

Table 3.6: Summary of current and future financing and sources of funds (or refer to pages 65 and 66 of the cMYP)

|  |  | Estimated financing per annum in US$ (,000) |
| --- | --- | --- |
| Cost category | Source of funds | 2006 Base year | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| Recurring costs |  |  |  |  |  |  |
| 1. Traditional vaccines | 1 Government | 430,132 | 513 826 | 419 466 | 419,342 | 434,971 | 447,150 |
| 2. New and underused vaccines | 2. Government/GAVI | 322,263 | 2 454 079 | 4 126 403 | 3,977,042 | 4,074,707 | 3,941,231 |
| 3. Injection supplies | 3. Government | 108,984 | 232 708 | 274 104 | 289,145 | 311,680 | 320,407 |
| 4. Personnel | 4 Government | 340,241 | 390 157 | 417 503 | 435,296 | 453,634 | 472,530 |
| . Salaries for full-time personnel | . Government | 72,558 | 97 203 | 105 255 | 107,360 | 109,507 | 111,697 |
| Per-diems for the advanced strategy/ mobile teams | UNICEF/Local Partners/ Community | 83,048 | 93 281 | 105 690 | 117,247 | 129,223 | 141,632 |
| 5. Per-diems for supervision | 5 Government/ Partners | 184,634 | 199 672 | 206 559 | 210,690 | 214,903 | 219,202 |
| 6 Transportation | 6. Government | 30,080 | 30, 684 | 31, 321 | 31,964 | 32,541 | 33,217 |
| Fixed strategy and delivery of vaccines | Government | 18,983 | 19 364 | 19 764 | 20,168 | 20,536 | 20,960 |
| Advanced and mobile strategy | Partners | 11,097 | 11, 320 | 11, 557 | 11,796 | 12,005 | 12,257 |
| 7. Maintenance and overhead | 7 Government/GAVI | 1,166,852 | 1, 212, 969 | 1, 255, 265 | 1,306,521 | 1,198,239 | 1,240,002 |
| Cold chains | Government/GAVI UNICEF/WHO/FED | 677,707 | 711, 729 | 733, 330 | 765,955 | 702,577 | 723,301 |
| Other equipment | Government | 56,107 | 59, 540 | 71, 403 | 81,022 | 26,927 | $38,592 |
| Buildings | Government | 433,038 | 441 699 | 450 533 | 459,544 | 468,734 | 478,109 |
| 8. Short-term training | 8. Partners | 93,860 | 119 570 | 72, 663 | 74,116 | 75,599 | 77,111 |
| 9. Social mobilisation and IE | 9. UNICEF | 65,307 | 66, 613 | 67, 945 | 69,304 | 70,690 | 72,104 |

| 10. Disease control and surveillance | 10. WHO | 313,904 | 224,883 | 229,380 | 233,968 | 238,647 | 243,420 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11. Programme management | 11. Government | 14,689 | 14,983 | 25,997 | 15,588 | 15,900 | 141,294 |
| 12. Other recurring costs | 12. Government |  | 98,757 | 21,229 | 21,653 | 22,086 | 22,528 |
| TOTAL recurring costs |  | 2,886,313 | 5,359,228 | 6,941,278 | 6,873,940 | 6,928,694 | 7,010,994 |
| Equipment costs |  |  |  |  |  |  |
| 1. Vehicles | 1. Government/ Partners | 70,031 | 3,782 | 61,288 | 21,639 |  | 65,040 |
| 2. Cold chain equipment | 2. Government/GAVI UNICEF/WHO/FED | 46,200 | 976,535 | 550,722 | 801,508 | 861,025 | 1,131,136 |
| 3. Other capital costs | 3. Government | 22,286 | 5,883 | 105,433 | 106,121 | 100,328 | 151,569 |
| TOTAL Equipment |  | 138,517 | 986,200 | 717,443 | 929,269 | 961,354 | 1,347,745 |
| Campaigns |  |  |  |  |  |  |
| 1. Polio | 1. WHO/UNICEF/ ROTARY/Government | 2,250,757 | 4,185,762 | 1,316,566 | 1,147,003 |  |  |
| 2. Measles | 2. WHO/UNICEF/ Government | 2,068,099 | 3,700,768 |  |  | 4,131,894 | 0 |
| 3. NN tetanus | 3. WHO/UNICEF/ Government | 0 | 9,238,247 | 9,701,626 | 10,158,860 | 10,637,908 | 0 |
| GRAND TOTAL | 7,343,686 | 23,470,205 | 18,676,913 | 19,109,071 | 22,659,850 | 8,358,739 |

## 4. Immunisation Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 4.1: Estimate of funds expected from ISS

|  | Base year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate |  |  |  |  |  |  |
| Number of infants reported / planned to be vaccinated with DTP3 (as in Table 3.4) |  |  |  |  |  |  |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  |  |  |  |  |  |
| Funds expected ($20 per additional infant) |  |  |  |  |  |  |

*  Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |

If you have not received ISS support before, please indicate:

a) when you would like the support to begin:

b) when you would like the first DQA to occur:

c) how you propose to channel the funds from GAVI into the country:

d) how you propose to manage the funds in-country:

e) who will be responsible for authorising and approving expenditures:

  - Please complete the banking form (annex 1) if required.

## 5. Injection Safety Support

  - Please attach the National Policy on Injection Safety including safe medical waste disposal (or reference the appropriate section of the Comprehensive Multi-Year Plan for Immunisation), and confirm the status of the document: DOCUMENT NUMBER……Not applicable…………

  - Please attach a copy of any action plans for improving injection safety and safe management of sharps waste in the immunisation system (and reference the Comprehensive Multi-Year Plan for Immunisation).  DOCUMENT NUMBER….. Not applicable……….

Table 5.1: Current cost of injection safety supplies for routine immunisation

Please indicate the current cost of the injection safety supplies for routine immunisation.

|  | Annual requirements | Cost per item (US$) | Total Cost (US$) |
| --- | --- | --- | --- |
| Year | Syringes | Safety Boxes | Syringes | Safety Boxes |  |
| 20… |  |  |  |  |  |

Table 5.2: Estimated supply for safety of immunisation with not applicable vaccine

(Please use one table for each vaccine BCG(1 dose), DTP(3 doses), TT(2 doses) 1, Measles(1 dose) and Yellow Fever(1 dose), and number them from 5.1 to 5.5)

|  |  | Formula | Year 1 2009 | Year 2 2010 | Year 3 2011 | Year 4 20… | Year 5 20… |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Number of children to be vaccinated 2 | # | NA | NA | NA | NA | NA |
| B | Percentage of vaccines requested from GAVI 3 | % | NA | NA | NA | NA | NA |
| C | Number of doses per child | # | NA | NA | NA | NA | NA |
| D | Number of doses | A x B/100 x C | NA | NA | NA | NA | NA |
| E | Standard vaccine wastage factor 4 | Either 2.0 or 1.6 | NA | NA | NA | NA | NA |
| F | Number of doses (including wastage) | A x B/100 x C x E | NA | NA | NA | NA | NA |
| G | Vaccines buffer stock 5 | F x 0.25 | NA | NA | NA | NA | NA |
| H | Number of doses per vial | # | NA | NA | NA | NA | NA |
| I | Total vaccine doses | F + G | NA | NA | NA | NA | NA |
| J | Number of AD syringes (+ 10% wastage) requested | (D + G) x 1.11 | NA | NA | NA | NA | NA |
| K | Re-constitution syringes (+ 10% wastage) requested 6 | I / H x 1.11 | NA | NA | NA | NA | NA |
| L | Total of safety boxes (+ 10% of extra need) requested | (J + K) / 100 x 1.11 | NA | NA | NA | NA | NA |

1 GAVI supports the procurement of AD syringes to deliver two doses of TT to pregnant women. If the immunisation policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of two doses for Pregnant Women (estimated as total births)

2 To insert the number of infants that will complete immunisations with all scheduled doses of a specific vaccine.

3 Estimates of 100% of target number of children is adjusted if a phased-out of GAVI/VF support is intended.

4 A standard wastage factor of 2.0 for BCG and of 1.6 for DTP, Measles, TT, and YF vaccines is used for calculation of INS support

5 The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the immunisation in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.

6 It applies only for lyophilized vaccines; write zero for other vaccines.

  - If you do not intend to procure your supplies through UNICEF, please provide evidence that the alternative supplier complies with WHO requirements by attaching supporting documents as available. NA

## 6. New and Under-Used Vaccines (NVS)

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc): Although there are no structured studies that reflect the chronic carriage rate of the Hepatitis B virus in the general population, Chad, like all the other countries in Africa south of the Sahara, is ranked among the pays with high endemicity for viral Hepatitis B. According to its data, the blood bank estimates that the surface antigen is present in 15% of volunteer blood donors. In Africa south of the Sahara, primitive liver cancer ranks first in men as the cause of death and third in women. For this reason, it is important to control the Hepatitis B virus by immunising infants. Therefore, the country plans to introduce the Hepatitis B vaccine in 2008 to prevent hepatitic complications caused by this virus, such as cirrhoses and primitive liver cancers. Chad has no statistical data on the burden of the disease (haemophilus influenzae type b). However, studies performed in four countries of the region (Uganda, Ghana, Niger and the Republic of South Africa) have demonstrated that haemophilus influenzae type b infection causes death in 30 to 70 cases of a population of 100,000 children under five. Children who survive the infection often develop after-effects for their entire life (for example, mental retardation, deafness, language difficulties, etc.), that are difficult for the individual and those who surround him to manage. Since Chad subscribed to the WHO Advisory Technical Committee “Due to their effectiveness and demonstrated safety, the conjugate Hib vaccines should be introduced in all routine children’s immunisation programs,” it made provisions to introduce the two new vaccines in 2008 to protect the population from these two diseases (Hib and Hepatitis B infection).

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please use attached excel annex 2a (Tab 6) on the Cold Chain. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap. In Chad, the Immunisation Division has two positive cold chambers with a gross capacity of 9 and 25 cubic meters, and one negative cold chamber with 20 gross cubic meters as well. In addition to these preservation units, the EPI has three sub-national warehouses, each with a positive cold chamber with a gross capacity of 15 cubic meters. These sub-national warehouses will be operational by end-2007 with a gross capacity of 15 cubic meters each in positive volume.

Table 6 a: Existing cold-chain storage volume, central and sub-national level

| Number of units | Total volume T°positive (litres) | Volume factor |
| --- | --- | --- |
| Two positive cold chambers | Gross | Net |  |
|  | 34,000 | 10,625 | 3.2 |
| Three sub-national positive cold chambers | 45,000 | 14,062.5 | 3.2 |
| TOTAL | 79,000 | 24,687.5 | 3.2 |
| Total volume T° negative (litres) |
| One negative cold chamber | Gross | Net |  |
|  | 20,000 | 6,250 | 3.2 |

The following table gives the required volumes

Table 6 b: Vaccine storage volumes

| Net vaccine storage volume (litres) |  | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| BCG vaccine |  | 950 l | 979 l | 1,009 l | 1,040 l | 1,073 l |
| Polio Oral VPO vaccine |  | 3,552 l | 3,318 l | 3,292 l | 3,206 l | 3,306 l |
| DTP vaccine DTP |  | 2,115 l | 0 l | 0 l | 0 l | 0 l |
| Measles vaccine VAR |  | 1,554 l | 1,586 l | 1,617 l | 1,666 l | 1,719 l |
| VAT vaccine VAT |  | 4,419 l | 4,236 l | 4,353 l | 4,473 l | 4,611 l |
| VAA vaccine VAA |  | 1,110 l | 1,133 l | 1,155 l | 1,190 l | 1,228 l |
| Pentavalent vaccine DTP-HepB-Hib |  | 5,955 l | 13,509 l | 14,243 l | 15,494 l | 15,984 l |
| Supply frequency (number supplied per year) |  | 2 | 2 | 2 | 2 | 2 |
| Net vaccine storage volume in positive CC (litres) |  | 10,065 l | 13,401 l | 13,986 l | 14,414 l | 15,383 l |
| BCG/VPO/VAR/VAT/DTP |  | at +5°C | 5,649 l | 4,250 l | 4,362 l | 4,487 l | 4,626 l |
| VAA/Rubella/HepB/Hib/DTPcombo |  | at +5°C | 4,416 l | 9,151 l | 9,624 l | 10,427 l | 10,757 l |
| Net vaccine storage volume in negative CC (litres) |  | 2,220 l | 2,074 l | 2,058 l | 2,004 l | 2,066 l |
| BCG/VPO/VAR/VAT/DTP |  | at -20°C | 2,220 l | 2,074 l | 2,058 l | 2,115 l | 2,180 l |
| Additional CC capacity (litres) |  |  |  |  |  |  |
| in positive cold chain (+2°C to +8°C) | at +5°C | - 14,623 l | - 11,286 l | - 10,701 l | - 9,773 l | - 9,304 l |
| in negative cold chain (-25°C to -15°C) | at -20°C | - 4,030 l | - 4,176 l | - 4,193 l | - 4,246 l | - 4,184 l |

Moreover, it should be noted that according to the projections in the cMYP document, a fourth sub-regional warehouse will be set up in Mongo in 2010.

| Table 6C: STORAGE VOLUME CAPACITY IN LITRES AT THE REGIONAL AND DISTRICT LEVEL |
| --- |
|  | POSITIVE | NEGATIVE |
| YEARS | Required | Existing | Gap | Required | Existing | Gap |
| 2008 | 4,110 | 6,904 | - 2,794 | 888 | 16,372 | - 15,484 |
| 2009 | 5,360 | 6,904 | - 1,544 | 830 | 16,372 | - 15,542 |

Supply and storage period by level

| N° | Warehouse | Supply period | Supply number |
| --- | --- | --- | --- |
| 01 | Central level | twice-yearly | 02 |
| 02 | Regional level | quarterly | 04 |
| 03 | District level | Bi-monthly | 06 |
| 04 | Health Centre level | Monthly | 12 |

The standard of equipment for each level is as follows:

|  | STANDARDS |
| --- | --- |
| STRUCTURE | NUM. | Freezer | Refrigerator | RCW25 coolbox | Vaccine carrier |
|  |  | 220 l | 55 l | 20 l | 3 l |
| REGIONS | 18 | 2 | 3 | 4 | 0 |
| DISTRICTS | 56 | 1 | 2 | 2 | - |
| HEALTH CENTRE | 639 | 0 | 1 | - | 2 |

Conclusion

As part of routine immunisation activities, cold chain availability at the central level for positive storage and negative storage, at the rate of two supplies per year, shows a surplus that indicates that the introduction of the pentavalent into the programme in 2008 will not cause any storage problems.

Table 6.1: Capacity and cost (for positive storage) (Refer to Tab 6 of Annex 2a or Annex 2b)

|  |  | Formula | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Annual positive volume requirement, including new vaccine (specify:: _in litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 10,065 | 13,401 | 13,986 | 14,407 | 14,852 |
| B | Annual positive capacity, including new vaccine (specify: in litres m3) | # | 24,687.5 | 24,687.5 | 24,687.5 | 24,687.5 | 24,687.5 |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 0.40 | 0.54 | 0.56 | 0.58 | 0.60 |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 2 | 2 | 2 |
| E | Gap (if any) | ((A / D) - B) | -19,655 | -17,987 | -17,694.5 | -17,784 | -17,261.5 |
| F | Estimated cost for expansion | US $ |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for

the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP):

The financing strategy that the Ministry of Health adopted consists of making the EPI budget line items secure for purchasing vaccines and consumables, including fuel for supervision and the cold chain. Thee will be a grant to the MOPH for this and the funds will be transferred into an account in which mobilisation will be subject to streamlined procedures.

Hence, the strategic financing plan will be centred on the following strategies:

a) Entering a secure budget line item

b) Adopting a streamlined procedure for releasing funds (grant through a MOPH account).

Table 6.2: Assessment of burden of relevant diseases (if available): NA

| Disease | Title of the evaluation | Date | Results |
| --- | --- | --- | --- |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learnt from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc., and suggest solutions to address them:

| Lessons learned | Solutions / Action Points |
| --- | --- |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation):

First Preference Vaccine

As reported in the cMYP, the country plans to introduce the Haemophilus influenzae Hepatitis B (antigen) vaccine, using the DTP HepB-Hib pentavalent vaccine, in a single-dose vial (number of doses per vial) in liquid form (lyophilized or liquid).

Please refer to the excel spreadsheet Annex 2a or Annex 2b (for Rotavirus and Pneumo vaccines) and proceed as follows:

  - Please complete the “Country Specifications” Table in Tab 1 of Annex 2a or Annex 2b, using the data available in the other Tabs: Tab 3 for the commodities price list, Tab 5 for the vaccine wastage factor and Tab 4 for the minimum co-financing levels per dose.

- Please summarise the list of specifications of the vaccines and the related immunisation programme in Table 6.3 below, using the population data (from Table 3.4 of this application) and the price list and co-financing levels (in Tables B, C, and D of Annex 2a or Annex 2b).

  - Then please copy the data from Annex 2a or 2b (Tab “Support Requested”) into Tables 6.4 and 6.5 (below) to summarize the support requested, and co-financed by GAVI and by the country.

  - Please submit the electronic version of the excel spreadsheets Annex 2a or 2b together with the application

Table 6.3: Specifications of immunisations with new vaccine

|  | Use data in: |  | Year 1 2008 | Year 2 2009 | Year 3 2010 | Year 4 2011 | Year 5 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine: single-dose liquid vial | Table 3.4 | # | 124,289 | 291,862 | 313,826 | 340,536 | 350,071 |
| Number of children to be vaccinated with the third dose | Table 3.4 | # | 40% | 88% | 90% | 95% | 95% |
| Target immunisation coverage with the third dose | Table 3.4 | # | 347,277 | 358,043 | 369,142 | 380,587 | 392,384 |
| Number of children to be vaccinated with the first dose | Annex 2a or 2b Table E - tab 5 | # | 1.11 | 1.05 | 1.05 | 1.05 | 1.05 |
| Estimated vaccine wastage factor | Annex 2a or 2b Table D - tab 4 | $ | 0.15 | 0.15 | 0.15 | 0.20 | 0.20 |

* Total price per dose includes vaccine cost, plus freight, supplies, insurance, fees, etc.

Table 6.4: Portion of supply to be co-financed by the country (and cost estimate, US$)

| Table 6.4: Rounded-off share of supplies purchased by the country and estimate of related costs in US$ |
| --- |
| Items necessary |  | 2008 | 2009 | 2010 | 2011 | 2012 |
| Number of vaccine doses | # | 71,300 | 63,300 | 72,300 | 118,900 | 130,900 |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |
| Total amount to be co-financed by the country | $ | 259,500 | 230,500 | 233,500 | 360,000 | 370,500 |

Table 6.5: Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

| Items necessary |  | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,224,200 | 1,087,500 | 1,095,100 | 1,081,200 | 1,102,800 |
| Number of AD syringes | # | 0 | 0 | 0 | 0 | 0 |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 | 0 |
| Number of safety boxes | # | 0 | 0 | 0 | 0 | 0 |
| Total amount to be co-financed by GAVI | $ | 4,451,500 | 3,954,000 | 3,539,500 | 3,276,000 | 3,119,000 |

Please refer to http://www.unicef.org/supply/index_gavi.html for the most recent GAVI Alliance Vaccine Product Selection Menu, and review the GAVI Alliance NVS Support Country Guidelines to identify the appropriate country category, and the minimum country co-financing level for each category.

Second Preference Vaccine

If the first preference of vaccine is in limited supply or currently not available, please indicate below the alternative vaccine presentation: Pentavalent, two doses in vials, lyophilized

- Please complete tables 6.3 – 6.4 for the new vaccine presentation

- Please complete the excel spreadsheets Annex 2a or Annex 2b for the new vaccine presentation and submit them alongside the application.

Procurement and Management of New and Under-Used Vaccines

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):

Chad plans to continue to obtain supplies of vaccines and consumables for the EPI through UNICEF.

b) If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document:

- Other vaccines or immunisation commodities procured by the country and description of the mechanisms used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality. The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality

c) Please describe the introduction of the vaccines (refer to cMYP):

d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

e) Please indicate how the co-financing amounts will be paid (and who is responsible for this)

f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP):

New and Under-Used Vaccine Introduction Grant

Table 6.5: calculation of lump-sum

| Year of New Vaccine introduction | N° of births (from table 3.4) | Share per birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2008 | 365,566 | $0.30 | 109,670 |

Please indicate in the tables below how the one-time Introduction Grant will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Table 6.6: Cost (and finance) to introduce the first preference vaccine (US$)

| Cost Category | Full needs for new vaccine introduction | Funded with new vaccine introduction grant |
| --- | --- | --- |
|  | US$ | US$ |
| Training | 46,331 | 46,331 |
| Social Mobilisation, IEC and Advocacy | 35,099 | 26,700 |
| Cold Chain Equipment and Maintenance | 0 | 0 |
| Vehicle and Transport | 0 | 0 |
| Programme Management | 0 | 0 |
| Surveillance and Monitoring | 0 | 0 |
| Human Resources | 0 | 0 |
| Waste Management | 0 | 0 |
| Technical Assistance | 0 | 0 |
| Supervision | 77,944 | 0 |
| Revision of management tools | 31,514 | 31,514 |
| Evaluation of the introduction | 10,715 | 0 |
| Launch ceremony | 5,125 | 5,125 |
| Total | 206,728 | 109,670 |

  - Please complete the banking form (annex 1) if required

Please complete a table similar to the one above for the second choice vaccine (if relevant) and title it Table 6.7: Cost (and finance) to introduce the second preference vaccine (US$)

## 7. Additional comments and recommendations from the National Coordinating Body (ICC/HSCC)

The multi-year EPI plan raises the issue of the sustainability of health sector financing. Chad’s plan requires close monitoring with regard to the mobilisation of resources to effectively carry out the activities. The vaccines acquired under this project must be equitably distributed throughout the country so that all children benefit without discrimination.

The sector financing issue calls to action all the stakeholders (government and partners). Also, for the good prospects being offered to Chad through the exploitation of its oil, the Ministry of Health must be proactive and effectively take the lead in mobilising resources.

The issue of governance must be the measure of our financing capacity so that the resources that are mobilised are beneficial for the people and contribute to lowering morbidity and infant and maternal mortality, all of which are very high in Chad.

## 8. Documents required for each type of support

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form (last two) | 3 | 2005 and 2006 |
| ALL | Comprehensive Multi-Year Plan (cMYP) | 2 | 2007-2011 |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed |  |  |
| ALL | Endorsed minutes of the ICC/HSCC meeting where the GAVI proposal was discussed | 1 |  |
| ALL | Minutes of the three most recent ICC/HSCC meetings | 4 |  |
| ALL | ICC/HSCC workplan for the forthcoming 12 months | 5 |  |
| Injection Safety | National Policy on Injection Safety including safe medical waste disposal (if separate from cMYP) |  |  |
| Injection Safety | Action plans for improving injection safety and safe management of sharps waste (if separate from cMYP) |  |  |
| Injection Safety | Evidence that alternative supplier complies with WHO requirements (if not procuring supplies from UNICEF) |  |  |
| New and Under-used Vaccines | Plan for introduction of the new vaccine (if not already included in the cMYP) | 6 |  |

* Please indicate the duration of the plan / assessment / document where appropriate

ANNEX 1

| Banking Form |
| --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on financial support made by the GAVI Alliance dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |
| Name of Institution: (Account Holder) |  |
| Address: |  |
| City – Country: |  |
| Telephone No.: |  | Telephone No.: |  |
| Amount in USD: | (To be filled in by GAVI Secretariat) | Amount in USD: | (To be filled in by GAVI Secretariat) |
| For credit to: Bank account’s title |  |
| Bank account No.: |  |
| At: Bank’s name |  |
| Is the bank account exclusively to be used by this program? | YES ( ) NO ( ) |
| By whom is the account audited? |  |
| Signature of Government’s authorizing official: By signing below, the authorizing official confirms that the bank account mentioned above is known to the Ministry of Finance and is under the oversight of the Auditor General. |
| Name: |  | Seal: |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |
| Address and Phone number |  |  |
| Fax number |  |  |
| Email address: |  |  |

| SECTION 2 (To be completed by the Bank) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name: |  |  |
| Branch Name: |  |  |
| Address: |  |  |
| City – Country: |  |  |
| Swift code: |  |  |
| Sort code: |  |  |
| ABA No.: |  |  |
| Telephone No.: |  |  |
| Fax No.: |  |  |
| Bank Contact Name and Phone Number: |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: | Name of bank’s authorizing official: |
| 1 Name: Title: |  | Signature: |  |
|  |  | Date: |  |
| 2 Name: Title: |  | Seal: |
| 3 Name: Title: |  |  |
| 4 Name: Title: |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI Alliance – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |
| --- |
|  | Name |  |  | Title |
| Government’s authorising official |  |  |  |  |
| Bank’s authorising official |  |  |  |  |
| Signature of UNICEF Representative: |
| Name |  |
| Signature |  |
| Date |  |

# Footnotes

Inter-agency coordinating committee or Health sector coordinating committee, whichever is applicable.

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

Use results from table 5.2. Make the sum-product of the total vaccine doses row (I) by the unit packed volume for each vaccine in the national immunisation schedule. All vaccines are stored at positive temperatures (+5°C) except OPV which is stored at negative temperatures (-20°C).

Table D1 should be used for the first vaccine, with tables D2 and D3 for the second and third vaccine co-financed by the country

The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000